## Sheet1
Id | SysDate | SysTime | SessionId | CompId | FinYearId | CustomerId | EnqId | POId | PONo | CId | SCId | WONo | TaskWorkOrderDate | TaskProjectTitle | TaskProjectLeader | TaskBusinessGroup | TaskTargetDAP_FDate | TaskTargetDAP_TDate | TaskDesignFinalization_FDate | TaskDesignFinalization_TDate | TaskTargetManufg_FDate | TaskTargetManufg_TDate | TaskTargetTryOut_FDate | TaskTargetTryOut_TDate | TaskTargetDespach_FDate | TaskTargetDespach_TDate | TaskTargetAssembly_FDate | TaskTargetAssembly_TDate | TaskTargetInstalation_FDate | TaskTargetInstalation_TDate | TaskCustInspection_FDate | TaskCustInspection_TDate | ShippingAdd | ShippingCountry | ShippingState | ShippingCity | ShippingContactPerson1 | ShippingContactNo1 | ShippingEmail1 | ShippingContactPerson2 | ShippingContactNo2 | ShippingEmail2 | ShippingFaxNo | ShippingEccNo | ShippingTinCstNo | ShippingTinVatNo | InstractionPrimerPainting | InstractionPainting | InstractionSelfCertRept | InstractionOther | InstractionExportCaseMark | InstractionAttachAnnexure | ReleaseWIS | DryActualRun | UpdateWO | Batches | CloseOpen | Remarks | ManufMaterialDate | BoughtoutMaterialDate | Buyer | r_person | Critics
13 | 2015-07-13 | 10:53:06 AM | Sapl0005 | 1 | 1 | M005 | 18 | 23 | A007/A72/3200057494 | 35 | 0 | N0004 | 2013-04-09 | MULTI SPOT WELDING SPM | Joshi Padmsinha Arunkumar | 3 | 2013-03-15 | 2015-02-28 | 2013-04-01 | 2015-02-28 | 2013-04-10 | 2013-04-23 | 2013-05-01 | 2013-05-10 | 2013-05-13 | 2013-05-20 | 2013-04-24 | 2013-04-30 | 2013-05-01 | 2013-05-30 | 2013-05-02 | 2013-04-11 | Mahindra Vehicle Manufacturers Limited,Plot no. A-1,Phase-IV, MIDC, At Post : Chakan Dist. Pune 410 510 | 1 | 21 | 405 | KAKADE ASARAM | - | KAKADE.ASARAM@mahindra.com | RAJESH KUMAR | - | RAJESHKUMAR@MAHINDRA.COM | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-04-02 | 2013-04-03 | 1 |  | Joshi Padmsinha Arunkumar
38 | 2018-01-11 | 1:43:43 PM | Sapl0005 | 1 | 1 | S006 | 42 | 52 | VERBAL | 35 | 0 | N0012 | 2013-04-24 | DEMO MANIPULATOR | More Tushar Ramchandra | 2 | 2013-04-24 | 2013-04-24 | 2013-04-27 | 2013-04-30 | 2013-05-02 | 2013-05-08 | 2013-05-09 | 2013-05-15 | 2013-05-15 | 2013-05-15 | 2013-05-16 | 2013-05-20 | 2013-05-21 | 2013-05-24 | 2013-05-15 | 2013-05-15 | SYNERGYTECH AUTOMATION PVT. LTD. PUNE | 1 | 21 | 405 | - | - | SDF@SDCFVG.COM | - | - | SDF@SDCFVG.COM | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-04-24 | 2013-04-24 | 1 |  | More Tushar Ramchandra
40 | 2018-01-11 | 1:43:59 PM | Sapl0005 | 1 | 1 | S006 | 44 | 55 | VERBAL1 | 35 | 0 | N0013 | 2013-04-27 | MODIFICATION IN EXISTING OLD PROJECTS | MILIND TERAWDE | 13 | 2013-04-27 | 2013-04-27 | 2013-04-27 | 2013-04-27 | 2013-04-27 | 2013-04-27 | 2013-04-27 | 2013-04-27 | 2013-04-27 | 2013-04-27 | 2013-04-27 | 2013-04-27 | 2013-04-27 | 2013-04-27 | 2013-04-27 | 2013-04-27 | Synergytech Automation Pvt. Ltd., Gat No. 205, Kasurdi, Khed Shivapur, Pune - Satara Road, Taluka Bhor, District Pune 412205. Maharashtra, India. | 1 | 21 | 405 | - | - | ASDF@DFG.COM | - | - | ASDF@DFG.COM | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-04-27 | 2013-04-27 | 1 |  | MILIND TERAWDE
45 | 2015-03-07 | 12:01:19 PM | Sapl0005 | 1 | 1 | S006 | 49 | 60 | verb | 38 | 0 | J0015 | 2013-05-07 | FABRICATION, MACHINING & FINAL PROCESS | SANJAY SHINDE | 13 | 2013-05-07 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2014-03-31 | 2013-12-30 | 2013-05-07 | 2013-05-07 | 2014-03-31 | 2014-03-31 | 2014-03-31 | 2014-03-31 | 2013-05-07 | 2014-03-31 | 2013-05-07 | 2013-05-07 | synergytech | 1 | 21 | 405 | - | - | as@sdf.com | - | - | as@sdf.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-03-31 | 2014-03-31 | 1 |  | SANJAY SHINDE
50 | 2013-08-28 | 10:40:07 AM | Sapl0005 | 1 | 1 | G011 | 54 | 65 | genix | 34 | 0 | S0010 | 2013-05-17 | Risers GI 1015–300 | SANJAY SHINDE | 13 | 2013-05-17 | 2013-05-17 | 2013-05-17 | 2013-05-17 | 2013-05-17 | 2013-05-17 | 2013-05-17 | 2013-05-17 | 2013-05-25 | 2013-05-25 | 2013-05-17 | 2013-05-17 | 2013-05-17 | 2013-05-17 | 2013-05-17 | 2013-05-17 | GENIX AUTOMATION PVT LTD GAT NO 40,VILLAGE CHIMBLI,Tal: KHED, CHAKAN | 1 | 21 | 405 | Girish Purohit | 9011078384 | girish@genixautomation.com | - | - | girish@genixautomation.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-05-17 | 2013-05-17 | 1 |  | SANJAY SHINDE
68 | 2013-08-28 | 10:46:50 AM | Sapl0005 | 1 | 1 | M001 | 71 | 81 | 3100258150 | 35 | 0 | N0018 | 2013-06-06 | BWF UNITS 13F465 | MANOJ SHINDE | 3 | 2013-06-06 | 2013-06-06 | 2013-06-07 | 2013-06-07 | 2013-06-08 | 2013-06-17 | 2013-06-18 | 2013-06-19 | 2013-06-20 | 2013-06-20 | 2013-06-21 | 2013-06-21 | 2013-06-22 | 2013-06-22 | 2013-06-21 | 2013-06-21 | Plant II, 80,MIDC ,Satpur, Nasik 422007 Maharashtra India | 1 | 21 | 402 | Snehal Malge | +91 253 6613052 | MALGE.SNEHAL@mahindra.com | DEOGHARE.ROOPAL | - | DEOGHARE.ROOPAL@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2013-06-07 | 2013-06-07 | 1 |  | MANOJ SHINDE
74 | 2015-01-12 | 12:20:53 PM | Sapl0005 | 1 | 1 | K007 | 77 | 88 | kpcl1 | 35 | 0 | N0022 | 2013-06-18 | MANUAL TOD | TUSHAR MORE | 2 | 2013-06-18 | 2013-06-26 | 2013-06-27 | 2013-07-04 | 2013-07-05 | 2013-07-17 | 2013-07-26 | 2013-07-29 | 2013-07-30 | 2013-07-30 | 2013-07-18 | 2013-07-25 | 2013-07-26 | 2013-08-02 | 2013-07-25 | 2013-07-29 | KIRLOSKAR PNEUMATICS CO. LTD., SASWAD | 1 | 21 | 405 | SHINDE M. M | - | shindemm@kpcl.net | SACHIN PEDNEKAR | - | pednekarss@kpcl.co.in | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-07-01 | 2013-07-01 | 1 |  | TUSHAR MORE
75 | 2018-03-13 | 2:04:27 PM | Sapl0005 | 1 | 1 | M009 | 76 | 87 | MUSCO1 | 35 | 0 | N0023 | 2013-06-18 | P106 CARGO : WELDING FIXTURES FOR ST-10 | MANOJ SHINDE | 3 | 2013-06-18 | 2015-05-18 | 2014-01-31 | 2015-05-18 | 2013-12-15 | 2015-02-28 | 2013-11-22 | 2015-02-28 | 2014-01-31 | 2015-02-06 | 2013-11-15 | 2015-01-22 | 2013-11-22 | 2015-02-18 | 2013-11-22 | 2015-01-27 | MAHINDRA UGINE STEEL CO. LTD, ZAHIRABAD | 1 | 21 | 405 | SATYAPRAKASH MISHRA | - | MISHRA.SATYAPRAKASH@mahindra.com | NIRANJAN | - | UPALKAR.NIRANJAN@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-07-22 | 2013-07-22 | 1 |  | MANOJ SHINDE
76 | 2016-03-31 | 11:00:58 AM | Sapl0005 | 1 | 1 | M008 | 78 | 89 | MUSCO2 | 35 | 0 | N0024 | 2013-06-18 | P106 CARGO : WELDING FIXTURES FOR ST-20 | MANOJ SHINDE | 3 | 2013-06-18 | 2015-02-28 | 2014-01-31 | 2015-02-28 | 2013-07-31 | 2015-02-28 | 2013-11-22 | 2013-11-29 | 2014-01-31 | 2014-01-31 | 2013-11-15 | 2013-11-21 | 2013-11-22 | 2013-12-16 | 2013-11-22 | 2013-11-29 | MAHINDRA UGINE STEEL CO?. ?LTD?,? ZAHIRABAD | 1 | 21 | 405 | SATYAPRAKASH MISHRA | - | MISHRA.SATYAPRAKASH@mahindra.com | NIRANJAN | - | UPALKAR.NIRANJAN@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-07-22 | 2013-07-22 | 1 |  | MANOJ SHINDE
77 | 2016-03-31 | 11:02:45 AM | Sapl0005 | 1 | 1 | M008 | 79 | 90 | MUSCO3 | 35 | 0 | N0025 | 2013-06-18 | P106 CARGO : WELDING FIXTURES FOR ST - 30 | MANOJ SHINDE | 3 | 2013-06-18 | 2015-02-28 | 2014-01-31 | 2015-02-28 | 2013-10-31 | 2015-02-28 | 2013-11-22 | 2013-11-29 | 2014-01-31 | 2014-01-31 | 2013-11-15 | 2013-11-21 | 2013-11-22 | 2013-12-16 | 2013-11-22 | 2013-11-29 | MAHINDRA UGINE STEEL CO?. ?LTD?,? ZAHIRABAD? | 1 | 21 | 405 | SATYAPRAKASH MISHRA | - | MISHRA.SATYAPRAKASH@mahindra.com | NIRANJAN | - | UPALKAR.NIRANJAN@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-07-22 | 2013-07-22 | 1 |  | MANOJ SHINDE
78 | 2018-03-13 | 2:04:47 PM | Sapl0005 | 1 | 1 | M008 | 80 | 91 | MUSCO4 | 35 | 0 | N0026 | 2013-06-18 | P106 CARGO : WELDING FIXTURES FOR OP-10 | MANOJ SHINDE | 3 | 2013-06-18 | 2015-02-28 | 2014-01-31 | 2015-02-28 | 2013-10-31 | 2013-11-14 | 2013-11-22 | 2013-11-29 | 2014-01-31 | 2014-01-31 | 2013-11-15 | 2013-11-21 | 2013-11-22 | 2013-12-16 | 2013-11-22 | 2013-11-29 | MAHINDRA UGINE STEEL CO??. ???LTD?. ZAHIRABAD | 1 | 21 | 405 | SATYAPRAKASH MISHRA | - | MISHRA.SATYAPRAKASH@mahindra.com | NIRANJAN | - | UPALKAR.NIRANJAN@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-07-22 | 2013-07-22 | 1 |  | MANOJ SHINDE
79 | 2018-03-13 | 2:05:24 PM | Sapl0005 | 1 | 1 | M003 | 81 | 92 | MUSCO5 | 35 | 0 | N0027 | 2013-06-18 | P106 CARGO : WELDING FIXTURES FOR OP - 20 | MANOJ SHINDE | 3 | 2013-06-18 | 2015-02-28 | 2014-01-31 | 2015-02-28 | 2013-10-31 | 2015-02-28 | 2013-11-22 | 2013-11-29 | 2014-01-31 | 2014-03-22 | 2013-11-15 | 2013-11-21 | 2013-11-22 | 2013-12-19 | 2013-11-22 | 2013-11-29 | MAHINDRA UGINE STEEL CO?. ?LTD. ZAHIRABAD? | 1 | 21 | 405 | SATYAPRAKASH MISHRA | - | MISHRA.SATYAPRAKASH@mahindra.com | NIRANJAN | - | UPALKAR.NIRANJAN@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-07-22 | 2013-07-22 | 1 |  | MANOJ SHINDE
80 | 2016-03-31 | 11:03:05 AM | Sapl0005 | 1 | 1 | M003 | 81 | 92 | MUSCO5 | 35 | 0 | N0028 | 2013-06-18 | P106 CARGO : WELDING FIXTURES FOR OP-20 | MANOJ SHINDE | 3 | 2013-06-18 | 2015-02-28 | 2014-01-31 | 2015-02-28 | 2013-10-31 | 2015-02-28 | 2013-11-22 | 2013-11-30 | 2014-01-31 | 2014-01-31 | 2013-11-15 | 2013-11-21 | 2013-11-22 | 2013-12-17 | 2013-11-22 | 2013-11-30 | MAHINDRA UGINE STEEL CO?. ??LTD?. ZAHIRABAD? | 1 | 21 | 405 | SATYAPRAKASH | - | MISHRA.SATYAPRAKASH@mahindra.com | NIRANJAN | - | UPALKAR.NIRANJAN@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-07-22 | 2013-07-22 | 1 |  | MANOJ SHINDE
81 | 2016-03-31 | 11:03:30 AM | Sapl0005 | 1 | 1 | M003 | 82 | 94 | MUS | 35 | 0 | N0029 | 2013-06-18 | WELDING FIXTURES FOR OP-30 | MANOJ SHINDE | 3 | 2013-06-18 | 2015-02-28 | 2014-01-31 | 2015-02-28 | 2013-10-31 | 2015-02-28 | 2013-11-22 | 2013-11-29 | 2014-01-31 | 2014-01-31 | 2013-11-15 | 2013-11-21 | 2013-11-22 | 2013-12-17 | 2013-11-22 | 2013-11-29 | MAHINDRA UGINE STEEL CO. ???LTD?. ZAHIRABAD? | 1 | 21 | 405 | SATYAPRAKASH | - | MISHRA.SATYAPRAKASH@mahindra.com | NIRANJAN | - | UPALKAR.NIRANJAN@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-07-22 | 2013-07-22 | 1 |  | MANOJ SHINDE
82 | 2016-03-31 | 11:03:39 AM | Sapl0005 | 1 | 1 | M003 | 83 | 95 | MUS1 | 35 | 0 | N0030 | 2013-06-18 | WELDING FIXTURES FOR OP-40 | MANOJ SHINDE | 3 | 2013-06-18 | 2015-02-28 | 2014-01-31 | 2015-02-28 | 2013-10-31 | 2015-02-28 | 2013-11-22 | 2013-11-29 | 2014-01-31 | 2014-01-31 | 2013-11-15 | 2013-11-22 | 2013-11-22 | 2013-12-16 | 2013-08-29 | 2013-09-26 | MAHINDRA UGINE STEEL CO?. ?LTD?. ZAHIRABAD? | 1 | 21 | 405 | SATYAPRAKASH | - | MISHRA.SATYAPRAKASH@mahindra.com | NIRANJAN | - | UPALKAR.NIRANJAN@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-07-22 | 2013-07-22 | 1 |  | MANOJ SHINDE
83 | 2016-03-31 | 11:03:49 AM | Sapl0005 | 1 | 1 | M003 | 84 | 96 | MUS2 | 35 | 0 | N0031 | 2013-06-18 | WELDING FIXTURES FOR OP-50 | MANOJ SHINDE | 3 | 2013-06-18 | 2015-02-28 | 2014-01-31 | 2015-02-28 | 2013-10-31 | 2015-02-28 | 2013-11-22 | 2013-11-29 | 2014-01-31 | 2014-01-31 | 2013-11-14 | 2013-11-22 | 2013-11-22 | 2013-12-17 | 2013-11-22 | 2013-11-29 | MAHINDRA UGINE STEEL CO?. ?LTD?.? ZAHIRABAD? | 1 | 21 | 405 | SATYAPRAKASH | - | MISHRA.SATYAPRAKASH@mahindra.com | UPALKAR.NIRANJAN | - | UPALKAR.NIRANJAN@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-07-22 | 2013-07-22 | 1 |  | MANOJ SHINDE
84 | 2016-03-31 | 11:03:59 AM | Sapl0005 | 1 | 1 | M003 | 85 | 97 | MUS3 | 35 | 0 | N0032 | 2013-06-18 | WELDING FIXTURES FOR OP-60 & OP-70 | MANOJ SHINDE | 3 | 2013-06-18 | 2015-02-28 | 2014-01-31 | 2015-02-28 | 2013-07-31 | 2015-02-28 | 2013-11-22 | 2013-11-29 | 2014-01-31 | 2014-03-29 | 2013-11-15 | 2013-11-22 | 2013-11-22 | 2013-12-12 | 2013-11-22 | 2013-11-29 | MAHINDRA UGINE STEEL CO?. ?LTD. ZAHIRABAD? | 1 | 21 | 405 | SATYAPRAKASH | - | MISHRA.SATYAPRAKASH@mahindra.com | NIRANJAN | - | UPALKAR.NIRANJAN@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-07-22 | 2013-07-22 | 1 |  | MANOJ SHINDE
85 | 2016-03-31 | 11:04:11 AM | Sapl0005 | 1 | 1 | M003 | 86 | 98 | MUSC4 | 35 | 0 | N0033 | 2013-06-18 | INSPECTION FIXTURES FOR OP-80 | MANOJ SHINDE | 3 | 2013-06-18 | 2015-02-28 | 2014-01-31 | 2015-02-28 | 2013-10-31 | 2015-02-28 | 2013-11-22 | 2013-11-29 | 2014-01-31 | 2014-03-22 | 2013-11-15 | 2013-11-22 | 2013-11-22 | 2013-12-13 | 2013-11-22 | 2013-11-29 | MAHINDRA UGINE STEEL CO?.?LTD?.? ZAHIRABAD | 1 | 21 | 405 | SATYAPRAKASH | - | MISHRA.SATYAPRAKASH@mahindra.com | UPALKAR.NIRANJAN | - | UPALKAR.NIRANJAN@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-07-22 | 2013-07-22 | 1 |  | MANOJ SHINDE
86 | 2016-03-31 | 11:05:04 AM | Sapl0005 | 1 | 1 | M003 | 87 | 99 | MUSC5 | 35 | 0 | N0034 | 2013-06-18 | HAND FIXTURES | MANOJ SHINDE | 3 | 2013-06-18 | 2015-02-28 | 2014-01-31 | 2015-02-28 | 2013-10-31 | 2015-02-28 | 2013-11-22 | 2013-11-29 | 2014-01-31 | 2014-01-31 | 2013-11-15 | 2013-11-22 | 2013-11-22 | 2013-12-13 | 2013-11-22 | 2013-11-29 | MAHINDRA UGINE STEEL CO. LTD., ZAHIRABAD | 1 | 21 | 405 | SATYAPRAKASH | - | MISHRA.SATYAPRAKASH@mahindra.com | NIRANJAN | - | NIRANJAN@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-07-22 | 2013-07-22 | 1 |  | MANOJ SHINDE
87 | 2016-03-31 | 11:05:15 AM | Sapl0005 | 1 | 1 | M003 | 88 | 100 | MUSC6 | 35 | 0 | N0035 | 2013-06-19 | OVERHEAD GANTRY SYSTEM | MANOJ SHINDE | 3 | 2013-06-19 | 2015-02-28 | 2014-01-31 | 2015-02-28 | 2013-10-31 | 2015-02-28 | 2013-11-22 | 2013-11-29 | 2014-01-31 | 2014-01-31 | 2013-11-15 | 2013-11-22 | 2013-11-22 | 2013-12-19 | 2013-11-22 | 2013-11-29 | MAHINDRA UGINE STEEL CO. LTD. | 1 | 21 | 405 | SATYAPRAKASH | - | MISHRA.SATYAPRAKASH@mahindra.com | NIRANJAN | - | NIRANJAN@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-07-22 | 2013-07-22 | 1 |  | MANOJ SHINDE
88 | 2015-06-01 | 10:08:22 AM | Sapl0005 | 1 | 1 | M003 | 89 | 101 | MUSC7 | 35 | 0 | N0036 | 2013-06-19 | GRIPPER FOR OP -10 | MANOJ SHINDE | 3 | 2013-06-19 | 2015-02-28 | 2014-01-31 | 2015-02-28 | 2013-10-31 | 2015-02-28 | 2013-11-22 | 2013-11-29 | 2014-01-31 | 2014-01-31 | 2013-11-15 | 2013-11-22 | 2013-11-22 | 2013-12-12 | 2013-11-22 | 2013-11-29 | MAHINDRA UGINE STEEL CO LTD. | 1 | 21 | 405 | SATYAPRKASH | - | MISHRA.SATYAPRAKASH@mahindra.com | NIRANJAN | - | NIRANJAN@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | COMPLETE | 2013-07-22 | 2013-07-22 | 1 |  | MANOJ SHINDE
92 | 2013-08-28 | 10:30:04 AM | Sapl0005 | 1 | 1 | C002 | 92 | 104 | 10305328 | 38 | 0 | J0028 | 2013-06-20 | SHIMS | MILIND TERAWDE | 13 | 2013-06-20 | 2013-06-21 | 2013-06-22 | 2013-06-23 | 2013-06-24 | 2013-06-25 | 2013-06-26 | 2013-06-27 | 2013-06-28 | 2013-06-28 | 2013-06-27 | 2013-06-27 | 2013-06-29 | 2013-06-29 | 2013-06-26 | 2013-06-27 | COMAU INDIA , SHIKRAPUR | 1 | 21 | 405 | SANTOSH.SAPARE | - | santosh.sapare@comau.com | SUJEET KULKARNI | - | sujeet.kulkarni@comau.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-06-25 | 2013-06-25 | 1 |  | MILIND TERAWDE
93 | 2013-08-28 | 10:34:34 AM | Sapl0005 | 1 | 1 | C002 | 93 | 105 | 10305450 | 38 | 0 | J0029 | 2013-06-21 | RISER (SP) & SHIM | MILIND TERAWDE | 13 | 2013-06-21 | 2013-06-21 | 2013-06-22 | 2013-06-22 | 2013-06-24 | 2013-06-24 | 2013-06-25 | 2013-06-26 | 2013-06-28 | 2013-06-28 | 2013-06-27 | 2013-06-27 | 2013-06-29 | 2013-06-29 | 2013-06-26 | 2013-06-27 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | PRASAD Dheeraj | - | dheeraj.prasad@comau.com | SANTOSH SAPARE | - | santosh.sapare@comau.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-06-24 | 2013-06-24 | 1 |  | MILIND TERAWDE
94 | 2013-08-28 | 10:38:50 AM | Sapl0005 | 1 | 1 | P011 | 94 | 106 | 200221 | 34 | 0 | S0016 | 2013-06-21 | CROSS RAIL C63 SECTION | RAJKUMAR JAGTAP | 2 | 2013-06-21 | 2013-06-21 | 2013-06-21 | 2013-06-21 | 2013-06-22 | 2013-06-22 | 2013-06-23 | 2013-06-23 | 2013-06-24 | 2013-06-24 | 2013-06-23 | 2013-06-23 | 2013-06-25 | 2013-06-25 | 2013-06-26 | 2013-06-26 | PLATEMASTER, PLOT NO. 97, SECTOR 10, PCNTDA, BHOSARI | 1 | 21 | 405 | SURYAKANT RATHI | - | platemasters@yahoo.in | - | - | platemasters@yahoo.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-06-22 | 2013-06-22 | 1 |  | RAJKUMAR JAGTAP
95 | 2013-08-28 | 10:38:38 AM | Sapl0005 | 1 | 1 | P011 | 95 | 107 | 200222 | 34 | 0 | S0017 | 2013-06-21 | TROLLEY SET FOR C63 SECTION | RAJKUMAR JAGTAP | 2 | 2013-06-21 | 2013-06-21 | 2013-06-21 | 2013-06-22 | 2013-06-23 | 2013-06-23 | 2013-06-23 | 2013-06-23 | 2013-06-24 | 2013-06-24 | 2013-06-23 | 2013-06-23 | 2013-06-25 | 2013-06-25 | 2013-06-26 | 2013-06-26 | PLATEMASTERS, PLOT NO. 97, SECTOR NO. 10, PCNTDA, BHOSARI | 1 | 21 | 405 | SURYAKANT RATHI | - | platemasters@gmail.com | - | - | platemasters@gmail.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-06-22 | 2013-06-22 | 1 |  | RAJKUMAR JAGTAP
96 | 2013-08-22 | 10:38:12 AM | Sapl0005 | 1 | 1 | C002 | 96 | 108 | 10305423 | 38 | 0 | J0030 | 2013-06-21 | PLATE & WELDMENT | MILIND TERAWDE | 13 | 2013-06-21 | 2013-06-26 | 2013-06-27 | 2013-06-28 | 2013-06-29 | 2013-07-19 | 2013-07-23 | 2013-07-23 | 2013-07-22 | 2013-07-22 | 2013-07-20 | 2013-07-21 | 2013-07-23 | 2013-07-23 | 2013-07-18 | 2013-07-20 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | RAVAL MANISH | - | manish.raval@comau.com | SANTOSH SAPARE | - | santosh.sapare@comau.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2013-06-29 | 2013-06-29 | 1 |  | MILIND TERAWDE
97 | 2015-01-21 | 11:06:49 AM | Sapl0005 | 1 | 1 | T002 | 97 | 109 | 9000025816 | 34 | 0 | S0018 | 2013-06-22 | Frictionless rails for gun suspension for SFC 407 BIW | RAJKUMAR JAGTAP | 2 | 2013-06-24 | 2013-06-25 | 2013-06-26 | 2013-06-29 | 2013-07-01 | 2013-07-18 | 2013-08-05 | 2013-08-06 | 2013-07-29 | 2013-07-30 | 2013-07-19 | 2013-07-24 | 2013-07-31 | 2013-08-03 | 2013-07-31 | 2013-07-03 | PUNE AUTO Tata Motors Ltd. Pune, PUNE 411018 | 1 | 21 | 405 | N. DODAKE | - | n.dodake@tatamotors.com | ABHIJEET MEDHEKAR | - | abhijit.medhekar@tatamotors.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 1 | COMPLETE | 2013-06-26 | 2013-06-26 | 1 |  | RAJKUMAR JAGTAP
98 | 2013-08-28 | 10:38:18 AM | Sapl0005 | 1 | 1 | S011 | 98 | 110 | PUOR13001147 | 34 | 0 | S0019 | 2013-06-22 | LIFTO HOIST 500KGS | HEMAKSH PATIL | 4 | 2013-06-22 | 2013-06-22 | 2013-06-22 | 2013-06-22 | 2013-06-22 | 2013-06-22 | 2013-06-22 | 2013-06-22 | 2013-06-22 | 2013-06-22 | 2013-06-22 | 2013-06-22 | 2013-06-22 | 2013-06-22 | 2013-06-22 | 2013-06-22 | SHANTI IRON & STEEL, 690, Udyambag Industrial Estate, BELGAUM | 1 | 17 | 295 | AMIT | - | amit.k@shantiiron.net | MN.PATIL | - | svp@shantiiron.net | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2013-06-22 | 2013-06-22 | 1 |  | HEMAKSH PATIL
101 | 2018-01-12 | 9:07:42 AM | Sapl0005 | 1 | 1 | S006 | 101 | 113 | v1 | 38 | 0 | J0031 | 2013-07-02 | CONSUMABLES | MILIND TERAWDE | 13 | 2013-07-02 | 2013-07-02 | 2013-07-02 | 2013-07-02 | 2013-07-02 | 2013-07-02 | 2013-07-02 | 2013-07-02 | 2013-07-02 | 2013-07-02 | 2013-07-02 | 2013-07-02 | 2013-07-02 | 2013-07-02 | 2013-07-02 | 2013-07-02 | Synergytech Automation Pvt. Ltd. | 1 | 21 | 405 | - | - | sales@synergytechs.com | - | - | sales@synergytechs.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-07-02 | 2013-07-02 | 1 |  | MILIND TERAWDE
102 | 2013-08-28 | 10:42:40 AM | Sapl0005 | 1 | 1 | S011 | 102 | 114 | PUOR13001361 | 37 | 0 | P0008 | 2013-07-03 | BREAK COIL | HEMAKSH PATIL | 4 | 2013-07-03 | 2013-07-03 | 2013-07-03 | 2013-07-03 | 2013-07-03 | 2013-07-03 | 2013-07-03 | 2013-07-03 | 2013-07-03 | 2013-07-03 | 2013-07-03 | 2013-07-03 | 2013-07-03 | 2013-07-03 | 2013-07-03 | 2013-07-03 | 690, Udyambag Industrial Estate, BELGAUM - 590 008 KARNATAKA - INDIA | 1 | 17 | 295 | M N PATIL | +91 831 4218328 | purchase@shantiiron.net | S. RAWOOL | - | subcon@shantiiron.net | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 1 |  | 1 | COMPLETED | 2013-07-03 | 2013-07-03 | 1 |  | HEMAKSH PATIL
104 | 2013-08-28 | 10:42:09 AM | Sapl0005 | 1 | 1 | W003 | 105 | 116 | 0116/M/P6/13-14 | 37 | 0 | P0009 | 2013-07-08 | BREAK COIL 415V AC LIFTO | HEMAKSH PATIL | 4 | 2013-07-08 | 2013-07-08 | 2013-07-08 | 2013-07-08 | 2013-07-08 | 2013-07-08 | 2013-07-08 | 2013-07-08 | 2013-07-08 | 2013-07-08 | 2013-07-08 | 2013-07-08 | 2013-07-08 | 2013-07-08 | 2013-07-08 | 2013-07-08 | GAT NO. 203, AT MURHE VASTI, TAL. KHED POST KURULI, CHAKAN, PUNE 410501 | 1 | 21 | 405 | VIJAY PATIL | - | vijay.patil@windalsauto.com | DEEPAK RAWAT | - | deepak.rawat@windalsauto.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 1 |  | 1 | COMPLETED | 2013-07-08 | 2013-07-08 | 1 |  | HEMAKSH PATIL
105 | 2018-08-04 | 9:29:57 AM | Sapl0005 | 1 | 1 | S006 | 106 | 117 | V2 | 34 | 0 | S0021 | 2013-07-11 | STANDARD ASSEMBLY FOR FIXTURES | AMIT POTDAR | 3 | 2013-07-11 | 2013-07-11 | 2013-07-11 | 2013-07-11 | 2013-07-11 | 2013-07-11 | 2013-07-11 | 2013-07-11 | 2013-07-11 | 2013-07-11 | 2013-07-11 | 2013-07-11 | 2013-07-11 | 2013-07-11 | 2013-07-11 | 2013-07-11 | Synergytech Automation Pvt. Ltd. | 1 | 21 | 405 | - | - | sales@synergytechs.com | - | - | sales@synergytechs.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-07-11 | 2013-07-11 | 1 |  | AMIT POTDAR
106 | 2013-08-28 | 10:37:22 AM | Sapl0005 | 1 | 1 | P009 | 107 | 118 | PMW/D/2013-14/043 | 43 | 0 | T0005 | 2013-07-11 | MESSUNG MAKE NG2K PLUS AC POWER SUPPLY 3A P2115 | HEMAKSH PATIL | 4 | 2013-07-11 | 2013-07-11 | 2013-07-11 | 2013-07-11 | 2013-07-11 | 2013-07-11 | 2013-07-11 | 2013-07-11 | 2013-07-11 | 2013-07-11 | 2013-07-11 | 2013-07-11 | 2013-07-11 | 2013-07-11 | 2013-07-11 | 2013-07-11 | Fact. – Plot No.’E’ S.No.44-8/3, Ganesh Industrial Estate, Near RPG Raychem, Village: Waliv, Tal. Vasai, Dist. Thane - 401 208. | 1 | 21 | 398 | maninder singh | - | maninder@pmwindia.com | maninder singh | - | maninder@pmwindia.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-07-11 | 2013-07-11 | 1 |  | HEMAKSH PATIL
107 | 2013-08-28 | 10:45:59 AM | Sapl0005 | 1 | 1 | C002 | 108 | 119 | 10300694 | 35 | 0 | N0038 | 2013-07-15 | TROLLEYS | SANJAY SHINDE | 13 | 2013-07-15 | 2013-07-15 | 2013-07-15 | 2013-07-15 | 2013-07-15 | 2013-07-15 | 2013-07-15 | 2013-07-15 | 2013-07-15 | 2013-07-15 | 2013-07-15 | 2013-07-15 | 2013-07-15 | 2013-07-15 | 2013-07-15 | 2013-07-15 | COMAU INDIA PVT. LTD. | 1 | 21 | 405 | - | - | vishwas.gangakhedkar@comau.com | - | - | vishwas.gangakhedkar@comau.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-07-15 | 2013-07-15 | 1 |  | SANJAY SHINDE
109 | 2013-08-28 | 5:06:24 PM | Sapl0005 | 1 | 1 | C002 | 110 | 121 | 10308232 | 38 | 0 | J0033 | 2013-07-17 | SHIMPACK | MILIND TERAWDE | 13 | 2013-07-17 | 2013-07-19 | 2013-07-20 | 2013-07-20 | 2013-07-21 | 2013-07-24 | 2013-07-24 | 2013-07-24 | 2013-07-25 | 2013-07-25 | 2013-07-23 | 2013-07-24 | 2013-07-26 | 2013-07-26 | 2013-07-24 | 2013-07-24 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | dheeraj.prasad | - | dheeraj.prasad@comau.com | SUJEET KULKARNI | - | sujeet.kulkarni@comau.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-07-17 | 2013-07-17 | 1 |  | MILIND TERAWDE
113 | 2016-02-08 | 9:46:06 AM | Sapl0005 | 1 | 1 | M005 | 114 | 125 | MML1 | 35 | 0 | N0039 | 2013-07-24 | SUB ASSLY SA10, SA20 & SA30 | PADMASINHA JOSHI | 3 | 2013-07-24 | 2015-01-31 | 2014-01-31 | 2015-01-31 | 2013-12-31 | 2014-04-02 | 2013-09-19 | 2014-03-29 | 2014-01-31 | 2014-03-29 | 2013-09-02 | 2014-03-31 | 2013-09-19 | 2014-03-31 | 2013-09-19 | 2014-03-30 | MAHINDRA & MAHINDRA , CHAKAN | 1 | 21 | 405 | JAI VERMA | - | VERMA.JAI@mahindra.com | DAS DEBJIT | - | DAS.DEBJIT@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-11-30 | 2013-11-30 | 1 |  | PADMASINHA JOSHI
115 | 2014-06-03 | 4:49:53 PM | Sapl0005 | 1 | 1 | M005 | 115 | 126 | MML2 | 35 | 0 | N0040 | 2013-07-24 | WELDING FIXTURES FOR ST-10 | PADMASINHA JOSHI | 3 | 2013-07-24 | 2014-05-30 | 2014-01-31 | 2014-05-30 | 2014-01-31 | 2014-03-05 | 2013-11-22 | 2014-03-06 | 2014-02-04 | 2014-03-07 | 2013-11-15 | 2014-03-06 | 2013-11-22 | 2014-03-31 | 2013-11-22 | 2014-03-06 | M&M,CHAKAN | 1 | 21 | 405 | JAI VERMA | - | VERMA.JAI@mahindra.com | DAS DEBJIT | - | DAS.DEBJIT@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2013-07-31 | 2013-07-31 | 1 |  | PADMASINHA JOSHI
116 | 2015-01-21 | 11:10:43 AM | Sapl0005 | 1 | 1 | M005 | 116 | 127 | MML3 | 35 | 0 | N0041 | 2013-07-24 | WELDING FIXTURES FOR ST-20 | PADMASINHA JOSHI | 3 | 2013-07-24 | 2014-12-24 | 2014-01-31 | 2014-12-24 | 2014-02-03 | 2014-03-05 | 2013-11-22 | 2014-03-06 | 2014-02-14 | 2014-03-07 | 2013-11-15 | 2014-03-06 | 2013-11-22 | 2014-03-30 | 2013-11-22 | 2014-03-06 | M&M, CHAKAN | 1 | 21 | 405 | JAI VERMA | - | VERMA.JAI@mahindra.com | DAS DEBJIT | - | DAS.DEBJIT@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-07-30 | 2013-07-30 | 1 |  | PADMASINHA JOSHI
117 | 2014-06-03 | 4:50:38 PM | Sapl0005 | 1 | 1 | M005 | 117 | 128 | MML4 | 35 | 0 | N0042 | 2013-07-24 | WELDING FIXTURES FOR ST-30 | PADMASINHA JOSHI | 3 | 2013-07-24 | 2014-05-30 | 2014-01-31 | 2014-05-30 | 2014-02-04 | 2014-03-06 | 2013-11-22 | 2014-03-06 | 2014-02-19 | 2014-03-07 | 2013-11-15 | 2014-03-06 | 2013-11-22 | 2014-03-30 | 2013-11-22 | 2014-03-06 | M&M, CHAKAN | 1 | 21 | 405 | JAI VERMA | - | VERMA.JAI@mahindra.com | DAS DEBJIT | - | DAS.DEBJIT@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2013-07-26 | 2013-07-26 | 1 |  | PADMASINHA JOSHI
118 | 2015-01-21 | 11:10:52 AM | Sapl0005 | 1 | 1 | M005 | 118 | 129 | MML5 | 35 | 0 | N0043 | 2013-07-24 | WELDING FIXTURES FOR ST-40 | PADMASINHA JOSHI | 3 | 2013-07-24 | 2014-05-30 | 2014-01-31 | 2014-05-30 | 2014-02-03 | 2014-03-06 | 2013-11-22 | 2014-03-06 | 2014-02-15 | 2014-03-07 | 2013-11-15 | 2014-03-06 | 2013-11-22 | 2014-03-30 | 2013-11-22 | 2014-03-06 | M&M,CHAKAN | 1 | 21 | 405 | JAI VERMA | - | VERMA.JAI@mahindra.com | DAS DEBJIT | - | DAS.DEBJIT@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-07-27 | 2013-07-27 | 1 |  | PADMASINHA JOSHI
119 | 2015-01-21 | 11:11:04 AM | Sapl0005 | 1 | 1 | M005 | 119 | 130 | MML6 | 35 | 0 | N0044 | 2013-07-24 | WELDING FIXTURES FOR ST-50 | PADMASINHA JOSHI | 3 | 2013-07-24 | 2014-05-30 | 2014-01-31 | 2014-05-30 | 2013-10-31 | 2014-03-06 | 2013-11-22 | 2014-03-06 | 2014-02-19 | 2014-03-30 | 2013-11-15 | 2014-03-25 | 2013-11-22 | 2014-03-31 | 2013-11-22 | 2014-01-27 | M&M, CHAKAN | 1 | 21 | 405 | JAI VERMA | - | VERMA.JAI@mahindra.com | DAS DEBJIT | - | DAS.DEBJIT@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-07-27 | 2013-07-27 | 1 |  | PADMASINHA JOSHI
120 | 2015-01-21 | 11:11:15 AM | Sapl0005 | 1 | 1 | M005 | 120 | 131 | MML7 | 35 | 0 | N0045 | 2013-07-24 | WELDING FIXTURES FOR ST-60 | PADMASINHA JOSHI | 3 | 2013-07-24 | 2014-05-30 | 2014-01-31 | 2014-05-30 | 2014-02-04 | 2014-03-06 | 2013-11-22 | 2014-03-06 | 2014-02-21 | 2014-03-07 | 2013-11-15 | 2014-03-06 | 2013-11-22 | 2014-03-30 | 2013-11-22 | 2014-03-07 | M&M, CHAKAN | 1 | 21 | 405 | JAI VERMA | - | VERMA.JAI@mahindra.com | DAS DEBJIT | - | DAS.DEBJIT@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-07-27 | 2013-07-27 | 1 |  | PADMASINHA JOSHI
121 | 2015-11-16 | 11:36:07 AM | Sapl0005 | 1 | 1 | M005 | 121 | 132 | MML8 | 35 | 0 | N0046 | 2013-07-24 | SPM FOR ST-70 | PADMASINHA JOSHI | 3 | 2013-07-24 | 2014-05-30 | 2014-01-31 | 2014-05-30 | 2013-10-31 | 2014-03-06 | 2013-11-22 | 2014-03-06 | 2014-01-31 | 2014-03-07 | 2013-11-15 | 2014-03-06 | 2013-11-22 | 2014-03-30 | 2013-11-22 | 2014-03-06 | M&M, CHAKAN | 1 | 21 | 405 | JAI VERMA | - | VERMA.JAI@mahindra.com | DAS DEBJIT | - | DAS.DEBJIT@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-07-27 | 2013-07-27 | 1 |  | PADMASINHA JOSHI
122 | 2015-07-13 | 10:56:26 AM | Sapl0005 | 1 | 1 | M005 | 122 | 133 | MML9 | 35 | 0 | N0047 | 2013-07-24 | FIXTURES FOR ST-80 | PADMASINHA JOSHI | 3 | 2013-07-24 | 2015-07-11 | 2014-01-31 | 2015-07-11 | 2013-10-31 | 2014-03-06 | 2013-11-22 | 2014-03-06 | 2014-01-31 | 2014-03-07 | 2013-11-15 | 2014-03-06 | 2013-11-22 | 2014-03-30 | 2013-11-22 | 2014-03-06 | M&M, CHAKAN | 1 | 21 | 405 | JAI VERMA | - | VERMA.JAI@mahindra.com | DAS DEBJIT | - | DAS.DEBJIT@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-07-31 | 2013-07-31 | 1 |  | PADMASINHA JOSHI
123 | 2015-01-21 | 11:11:47 AM | Sapl0005 | 1 | 1 | M005 | 123 | 134 | MM12 | 35 | 0 | N0048 | 2013-07-24 | FIXTURES FOR ST-90 | PADMASINHA JOSHI | 3 | 2013-07-24 | 2014-05-30 | 2014-01-31 | 2014-05-30 | 2014-02-04 | 2014-02-15 | 2013-11-22 | 2013-11-29 | 2014-02-24 | 2014-02-28 | 2013-11-15 | 2013-11-22 | 2013-11-22 | 2013-12-17 | 2013-11-22 | 2013-11-29 | M&M,CHAKAN | 1 | 21 | 405 | JAI VERMA | - | VERMA.JAI@mahindra.com | DAS DEBJIT | - | DAS.DEBJIT@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-07-31 | 2013-07-31 | 1 |  | PADMASINHA JOSHI
124 | 2015-01-21 | 11:11:57 AM | Sapl0005 | 1 | 1 | M005 | 124 | 135 | M12 | 35 | 0 | N0049 | 2013-07-24 | LIFT & CARRY | PADMASINHA JOSHI | 3 | 2013-07-24 | 2014-05-30 | 2014-01-31 | 2014-05-30 | 2014-02-04 | 2014-02-15 | 2013-11-22 | 2013-11-29 | 2014-02-22 | 2014-02-28 | 2013-11-15 | 2013-11-21 | 2013-11-22 | 2013-12-18 | 2013-11-22 | 2013-11-29 | M&M,CHAKAN | 1 | 21 | 405 | JAI VERMA | - | VERMA.JAI@mahindra.com | DAS DEBJIT | - | DAS.DEBJIT@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-07-31 | 2013-07-31 | 1 |  | PADMASINHA JOSHI
127 | 2013-09-21 | 10:17:13 AM | Sapl0005 | 1 | 1 | C011 | 127 | 138 | IND2384257 | 36 | 0 | E0003 | 2013-07-27 | INSTALLATION & COMMISSIONING | HEMAKSH PATIL | 4 | 2013-07-27 | 2013-07-27 | 2013-07-27 | 2013-07-27 | 2013-07-27 | 2013-07-27 | 2013-07-27 | 2013-07-27 | 2013-07-27 | 2013-07-27 | 2013-07-27 | 2013-07-27 | 2013-07-27 | 2013-07-27 | 2013-07-27 | 2013-07-27 | PLOT NO. B-2, PHALTAN | 1 | 21 | 405 | SANDIP BHADANE | - | sandip.v.bhadane@cummins.com | SANDIP BHADANE | - | sandip.v.bhadane@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-07-27 | 2013-07-27 | 1 |  | HEMAKSH PATIL
128 | 2013-08-28 | 10:37:41 AM | Sapl0005 | 1 | 1 | A022 | 135 | 139 | afspl | 34 | 0 | S0023 | 2013-07-27 | LONG RAIL, CROSS RAIL & TROLLEY SET | RAJKUMAR JAGTAP | 2 | 2013-07-27 | 2013-07-27 | 2013-07-27 | 2013-07-27 | 2013-07-27 | 2013-07-27 | 2013-07-27 | 2013-07-27 | 2013-07-29 | 2013-07-29 | 2013-07-27 | 2013-07-27 | 2013-07-27 | 2013-07-30 | 2013-07-30 | 2013-07-30 | Gat No. 418, villange ambethan, taluka khed, 410501 | 1 | 21 | 405 | Amit K Srivastav | 8605003212 | amit.srivastav@arkayindia.com | rajesh pal | - | rajeshk.pal@arkayindia.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2013-07-27 | 2013-07-27 | 1 |  | RAJKUMAR JAGTAP
130 | 2015-11-19 | 12:30:46 PM | Sapl0005 | 1 | 1 | S006 | 130 | 141 | RAIL_VERB | 34 | 0 | S0024 | 2013-07-31 | LONG RAIL & CROSS RAIL | RAJKUMAR JAGTAP | 2 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-07-31 | SYNERGYTECH AUTOMATION, PUNE | 1 | 21 | 405 | - | - | sales@synergytechs.com | - | - | sales@synergytechs.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | com | 2013-07-31 | 2013-07-31 | 1 |  | RAJKUMAR JAGTAP
132 | 2013-08-28 | 10:36:08 AM | Sapl0005 | 1 | 1 | A002 | 132 | 143 | Con\2013\0446\2 | 34 | 0 | S0025 | 2013-08-02 | long rail & trolley set | RAJKUMAR JAGTAP | 2 | 2013-08-02 | 2013-08-02 | 2013-08-02 | 2013-08-02 | 2013-08-02 | 2013-08-02 | 2013-08-02 | 2013-08-02 | 2013-08-02 | 2013-08-02 | 2013-08-02 | 2013-08-02 | 2013-08-02 | 2013-08-02 | 2013-08-02 | 2013-08-02 | anusaya Auto Press Parts | 1 | 21 | 405 | SANTOSH PUDAKE | - | snpudake@wadhokar.com | santosh pudake | - | snpudake@wadhokar.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-08-02 | 2013-08-02 | 1 |  | RAJKUMAR JAGTAP
141 | 2014-01-04 | 5:30:43 PM | Sapl0005 | 1 | 1 | T014 | 142 | 152 | LOI1 | 35 | 0 | N0053 | 2013-08-19 | POWERISED ROLLER CONVEYOR WITH CONTACTOR | RAJKUMAR JAGTAP | 2 | 2013-08-20 | 2013-12-31 | 2013-12-31 | 2014-01-11 | 2013-09-03 | 2013-09-10 | 2013-09-17 | 2013-09-19 | 2013-09-20 | 2013-09-21 | 2013-09-11 | 2013-09-16 | 2013-09-17 | 2013-09-23 | 2013-09-22 | 2013-09-23 | TCL-3, PHALTAN, MAHARASHTRA STATE INDIA | 1 | 21 | 405 | RAHUL AGARWAL | - | rahul.agarwal@cummins.com | - | - | rahul.agarwal@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2013-08-26 | 2013-08-26 | 1 |  | RAJKUMAR JAGTAP
148 | 2013-09-30 | 5:38:39 PM | Sapl0005 | 1 | 1 | A016 | 149 | 159 | PO513000189 | 37 | 0 | P0010 | 2013-09-03 | BRAKE COIL, BRAKE SHOE ASSLY & TRANSFORMER | HEMAKSH PATIL | 4 | 2013-09-03 | 2013-09-03 | 2013-09-03 | 2013-09-03 | 2013-09-03 | 2013-09-03 | 2013-09-03 | 2013-09-03 | 2013-09-04 | 2013-09-05 | 2013-09-03 | 2013-09-03 | 2013-09-03 | 2013-09-03 | 2013-09-07 | 2013-09-07 | ALF ENGINEERING COMPANY, HARIDVAR | 1 | 33 | 576 | VED PRAKASH | 9759500225 | vedprakash@alfengineering.com | VED PRAKASH | - | vedprakash@alfengineering.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2013-09-03 | 2013-09-03 | 1 |  | HEMAKSH PATIL
150 | 2014-01-13 | 12:51:05 PM | Sapl0005 | 1 | 1 | V002 | 151 | 161 | 8000037180 | 43 | 0 | T0007 | 2013-09-06 | HVAC Test Bench with under rack | HEMAKSH PATIL | 4 | 2013-09-06 | 2013-11-26 | 2013-11-27 | 2013-12-28 | 2013-09-23 | 2013-12-28 | 2013-10-21 | 2013-12-28 | 2013-12-02 | 2013-12-30 | 2013-10-11 | 2013-12-28 | 2013-10-21 | 2014-01-03 | 2013-10-26 | 2013-12-30 | Volkswagen India Private Limited E-1, MIDC Industrial Area (Phase III) Chakan, Village Nigoje Mhalunge Kharabwadi, Tal : Khed Chakan, Pune - 410 501 Maharashtra, India | 1 | 21 | 405 | Shashank Kumar | 91-2135-331438 | Shashank.Kumar@volkswagen.co.in | Sardana, Sumit | - | Sumit.Sardana@volkswagen.co.in | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-11-25 | 2013-11-25 | 1 |  | HEMAKSH PATIL
156 | 2013-10-10 | 10:13:47 AM | Sapl0005 | 1 | 1 | C002 | 156 | 167 | 10314336 | 38 | 0 | J0052 | 2013-09-14 | SHIMS | MILIND TERAWDE | 13 | 2013-09-14 | 2013-09-16 | 2013-09-17 | 2013-09-17 | 2013-09-17 | 2013-09-17 | 2013-09-17 | 2013-09-17 | 2013-09-20 | 2013-09-20 | 2013-09-17 | 2013-09-17 | 2013-09-17 | 2013-09-21 | 2013-09-23 | 2013-09-23 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | SAYEED SAMEER | - | SAYEED.SAMEER@COMAU.COM | SUJEET KULKARNI | - | sujeet.kulkarni@comau.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-09-14 | 2013-09-14 | 1 |  | MILIND TERAWDE
158 | 2013-10-10 | 10:14:35 AM | Sapl0005 | 1 | 1 | C002 | 159 | 169 | 10314749 | 38 | 0 | J0053 | 2013-09-18 | RISERS (SP) | MILIND TERAWDE | 13 | 2013-09-18 | 2013-09-18 | 2013-09-18 | 2013-09-18 | 2013-09-18 | 2013-09-20 | 2013-09-20 | 2013-09-20 | 2013-09-20 | 2013-09-20 | 2013-09-19 | 2013-09-20 | 2013-09-21 | 2013-09-21 | 2013-09-21 | 2013-09-21 | COMAU INDIA LTD., SHIKRAPUR | 1 | 21 | 405 | SAYEED SAMEER | - | SAYEED.SAMEER@COMAU.COM | SUJEET KULKARNI | - | sujeet.kulkarni@comau.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-09-18 | 2013-09-18 | 1 |  | MILIND TERAWDE
160 | 2013-09-30 | 5:39:05 PM | Sapl0005 | 1 | 1 | S011 | 161 | 171 | PUOR13002723 | 37 | 0 | P0012 | 2013-09-25 | BREAK COIL & BRAKE SHOE ASSLY | HEMAKSH PATIL | 4 | 2013-09-25 | 2013-09-25 | 2013-09-25 | 2013-09-25 | 2013-09-25 | 2013-09-25 | 2013-09-25 | 2013-09-25 | 2013-09-25 | 2013-09-25 | 2013-09-25 | 2013-09-25 | 2013-09-25 | 2013-09-25 | 2013-09-25 | 2013-09-25 | # 690, Udyambag Industrial Estate, BELGAUM - 590 008 KARNATAKA - INDIA | 1 | 17 | 295 | MNPATIL | 91 831 4218328 | purchase@shantiiron.net | AMIT K | - | amit.k@shantiiron.net | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2013-09-25 | 2013-09-25 | 1 |  | HEMAKSH PATIL
161 | 2014-03-31 | 5:35:02 PM | Sapl0005 | 1 | 1 | C004 | 162 | 172 | VERBCUMM | 43 | 0 | T0008 | 2013-09-25 | WIRING MATERIAL FOR MAIN CONTROL PANEL | HEMAKSH PATIL | 4 | 2013-09-25 | 2013-09-27 | 2013-09-28 | 2013-11-23 | 2013-10-03 | 2013-11-23 | 2013-09-18 | 2013-11-23 | 2013-10-14 | 2013-11-23 | 2013-10-08 | 2013-10-12 | 2013-09-18 | 2013-10-18 | 2013-10-15 | 2013-10-15 | CUMMINS INDIA LTD., KOTHRUD | 1 | 21 | 405 | MOHINI PAWAR | 9881949602 | mohini.a.pawar@cummins.com | AMIT MAHADESHWAR | - | amit.m.mahadeshwar@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2013-09-27 | 2013-09-27 | 1 |  | HEMAKSH PATIL
162 | 2014-01-13 | 12:00:07 PM | Sapl0005 | 1 | 1 | C004 | 163 | 173 | VERBCUMM1 | 43 | 0 | T0009 | 2013-09-25 | WIRING MATERIAL TO INTERFACE OPTO MODULES WITH TRANSDUCER IN TRANSDUCER PANEL | HEMAKSH PATIL | 4 | 2013-09-25 | 2013-09-27 | 2013-09-28 | 2013-10-02 | 2013-10-03 | 2013-10-09 | 2013-10-18 | 2013-10-19 | 2013-09-13 | 2013-09-14 | 2013-10-10 | 2013-10-12 | 2013-10-18 | 2013-10-18 | 2013-10-16 | 2013-10-16 | CUMMINS INDIA LTD., KOTHRUD | 1 | 21 | 405 | MOHINI PAWAR | 9881949602 | mohini.a.pawar@cummins.com | AMIT MAHADESHWAR | - | amit.m.mahadeshwar@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-09-30 | 2013-09-30 | 1 |  | HEMAKSH PATIL
163 | 2014-01-13 | 12:00:25 PM | Sapl0005 | 1 | 1 | C004 | 164 | 174 | CUMM2 | 43 | 0 | T0010 | 2013-09-25 | TRANSDUCER PANEL TO MOUNT TRANSDUCER WITH OPTO MODULE IN TEST CELL | HEMAKSH PATIL | 4 | 2013-09-25 | 2013-11-25 | 2013-11-25 | 2013-11-28 | 2013-11-28 | 2013-11-30 | 2013-10-23 | 2013-10-24 | 2013-10-15 | 2013-10-16 | 2013-10-09 | 2013-10-14 | 2013-10-23 | 2013-10-23 | 2013-10-16 | 2013-10-16 | CUMMINS INDIA LTD., KOTHRUD | 1 | 21 | 405 | MOHINI PAWAR | 9881949602 | mohini.a.pawar@cummins.com | AMIT MAHADESHWAR | - | amit.m.mahadeshwar@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-11-05 | 2013-11-05 | 1 |  | HEMAKSH PATIL
165 | 2013-10-04 | 7:14:08 PM | Sapl0005 | 1 | 1 | A013 | 166 | 176 | PO613000409 | 37 | 0 | P0013 | 2013-09-30 | Device Net Coupler, Make : Phoenix contact IL DN BK3-PAC | HEMAKSH PATIL | 4 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-10-01 | 2013-10-01 | 2013-09-30 | 2013-09-30 | 2013-10-02 | 2013-10-02 | 2013-10-01 | 2013-10-01 | Plot No. A-1/3,MVML Supplier Park, Phase - IV,, Village Nigoje,TalP-Bunheo,r Maharashtra, PIN : 410501 | 1 | 21 | 405 | Sunil Lokhande | 9970067340 | sunillokhande@alfengineering.com | vinod Tipre | - | kalidasbarne@alfengineering.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2013-09-30 | 2013-09-30 | 1 |  | HEMAKSH PATIL
168 | 2017-12-08 | 4:44:18 PM | Sapl0005 | 1 | 1 | C004 | 169 | 179 | 12345 | 35 | 0 | N0054 | 2013-10-11 | JIG BOOM | RAJESHKUMAR JAGTAP | 2 | 2013-10-11 | 2013-10-18 | 2013-10-19 | 2013-11-25 | 2013-10-23 | 2013-11-06 | 2013-11-15 | 2013-11-19 | 2013-11-20 | 2013-11-22 | 2013-11-07 | 2013-11-14 | 2013-11-15 | 2013-11-25 | 2013-11-16 | 2013-11-18 | CUMMINS INDIA LTD., PUNE | 1 | 21 | 405 | MOHINI PAWAR | - | mohini.a.pawar@cummins.com | AMIT MAHADESHWAR | - | amit.m.mahadeshwar@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-10-25 | 2013-10-25 | 1 |  | RAJESHKUMAR JAGTAP
169 | 2013-11-12 | 2:17:49 PM | Sapl0005 | 1 | 1 | C002 | 170 | 180 | 10317165 | 38 | 0 | J0055 | 2013-10-12 | PLATE, WELDMENT, BASE FRAME, BRACKETS | MILIND TERAWDE | 13 | 2013-10-12 | 2013-10-12 | 2013-10-13 | 2013-10-13 | 2013-10-14 | 2013-10-19 | 2013-10-22 | 2013-10-22 | 2013-10-21 | 2013-10-21 | 2013-10-18 | 2013-10-19 | 2013-10-22 | 2013-10-22 | 2013-10-17 | 2013-10-19 | COMAU INDIA PVT. LTD., SHIKRAPUR | 1 | 21 | 405 | manish.raval | - | manish.raval@comau.com | SUJEET KULKARNI | - | sujeet.kulkarni@comau.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-10-14 | 2013-10-14 | 1 |  | MILIND TERAWDE
170 | 2015-03-07 | 12:03:41 PM | Sapl0005 | 1 | 1 | B008 | 171 | 181 | BAGHIRATH1 | 35 | 0 | N0055 | 2013-10-14 | ROBOTIC WELDING FIXTURES FOR SIDE PILLARS | HEMAKSH PATIL | 4 | 2013-10-15 | 2014-06-06 | 2013-11-07 | 2014-06-06 | 2013-11-18 | 2014-03-31 | 2013-12-04 | 2014-03-27 | 2013-12-13 | 2014-03-28 | 2013-11-27 | 2014-03-28 | 2013-12-04 | 2014-03-29 | 2013-12-04 | 2014-03-27 | Bhagirath Coach & Metal Fab.P.Ltd. Plot No.202, Sector 1 Pithampur Dist. Dhar (M.P.) 454775 | 1 | 20 | 347 | RAJENDRA PATIDAR | 91 99930 91501 | rpatidar@bhagirathbrothers.org | ADITYA SHARMA | - | adityasharma@bhagirathbrothers.co.in | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-11-07 | 2013-11-07 | 1 |  | HEMAKSH PATIL
173 | 2015-01-21 | 11:18:19 AM | Sapl0005 | 1 | 1 | T002 | 174 | 184 | 2410178479 | 37 | 0 | P0014 | 2013-10-17 | AIR COMPRESSOR | HEMAKSH PATIL | 4 | 2013-10-17 | 2013-10-17 | 2013-10-17 | 2013-10-17 | 2013-10-18 | 2013-10-18 | 2013-10-21 | 2013-10-21 | 2013-10-21 | 2013-10-21 | 2013-10-18 | 2013-10-18 | 2013-10-22 | 2013-10-22 | 2013-10-21 | 2013-10-21 | TATA MOTORS LTD., PIMPRI | 1 | 21 | 405 | anant.natu | 7276097477 | anant.natu@tatamotors.com | ajay.phadtare | - | ajay.phadtare@tatamotors.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2013-10-21 | 2013-10-21 | 1 |  | HEMAKSH PATIL
176 | 2018-01-11 | 1:45:36 PM | Sapl0005 | 1 | 1 | M001 | 177 | 187 | LOI12 | 35 | 0 | N0056 | 2013-10-23 | BWF FIXTURES | PADMASINHA JOSHI | 3 | 2013-10-23 | 2014-01-17 | 2014-01-18 | 2014-01-25 | 2013-11-16 | 2013-11-27 | 2013-12-03 | 2013-12-10 | 2014-01-31 | 2014-01-31 | 2013-11-28 | 2013-12-02 | 2013-12-03 | 2013-12-20 | 2013-12-03 | 2013-12-07 | MAHINDRA & MAHINDRA, NASHIK | 1 | 21 | 402 | Snehal Malge | 253 6613052 | MALGE.SNEHAL@mahindra.com | DEOGHARE ROOPAL | - | DEOGHARE.ROOPAL@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-11-15 | 2013-11-15 | 1 |  | PADMASINHA JOSHI
177 | 2018-01-11 | 1:46:34 PM | Sapl0005 | 1 | 1 | M005 | 178 | 188 | VERBMAH | 35 | 0 | N0057 | 2013-10-24 | STATION 00 | PADMASINHA JOSHI | 3 | 2013-10-24 | 2014-05-30 | 2014-01-31 | 2014-05-30 | 2013-11-15 | 2013-11-21 | 2013-12-01 | 2013-12-05 | 2014-01-31 | 2014-01-31 | 2013-11-22 | 2013-11-30 | 2013-12-01 | 2013-12-26 | 2013-12-01 | 2013-12-06 | MAHINDRA & MAHINDRA, CHAKAN | 1 | 21 | 405 | JAI VERMA | - | VERMA.JAI@mahindra.com | DAS.DEBJIT | - | DAS.DEBJIT@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-10-30 | 2013-10-30 | 1 |  | PADMASINHA JOSHI
179 | 2018-01-11 | 1:46:50 PM | Sapl0005 | 1 | 1 | M005 | 180 | 190 | VERMAH1 | 35 | 0 | N0058 | 2013-10-25 | SA 40 | PADMASINHA JOSHI | 3 | 2013-10-25 | 2014-05-30 | 2014-01-31 | 2014-05-30 | 2013-10-31 | 2013-11-14 | 2013-11-23 | 2013-12-03 | 2014-01-31 | 2014-01-31 | 2013-11-15 | 2013-11-22 | 2013-11-23 | 2013-12-28 | 2013-11-23 | 2013-12-03 | MAHINDRA & MAHINDRA, CHAKAN | 1 | 21 | 405 | JAI VERMA | - | VERMA.JAI@mahindra.com | DAS.DEBJIT | - | DAS.DEBJIT@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-10-29 | 2013-10-29 | 1 |  | PADMASINHA JOSHI
182 | 2015-01-12 | 12:26:48 PM | Sapl0005 | 1 | 1 | M001 | 183 | 193 | LOIM | 35 | 0 | N0059 | 2013-11-18 | BWF FIXTURES 13F485 & 13F487 | PADMASINHA JOSHI | 3 | 2013-10-23 | 2014-01-13 | 2014-01-13 | 2014-01-25 | 2013-11-16 | 2013-12-03 | 2013-12-13 | 2013-12-14 | 2014-01-31 | 2014-01-31 | 2013-12-04 | 2013-12-12 | 2013-12-13 | 2013-12-19 | 2013-12-13 | 2013-12-14 | MAHINDRA & MAHINDRA LTD., NASHIK | 1 | 21 | 402 | MALGE SNEHAL | - | MALGE.SNEHAL@mahindra.com | ROOPAL DEOGHARE | - | DEOGHARE.ROOPAL@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-11-18 | 2013-11-18 | 1 |  | PADMASINHA JOSHI
183 | 2015-01-12 | 12:27:01 PM | Sapl0005 | 1 | 1 | M001 | 184 | 194 | LOIM | 35 | 0 | N0060 | 2013-11-18 | BWF FIXTURES 14F556 & 14F467 | PADMASINHA JOSHI | 3 | 2013-10-26 | 2014-01-13 | 2014-01-13 | 2014-01-25 | 2013-11-23 | 2013-12-04 | 2013-12-13 | 2013-12-14 | 2014-01-31 | 2014-01-31 | 2013-12-05 | 2013-12-12 | 2013-12-13 | 2013-12-19 | 2013-12-13 | 2013-12-14 | MAHINDRA & MAHINDRA, NASHIK | 1 | 21 | 402 | MALGE SNEHAL | - | MALGE.SNEHAL@mahindra.com | ROOPAL DEOGHARE | - | DEOGHARE.ROOPAL@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-11-18 | 2013-11-18 | 1 |  | PADMASINHA JOSHI
184 | 2015-01-12 | 12:27:11 PM | Sapl0005 | 1 | 1 | M001 | 185 | 195 | LOIM | 35 | 0 | N0061 | 2013-11-18 | BWF FIXTURES 13F463 & 13F466 | PADMASINHA JOSHI | 3 | 2013-10-24 | 2014-01-13 | 2014-01-13 | 2014-01-25 | 2013-11-23 | 2013-12-04 | 2013-12-13 | 2013-12-14 | 2014-01-31 | 2014-01-31 | 2013-12-05 | 2013-12-12 | 2013-12-13 | 2013-12-20 | 2013-12-13 | 2013-12-14 | MAHINDRA & MAHINDRA LTD., NASHIK | 1 | 21 | 402 | MALGE SNEHAL | - | MALGE.SNEHAL@mahindra.com | ROOPAL DEOGHARE | - | DEOGHARE.ROOPAL@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-11-18 | 2013-11-18 | 1 |  | PADMASINHA JOSHI
185 | 2014-01-13 | 12:09:50 PM | Sapl0005 | 1 | 1 | C002 | 186 | 196 | 10323009 | 38 | 0 | J0058 | 2013-11-25 | 5102-ET-MFL-03-00-TROLLEY | MILIND TERAWDE | 13 | 2013-11-25 | 2013-12-04 | 2013-12-04 | 2013-12-07 | 2013-12-08 | 2013-12-12 | 2013-12-12 | 2013-12-12 | 2013-12-13 | 2013-12-13 | 2013-12-08 | 2013-12-12 | 2013-12-12 | 2013-12-12 | 2013-12-10 | 2013-12-12 | COMAU INDIA PVT. LTD., SHIKRAPUR | 1 | 21 | 405 | SANTOSH SAPARE | - | santosh.sapare@comau.com | SANTOSH SAPARE | - | santosh.sapare@comau.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-12-07 | 2013-12-07 | 1 |  | MILIND TERAWDE
186 | 2014-01-13 | 11:58:32 AM | Sapl0005 | 1 | 1 | M018 | 187 | 197 | 13-14_Z-0878 | 34 | 0 | S0036 | 2013-11-28 | OVERHEAD RAIL C75 | RAJKUMAR JAGTAP | 2 | 2013-11-28 | 2013-11-28 | 2013-11-28 | 2013-11-28 | 2013-11-28 | 2013-11-28 | 2013-11-28 | 2013-11-28 | 2013-11-28 | 2013-11-28 | 2013-11-28 | 2013-11-28 | 2013-11-28 | 2013-11-29 | 2013-11-28 | 2013-11-28 | MASTER ZIPPEL, KONDHAPURI | 1 | 21 | 405 | NAGESH JADHAV | - | njadhav@masterzippel.com | MANOJ PAWAR | - | mpawar@masterzippel.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | COMPLETE | 2013-11-28 | 2013-11-28 | 1 |  | RAJKUMAR JAGTAP
187 | 2014-01-13 | 12:10:09 PM | Sapl0005 | 1 | 1 | C002 | 188 | 198 | 10324822 | 38 | 0 | J0059 | 2013-12-06 | STRUCTURE, WELDMENT, PLATE, SPACER | MILIND TERAWDE | 13 | 2013-12-06 | 2013-12-10 | 2013-12-10 | 2013-12-14 | 2013-12-11 | 2013-12-14 | 2013-12-15 | 2013-12-15 | 2013-12-16 | 2013-12-16 | 2013-12-11 | 2013-12-15 | 2013-12-15 | 2013-12-17 | 2013-12-14 | 2013-12-14 | COMAU INDIA LTD., SHIKRAPUR | 1 | 21 | 405 | DHEERAJ PRASAD | - | dheeraj.prasad@comau.com | DHEERAJ PRASAD | - | dheeraj.prasad@comau.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | COMPLETE | 2013-12-10 | 2013-12-10 | 1 |  | MILIND TERAWDE
188 | 2014-01-13 | 11:58:53 AM | Sapl0005 | 1 | 1 | J014 | 189 | 199 | 4300012565 | 34 | 0 | S0037 | 2013-12-21 | LONG RAIL C63, CROSS RAIL C63 & TROLLEY SET | RAJKUMAR JAGTAP | 2 | 2013-12-21 | 2013-12-24 | 2013-12-24 | 2013-12-25 | 2013-12-25 | 2013-12-25 | 2013-12-25 | 2013-12-25 | 2013-12-25 | 2013-12-25 | 2013-12-25 | 2013-12-25 | 2013-12-28 | 2013-12-30 | 2013-12-28 | 2013-12-28 | PLOT NO.: SP1-891,RIICO IND. AREA, NEXT TO SHRI RAM PISTONS 110092 PATHREDI (ALWAR), INDIA | 1 | 29 | 500 | Akshay.Bhardwaj | 08826681823 | Akshay.Bhardwaj1@jbm.co.in | dharmendra.kumar | - | dharmendra.kumar1@jbm.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-12-24 | 2013-12-24 | 1 |  | RAJKUMAR JAGTAP
189 | 2014-01-13 | 11:59:15 AM | Sapl0005 | 1 | 1 | S011 | 190 | 200 | PUOR13004189 | 34 | 0 | S0038 | 2013-12-27 | 500kg LIFTO Hoist | HEMAKSH PATIL | 4 | 2013-12-31 | 2013-12-31 | 2013-12-31 | 2013-12-31 | 2013-12-31 | 2013-12-31 | 2013-12-31 | 2013-12-31 | 2013-12-31 | 2013-12-31 | 2013-12-31 | 2013-12-31 | 2013-12-31 | 2013-12-31 | 2013-12-31 | 2013-12-31 | 690,, Udyambag,, Belgaum., Belgaum, PIN : . Karnataka, India | 1 | 17 | 295 | AMIT | +91 9844577876 | amit.k@shantiiron.net | amit | - | amit.k@shantiiron.net | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | COMPLETE | 2013-12-31 | 2013-12-31 | 1 |  | HEMAKSH PATIL
191 | 2014-11-28 | 11:42:07 AM | Sapl0005 | 1 | 1 | C004 | 192 | 202 | IND2680958 | 36 | 0 | E0005 | 2013-12-13 | TRANSDUCER PANEL & JIG BOOM LABOR CHARGES | HEMAKSH PATIL | 4 | 2013-12-13 | 2013-12-13 | 2013-12-13 | 2013-12-13 | 2013-12-13 | 2013-12-13 | 2013-12-13 | 2013-12-13 | 2013-12-13 | 2013-12-13 | 2013-12-13 | 2013-12-13 | 2013-12-13 | 2013-12-13 | 2013-12-13 | 2013-12-13 | CUMMINS INDIA LTD., KOTHRUD, PUNE | 1 | 21 | 405 | MOHINI PAWAR | - | mohini.a.pawar@cummins.com | AMIT MAHADESHWAR | - | amit.m.mahadeshwar@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | COMPLETE | 2013-12-13 | 2013-12-13 | 1 |  | HEMAKSH PATIL
192 | 2014-11-28 | 11:42:16 AM | Sapl0005 | 1 | 1 | C011 | 193 | 203 | IND2703440 | 36 | 0 | E0006 | 2014-01-08 | Rail Replcement For UK-40 | HEMAKSH PATIL | 4 | 2014-01-08 | 2014-01-08 | 2014-01-08 | 2014-01-08 | 2014-01-08 | 2014-01-08 | 2014-01-08 | 2014-01-08 | 2014-01-08 | 2014-01-08 | 2014-01-08 | 2014-01-08 | 2014-01-11 | 2014-01-11 | 2014-01-11 | 2014-01-11 | Plot No.B-2 , Phaltan SEZ Industrial Area , Village-Nandal and Surawadi , Tal-Phaltan , Dist- Satara , 415523 , Maharashtra , India | 1 | 21 | 409 | SANDIP BHADANE | 9922434636 | sandip.v.bhadane@cummins.com | SANDIP BHADANE | - | sandip.v.bhadane@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | COMPLETE | 2014-01-08 | 2014-01-08 | 1 |  | HEMAKSH PATIL
193 | 2015-02-28 | 10:17:10 AM | Sapl0005 | 1 | 1 | J006 | 194 | 204 | 4300012662 | 35 | 0 | N0062 | 2014-01-10 | Welding & Checking Fixtures For 66100 | AMIT POTDAR | 3 | 2014-01-10 | 2014-02-05 | 2014-02-05 | 2014-02-20 | 2014-01-25 | 2014-02-20 | 2014-02-07 | 2014-02-08 | 2014-02-10 | 2014-02-12 | 2014-01-28 | 2014-02-06 | 2014-02-07 | 2014-02-21 | 2014-02-06 | 2014-02-08 | Jay Bharat Maruti Ltd., Gurgaon | 1 | 13 | 171 | saroj.chaudhary | 91-9818459495 | saroj.chaudhary@jbm.co.in | J C Pathak | - | jcpathak@jbm.co.in | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-01-25 | 2014-01-25 | 1 |  | AMIT POTDAR
194 | 2015-03-07 | 12:23:05 PM | Sapl0005 | 1 | 1 | K007 | 195 | 205 | 2411404910 | 43 | 0 | T0011 | 2014-01-11 | Control Panel Two Stage | HEMAKSH PATIL | 4 | 2014-01-11 | 2014-03-07 | 2014-01-16 | 2014-03-07 | 2014-01-19 | 2014-03-07 | 2014-01-30 | 2014-03-07 | 2014-01-31 | 2014-03-07 | 2014-01-25 | 2014-03-07 | 2014-01-30 | 2014-03-14 | 2014-01-30 | 2014-03-14 | Saswad,S.NO.606/1, 606/2A, Saswad Works, Pune-Saswad Road,Taluka | 1 | 21 | 405 | Agwan Abhay A. | - | agwanaa@kpcl.net | Chhapkhane Anand S | - | achhapkhane@kpcl.net | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-01-18 | 2014-01-18 | 1 |  | HEMAKSH PATIL
195 | 2014-05-12 | 1:38:00 PM | Sapl0005 | 1 | 1 | K007 | 196 | 206 | 2411404911 | 43 | 0 | T0012 | 2014-01-13 | Control Panel Single Stage | HEMAKSH PATIL | 4 | 2014-01-13 | 2014-03-24 | 2014-01-18 | 2014-03-24 | 2014-01-22 | 2014-03-26 | 2014-01-30 | 2014-03-26 | 2014-01-30 | 2014-03-26 | 2014-01-27 | 2014-03-27 | 2014-01-30 | 2014-03-29 | 2014-01-30 | 2014-03-26 | Saswad,S.NO.606/1, 606/2A, Saswad Works, Pune-Saswad Road,Taluka | 1 | 21 | 405 | Agwan Abhay A. | - | agwanaa@kpcl.net | Chhapkhane Anand S | - | achhapkhane@kpcl.net | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2014-01-22 | 2014-01-22 | 1 |  | HEMAKSH PATIL
196 | 2014-05-05 | 6:38:37 PM | Sapl0005 | 1 | 1 | K007 | 197 | 207 | 2411404908 | 43 | 0 | T0013 | 2014-01-15 | Control Panel Box Single Stage | HEMAKSH PATIL | 4 | 2014-01-15 | 2014-03-07 | 2014-01-21 | 2014-03-07 | 2014-01-27 | 2014-03-07 | 2014-02-17 | 2014-03-07 | 2014-02-20 | 2014-03-07 | 2014-02-08 | 2014-02-07 | 2014-02-17 | 2014-03-14 | 2014-02-17 | 2014-03-14 | Kirloskar Pneumatic Co. Ltd.,Near Waghere College, Saswad,S.NO.606/1, 606/2A, Saswad Works, Pune-Saswad Road,Taluka Purandar, District Pune - 412 301,, India | 1 | 21 | 405 | Agwan Abhay A. | - | agwanaa@kpcl.net | Chhapkhane Anand S | - | achhapkhane@kpcl.net | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-01-25 | 2014-01-25 | 1 |  | HEMAKSH PATIL
197 | 2015-11-16 | 11:36:47 AM | Sapl0005 | 1 | 1 | B008 | 198 | 208 | verbha | 35 | 0 | N0063 | 2014-01-16 | WELDING FIXTURES FOR SIDE PILLAR | HEMAKSH PATIL | 4 | 2013-10-15 | 2014-05-30 | 2013-11-07 | 2014-05-30 | 2014-01-31 | 2014-02-08 | 2014-02-13 | 2014-02-20 | 2014-02-24 | 2014-02-28 | 2014-01-23 | 2014-02-13 | 2014-02-13 | 2014-03-08 | 2014-02-14 | 2014-02-18 | BHAGIRATH COACH AND METAL FABRICATORS PVT. LTD. | 1 | 20 | 347 | RAJENDRA PATIDAR | 91 99930 91501 | patidarraj2003@yahoo.com | ADITYA SHARMA | - | adityasharma@bhagirathbrothers.co.in | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-01-30 | 2014-01-30 | 1 |  | HEMAKSH PATIL
202 | 2014-03-31 | 5:28:57 PM | Sapl0005 | 1 | 1 | S011 | 203 | 213 | PUOR13004812 | 37 | 0 | P0015 | 2014-01-31 | Break Coil & Brake Shoe Assly LH & RH | HEMAKSH PATIL | 4 | 2014-01-31 | 2014-02-01 | 2014-02-01 | 2014-03-02 | 2014-03-02 | 2014-03-02 | 2014-03-02 | 2014-03-02 | 2014-03-02 | 2014-03-02 | 2014-03-02 | 2014-03-02 | 2014-03-02 | 2014-03-02 | 2014-03-02 | 2014-03-02 | 690,, Udyambag,, Belgaum., Belgaum, PIN : . Karnataka, India | 1 | 17 | 295 | M.N.Patil | 91 831 4218328 | purchase@shantiiron.net | amit | - | amit.k@shantiiron.net | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2014-03-02 | 2014-03-02 | 1 |  | HEMAKSH PATIL
203 | 2018-02-19 | 4:26:57 PM | Sapl0005 | 1 | 1 | M005 | 204 | 214 | MVERB1 | 35 | 0 | N0065 | 2014-02-03 | DRILLING JIG | RAJKUMAR JAGTAP | 2 | 2014-02-03 | 2014-02-12 | 2014-02-12 | 2014-02-20 | 2014-02-21 | 2014-02-28 | 2014-03-07 | 2014-03-12 | 2014-03-12 | 2014-03-14 | 2014-03-01 | 2014-03-07 | 2014-03-15 | 2014-03-17 | 2014-03-07 | 2014-03-12 | M&M CHAKAN | 1 | 21 | 405 | AMOL DESHMUKH | - | DESHMUKH.AMOL4@mahindra.com | DAS DEBJIT | - | DAS.DEBJIT@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-02-18 | 2014-02-18 | 1 |  | RAJKUMAR JAGTAP
206 | 2014-03-31 | 5:29:13 PM | Sapl0005 | 1 | 1 | A016 | 207 | 217 | PO513000423 | 37 | 0 | P0016 | 2014-02-25 | MAGNETIC PLUNGER WITH BREAK COIL | HEMAKSH PATIL | 4 | 2014-02-25 | 2014-02-25 | 2014-02-25 | 2014-02-25 | 2014-02-25 | 2014-02-25 | 2014-02-25 | 2014-02-25 | 2014-02-25 | 2014-02-25 | 2014-02-25 | 2014-02-25 | 2014-02-25 | 2014-02-25 | 2014-02-25 | 2014-02-25 | ALF ENGINEERING COMPANY, HARIDVAR | 1 | 34 | 679 | MEGHA MITTAL | - | meghamittal@alfengineering.com | VED PRAKASH | - | vedprakash@alfengineering.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2014-02-25 | 2014-02-25 | 1 |  | HEMAKSH PATIL
207 | 2014-11-28 | 11:42:24 AM | Sapl0005 | 1 | 1 | A025 | 208 | 218 | PO713000451 | 36 | 0 | E0007 | 2014-02-28 | Annual Maintenance Contract for QG-software | Ashish Mahindre | 11 | 2014-02-28 | 2014-02-28 | 2014-02-28 | 2014-02-28 | 2014-02-28 | 2014-02-28 | 2014-02-28 | 2014-02-28 | 2014-02-28 | 2014-03-04 | 2014-02-28 | 2014-02-28 | 2014-02-28 | 2014-02-28 | 2014-02-28 | 2014-02-28 | Survey No. 320/1 A, 320/1B, Muruthandapali Village, Shoolagiri Post- Hosur Taluka, Pin- 635117 | 1 | 31 | 680 | Madan Kumar S | 0-88831 88933 | madhankumar@alfengineering.com | venkateshgowda | - | venkateshgowda@alfengineering.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-02-28 | 2014-02-28 | 1 |  | Ashish Mahindre
208 | 2014-03-31 | 5:29:39 PM | Sapl0005 | 1 | 1 | S011 | 209 | 219 | PUOR13005495 | 37 | 0 | P0017 | 2014-03-08 | BREAK COIL | HEMAKSH PATIL | 4 | 2014-03-08 | 2014-03-08 | 2014-03-08 | 2014-03-08 | 2014-03-08 | 2014-03-08 | 2014-03-08 | 2014-03-08 | 2014-03-08 | 2014-03-08 | 2014-03-08 | 2014-03-08 | 2014-03-08 | 2014-03-08 | 2014-03-08 | 2014-03-08 | 690, Udyambag Industrial Estate, BELGAUM - 590 008 KARNATAKA - INDIA | 1 | 17 | 295 | M.N.Patil | 831 4218328 | purchase@shantiiron.net | amit | - | amit.k@shantiiron.net | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-03-08 | 2014-03-08 | 1 |  | HEMAKSH PATIL
209 | 2014-03-31 | 5:29:48 PM | Sapl0005 | 1 | 1 | A013 | 210 | 220 | PO613000737 | 37 | 0 | P0018 | 2014-03-08 | Gantry System Contactor | HEMAKSH PATIL | 4 | 2014-03-08 | 2014-03-08 | 2014-03-08 | 2014-03-10 | 2014-03-08 | 2014-03-08 | 2014-03-08 | 2014-03-08 | 2014-03-10 | 2014-03-10 | 2014-03-08 | 2014-03-08 | 2014-03-08 | 2014-03-08 | 2014-03-08 | 2014-03-08 | Plot No. A-1/3,MVML Supplier Park, Phase - IV,, Village NTalP-Bunheo,r Maharashtra, PIN : 410501 | 1 | 21 | 405 | Sunil Lokhande | 99700 67340 | sunillokhande@alfengineering.com | Kalidas Barne | - | kalidasbarne@alfengineering.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-03-08 | 2014-03-08 | 1 |  | HEMAKSH PATIL
210 | 2014-08-30 | 11:42:22 AM | Sapl0005 | 1 | 1 | C002 | 211 | 221 | 10334993 | 34 | 0 | S0045 | 2014-03-08 | Angebot Tragrollen- Walther Flender | SANJAY SHINDE | 13 | 2014-03-08 | 2014-03-10 | 2014-03-11 | 2014-03-18 | 2014-03-18 | 2014-03-18 | 2014-03-19 | 2014-03-19 | 2014-03-20 | 2014-03-20 | 2014-03-19 | 2014-03-19 | 2014-03-21 | 2014-03-21 | 2014-03-21 | 2014-03-21 | COMAU INDIA PVT LTD.BW & A GAT NO 1394, 1395, 1397 Village Shikrapur, Tal shirur 412208 PUNE India | 1 | 21 | 405 | SUJEET KULKARNI | 09923200755 | sujeet.kulkarni@comau.com | AMIT KOKANE | - | amit.kokane@comau.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2014-03-10 | 2014-03-10 | 1 |  | SANJAY SHINDE
211 | 2015-09-09 | 1:56:07 PM | Sapl0005 | 1 | 1 | T002 | 212 | 222 | TAverb | 35 | 0 | N0066 | 2014-03-13 | Modification in design for Safari Storm | RAJKUMAR JAGTAP | 2 | 2014-03-13 | 2015-01-31 | 2014-04-07 | 2015-01-31 | 2014-04-17 | 2014-04-27 | 2014-05-02 | 2014-05-10 | 2014-05-11 | 2014-05-11 | 2014-04-28 | 2014-05-01 | 2014-05-02 | 2014-05-21 | 2014-05-02 | 2014-05-10 | TATA MOTORS LTD. | 1 | 21 | 405 | abhijit.medhekar | - | abhijit.medhekar@tatamotors.com | abhijit.medhekar | - | abhijit.medhekar@tatamotors.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-04-17 | 2014-04-17 | 1 |  | RAJKUMAR JAGTAP
212 | 2015-03-07 | 12:20:57 PM | Sapl0005 | 1 | 1 | S011 | 213 | 223 | PUOR13005644 | 34 | 0 | S0046 | 2014-03-15 | HC3050NH CAP.500KGSX5MTR LI | HEMAKSH PATIL | 4 | 2014-03-17 | 2014-03-17 | 2014-03-17 | 2014-03-17 | 2014-03-17 | 2014-03-17 | 2014-03-17 | 2014-03-17 | 2014-03-17 | 2014-03-17 | 2014-03-17 | 2014-03-17 | 2014-03-17 | 2014-03-17 | 2014-03-17 | 2014-03-17 | 690, Udyambag Industrial Estate, BELGAUM - 590 008 KARNATAKA - INDIA | 1 | 17 | 295 | AMIT | +91 9844577876 | amit.k@shantiiron.net | M.N.PATIL | - | purchase@shantiiron.net | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | incomplete | 2014-03-15 | 2014-03-15 | 1 |  | HEMAKSH PATIL
213 | 2018-01-11 | 1:47:23 PM | Sapl0005 | 1 | 1 | M005 | 214 | 224 | mmverbnw | 35 | 0 | N0067 | 2014-03-17 | Station 100 | PADMASINHA JOSHI | 3 | 2014-03-17 | 2014-05-30 | 2014-04-01 | 2014-05-30 | 2014-04-13 | 2014-04-19 | 2014-04-26 | 2014-04-30 | 2014-05-01 | 2014-05-08 | 2014-04-19 | 2014-04-25 | 2014-04-26 | 2014-05-20 | 2014-04-26 | 2014-04-30 | M&M CHAKAN | 1 | 21 | 405 | JAI VERMA | - | Jai.verma@mahindra.com | DAS DEBJIT | - | DAS.DEBJIT@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-04-01 | 2014-04-01 | 1 |  | PADMASINHA JOSHI
214 | 2018-08-04 | 9:30:51 AM | Sapl0005 | 1 | 1 | S006 | 215 | 225 | inter | 43 | 0 | T0014 | 2014-03-20 | Electric Lifter | Mr. Hemaksh Patil | 4 | 2014-03-20 | 2014-04-04 | 2014-04-04 | 2014-04-20 | 2014-04-20 | 2014-04-28 | 2014-04-28 | 2014-05-02 | 2014-05-02 | 2014-05-10 | 2014-05-10 | 2014-05-30 | 2014-04-28 | 2014-06-10 | 2014-06-10 | 2014-06-17 | synergytech | 1 | 21 | 405 | - | - | sales@synergytechs.com | - | - | sales@synergytechs.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-04-20 | 2014-04-20 | 1 |  | Mr. Hemaksh Patil
215 | 2014-11-28 | 11:42:30 AM | Sapl0005 | 1 | 1 | A013 | 216 | 226 | SCPO13000090 | 36 | 0 | E0008 | 2014-03-21 | SITE VISIT CHARGES FOR MPV KUKA ROBOT SPOTTING PROBLEM | HEMAKSH PATIL | 4 | 2014-03-21 | 2014-03-21 | 2014-03-21 | 2014-03-21 | 2014-03-21 | 2014-03-21 | 2014-03-21 | 2014-03-21 | 2014-03-21 | 2014-03-21 | 2014-03-21 | 2014-03-21 | 2014-03-21 | 2014-03-21 | 2014-03-21 | 2014-03-21 | Plot No. A-1/3,MVML Supplier Park, Phase - IV,, Village Nigoje | 1 | 21 | 405 | Sunil Lokhande | 9970067340 | sunillokhande@alfengineering.com | Kalidas Barne | - | kalidasbarne@alfengineering.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-03-21 | 2014-03-21 | 1 |  | HEMAKSH PATIL
216 | 2014-03-31 | 5:36:38 PM | Sapl0005 | 1 | 1 | A021 | 217 | 227 | 7013004024 | 34 | 0 | S0047 | 2014-03-21 | Load Trolley 63mm | RAJKUMAR JAGTAP | 2 | 2014-03-21 | 2014-03-25 | 2014-03-25 | 2014-03-27 | 2014-03-27 | 2014-03-27 | 2014-03-27 | 2014-03-27 | 2014-03-27 | 2014-03-27 | 2014-03-27 | 2014-03-27 | 2014-03-27 | 2014-03-27 | 2014-03-27 | 2014-03-27 | AUTOCOMPS CORPORATION PANSE PVT LTD (MOSHI UNIT II) Gat No.198, Village Borhadewadi, Dehu-Alandi Road, Moshi Pune- 412105 | 1 | 21 | 405 | YOGESH SHIRSAT | - | papl1.purchase2@pansegroup.com | Yogesh Shirsat | - | papl1.purchase2@pansegroup.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-03-27 | 2014-03-27 | 1 |  | RAJKUMAR JAGTAP
217 | 2016-05-12 | 12:32:54 PM | Sapl0005 | 1 | 1 | M017 | 218 | 228 | C/00269 | 35 | 0 | N0068 | 2014-03-21 | P405 Cargo | PADMASINHA JOSHI | 3 | 2014-03-21 | 2014-03-31 | 2014-03-31 | 2014-04-04 | 2014-04-04 | 2014-04-04 | 2014-04-04 | 2014-04-04 | 2014-04-04 | 2014-04-04 | 2014-04-04 | 2014-04-04 | 2014-04-04 | 2014-04-04 | 2014-04-04 | 2014-04-04 | A-1/5, MVML SUPPLIER PARK, MIDC CHAKAN, PHASE-IV, - 410501 Pincode - 410501 INDIA | 1 | 21 | 405 | MILIND WAGHODE | - | milind@munginsk.com | prakash | - | prakash@mungiindia.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-03-22 | 2014-03-22 | 1 |  | PADMASINHA JOSHI
218 | 2018-01-11 | 1:47:38 PM | Sapl0005 | 1 | 1 | M005 | 219 | 229 | mverbsa | 35 | 0 | N0069 | 2014-03-25 | SA40 | PADMASINHA JOSHI | 3 | 2014-03-25 | 2014-05-30 | 2014-04-05 | 2014-05-30 | 2014-04-10 | 2014-04-16 | 2014-04-17 | 2014-04-19 | 2014-04-20 | 2014-04-23 | 2014-04-24 | 2014-04-29 | 2014-04-17 | 2014-05-07 | 2014-04-17 | 2014-04-19 | M&M,CHAKAN | 1 | 21 | 405 | JAI VERMA | - | Jai.verma@mahindra.com | DAS DEBJIT | - | DAS.DEBJIT@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-04-05 | 2014-04-03 | 1 |  | PADMASINHA JOSHI
220 | 2014-05-06 | 2:23:12 PM | Sapl0005 | 1 | 1 | C002 | 221 | 231 | 10337244 | 38 | 0 | J0060 | 2014-03-27 | 7540-1-1-BASE PLATE | MILIND TERAWDE | 13 | 2014-03-27 | 2014-03-29 | 2014-03-30 | 2014-03-31 | 2014-04-01 | 2014-04-03 | 2014-05-03 | 2014-05-03 | 2014-04-04 | 2014-04-04 | 2014-04-04 | 2014-04-04 | 2014-04-04 | 2014-04-04 | 2014-05-03 | 2014-05-03 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | manish.raval | - | manish.raval@comau.com | manish.raval | - | manish.raval@comau.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-03-29 | 2014-03-29 | 1 |  | MILIND TERAWDE
223 | 2014-05-06 | 2:23:41 PM | Sapl0005 | 1 | 1 | C002 | 224 | 234 | 10336963 | 38 | 0 | J0061 | 2014-03-29 | BASE FRMAE (OG-11)SO-288 | MILIND TERAWDE | 13 | 2014-03-29 | 2014-03-30 | 2014-03-30 | 2014-03-30 | 2014-03-31 | 2014-04-03 | 2014-04-03 | 2014-04-03 | 2014-04-04 | 2014-04-04 | 2014-04-03 | 2014-04-03 | 2014-04-05 | 2014-04-05 | 2014-04-03 | 2014-04-03 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | PRASAD Dheeraj (COMAU) | - | dheeraj.prasad@comau.com | SANTOSH SAPARE | - | santosh.sapare@comau.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-03-30 | 2014-03-30 | 1 |  | MILIND TERAWDE
224 | 2015-01-12 | 12:38:29 PM | Sapl0005 | 1 | 1 | A026 | 225 | 235 | VERBAL | 37 | 0 | P0019 | 2014-03-22 | Scrap | Tejas Lasulkar | 1 | 2014-03-22 | 2014-03-22 | 2014-03-22 | 2014-03-22 | 2014-03-22 | 2014-03-22 | 2014-03-22 | 2014-03-22 | 2014-03-22 | 2014-03-22 | 2014-03-22 | 2014-03-22 | 2014-03-22 | 2014-03-22 | 2014-03-22 | 2014-03-22 | Katraj | 1 | 21 | 405 | Mr.khan | - | khan@arihant.com | Mr.khan | - | khan@arihant.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-03-22 | 2014-03-22 | 1 |  | Tejas Lasulkar
225 | 2015-01-12 | 12:31:35 PM | Sapl0005 | 1 | 1 | T002 | 226 | 236 | 9000027324 | 35 | 0 | N0071 | 2014-03-29 | Air Hoist with Tackle for narrow subassembly for Ultra BIW | RAJKUMAR JAGTAP | 2 | 2014-03-29 | 2014-05-15 | 2014-05-15 | 2014-05-20 | 2014-03-29 | 2014-03-29 | 2014-03-29 | 2014-03-29 | 2014-03-29 | 2014-03-29 | 2014-03-29 | 2014-03-29 | 2014-03-29 | 2014-03-29 | 2014-03-29 | 2014-03-29 | CV PUN Direct Mat Tata Motors Ltd. Pune PIMPRI - 411018 | 1 | 21 | 405 | abhijit.medhekar | - | abhijit.medhekar@tatamotors.com | umesh.patil | - | umesh.patil@tatamotors.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-03-29 | 2014-03-29 | 1 |  | RAJKUMAR JAGTAP
226 | 2015-01-12 | 12:38:52 PM | Sapl0005 | 1 | 1 | A026 | 227 | 237 | Verb1 | 37 | 0 | P0020 | 2014-03-29 | Scrap material | Tejas Lasulkar | 1 | 2014-03-29 | 2014-03-29 | 2014-03-29 | 2014-03-29 | 2014-03-29 | 2014-03-29 | 2014-03-29 | 2014-03-29 | 2014-03-29 | 2014-03-29 | 2014-03-29 | 2014-03-29 | 2014-03-29 | 2014-03-29 | 2014-03-29 | 2014-03-29 | Arihant , katraj | 1 | 21 | 405 | Mr.khan | - | khan@arihant.com | Mr.khan | - | khan@arihant.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-03-29 | 2014-03-29 | 1 |  | Tejas Lasulkar
227 | 2015-03-07 | 12:18:06 PM | Sapl0005 | 1 | 1 | M005 | 228 | 238 | A007/A72/3200058851 | 35 | 0 | N0072 | 2013-04-08 | MSW2 | PADMASINHA JOSHI | 3 | 2013-04-08 | 2013-04-20 | 2013-04-20 | 2013-04-30 | 2013-05-01 | 2013-05-20 | 2013-06-01 | 2013-06-15 | 2013-06-16 | 2013-06-26 | 2013-05-21 | 2013-05-30 | 2013-06-27 | 2013-07-15 | 2013-06-01 | 2013-06-15 | Mahindra & Mahindra | 1 | 21 | 405 | Rajesh Kumar | - | RAJESHKUMAR@MAHINDRA.COM | RAJESH KUMAR | - | RAJESHKUMAR@MAHINDRA.COM | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2013-04-25 | 2013-04-25 | 1 |  | PADMASINHA JOSHI
230 | 2018-05-08 | 1:19:57 PM | Sapl0005 | 1 | 1 | N003 | 231 | 241 | 011415CPMTOT008 | 34 | 0 | S0050 | 2014-04-05 | TOOL TROLLEY & LOAD TROLLEY | RAJKUMAR JAGTAP | 2 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | NEEL AUTO PVT. LTD., HOSUR | 1 | 31 | 680 | sathish.narashiman | 8220007523 | sathish.narashiman@jbm-group.com | ravindran.rengasamy | - | ravindran.rengasamy@jbm-group.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | cmplte | 2014-04-05 | 2014-04-05 | 1 |  | RAJKUMAR JAGTAP
231 | 2015-01-12 | 12:14:48 PM | Sapl0005 | 1 | 1 | C002 | 232 | 242 | 10338955 | 38 | 0 | J0062 | 2014-04-09 | Fencing For COSMA | MILIND TERAWDE | 13 | 2014-04-09 | 2014-04-12 | 2014-04-12 | 2014-04-14 | 2014-04-14 | 2014-04-23 | 2014-04-24 | 2014-04-24 | 2014-04-25 | 2014-04-25 | 2014-04-23 | 2014-04-24 | 2014-04-26 | 2014-04-26 | 2014-04-24 | 2014-04-24 | CIL, Shikhrapur | 1 | 21 | 405 | baburao.ratkal | - | baburao.ratkal@comau.com | SUJEET KULKARNI | - | sujeet.kulkarni@comau.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-04-14 | 2014-04-14 | 1 |  | MILIND TERAWDE
232 | 2014-08-30 | 3:55:20 PM | Sapl0005 | 1 | 1 | C002 | 233 | 243 | 10339233 | 43 | 0 | T0015 | 2014-04-14 | PLC PANEL | HEMAKSH PATIL | 4 | 2014-04-14 | 2014-06-25 | 2014-04-22 | 2014-06-25 | 2014-04-26 | 2014-05-05 | 2014-05-09 | 2014-05-14 | 2014-05-15 | 2014-05-15 | 2014-05-05 | 2014-05-08 | 2014-05-09 | 2014-05-19 | 2014-05-09 | 2014-05-10 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | NILESH KHAIRNAR | 91206678036 | khairnar.nilesh@comau.com | SUJEET KULKARNI | - | kulkarni.sujeet@comau.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-04-22 | 2014-04-22 | 1 |  | HEMAKSH PATIL
233 | 2014-05-06 | 2:24:14 PM | Sapl0005 | 1 | 2 | C002 | 234 | 244 | 10340018 | 38 | 0 | J0063 | 2014-04-21 | ROBOT PEDESTAL | MILIND TERAWDE | 13 | 2014-04-21 | 2014-04-23 | 2014-04-23 | 2014-04-27 | 2014-04-23 | 2014-04-27 | 2014-04-27 | 2014-04-27 | 2014-04-28 | 2014-04-28 | 2014-04-26 | 2014-04-27 | 2014-04-29 | 2014-04-29 | 2014-04-27 | 2014-04-27 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 | 1 | 21 | 405 | Soumyaranjan Priyadarshi | 8149144553 | soumyaranjan.priyadarshi@comau.com | SANTOSH SAPARE | - | santosh.sapare@comau.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 1 |  | 1 | COMPLETE | 2014-04-24 | 2014-04-24 | 1 |  | MILIND TERAWDE
234 | 2016-03-31 | 11:17:55 AM | Sapl0005 | 1 | 2 | S006 | 235 | 245 | verbal2 | 34 | 0 | S0051 | 2014-04-21 | Hoist 500kg , Hoist 2 ton | HEMAKSH PATIL | 4 | 2014-04-18 | 2015-06-30 | 2014-05-01 | 2015-06-30 | 2014-05-11 | 2014-05-17 | 2014-05-18 | 2014-05-24 | 2014-05-31 | 2014-05-31 | 2014-05-25 | 2014-05-31 | 2014-05-18 | 2014-05-31 | 2014-05-23 | 2014-05-23 | Synergytech Automation | 1 | 21 | 405 | - | - | sales@synergytechs.com | - | - | sales@synergytechs.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-04-21 | 2014-04-21 | 1 |  | HEMAKSH PATIL
235 | 2014-12-08 | 2:30:46 PM | Sapl0005 | 1 | 2 | A027 | 236 | 246 | UKD05_PO1415_ 000497 | 37 | 0 | P0021 | 2014-04-29 | MAGNETIC PLUNGER WITH BREAK COIL 415v | HEMAKSH PATIL | 4 | 2014-05-29 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | 2014-05-01 | Autoline Industries Ltd. (Plot No.5) Plot No.05,Sector 11, (Tata Vendor Park), Sidcul, IIE, Pantnagar, Rudrapur263153,Uttarakhan, India | 1 | 34 | 679 | Gaurav Bisht | 9634093368 | gaurav.bisht@autolineind.com | dattatraya.kute | - | dattatraya.kute@autolineind.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-05-01 | 2014-05-01 | 1 |  | HEMAKSH PATIL
236 | 2014-12-08 | 2:30:30 PM | Sapl0005 | 1 | 2 | S011 | 237 | 247 | PUOR14000454 | 37 | 0 | P0022 | 2014-04-29 | BREAK COIL | HEMAKSH PATIL | 4 | 2014-04-29 | 2014-04-29 | 2014-04-29 | 2014-04-29 | 2014-04-29 | 2014-04-29 | 2014-04-29 | 2014-04-29 | 2014-04-29 | 2014-04-29 | 2014-04-29 | 2014-04-29 | 2014-04-29 | 2014-04-29 | 2014-04-29 | 2014-04-29 | 690, Udyambag Industrial Estate, BELGAUM - 590 008 KARNATAKA - INDIA | 1 | 17 | 295 | M.N.Patil | - | purchase@shantiiron.net | M.N.PATIL | - | purchase@shantiiron.net | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-04-29 | 2014-04-29 | 1 |  | HEMAKSH PATIL
237 | 2014-11-28 | 11:42:42 AM | Sapl0005 | 1 | 2 | C002 | 238 | 248 | 60010712 | 36 | 0 | E0009 | 2014-05-03 | Installation & Commissioning of Cosma | SANJAY SHINDE | 13 | 2014-05-08 | 2014-05-08 | 2014-05-08 | 2014-05-08 | 2014-05-08 | 2014-05-08 | 2014-05-08 | 2014-05-08 | 2014-05-08 | 2014-05-08 | 2014-05-08 | 2014-05-08 | 2014-05-08 | 2014-05-08 | 2014-05-08 | 2014-05-08 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | SUJEET KULKARNI | - | sujeet.kulkarni@comau.com | AMIT KOKANE | - | amit.kokane@comau.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2014-05-08 | 2014-05-08 | 1 |  | SANJAY SHINDE
238 | 2014-05-06 | 2:35:21 PM | Sapl0005 | 1 | 2 | C002 | 239 | 249 | 10341157 | 34 | 0 | S0052 | 2014-05-03 | Anchor Bolt M12 X 100# 800 Set | SANJAY SHINDE | 13 | 2014-05-03 | 2014-05-10 | 2014-05-11 | 2014-05-15 | 2014-05-15 | 2014-05-15 | 2014-05-15 | 2014-05-15 | 2014-05-15 | 2014-05-15 | 2014-05-15 | 2014-05-15 | 2014-05-15 | 2014-05-15 | 2014-05-15 | 2014-05-15 | COMAU INDIA PVT LTD.BW & A GAT NO 1394, 1395, 1397 Village Shikrapur, Tal shirur 412208 PUNE India | 1 | 21 | 405 | SUJEET KULKARNI | - | sujeet.kulkarni@comau.com | AMIT KOKANE | - | amit.kokane@comau.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-05-10 | 2014-05-10 | 1 |  | SANJAY SHINDE
239 | 2015-01-12 | 12:39:43 PM | Sapl0005 | 1 | 2 | W003 | 240 | 250 | 0036/P6/14-15 | 37 | 0 | P0023 | 2014-05-03 | MAGNETIC PLUNGER WITH BREAK COIL & TANSFORMER | HEMAKSH PATIL | 4 | 2014-05-03 | 2014-05-10 | 2014-05-10 | 2014-05-10 | 2014-05-10 | 2014-05-10 | 2014-05-10 | 2014-05-10 | 2014-05-10 | 2014-05-10 | 2014-05-10 | 2014-05-10 | 2014-05-10 | 2014-05-10 | 2014-05-10 | 2014-05-10 | Windals Auto Pvt. Ltd. - Unit 8 Gat No 203,At Murhe Vasti Tal-Khed,Post-Kuruli,Chakan Pune-410501 | 1 | 21 | 405 | deepak.rawat | 8605017919 | deepak.rawat@windalsauto.com | arun.doke | - | arun.doke@windalsauto.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-05-10 | 2014-05-10 | 1 |  | HEMAKSH PATIL
240 | 2014-05-06 | 2:32:14 PM | Sapl0005 | 1 | 2 | A015 | 241 | 251 | PO114000172 | 37 | 0 | P0024 | 2014-05-05 | HOIST SPARES | HEMAKSH PATIL | 4 | 2014-05-05 | 2014-05-05 | 2014-05-05 | 2014-05-05 | 2014-05-05 | 2014-05-05 | 2014-05-05 | 2014-05-05 | 2014-05-05 | 2014-05-05 | 2014-05-05 | 2014-05-05 | 2014-05-05 | 2014-05-05 | 2014-05-05 | 2014-05-05 | Plot No. E-60/61/62,, MIDC,, Ambad,, Nasik, PIN : 422010. Maharashtra, India | 1 | 21 | 402 | ANIL PATIL | - | sujitnair@alfengineering.com | ANIL PATIL | - | sujitnair@alfengineering.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-05-05 | 2014-05-05 | 1 |  | HEMAKSH PATIL
241 | 2014-06-03 | 4:57:18 PM | Sapl0005 | 1 | 2 | A021 | 243 | 252 | acpplverb | 34 | 0 | S0053 | 2014-05-09 | LONG RAIL C63, CROSS RAIL C63 & TROLLEY SET | RAJKUMAR JAGTAP | 4 | 2014-05-09 | 2014-05-22 | 2014-05-16 | 2014-05-22 | 2014-05-16 | 2014-05-16 | 2014-05-16 | 2014-05-16 | 2014-05-16 | 2014-05-23 | 2014-05-16 | 2014-05-16 | 2014-05-16 | 2014-05-16 | 2014-05-16 | 2014-05-16 | ACPPL MOSHI PLANT | 1 | 21 | 405 | YOGESH SHIRSAT | - | papl1.purchase2@pansegroup.com | Yogesh Shirsat | - | papl1.purchase2@pansegroup.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | COMPLETED | 2014-05-09 | 2014-05-09 | 1 |  | RAJKUMAR JAGTAP
242 | 2014-08-30 | 11:43:38 AM | Sapl0005 | 1 | 2 | N003 | 244 | 253 | 011415CPCAPX015 | 34 | 0 | S0054 | 2014-05-09 | LONG RAIL C63 & CROSS RAIL C63 | RAJKUMAR JAGTAP | 2 | 2014-05-09 | 2014-05-16 | 2014-05-16 | 2014-05-16 | 2014-05-16 | 2014-05-16 | 2014-05-16 | 2014-05-16 | 2014-05-19 | 2014-05-20 | 2014-05-16 | 2014-05-16 | 2014-05-26 | 2014-05-29 | 2014-05-22 | 2014-05-15 | Neel Auto Pvt Ltd No.1,2,5&6,TVS Indl Estate, Harita,Hosur-635109 | 1 | 31 | 680 | N.Sathish | 91-8220007523 | sathish.narashiman@jbm-group.com | ravindran.rengasamy | - | ravindran.rengasamy@jbm-group.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | complte | 2014-05-12 | 2014-05-12 | 1 |  | RAJKUMAR JAGTAP
243 | 2015-01-12 | 12:31:24 PM | Sapl0005 | 1 | 2 | J007 | 245 | 254 | 4300014205 | 35 | 0 | N0073 | 2014-05-10 | Checking fixtures for B6 | Prajyot Genji | 3 | 2014-05-10 | 2014-06-26 | 2014-05-12 | 2014-06-26 | 2014-05-20 | 2014-05-30 | 2014-06-13 | 2014-06-15 | 2014-06-16 | 2014-06-21 | 2014-05-30 | 2014-06-13 | 2014-06-13 | 2014-06-30 | 2014-06-13 | 2014-06-15 | Jay Bharat Maruti Limited Plot no.15&22, Sector-3A, Maruti Supplier Park, IMT Manesar 122050 Gurgaon | 1 | 13 | 171 | shersingh | 09999301363 | shersingh@jbm.co.in | SANJAY MURGAI | - | smurgai@jbm.co.in | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-05-16 | 2014-05-16 | 1 |  | Prajyot Genji
244 | 2014-12-08 | 2:30:07 PM | Sapl0005 | 1 | 2 | S011 | 246 | 255 | PUOR14000638 | 37 | 0 | P0025 | 2014-05-12 | BREAK COIL | HEMAKSH PATIL | 4 | 2014-05-12 | 2014-05-24 | 2014-05-24 | 2014-05-24 | 2014-05-24 | 2014-05-24 | 2014-05-24 | 2014-05-24 | 2014-05-24 | 2014-05-24 | 2014-05-24 | 2014-05-24 | 2014-05-24 | 2014-05-24 | 2014-05-24 | 2014-05-24 | 690, Udyambag Industrial Estate, BELGAUM - 590 008 KARNATAKA - INDIA | 1 | 17 | 295 | M.N.Patil | +91 831 4218328 | purchase@shantiiron.net | M.N.PATIL | - | purchase@shantiiron.net | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-05-12 | 2014-05-12 | 1 |  | HEMAKSH PATIL
247 | 2018-02-19 | 4:27:41 PM | Sapl0005 | 1 | 2 | M001 | 249 | 258 | 3100344096 | 35 | 0 | N0075 | 2014-05-22 | ECN MATERIAL AS PER BOM - 13F466 | PADMASINHA JOSHI | 3 | 2014-05-22 | 2014-05-24 | 2014-05-24 | 2014-05-24 | 2014-05-24 | 2014-05-24 | 2014-05-24 | 2014-05-24 | 2014-05-24 | 2014-05-24 | 2014-05-24 | 2014-05-24 | 2014-05-24 | 2014-05-24 | 2014-05-24 | 2014-05-24 | M&M Automotive Sector Nasik Plant-2 Plant II, 80,MIDC ,Satpur, Nasik 422007 | 1 | 21 | 402 | Snehal Malge | 91 253 6613052 | MALGE.SNEHAL@mahindra.com | Snehal Malge | - | MALGE.SNEHAL@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-05-24 | 2014-05-24 | 1 |  | PADMASINHA JOSHI
248 | 2015-01-12 | 12:35:21 PM | Sapl0005 | 1 | 2 | J007 | 250 | 259 | verbal123 | 35 | 0 | N0076 | 2014-05-28 | CHECKING FIXTURES | Prajyot Genji | 3 | 2014-05-10 | 2014-06-26 | 2014-05-12 | 2014-06-26 | 2014-05-20 | 2014-05-30 | 2014-06-13 | 2014-06-15 | 2014-06-16 | 2014-06-21 | 2014-05-30 | 2014-06-13 | 2014-06-13 | 2014-06-30 | 2014-06-13 | 2014-06-15 | Plot no.15&22, Sector-3A, Maruti Supplier Park, IMT Manesar 122050 Gurgaon INDIA | 1 | 13 | 171 | Rajesh ajmera | 9873142039 | rajmera@jbm.co.in | RK.Dogra | - | RK.Dogra@Jbm.co.in | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-05-30 | 2014-05-30 | 1 |  | Prajyot Genji
249 | 2015-01-12 | 12:35:33 PM | Sapl0005 | 1 | 2 | J007 | 251 | 260 | verb28 | 35 | 0 | N0077 | 2014-05-28 | CHECKING FIXTURES | Prajyot Genji | 3 | 2014-05-10 | 2014-06-26 | 2014-05-12 | 2014-06-26 | 2014-05-20 | 2014-05-30 | 2014-06-13 | 2014-06-15 | 2014-06-13 | 2014-06-21 | 2014-06-30 | 2014-06-13 | 2014-06-13 | 2014-06-30 | 2014-06-13 | 2014-06-16 | Plot no.15&22, Sector-3A, Maruti Supplier Park, IMT Manesar 122050 Gurgaon INDIA | 1 | 13 | 171 | Rajesh ajmera | - | rajmera@jbm.co.in | RK.Dogra | - | RK.Dogra@Jbm.co.in | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-05-28 | 2014-05-28 | 1 |  | Prajyot Genji
250 | 2015-01-12 | 12:19:35 PM | Sapl0005 | 1 | 2 | C002 | 252 | 261 | 10344452 | 38 | 0 | J0064 | 2014-06-02 | NON STANDARD FENCE | MILIND TERAWDE | 13 | 2014-06-02 | 2014-06-05 | 2014-06-05 | 2014-06-05 | 2014-06-05 | 2014-06-05 | 2014-06-05 | 2014-06-05 | 2014-06-05 | 2014-06-05 | 2014-06-05 | 2014-06-05 | 2014-06-05 | 2014-06-05 | 2014-06-05 | 2014-06-05 | CIPL,SHIKRAPUR,PUNE | 1 | 21 | 405 | SUJEET KULKARNI | - | sujeet.kulkarni@comau.com | BISHNOI Sudhir | - | sudhir.bishnoi@comau.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-06-03 | 2014-06-03 | 1 |  | MILIND TERAWDE
251 | 2015-01-12 | 12:19:50 PM | Sapl0005 | 1 | 2 | C002 | 253 | 262 | 10344496 | 38 | 0 | J0065 | 2014-06-03 | NON STD-FENCE-500L | MILIND TERAWDE | 13 | 2014-06-03 | 2014-06-06 | 2014-06-06 | 2014-06-06 | 2014-06-06 | 2014-06-09 | 2014-06-10 | 2014-06-10 | 2014-06-10 | 2014-06-10 | 2014-06-10 | 2014-06-10 | 2014-06-10 | 2014-06-10 | 2014-06-09 | 2014-06-09 | COMAU INDIA PVT. LTD., SHIKHRAPUR | 1 | 21 | 405 | SUJEET KULKARNI | - | sujeet.kulkarni@comau.com | SUJEET KULKARNI | - | sujeet.kulkarni@comau.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-06-04 | 2014-06-04 | 1 |  | MILIND TERAWDE
252 | 2016-01-06 | 1:52:20 PM | Sapl0005 | 1 | 2 | A025 | 254 | 263 | REVA1 | 35 | 0 | N0078 | 2014-06-03 | NEW FIXTURES FOR CAGE ASSLY & NEW FIXTURES FOR BODY FRAME ASSLY | Kiran Kadam | 3 | 2014-06-05 | 2015-10-31 | 2014-06-16 | 2015-10-31 | 2014-06-27 | 2015-01-15 | 2014-07-10 | 2014-07-15 | 2014-07-15 | 2014-11-30 | 2014-07-03 | 2014-07-10 | 2014-07-10 | 2014-08-02 | 2014-07-10 | 2014-07-14 | ALF ENGINEERING HOSUR | 1 | 31 | 680 | DINESH RAUT | 09325379844 | dineshraut@alfengineering.com | VIVEK PATIL | - | vivekpatil@alfengineering.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-06-23 | 2014-06-23 | 1 |  | Kiran Kadam
253 | 2015-02-13 | 2:41:44 PM | Sapl0005 | 1 | 2 | A025 | 255 | 264 | REVA2 | 35 | 0 | N0079 | 2014-06-03 | MODIFICATION IN FLOOR ASSLY & FRONT ASSLY | Kiran Kadam | 3 | 2014-06-03 | 2014-11-30 | 2014-06-16 | 2014-11-30 | 2014-06-23 | 2014-11-30 | 2014-07-06 | 2014-07-12 | 2014-07-15 | 2014-11-30 | 2014-06-30 | 2014-07-05 | 2014-07-06 | 2014-08-09 | 2014-07-06 | 2014-07-12 | ALF ENGG., HOSUR | 1 | 31 | 680 | DINESH RAUT | 09325379844 | dineshraut@alfengineering.com | VIVEK PATIL | - | vivekpatil@alfengineering.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-06-23 | 2014-06-23 | 1 |  | Kiran Kadam
254 | 2014-08-30 | 11:51:24 AM | Sapl0005 | 1 | 2 | F007 | 256 | 265 | 4300014494 | 34 | 0 | S0056 | 2014-06-06 | RAIL SET | RAJKUMAR JAGTAP | 2 | 2014-06-06 | 2014-06-13 | 2014-06-13 | 2014-06-13 | 2014-06-13 | 2014-06-13 | 2014-06-13 | 2014-06-13 | 2014-06-13 | 2014-06-13 | 2014-06-13 | 2014-06-13 | 2014-06-13 | 2014-06-13 | 2014-06-13 | 2014-06-13 | FJM CYLINDERS PVT. LTD., PLOT 360, SECTOR 3, IMT, BAWAL | 1 | 13 | 183 | SANJAY MURGAI | - | smurgai@jbm.co.in | TUSHAR | - | purchase@fjmcylinders.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-06-06 | 2014-06-06 | 1 |  | RAJKUMAR JAGTAP
256 | 2014-12-08 | 2:27:08 PM | Sapl0005 | 1 | 2 | M009 | 259 | 267 | 3200079066 | 34 | 0 | S0058 | 2014-06-16 | LONG RAIL C63 | RAJKUMAR JAGTAP | 2 | 2014-06-16 | 2014-06-21 | 2014-06-21 | 2014-06-21 | 2014-06-21 | 2014-06-21 | 2014-06-21 | 2014-06-21 | 2014-06-23 | 2014-06-23 | 2014-06-21 | 2014-06-21 | 2014-06-24 | 2014-06-24 | 2014-06-23 | 2014-06-23 | MUSCO STAMPINGS MUSCO STAMPINGS AT & POST KANHE, TALUKA MAVAL | 1 | 21 | 405 | jagtap.sandip | 91-95525 04796 | jagtap.sandip@mahindra.com | ANAND SATALKAR | - | SATALKAR.ANAND@mahindra.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-06-21 | 2014-06-21 | 1 |  | RAJKUMAR JAGTAP
257 | 2014-11-29 | 9:36:05 AM | Sapl0005 | 1 | 2 | N003 | 260 | 268 | 011415CPCAPX055 | 36 | 0 | E0010 | 2014-06-16 | I & C LONG RAIL C63 & CROSS RAIL C63 | RAJKUMAR JAGTAP | 2 | 2014-06-16 | 2014-06-16 | 2014-06-16 | 2014-06-16 | 2014-06-16 | 2014-06-16 | 2014-06-16 | 2014-06-16 | 2014-06-16 | 2014-06-16 | 2014-06-16 | 2014-06-16 | 2014-06-16 | 2014-06-16 | 2014-06-16 | 2014-06-16 | Neel Auto Pvt Ltd No.1,2,5&6,TVS Indl Estate, Harita,Hosur-635109 | 1 | 31 | 680 | N.Sathish | 8220007523 | sathish.narashiman@jbm-group.com | N.Sathish | - | sathish.narashiman@jbm-group.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-06-16 | 2014-06-16 | 1 |  | RAJKUMAR JAGTAP
260 | 2015-01-12 | 12:47:30 PM | Sapl0005 | 1 | 2 | J015 | 263 | 271 | 4300014954 | 34 | 0 | S0059 | 2014-07-05 | LONG RAIL C63, CROSS RAIL C63 & TROLLEY SET | RAJKUMAR JAGTAP | 2 | 2014-07-05 | 2014-07-19 | 2014-07-19 | 2014-07-23 | 2014-07-23 | 2014-07-25 | 2014-07-25 | 2014-07-25 | 2014-07-26 | 2014-07-26 | 2014-07-25 | 2014-07-25 | 2014-07-25 | 2014-07-25 | 2014-07-29 | 2014-07-29 | JBM AUTO SYSTEM PRIVATE LIMITED Plot No AV-13, Bol Industrial Estate, GIDC, Sanand-II, 382170 Ahmedabad, Gujarat INDIA | 1 | 12 | 142 | Rohit Rakheja | 09999702774 | rohit.rakheja@jbm.co.in | SANJAY MURGAI | - | smurgai@jbm.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-07-25 | 2014-07-25 | 1 |  | RAJKUMAR JAGTAP
261 | 2015-01-12 | 12:07:34 PM | Sapl0005 | 1 | 2 | J015 | 264 | 272 | 4100034942 | 36 | 0 | E0011 | 2014-07-05 | Installation & Commissioning of rails | RAJKUMAR JAGTAP | 2 | 2014-07-05 | 2014-07-26 | 2014-07-26 | 2014-07-26 | 2014-07-26 | 2014-07-26 | 2014-07-26 | 2014-07-26 | 2014-07-26 | 2014-07-26 | 2014-07-26 | 2014-07-26 | 2014-07-29 | 2014-08-02 | 2014-07-28 | 2014-07-28 | Plot No AV-13, Bol Industrial Estate, GIDC, Sanand-II, 382170 Ahmedabad, Gujarat INDIA | 1 | 12 | 142 | Rohit Rakheja | 09999702774 | rohit.rakheja@jbm.co.in | SANJAY MURGAI | - | smurgai@jbm.co.in | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-07-17 | 2014-07-17 | 1 |  | RAJKUMAR JAGTAP
274 | 2015-01-12 | 12:37:32 PM | Sapl0005 | 1 | 2 | J006 | 277 | 286 | 4300014531 | 35 | 0 | N0082 | 2014-08-04 | I BEAM CLAMP WITH BOLT WASHER | MANOJ SHINDE | 3 | 2014-08-04 | 2014-08-04 | 2014-08-04 | 2014-08-04 | 2014-08-04 | 2014-08-04 | 2014-08-04 | 2014-08-04 | 2014-08-04 | 2014-08-04 | 2014-08-04 | 2014-08-04 | 2014-08-04 | 2014-08-04 | 2014-08-04 | 2014-08-04 | jAY BHARAT MARUTI LTD. PLANT1 | 1 | 13 | 171 | JRS YADAV | - | jyadav@jbm.co.in | JC PATHAK | - | jcpathak@jbm.co.in | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-09-04 | 2014-08-04 | 1 |  | MANOJ SHINDE
285 | 2015-01-17 | 4:28:42 PM | Sapl0005 | 1 | 2 | S024 | 288 | 297 | SDE/PUR/SR/0017 | 34 | 0 | S0074 | 2014-09-19 | Gunrail | RAJKUMAR JAGTAP | 2 | 2014-09-19 | 2014-09-19 | 2014-09-19 | 2014-09-19 | 2014-09-19 | 2014-09-19 | 2014-09-19 | 2014-09-19 | 2014-09-19 | 2014-09-19 | 2014-09-19 | 2014-09-19 | 2014-09-19 | 2014-09-19 | 2014-09-19 | 2014-09-19 | S.D ENGINEERSTECH PW.LTD, PLOT NO I77 SEGTOR. 24.FARIDABAD HARYANA 127OO5 | 1 | 13 | 169 | nishant soni | - | nishantp@sdengineers.in | saroj parida | - | saroj.parida@sdengineers.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-09-19 | 2014-09-19 | 1 |  | RAJKUMAR JAGTAP
287 | 2018-06-22 | 10:59:20 AM | Sapl0005 | 1 | 2 | A029 | 290 | 299 | MH_PO14-15_000722 | 35 | 0 | N0083 | 2014-09-26 | Welding Fixtures For Cowl Project | Prajyot Genji | 3 | 2014-09-26 | 2015-09-30 | 2014-10-08 | 2015-09-30 | 2014-10-15 | 2015-01-31 | 2014-10-27 | 2014-10-31 | 2014-11-01 | 2014-11-03 | 2014-10-23 | 2014-10-28 | 2014-10-27 | 2014-11-07 | 2014-11-03 | 2014-11-03 | Autoline lndustries Limited (MH) Gat No . 61312 , Chatan - Talegaon Road, Mahalunge , Tal- Khed, Puns-4l0501, Maharastra, lndia. | 1 | 21 | 405 | Sujeet Chaskar | - | sujeet.chaskar@autolineind.com | Satish.Satpute | - | Satish.Satpute@autolineind.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | close | 2014-10-27 | 2014-10-27 | 1 |  | Prajyot Genji
288 | 2018-06-22 | 10:59:33 AM | Sapl0005 | 1 | 2 | A029 | 292 | 301 | autoline_verb | 35 | 0 | N0084 | 2014-09-26 | Welding Fixtures | Prajyot Genji | 3 | 2014-09-26 | 2015-09-30 | 2014-10-03 | 2015-09-30 | 2014-10-17 | 2015-01-15 | 2014-10-24 | 2014-10-28 | 2014-10-29 | 2014-11-01 | 2014-11-03 | 2014-11-06 | 2014-10-24 | 2014-11-11 | 2014-11-01 | 2014-11-01 | Autoline lndustries Limited (MH) Gat No . 61312 , Chakan - Talegaon Road, Mahalunge , Tal- Khed, Puns-4l0501, Maharastra, lndh. | 1 | 21 | 405 | Sujeet Chaskar | - | sujeet.chaskar@autolineind.com | Satish.Satpute | - | Satish.Satpute@autolineind.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | close | 2014-10-17 | 2014-10-17 | 1 |  | Prajyot Genji
291 | 2015-06-13 | 4:50:37 PM | Sapl0005 | 1 | 2 | K007 | 294 | 303 | 2411503303 | 43 | 0 | T0017 | 2014-10-07 | SINGLE STAGE CONTROL PANEL | HEMAKSH PATIL | 4 | 2014-10-07 | 2014-10-13 | 2014-10-13 | 2014-10-18 | 2014-10-18 | 2014-10-22 | 2014-10-22 | 2014-10-25 | 2014-10-25 | 2014-10-25 | 2014-10-25 | 2014-10-25 | 2014-10-25 | 2014-10-25 | 2014-10-25 | 2014-10-25 | KIRLOSKAR PNEUMATICS, SASWAD | 1 | 21 | 405 | ABHAY AGWAN | - | ABHAY.AGWAN@KPCL.COM | ABHAY AGWAN | - | ABHAY.AGWAN@KPCL.COM | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-10-15 | 2014-10-14 | 1 |  | HEMAKSH PATIL
292 | 2015-01-21 | 11:18:40 AM | Sapl0005 | 1 | 2 | S011 | 295 | 304 | PUOR14003114 | 37 | 0 | P0029 | 2014-10-18 | BREAK COIL | HEMAKSH PATIL | 4 | 2014-10-18 | 2014-10-18 | 2014-10-18 | 2014-10-18 | 2014-10-18 | 2014-10-18 | 2014-10-18 | 2014-10-18 | 2014-10-18 | 2014-10-18 | 2014-10-18 | 2014-10-18 | 2014-10-18 | 2014-10-18 | 2014-10-18 | 2014-10-18 | SHANTI IRON & STEEL | 1 | 17 | 295 | MULLA MOHAMMEDZEM M | - | purchase@shantiiron.net | MULLA MOHAMMEDZEM M | - | purchase@shantiiron.net | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-10-18 | 2014-10-18 | 1 |  | HEMAKSH PATIL
293 | 2015-02-28 | 10:21:27 AM | Sapl0005 | 1 | 2 | J015 | 296 | 305 | 4300016382 | 34 | 0 | S0077 | 2014-10-27 | LONG RAIL C63, CROSS RAIL C63 & TROLLEY SET | RAJKUMAR JAGTAP | 2 | 2014-10-27 | 2014-10-29 | 2014-10-29 | 2014-10-29 | 2014-10-29 | 2014-10-29 | 2014-10-29 | 2014-10-29 | 2014-10-30 | 2014-10-30 | 2014-10-30 | 2014-10-30 | 2014-10-30 | 2014-10-30 | 2014-10-30 | 2014-10-30 | Plot No Av - 13 , Bol Industrial Estate , Gidc , Sanand - II , Ahmedabad, Gujarat, INDIA | 1 | 12 | 142 | JUGNU SHARMA | - | jugnu.sharma@jbm-group.com | ROHIT RAKHEJA | - | rohit.rakheja@jbm.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-10-27 | 2014-10-27 | 1 |  | RAJKUMAR JAGTAP
294 | 2015-07-13 | 10:57:46 AM | Sapl0005 | 1 | 2 | M017 | 297 | 306 | mungiverb | 35 | 0 | N0085 | 2014-10-28 | Trolleys & scissor lift | PADMASINHA JOSHI | 3 | 2014-10-28 | 2014-11-08 | 2014-11-08 | 2014-11-15 | 2014-11-16 | 2014-11-22 | 2014-11-23 | 2014-11-29 | 2014-12-03 | 2014-12-03 | 2014-11-29 | 2014-12-02 | 2014-12-04 | 2014-12-09 | 2014-12-03 | 2014-12-03 | Mungi Engineer Pvt. Ltd., Chakan | 1 | 21 | 405 | devkate | - | devkate@mungiindia.com | devkate | - | devkate@mungiindia.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-11-05 | 2014-11-05 | 1 |  | PADMASINHA JOSHI
295 | 2015-01-21 | 11:16:35 AM | Sapl0005 | 1 | 2 | M009 | 298 | 307 | verbmus28 | 35 | 0 | N0086 | 2014-10-28 | Fixture OP20B | MANOJ SHINDE | 3 | 2014-10-28 | 2015-02-28 | 2014-11-07 | 2015-02-28 | 2014-11-15 | 2015-02-28 | 2014-11-30 | 2014-12-04 | 2014-12-05 | 2014-12-05 | 2014-11-22 | 2014-11-29 | 2014-11-30 | 2014-12-15 | 2014-12-11 | 2014-12-11 | MAHINDRA UGINE STEEL CO. LTD. | 1 | 21 | 405 | S.P.Mishra | - | MISHRA.SATYAPRAKASH@mahindra.com | Sujit Barge | - | BARGE.SUJIT@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-11-07 | 2014-11-07 | 1 |  | MANOJ SHINDE
297 | 2016-11-03 | 10:37:12 AM | Sapl0005 | 1 | 2 | T014 | 300 | 309 | 50010586 | 35 | 0 | N0087 | 2014-11-13 | SUB ASSEMBLY TABLES & FIXTURE | RAJKUMAR JAGTAP | 2 | 2014-11-13 | 2016-04-30 | 2014-11-20 | 2016-04-30 | 2014-12-01 | 2014-12-31 | 2014-12-18 | 2014-12-25 | 2014-12-26 | 2014-12-29 | 2014-12-11 | 2014-12-17 | 2014-12-18 | 2015-01-02 | 2014-12-30 | 2014-12-30 | PLOT NO. A-1/1, A1/2/1, PHALTAN - LONAND ROAD, SURAVADI VILLAGE, -415522 | 1 | 21 | 405 | Rahul Aggarwal | 0091-9552530285 | rahul.aggarwal@cummins.com | rajat.chaturvedi | - | rajat.chaturvedi@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-11-20 | 2014-11-20 | 1 |  | RAJKUMAR JAGTAP
298 | 2014-11-29 | 9:46:54 AM | Sapl0005 | 1 | 2 | J014 | 301 | 310 | 4300016622 | 34 | 0 | S0078 | 2014-11-15 | LONG RAIL C63, CROSS RAIL C63 & TROLLEY SET | RAJKUMAR JAGTAP | 2 | 2014-11-15 | 2014-11-18 | 2014-11-18 | 2014-11-18 | 2014-11-18 | 2014-11-18 | 2014-11-18 | 2014-11-18 | 2014-11-18 | 2014-11-18 | 2014-11-18 | 2014-11-18 | 2014-11-21 | 2014-11-22 | 2014-11-20 | 2014-11-20 | JBM AUTO LTD. Plot No. SP1- 891, RIICO Industrial Area, Pathredi, Distt.- Alwar, Rajasthan-301707 | 1 | 29 | 500 | akhil.saini | 91-7728893196 | akhil.saini@jbm.co.in | arjun.kumar | - | arjun.kumar@jbm.co.in | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2014-11-15 | 2014-11-15 | 1 |  | RAJKUMAR JAGTAP
299 | 2014-12-08 | 2:29:20 PM | Sapl0005 | 1 | 2 | A015 | 302 | 311 | PO114001114 | 37 | 0 | P0031 | 2014-11-20 | REVERSE PHASE PROTECTOR & LIMIT SWITCH OF HOIST | HEMAKSH PATIL | 4 | 2014-11-20 | 2014-11-20 | 2014-11-20 | 2014-11-20 | 2014-11-20 | 2014-11-20 | 2014-11-20 | 2014-11-20 | 2014-11-20 | 2014-11-20 | 2014-11-20 | 2014-11-20 | 2014-11-20 | 2014-11-20 | 2014-11-20 | 2014-11-20 | ALF ENGINEERING PVT LTD-UNIT-1 Plot No. E-60/61/62,MaIlD-BCh,, Ambad,Nasik, Maharashtra, PIN : 422010 | 1 | 21 | 402 | ANIL PATIL | 0253-6628831 | sujitnair@alfengineering.com | ANIL PATIL | - | sujitnair@alfengineering.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-11-20 | 2014-11-20 | 1 |  | HEMAKSH PATIL
303 | 2015-01-12 | 12:40:20 PM | Sapl0005 | 1 | 2 | T002 | 306 | 315 | 2410190283 | 37 | 0 | P0032 | 2014-12-01 | AIR COMPRE AS19 O/P30-35L/MIN 240V HESNG | SANJAY SHINDE | 13 | 2014-12-01 | 2014-12-13 | 2014-12-13 | 2014-12-15 | 2014-12-15 | 2014-12-15 | 2014-12-15 | 2014-12-15 | 2014-12-16 | 2014-12-16 | 2014-12-16 | 2014-12-17 | 2014-12-17 | 2014-12-17 | 2014-12-17 | 2014-12-17 | CV PUN Auto Maint Tata Motors Ltd. Pune 411018 | 1 | 21 | 405 | deepak babre | - | deepak.b@tatamotors.com | deepak.b | - | deepak.b@tatamotors.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-12-06 | 2014-12-06 | 1 |  | SANJAY SHINDE
304 | 2015-01-21 | 11:16:01 AM | Sapl0005 | 1 | 2 | M008 | 307 | 317 | 3200082136 | 35 | 0 | N0088 | 2014-12-08 | TROLLEYS | MANOJ SHINDE | 3 | 2014-12-08 | 2014-12-08 | 2014-12-08 | 2014-12-08 | 2014-12-08 | 2014-12-08 | 2014-12-08 | 2014-12-08 | 2014-12-08 | 2014-12-08 | 2014-12-08 | 2014-12-08 | 2014-12-08 | 2014-12-08 | 2014-12-08 | 2014-12-08 | MUSCO, ZAHIRABAD | 1 | 2 | 11 | SUJIT BARGE | - | SUJIT@mahindra.com | Sujit Barge | - | SUJIT@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-12-08 | 2014-12-08 | 1 |  | MANOJ SHINDE
305 | 2015-03-05 | 2:52:28 PM | Sapl0005 | 1 | 2 | M009 | 308 | 318 | 3400162751 | 36 | 0 | E0019 | 2014-12-08 | ECN PO | MANOJ SHINDE | 3 | 2014-12-08 | 2014-12-08 | 2014-12-08 | 2014-12-08 | 2014-12-08 | 2014-12-08 | 2014-12-08 | 2014-12-08 | 2014-12-08 | 2014-12-08 | 2014-12-08 | 2014-12-08 | 2014-12-08 | 2014-12-08 | 2014-12-08 | 2014-12-08 | MUSCO, KANHE | 1 | 21 | 405 | SUJIT BARGE | - | SUJIT@mahindra.com | Sujit Barge | - | SUJIT@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-12-08 | 2014-12-08 | 1 |  | MANOJ SHINDE
306 | 2015-01-16 | 12:15:45 PM | Sapl0005 | 1 | 2 | A026 | 309 | 319 | ver11 | 38 | 0 | J0066 | 2014-12-11 | Scrap | Somnath Bhatkute | 15 | 2014-12-08 | 2014-12-11 | 2014-12-11 | 2014-12-11 | 2014-12-11 | 2014-12-11 | 2014-12-11 | 2014-12-11 | 2014-12-11 | 2014-12-11 | 2014-12-11 | 2014-12-11 | 2014-12-11 | 2014-12-11 | 2014-12-11 | 2014-12-11 | pune | 1 | 21 | 405 | gsdfh | - | dgdf@scrap.com | gffg | - | dgdf@scrap.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-12-11 | 2014-12-11 | 1 |  | Somnath Bhatkute
307 | 2018-08-04 | 9:30:19 AM | Sapl0005 | 1 | 2 | S006 | 310 | 320 | sapl | 35 | 0 | N0089 | 2014-12-13 | Standard Design Assembly | AMIT POTDAR | 3 | 2014-12-13 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2015-03-31 | Synergytech Automation Pvt. Ltd. | 1 | 21 | 405 | - | - | sales@synergytechs.com | - | - | sales@synergytechs.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 1 |  | 1 | COMPLETE | 2015-03-31 | 2015-03-31 | 1 |  | AMIT POTDAR
309 | 2015-02-13 | 2:45:01 PM | Sapl0005 | 1 | 2 | J018 | 312 | 322 | 4300017078 | 34 | 0 | S0081 | 2014-12-22 | LONG RAIL, CROSS RAIL & TROLLEY SET | RAJKUMAR JAGTAP | 2 | 2014-12-22 | 2014-12-23 | 2014-12-23 | 2014-12-23 | 2014-12-24 | 2014-12-25 | 2014-12-25 | 2014-12-25 | 2014-12-25 | 2014-12-25 | 2014-12-25 | 2014-12-25 | 2014-12-25 | 2014-12-25 | 2014-12-26 | 2014-12-26 | JBM Auto system, orgadam | 1 | 31 | 543 | anusha | 9840916963 | corppurchase.bg6@jbm-group.com | veerappan.balasundaram | - | veerappan.balasundaram@jbm-group.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-12-24 | 2014-12-24 | 1 |  | RAJKUMAR JAGTAP
311 | 2015-01-21 | 11:04:30 AM | Sapl0005 | 1 | 2 | T015 | 314 | 324 | 7230015910 | 34 | 0 | S0083 | 2014-12-29 | Handling system for outer side sill | RAJKUMAR JAGTAP | 2 | 2014-12-29 | 2015-01-19 | 2015-01-01 | 2015-01-19 | 2015-01-06 | 2015-01-09 | 2015-01-09 | 2015-01-10 | 2015-01-12 | 2015-01-12 | 2015-01-09 | 2015-01-10 | 2015-01-09 | 2015-01-16 | 2015-01-12 | 2015-01-12 | TAL MANUFACTURING SOLUTION, CHINCHWAD, PUNE | 1 | 21 | 405 | kiran.phatak | - | kiran.phatak@tal.co.in | jitendra.k | - | jitendra.k@tal.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2015-01-02 | 2015-01-02 | 1 |  | RAJKUMAR JAGTAP
315 | 2015-03-07 | 12:10:15 PM | Sapl0005 | 1 | 2 | M020 | 318 | 328 | 3200071537 | 35 | 0 | N0090 | 2015-01-08 | p601 cargo | MANOJ SHINDE | 3 | 2015-01-08 | 2015-01-08 | 2015-01-08 | 2015-01-08 | 2015-01-08 | 2015-01-08 | 2015-01-08 | 2015-01-08 | 2015-01-08 | 2015-01-08 | 2015-01-08 | 2015-01-08 | 2015-01-08 | 2015-01-08 | 2015-01-08 | 2015-01-08 | mahindra, zahirabad | 1 | 46 | 692 | SUJIT BARGE | - | SUJIT@mahindra.com | Sujit Barge | - | SUJIT@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-01-08 | 2015-01-08 | 1 |  | MANOJ SHINDE
316 | 2015-04-25 | 10:44:46 AM | Sapl0005 | 1 | 2 | M020 | 319 | 329 | mcieaver | 35 | 0 | N0091 | 2015-01-08 | P601_Hand jig & B Pillar Modification | MANOJ SHINDE | 3 | 2015-01-08 | 2015-01-20 | 2015-01-21 | 2015-01-28 | 2015-01-29 | 2015-02-04 | 2015-02-13 | 2015-02-13 | 2015-02-10 | 2015-02-11 | 2015-02-05 | 2015-02-09 | 2015-02-13 | 2015-02-13 | 2015-02-12 | 2015-02-12 | Mahindra CIE Automative | 1 | 46 | 692 | SATYAPRAKASH MISHRA | - | MISHRA.SATYAPRAKASH@MAHINDRACIE.COM | Sujit Barge | - | BARGE.SUJIT@MAHINDRACIE.COM | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-01-22 | 2015-01-22 | 1 |  | MANOJ SHINDE
317 | 2018-01-12 | 9:07:26 AM | Sapl0005 | 1 | 2 | S006 | 321 | 331 | verb19 | 43 | 0 | T0018 | 2015-01-19 | Demo Pick & Place, Lift & Carry system | HEMAKSH PATIL | 4 | 2015-01-19 | 2016-09-08 | 2015-01-26 | 2016-09-08 | 2015-02-07 | 2015-02-10 | 2015-02-10 | 2015-02-14 | 2015-02-14 | 2015-02-14 | 2015-02-14 | 2015-02-14 | 2015-02-10 | 2015-02-14 | 2015-02-14 | 2015-02-14 | Synergytech Automation Pvt. Ltd. | 1 | 21 | 405 | - | - | sales@synergytechs.com | - | - | sales@synergytechs.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2015-01-26 | 2015-01-26 | 1 |  | HEMAKSH PATIL
318 | 2015-06-13 | 4:49:42 PM | Sapl0005 | 1 | 2 | J018 | 322 | 332 | 4300017420 | 34 | 0 | S0085 | 2015-01-20 | CROSS RAIL | RAJKUMAR JAGTAP | 2 | 2015-01-20 | 2015-01-20 | 2015-01-20 | 2015-01-20 | 2015-01-20 | 2015-01-20 | 2015-01-20 | 2015-01-20 | 2015-01-20 | 2015-01-20 | 2015-01-20 | 2015-01-20 | 2015-01-20 | 2015-01-20 | 2015-01-20 | 2015-01-20 | JBM AUTO SYSTEM PVT. LTD, | 1 | 31 | 537 | anusha | - | veeraperumal.thavamani@jbm-group.com | ANUSHA | - | veeraperumal.thavamani@jbm-group.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-01-20 | 2015-01-20 | 1 |  | RAJKUMAR JAGTAP
319 | 2015-03-07 | 12:10:38 PM | Sapl0005 | 1 | 2 | M020 | 323 | 333 | 3200071537 | 35 | 0 | N0092 | 2015-01-21 | Gantry | MANOJ SHINDE | 2 | 2015-01-21 | 2015-01-21 | 2015-01-21 | 2015-01-21 | 2015-01-21 | 2015-01-21 | 2015-01-21 | 2015-01-21 | 2015-01-21 | 2015-01-21 | 2015-01-21 | 2015-01-21 | 2015-01-21 | 2015-01-21 | 2015-01-21 | 2015-01-21 | Mahindra CIE Automative | 1 | 46 | 692 | SUJIT BARGE | - | SUJIT@mahindra.com | Sujit Barge | - | SUJIT@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-01-21 | 2015-01-21 | 1 |  | MANOJ SHINDE
320 | 2015-03-07 | 12:22:42 PM | Sapl0005 | 1 | 2 | J008 | 324 | 334 | ver27 | 34 | 0 | S0086 | 2015-01-27 | LONG RAIL, CROSS RAIL & TROLLEY SET | RAJKUMAR JAGTAP | 2 | 2015-01-27 | 2015-01-29 | 2015-01-29 | 2015-01-31 | 2015-02-01 | 2015-02-03 | 2015-02-05 | 2015-02-05 | 2015-02-05 | 2015-02-06 | 2015-02-03 | 2015-02-05 | 2015-02-05 | 2015-02-12 | 2015-02-08 | 2015-02-08 | JBM sanand | 1 | 12 | 681 | ishwar.bhayani | 7600023281 | ishwar.bhayani@jbm-group.com | SANJAY MURGAI | - | smurgai@jbm.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | COMPLETE | 2015-01-30 | 2015-01-30 | 1 |  | RAJKUMAR JAGTAP
321 | 2016-11-03 | 10:37:52 AM | Sapl0005 | 1 | 2 | N005 | 320 | 330 | 132002 | 35 | 0 | N0093 | 2015-01-28 | C class Fixtures Phase 1 | PADMASINHA JOSHI | 3 | 2015-02-05 | 2016-08-31 | 2015-02-15 | 2016-08-31 | 2015-02-26 | 2016-01-07 | 2015-03-20 | 2016-01-07 | 2015-04-15 | 2016-01-07 | 2015-03-10 | 2016-01-07 | 2015-03-20 | 2016-01-21 | 2015-03-20 | 2016-01-21 | New Holland India | 1 | 21 | 405 | Manjunath Reddy | 7767804452 | manjunatha.reddy@cnhind.com | Devendra Pandey | - | devendrakumar.pandey@cnhind.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2016-01-07 | 2016-01-07 | 1 |  | PADMASINHA JOSHI
322 | 2015-11-19 | 12:31:58 PM | Sapl0005 | 1 | 2 | S006 | 325 | 335 | ver31 | 34 | 0 | S0087 | 2015-01-31 | Long rails, cross rail & trolley set | RAJKUMAR JAGTAP | 2 | 2015-01-31 | 2015-02-03 | 2015-02-03 | 2015-02-03 | 2015-02-03 | 2015-02-03 | 2015-02-03 | 2015-02-03 | 2015-02-03 | 2015-02-04 | 2015-02-03 | 2015-02-03 | 2015-02-05 | 2015-02-07 | 2015-02-05 | 2015-02-05 | Synergytech Automation | 1 | 21 | 405 | Rajkumar Jagtap | - | sales@synergytechs.com | Rajkumar Jagtap | - | sales@synergytechs.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | compl | 2015-01-31 | 2015-01-31 | 1 |  | RAJKUMAR JAGTAP
327 | 2016-11-03 | 10:38:26 AM | Sapl0005 | 1 | 2 | N005 | 330 | 340 | cnh2 | 35 | 0 | N0095 | 2015-02-14 | C class fixtures phase III | PADMASINHA JOSHI | 3 | 2015-02-05 | 2016-08-31 | 2015-02-15 | 2016-08-31 | 2015-02-26 | 2015-03-30 | 2015-03-20 | 2015-04-25 | 2015-04-15 | 2015-04-30 | 2015-03-10 | 2015-04-20 | 2015-03-20 | 2015-04-30 | 2015-03-20 | 2015-04-25 | New Holland India | 1 | 21 | 405 | Manjunath Reddy | 7767804452 | manjunath.reddy@cnhind.com | Devendra Pandey | - | devendrakumar.pandey@cnhind.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2015-02-20 | 2015-02-20 | 1 |  | PADMASINHA JOSHI
328 | 2016-11-03 | 10:38:41 AM | Sapl0005 | 1 | 2 | N005 | 331 | 341 | cnh3 | 35 | 0 | N0096 | 2015-02-14 | C Class Fixtures Phase iv | PADMASINHA JOSHI | 3 | 2015-02-05 | 2016-08-31 | 2015-02-15 | 2016-08-31 | 2015-02-26 | 2015-03-30 | 2015-03-20 | 2015-04-25 | 2015-04-15 | 2015-04-30 | 2015-03-10 | 2015-04-20 | 2015-03-20 | 2015-04-30 | 2015-03-20 | 2015-04-25 | New Holland India | 1 | 21 | 405 | Manjunath Reddy | 7767804452 | manjunath.reddy@cnhind.com | Devendrakumar Pandey | - | devendrkumar.pandey@cnhind.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2015-02-20 | 2015-02-20 | 1 |  | PADMASINHA JOSHI
329 | 2016-11-03 | 10:38:55 AM | Sapl0005 | 1 | 2 | N005 | 332 | 342 | cnh4 | 35 | 0 | N0097 | 2015-02-14 | C Class Fixtures Phase V | PADMASINHA JOSHI | 3 | 2015-02-05 | 2016-08-31 | 2015-02-15 | 2016-08-31 | 2015-02-26 | 2015-03-30 | 2015-03-20 | 2015-04-25 | 2015-04-15 | 2015-06-30 | 2015-03-10 | 2015-04-20 | 2015-03-20 | 2015-04-30 | 2015-03-20 | 2015-04-25 | New Holland India | 1 | 21 | 405 | Manjunath Reddy | 7767804452 | manjunath.reddy@cnhind.com | Devendrakumar Pandey | - | devendrakumar.pandey@cnhind.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2015-02-20 | 2015-02-20 | 1 |  | PADMASINHA JOSHI
330 | 2016-03-31 | 11:10:25 AM | Sapl0005 | 1 | 2 | S011 | 333 | 343 | PUOR14004938 | 37 | 0 | P0033 | 2015-02-14 | Break Coil & Break Liner | HEMAKSH PATIL | 4 | 2015-02-14 | 2015-02-14 | 2015-02-14 | 2015-02-14 | 2015-02-14 | 2015-02-14 | 2015-02-14 | 2015-02-14 | 2015-02-14 | 2015-02-14 | 2015-02-14 | 2015-02-14 | 2015-02-14 | 2015-02-14 | 2015-02-14 | 2015-02-14 | 690, Udyambag Industrial Estate, BELGAUM - 590 008 KARNATAKA - INDIA | 1 | 17 | 295 | MNPATIL | +91 831 4218328 | purchase@shantiiron.net | MNPATIL | - | purchase@shantiiron.net | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2015-02-14 | 2015-02-14 | 1 |  | HEMAKSH PATIL
331 | 2017-07-21 | 10:06:10 AM | Sapl0005 | 1 | 2 | M020 | 334 | 344 | mcieaver | 35 | 0 | N0098 | 2015-02-16 | Additional fixture | MANOJ SHINDE | 3 | 2015-02-16 | 2015-02-21 | 2015-02-21 | 2015-03-07 | 2015-03-07 | 2015-03-14 | 2015-03-19 | 2015-03-21 | 2015-03-23 | 2015-03-26 | 2015-03-16 | 2015-03-19 | 2015-03-27 | 2015-03-31 | 2015-03-27 | 2015-03-27 | Mahindra CIE , Zahirabad | 1 | 46 | 692 | S.P. Mishra | - | MISHRA.SATYAPRAKASH@MAHINDRACIE.COM | BARGE.SUJIT | - | BARGE.SUJIT@MAHINDRACIE.COM | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 1 |  | 1 | COMPLETE | 2015-03-10 | 2015-03-10 | 1 |  | MANOJ SHINDE
333 | 2015-02-28 | 10:14:34 AM | Sapl0005 | 1 | 2 | J018 | 336 | 346 | 4100042711 | 36 | 0 | E0020 | 2015-02-23 | INSTALLATION OF Rails | RAJKUMAR JAGTAP | 2 | 2015-02-23 | 2015-02-23 | 2015-02-23 | 2015-02-23 | 2015-02-23 | 2015-02-23 | 2015-02-23 | 2015-02-23 | 2015-02-23 | 2015-02-23 | 2015-02-23 | 2015-02-23 | 2015-02-23 | 2015-02-23 | 2015-02-23 | 2015-02-23 | JBM Auto system, orgadam | 1 | 31 | 688 | anusha | - | anusha.sriram@jbm-group.com | ANUSHA | - | anusha.sriram@jbm-group.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-02-23 | 2015-02-23 | 1 |  | RAJKUMAR JAGTAP
334 | 2015-07-13 | 11:01:58 AM | Sapl0005 | 1 | 2 | B001 | 337 | 347 | 4500053987 | 34 | 0 | S0091 | 2015-02-28 | LONG RAIL & ITS ACCESSORIES | RAJKUMAR JAGTAP | 2 | 2015-02-28 | 2015-03-02 | 2015-03-02 | 2015-03-03 | 2015-03-03 | 2015-03-04 | 2015-03-05 | 2015-03-05 | 2015-03-05 | 2015-03-05 | 2015-03-04 | 2015-03-05 | 2015-03-09 | 2015-03-11 | 2015-03-08 | 2015-03-08 | PLOT NO. 52, SECTOR 11, TATA MOTOR VENDOR PARK, IIE, SIDCUL, PANTNAGAR | 1 | 34 | 679 | SUMIT KHERA | 9927017318 | sumitkhera@badvegroup.com | P.N.PISE | - | pnpise@badvegroup.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 1 | cancel | 2015-03-02 | 2015-03-02 | 1 |  | RAJKUMAR JAGTAP
335 | 2015-11-19 | 12:31:34 PM | Sapl0005 | 1 | 2 | S006 | 338 | 348 | ver28 | 34 | 0 | S0092 | 2015-02-28 | LONG RAIL C63 & CROSS RAIL C63 | RAJKUMAR JAGTAP | 2 | 2015-02-28 | 2015-03-07 | 2015-03-07 | 2015-03-14 | 2015-03-14 | 2015-03-21 | 2015-03-28 | 2015-03-29 | 2015-03-29 | 2015-03-30 | 2015-03-21 | 2015-03-28 | 2015-03-30 | 2015-03-31 | 2015-03-31 | 2015-03-31 | Synergytech Automation | 1 | 21 | 405 | - | - | sales@synergytechs.com | - | - | sales@synergytechs.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | compl | 2015-03-10 | 2015-03-10 | 1 |  | RAJKUMAR JAGTAP
336 | 2016-11-03 | 11:20:13 AM | Sapl0005 | 1 | 2 | A015 | 341 | 352 | PO114001659 | 37 | 0 | P0034 | 2015-03-05 | break shoe assembly | HEMAKSH PATIL | 4 | 2015-03-05 | 2015-03-05 | 2015-03-05 | 2015-03-05 | 2015-03-05 | 2015-03-05 | 2015-03-05 | 2015-03-05 | 2015-03-05 | 2015-03-05 | 2015-03-05 | 2015-03-05 | 2015-03-05 | 2015-03-05 | 2015-03-05 | 2015-03-05 | Plot No. E-60/61/62, MaIlD-BCh,, Ambad,Nasik, Maharashtra, PIN : 422010 | 1 | 21 | 402 | ANIL PATIL | 0253-6628831 | sujitnair@alfengineering.com | ANIL PATIL | - | sujitnair@alfengineering.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-03-05 | 2015-03-05 | 1 |  | HEMAKSH PATIL
337 | 2015-11-23 | 9:24:33 AM | Sapl0005 | 1 | 2 | C004 | 342 | 353 | ver12mar | 38 | 0 | J0068 | 2015-03-12 | Trolley A606510 | MILIND TERAWDE | 5 | 2015-03-12 | 2015-03-16 | 2015-03-16 | 2015-03-21 | 2015-03-16 | 2015-03-23 | 2015-03-24 | 2015-03-24 | 2015-03-25 | 2015-03-25 | 2015-03-23 | 2015-03-24 | 2015-03-26 | 2015-03-26 | 2015-03-25 | 2015-03-26 | cummins india ltd., kothrud | 1 | 21 | 405 | MARY VYDANI | 7720048241 | mary.vydani@cummins.com | thakabhau.g.chindhe | - | thakabhau.g.chindhe@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-03-13 | 2015-03-13 | 1 |  | MILIND TERAWDE
338 | 2018-02-19 | 4:28:26 PM | Sapl0005 | 1 | 2 | M001 | 343 | 354 | LOI12mar | 35 | 0 | N0099 | 2015-03-14 | 15F733- UNITS | PADMASINHA JOSHI | 3 | 2015-03-14 | 2015-04-22 | 2015-03-16 | 2015-04-22 | 2015-03-18 | 2015-03-24 | 2015-03-27 | 2015-03-27 | 2015-03-28 | 2015-03-28 | 2015-03-24 | 2015-03-27 | 2015-03-27 | 2015-03-31 | 2015-03-26 | 2015-03-27 | M&M Nashik | 1 | 21 | 402 | MALGE SNEHAL | 02536613052 | MALGE.SNEHAL@mahindra.com | DEOGHARE ROOPAL | - | DEOGHARE.ROOPAL@mahindra.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2015-03-17 | 2015-03-17 | 1 |  | PADMASINHA JOSHI
339 | 2018-02-19 | 4:28:40 PM | Sapl0005 | 1 | 2 | M001 | 344 | 355 | LOI212mar | 35 | 0 | N0100 | 2015-03-14 | 15F748 BWF UNITS | PADMASINHA JOSHI | 3 | 2015-03-14 | 2015-03-26 | 2015-03-16 | 2015-03-26 | 2015-03-18 | 2015-03-24 | 2015-03-26 | 2015-03-27 | 2015-03-28 | 2015-03-28 | 2015-03-24 | 2015-03-26 | 2015-03-26 | 2015-03-31 | 2015-03-26 | 2015-03-27 | MAHINDRA & MAHINDRA, NASHIK | 1 | 21 | 402 | MALGE SNEHAL | - | MALGE.SNEHAL@mahindra.com | DEOGHARE ROOPAL | - | DEOGHARE.ROOPAL@mahindra.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2015-03-16 | 2015-03-16 | 1 |  | PADMASINHA JOSHI
341 | 2015-04-24 | 9:44:10 AM | Sapl0005 | 1 | 2 | A002 | 346 | 357 | Verbal_M.Hiremath | 34 | 0 | S0093 | 2015-04-07 | Gunrail & its accessories | RAJKUMAR JAGTAP | 2 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2015-04-07 | 2015-04-07 | Anusaya Auto Press parts Pvt. Ltd. | 1 | 21 | 405 | HIREMATH | 9881700801 | marulesh2002@gmail.com | santosh pudake | - | snpudake@wadhokar.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-04-07 | 2015-04-07 | 1 |  | RAJKUMAR JAGTAP
342 | 2016-11-03 | 10:39:24 AM | Sapl0005 | 1 | 2 | N005 | 348 | 359 | 132014 | 35 | 0 | N0102 | 2015-03-11 | Trollies | RAJKUMAR JAGTAP | 2 | 2015-04-10 | 2015-12-31 | 2015-04-23 | 2015-12-31 | 2015-05-08 | 2015-05-18 | 2015-05-20 | 2015-05-21 | 2015-05-22 | 2015-05-22 | 2015-05-18 | 2015-05-20 | 2015-05-20 | 2015-05-29 | 2015-05-20 | 2015-05-21 | New Holland Chakan | 1 | 21 | 405 | pratik.shah | - | pratik.shah@external.cnhind.com | pundeo.kumar | - | pundeo.kumar@cnhind.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2015-04-30 | 2015-04-30 | 1 |  | RAJKUMAR JAGTAP
343 | 2016-11-03 | 10:39:39 AM | Sapl0005 | 1 | 2 | N005 | 349 | 360 | 132016 | 35 | 0 | N0103 | 2015-04-11 | WORK BENCH FIXTURES | RAJKUMAR JAGTAP | 2 | 2015-04-10 | 2015-09-30 | 2015-04-23 | 2015-09-30 | 2015-05-09 | 2015-05-16 | 2015-05-20 | 2015-05-21 | 2015-05-22 | 2015-05-22 | 2015-05-16 | 2015-05-20 | 2015-05-20 | 2015-05-30 | 2015-05-20 | 2015-05-21 | New Holland Chakan | 1 | 21 | 405 | PRATIK SHAH | - | pratik.shah@external.cnhind.com | PUNDEO KUMAR | - | devendrakumar.pandey@cnhind.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2015-04-30 | 2015-04-30 | 1 |  | RAJKUMAR JAGTAP
344 | 2018-02-21 | 11:06:14 AM | Sapl0005 | 1 | 2 | N005 | 350 | 361 | 132018 | 35 | 0 | N0104 | 2015-04-16 | C CLASS WELDING FIXTURES | PADMASINHA JOSHI | 3 | 2015-04-16 | 2017-05-31 | 2015-04-25 | 2017-05-31 | 2015-05-10 | 2015-05-17 | 2015-05-25 | 2015-05-29 | 2015-05-30 | 2015-05-30 | 2015-05-18 | 2015-05-25 | 2015-05-25 | 2015-06-04 | 2015-05-25 | 2015-05-29 | NEW HOLLAND , CHAKAN | 1 | 21 | 405 | MURUGADASS Ravi | - | ravi.murugadass@cnhind.com | REDDY Manjunatha | - | manjunatha.reddy@cnhind.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2015-04-27 | 2015-04-27 | 1 |  | PADMASINHA JOSHI
345 | 2017-07-21 | 10:06:54 AM | Sapl0005 | 1 | 2 | N005 | 351 | 362 | CNH16 | 35 | 0 | N0105 | 2015-04-17 | Class C Fixtures | PADMASINHA JOSHI | 3 | 2015-04-17 | 2016-10-31 | 2015-04-25 | 2016-10-31 | 2015-05-07 | 2015-05-16 | 2015-05-24 | 2015-05-29 | 2015-05-30 | 2015-05-31 | 2015-05-17 | 2015-05-23 | 2015-05-24 | 2015-05-08 | 2015-05-24 | 2015-05-29 | New holland, Chakan | 1 | 21 | 405 | Manjunath Reddy | - | manjunatha.reddy@cnhind.com | ravi.murugadass | - | ravi.murugadass@cnhind.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2015-05-05 | 2015-05-05 | 1 |  | PADMASINHA JOSHI
346 | 2015-07-24 | 11:36:57 AM | Sapl0005 | 1 | 3 | C004 | 352 | 363 | ver24 | 38 | 0 | J0069 | 2015-04-24 | Tackles for KV Cylinder Block A14519 | Milind Terwade | 5 | 2015-04-24 | 2015-04-27 | 2015-04-27 | 2015-05-02 | 2015-05-03 | 2015-05-08 | 2015-05-11 | 2015-05-11 | 2015-05-12 | 2015-05-12 | 2015-05-08 | 2015-05-10 | 2015-05-13 | 2015-05-14 | 2015-05-11 | 2015-05-11 | Cummins India Ltd., Pune | 1 | 21 | 405 | Milind Bhagwat | - | milind.v.bhagwat@cummins.com | Milind Bhagwat | - | milind.v.bhagwat@cummins.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-04-28 | 2015-04-28 | 1 |  | Milind Terwade
347 | 2016-03-31 | 11:18:23 AM | Sapl0005 | 1 | 3 | S011 | 353 | 364 | PUOR15000337 | 34 | 0 | S0094 | 2015-04-25 | 500kg Hoist & Brake shoe assly | HEMAKSH PATIL | 4 | 2015-04-25 | 2015-04-25 | 2015-04-25 | 2015-04-25 | 2015-04-25 | 2015-04-25 | 2015-04-25 | 2015-04-25 | 2015-04-25 | 2015-04-25 | 2015-04-25 | 2015-04-25 | 2015-04-25 | 2015-04-25 | 2015-04-25 | 2015-04-25 | Shanti iron & steel , belgaum | 1 | 17 | 295 | suneel nagnathan | - | projects@shantiiron.net | mn patil | - | purchase@shantiiron.net | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-04-25 | 2015-04-25 | 1 |  | HEMAKSH PATIL
348 | 2018-06-22 | 10:56:33 AM | Sapl0005 | 1 | 3 | S026 | 354 | 365 | verbsa | 43 | 0 | T0019 | 2015-05-19 | OXYFUEL FLAMECUT MACHINE | Shweta | 4 | 2015-05-19 | 2015-06-30 | 2015-05-27 | 2015-06-30 | 2015-06-06 | 2015-06-12 | 2015-06-20 | 2015-06-25 | 2015-06-26 | 2015-06-27 | 2015-06-12 | 2015-06-19 | 2015-06-20 | 2015-06-30 | 2015-06-25 | 2015-06-25 | Sakshi Enterprises Pune | 1 | 21 | 405 | Kakade | - | kakade01@yahoo.com | Kakade | - | kakade01@yahoo.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | close | 2015-05-29 | 2015-05-29 | 1 |  | Shweta
349 | 2018-06-22 | 10:59:57 AM | Sapl0005 | 1 | 3 | A029 | 355 | 366 | MH_PO 14 -15_000722 | 35 | 0 | N0106 | 2015-05-25 | Welding Fixtures | MANOJ SHINDE | 3 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2015-05-25 | ail,pune | 1 | 21 | 405 | Sujeet Chaskar | - | sujeet.chaskar@autoline.com | sujeet chaskar | - | sujeet.chaskar@autoline.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | close | 2015-05-25 | 2015-05-25 | 1 |  | MANOJ SHINDE
350 | 2018-06-22 | 11:00:14 AM | Sapl0005 | 1 | 3 | A029 | 356 | 367 | MH _PO 14-15_000722 | 35 | 0 | N0107 | 2015-05-25 | Welding Fixtures | MANOJ SHINDE | 3 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2015-05-25 | ail | 1 | 21 | 405 | Sujeet Chaskar | - | sujeet.chaskar@autoline.com | sujeet chaskar | - | sujeet.chaskar@autoline.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | close | 2015-05-25 | 2015-05-25 | 1 |  | MANOJ SHINDE
351 | 2015-06-01 | 9:55:20 AM | Sapl0005 | 1 | 3 | V002 | 357 | 368 | 8000058208 | 34 | 0 | S0095 | 2015-05-27 | SLIDO Cross rail , Telescopic rails with its accessories | RAJKUMAR JAGTAP | 2 | 2015-05-27 | 2015-05-27 | 2015-05-27 | 2015-05-27 | 2015-05-27 | 2015-05-27 | 2015-05-27 | 2015-05-27 | 2015-05-27 | 2015-05-27 | 2015-05-27 | 2015-05-27 | 2015-05-27 | 2015-05-27 | 2015-05-27 | 2015-05-27 | Volkswagen India Private Limited E-1, MIDC Industrial Area (Phase III) Chakan, Village Nigoje Mhalunge Kharabwadi, Tal : Khed Chakan, Pune - 410 501 Maharashtra, India | 1 | 21 | 405 | Mahesh Dhole | - | himanshu.tiwari@volkswagen.co.in | himanshu tiwari | - | mahesh.dhole@volkswagen.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-05-27 | 2015-05-27 | 1 |  | RAJKUMAR JAGTAP
352 | 2017-12-09 | 9:51:34 AM | Sapl0005 | 1 | 3 | C004 | 358 | 369 | IND3209830 | 35 | 0 | N0108 | 2015-06-06 | Enclosure for bush boring SPM & Coolant recirculationTank | RAJKUMAR JAGTAP | 2 | 2015-06-06 | 2015-10-30 | 2015-06-08 | 2015-10-30 | 2015-06-09 | 2015-06-10 | 2015-06-11 | 2015-06-11 | 2015-06-12 | 2015-06-12 | 2015-06-10 | 2015-06-11 | 2015-06-11 | 2015-06-13 | 2015-06-12 | 2015-06-12 | CUMMINS INDIA LTD., KOTHRUD | 1 | 21 | 405 | SHAILESH SHIVAJI KAKADE | - | shailesh.shivaji.kakade@cummins.com | MAHESH BOHERSHETTI | - | mahesh.bhorshetti@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2015-06-08 | 2015-06-08 | 1 |  | RAJKUMAR JAGTAP
353 | 2015-07-13 | 11:03:52 AM | Sapl0005 | 1 | 3 | C004 | 359 | 370 | vercu | 43 | 0 | T0020 | 2015-06-06 | Material for Control Panel | HEMAKSH PATIL | 4 | 2015-06-06 | 2015-06-29 | 2015-06-08 | 2015-06-29 | 2015-06-08 | 2015-06-08 | 2015-06-08 | 2015-06-09 | 2015-06-10 | 2015-06-11 | 2015-06-08 | 2015-06-08 | 2015-06-08 | 2015-06-12 | 2015-06-10 | 2015-06-10 | cil, kothrud | 1 | 21 | 405 | archana karande | - | archana.karande@cummins.com | archana karande | - | archana.karande@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2015-06-06 | 2015-06-06 | 1 |  | HEMAKSH PATIL
354 | 2015-06-13 | 4:50:09 PM | Sapl0005 | 1 | 3 | S026 | 360 | 371 | 005 | 34 | 0 | S0096 | 2015-06-06 | Faro Machine | SANJAY SHINDE | 13 | 2015-06-06 | 2015-06-10 | 2015-06-10 | 2015-06-11 | 2015-06-12 | 2015-06-12 | 2015-06-13 | 2015-06-13 | 2015-06-15 | 2015-06-15 | 2015-06-12 | 2015-06-12 | 2015-06-12 | 2015-06-12 | 2015-06-13 | 2015-06-13 | sakshi enterprises | 1 | 21 | 405 | Kakade | - | info@sakshiindia.com | Kakade | - | info@sakshiindia.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-06-09 | 2015-06-09 | 1 |  | SANJAY SHINDE
355 | 2015-06-13 | 4:46:17 PM | Sapl0005 | 1 | 3 | T015 | 315 | 325 | 7140016946 | 36 | 0 | E0021 | 2014-12-29 | ERECTION & COMMISSIONING SOLUTIONS LTD. | RAJKUMAR JAGTAP | 2 | 2014-12-29 | 2014-12-29 | 2014-12-30 | 2015-01-10 | 2015-01-10 | 2015-01-10 | 2015-01-10 | 2015-01-10 | 2015-01-10 | 2015-01-10 | 2015-01-10 | 2015-01-10 | 2015-01-10 | 2015-01-10 | 2015-01-10 | 2015-01-10 | TAL MANUFATURING SOLUTION | 1 | 12 | 142 | SOURABH | - | SOURABH@TAL.CO.IN | KIRAN PHATAK | - | KIRAN.PHATAK@TAL.CO.IN | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-12-31 | 2014-12-31 | 1 |  | RAJKUMAR JAGTAP
358 | 2015-07-13 | 11:02:27 AM | Sapl0005 | 1 | 3 | S011 | 363 | 374 | PUOR15001115 | 34 | 0 | S0097 | 2015-06-16 | LONG RAIL, CROSS RAIL, TELESCOPIC RAIL & TROLLEY SET | RAJKUMAR JAGTAP | 2 | 2015-06-16 | 2015-06-16 | 2015-06-16 | 2015-06-19 | 2015-06-19 | 2015-06-20 | 2015-06-20 | 2015-06-21 | 2015-06-22 | 2015-06-23 | 2015-06-19 | 2015-06-21 | 2015-06-25 | 2015-06-27 | 2015-06-23 | 2015-06-25 | BELGAUM - 590 008 KARNATAKA - INDIA | 1 | 17 | 295 | Suneel Naghatn | 7899836619 | projects@shantiiron.net | M.N.PATIL | - | purchase@shantiiron.net | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-06-18 | 2015-06-18 | 1 |  | RAJKUMAR JAGTAP
361 | 2017-01-09 | 2:44:26 PM | Sapl0005 | 1 | 3 | J003 | 367 | 378 | LOI25 | 35 | 0 | N0109 | 2015-06-26 | Welding SPM | Hemaksh Patil | 4 | 2015-06-26 | 2015-07-31 | 2015-06-29 | 2015-07-31 | 2015-07-01 | 2015-07-02 | 2015-07-03 | 2015-07-04 | 2015-07-04 | 2015-07-04 | 2015-07-02 | 2015-07-03 | 2015-07-03 | 2015-07-08 | 2015-07-03 | 2015-07-04 | JBM MA AUTOMOTIVE PVT. LTD. | 1 | 21 | 405 | Aniruddha Raut | 8605004984 | aniruddha.raut@jbmmagnetto.com | Arvind Garg | - | agarg@jbmmagnetto.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2015-07-01 | 2015-07-01 | 1 |  | Hemaksh Patil
363 | 2015-09-11 | 9:39:34 AM | Sapl0005 | 1 | 3 | C004 | 369 | 380 | Ver1jul | 38 | 0 | J0071 | 2015-07-01 | Base Weldment, Shaft, tie rod | MILIND TERAWDE | 5 | 2015-07-01 | 2015-07-11 | 2015-07-02 | 2015-07-18 | 2015-07-06 | 2015-07-09 | 2015-07-10 | 2015-07-10 | 2015-07-11 | 2015-07-11 | 2015-07-09 | 2015-07-10 | 2015-07-10 | 2015-07-13 | 2015-07-10 | 2015-07-13 | Cummins India Ltd., Pune | 1 | 21 | 405 | Asis sahoo | 880536400 | asiskumar.sahoo@cummins.com | thakabhau.g.chindhe | - | thakabhau.g.chindhe@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-07-03 | 2015-07-03 | 1 |  | MILIND TERAWDE
365 | 2016-11-03 | 11:20:40 AM | Sapl0005 | 1 | 3 | T002 | 371 | 382 | 2410198800 | 37 | 0 | P0036 | 2015-07-24 | WELDMENT SHAFT PART NO-001340405 | HEMAKSH PATIL | 2 | 2015-07-24 | 2015-07-25 | 2015-07-26 | 2015-07-27 | 2015-07-26 | 2015-07-27 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 | tata motors ltd. , pimpri | 1 | 21 | 405 | waman.salvi | 07276052176 | waman.salvi@tatamotors.com | r.bavadekar | - | r.bavadekar@tatamotors.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-07-25 | 2015-07-25 | 1 |  | HEMAKSH PATIL
366 | 2015-08-31 | 4:55:49 PM | Sapl0005 | 1 | 3 | A007 | 372 | 383 | ver27jul | 34 | 0 | S0099 | 2015-07-27 | Long rail c63, Cross Rail C63, Trolley set | HEMAKSH PATIL | 2 | 2015-07-27 | 2015-07-29 | 2015-07-29 | 2015-07-31 | 2015-07-31 | 2015-08-01 | 2015-08-01 | 2015-08-01 | 2015-08-01 | 2015-08-01 | 2015-08-01 | 2015-08-01 | 2015-08-01 | 2015-08-04 | 2015-08-01 | 2015-08-01 | Asal , chakan | 1 | 21 | 405 | Shadul Shaikh | 7507263821 | Shadul.Shaikh@autostampings.com | Mohan.Datir | - | Mohan.Datir@autostampings.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 0 |  | 1 | COMPLETE | 2015-08-01 | 2015-08-01 | 1 |  | HEMAKSH PATIL
367 | 2015-11-19 | 12:31:14 PM | Sapl0005 | 1 | 3 | S006 | 373 | 384 | Ver28jul | 34 | 0 | S0100 | 2015-07-28 | LONG RAIL, CROSS RAIL & TROLLEY SET | HEMAKSH PATIL | 4 | 2015-07-28 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 2015-07-31 | 2015-07-31 | sapl | 1 | 21 | 405 | - | - | sales@synergytecvhs.com | - | - | sales@synergytecvhs.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | com | 2015-07-28 | 2015-07-28 | 1 |  | HEMAKSH PATIL
368 | 2017-01-09 | 2:45:41 PM | Sapl0005 | 1 | 3 | J003 | 374 | 385 | 4300019589 | 35 | 0 | N0110 | 2015-07-30 | SPM Welding TORCH ASSY. | HEMAKSH PATIL | 4 | 2015-07-30 | 2015-07-30 | 2015-07-30 | 2015-07-30 | 2015-07-30 | 2015-07-30 | 2015-07-30 | 2015-07-30 | 2015-07-30 | 2015-07-30 | 2015-07-30 | 2015-07-30 | 2015-07-30 | 2015-07-30 | 2015-07-30 | 2015-07-30 | JBM MA Automotive Pvt. Limited C-1/2, Chakan MIDC Area 410501 Pune INDIA | 1 | 21 | 405 | aniruddha.raut | 8605004984 | aniruddha.raut@jbmmagnetto.com | Arvind Garg | - | agarg@jbmmagnetto.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-07-30 | 2015-07-30 | 1 |  | HEMAKSH PATIL
369 | 2015-11-23 | 9:15:39 AM | Sapl0005 | 1 | 3 | S024 | 375 | 386 | SDE/PUR/SR/0029 | 34 | 0 | S0101 | 2015-08-04 | Gunrail & trolley set | HEMAKSH PATIL | 4 | 2015-08-04 | 2015-08-04 | 2015-08-04 | 2015-08-04 | 2015-08-04 | 2015-08-04 | 2015-08-04 | 2015-08-04 | 2015-08-05 | 2015-08-05 | 2015-08-04 | 2015-08-04 | 2015-08-05 | 2015-08-05 | 2015-08-05 | 2015-08-05 | S.D.Engineerstech Pvt. Ltd .Plot No - A-8/10/1 , Village Nighoje , MIDC Chakan Phase - IV , Tal - Khed Dist - Pune , City :- Chakan - 410501. | 1 | 21 | 405 | saroj.parida | 9822907993 | saroj.parida@sdengineers.in | saroj.parida | - | saroj.parida@sdengineers.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-08-04 | 2015-08-04 | 1 |  | HEMAKSH PATIL
370 | 2015-11-23 | 9:16:02 AM | Sapl0005 | 1 | 3 | S011 | 376 | 387 | PUOR15002190 | 34 | 0 | S0102 | 2015-08-14 | LONG RAIL | HEMAKSH PATIL | 4 | 2015-08-14 | 2015-08-14 | 2015-08-14 | 2015-08-14 | 2015-08-14 | 2015-08-14 | 2015-08-14 | 2015-08-14 | 2015-08-17 | 2015-08-17 | 2015-08-14 | 2015-08-14 | 2015-08-14 | 2015-08-14 | 2015-08-14 | 2015-08-14 | 690, Udyambag Industrial Estate, BELGAUM | 1 | 17 | 295 | shantilal porwal | - | svp@shantiiron.net | suneel nagthan | - | projects@shantiiron.net | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-08-14 | 2015-08-14 | 1 |  | HEMAKSH PATIL
371 | 2015-11-23 | 9:16:20 AM | Sapl0005 | 1 | 3 | N003 | 377 | 388 | 011516CPMTME168 | 34 | 0 | S0103 | 2015-08-27 | LONG RAIL C63, CROSS RAIL C63 & TROLLEY SET | HEMAKSH PATIL | 2 | 2015-08-27 | 2015-08-29 | 2015-08-29 | 2015-08-29 | 2015-08-29 | 2015-08-29 | 2015-08-29 | 2015-08-29 | 2015-08-29 | 2015-08-29 | 2015-08-29 | 2015-08-29 | 2015-08-29 | 2015-08-29 | 2015-08-29 | 2015-08-29 | NEEL AUTO PRIVATE LIMITED Plot #1,2,5 & 6, TVS Industrial Estate,, Harita, Hosur, Hosur | 1 | 31 | 680 | sathish.narashiman | 8220007523 | sathish.narashiman@jbm-group.com | sathish.narashiman | - | sathish.narashiman@jbm-group.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | COMPLETE | 2015-08-27 | 2015-08-27 | 1 |  | HEMAKSH PATIL
372 | 2015-11-23 | 9:16:38 AM | Sapl0005 | 1 | 3 | A004 | 378 | 389 | C2_PO1516_ 001970 | 34 | 0 | S0104 | 2015-08-31 | LONG RAIL C63 | HEMAKSH PATIL | 2 | 2015-08-31 | 2015-08-31 | 2015-08-31 | 2015-08-31 | 2015-08-31 | 2015-08-31 | 2015-08-31 | 2015-08-31 | 2015-09-01 | 2015-09-01 | 2015-08-31 | 2015-08-31 | 2015-08-31 | 2015-08-31 | 2015-08-31 | 2015-08-31 | Autoline Industries Limited (C2) S No. 313, 314, 320 to 323, Nanekarwadi, Chakan, Taluka Khed,, | 1 | 21 | 405 | Dnyaneshwar.Phalke | 9970169842 | Dnyaneshwar.Phalke@autolineind.com | atmaram.ghogare | - | atmaram.ghogare@autolineind.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-08-31 | 2015-08-31 | 1 |  | HEMAKSH PATIL
373 | 2017-01-23 | 2:54:08 PM | Sapl0005 | 1 | 3 | S026 | 379 | 390 | VER9 | 34 | 0 | S0105 | 2015-09-09 | Kemppi Machine | HEMAKSH PATIL | 4 | 2015-09-09 | 2015-09-11 | 2015-09-11 | 2015-09-14 | 2015-09-15 | 2015-09-15 | 2015-09-15 | 2015-09-15 | 2015-09-15 | 2015-09-15 | 2015-09-15 | 2015-09-15 | 2015-09-15 | 2015-09-15 | 2015-09-15 | 2015-09-15 | SAKSHI ENTERPRIESES | 1 | 21 | 405 | Kakade | - | info@sakshiindia.com | Kakade | - | info@sakshiindia.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-09-09 | 2015-09-09 | 1 |  | HEMAKSH PATIL
374 | 2015-11-23 | 9:17:10 AM | Sapl0005 | 1 | 3 | U002 | 380 | 391 | Verbal_02 | 34 | 0 | S0106 | 2015-09-09 | KEMPPI MACHINES | HEMAKSH PATIL | 4 | 2015-09-09 | 2015-09-09 | 2015-09-09 | 2015-09-09 | 2015-09-09 | 2015-09-09 | 2015-09-09 | 2015-09-09 | 2015-09-09 | 2015-09-09 | 2015-09-09 | 2015-09-09 | 2015-09-09 | 2015-09-09 | 2015-09-09 | 2015-09-09 | UNIQUE PRESSING, CHAKAN | 1 | 21 | 405 | ABC | - | ABC@UNIQUE.COM | ABC | - | ABC@UNIQUE.COM | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-09-09 | 2015-09-09 | 1 |  | HEMAKSH PATIL
375 | 2015-11-23 | 9:17:34 AM | Sapl0005 | 1 | 3 | J009 | 381 | 392 | JOAI/A/1500084 | 34 | 0 | S0107 | 2015-09-24 | CROSS TROLLEY 255 LENGTH | HEMAKSH PATIL | 2 | 2015-09-24 | 2015-09-28 | 2015-09-28 | 2015-09-28 | 2015-09-28 | 2015-09-28 | 2015-09-28 | 2015-09-28 | 2015-09-28 | 2015-09-28 | 2015-09-28 | 2015-09-28 | 2015-09-28 | 2015-09-28 | 2015-09-28 | 2015-09-28 | JOAI, BANGLORE | 1 | 17 | 293 | ARADHYE T. C | - | purchase@joai.co.in | shivaprasad | - | shivaprasad@joai.co.in | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-09-24 | 2015-09-24 | 1 |  | HEMAKSH PATIL
376 | 2016-11-03 | 11:20:59 AM | Sapl0005 | 1 | 3 | S011 | 382 | 393 | PUOR15002853 | 37 | 0 | P0037 | 2015-09-29 | BREAK COIL LIFTO | HEMAKSH PATIL | 4 | 2015-09-29 | 2015-10-30 | 2015-09-30 | 2015-10-01 | 2015-10-01 | 2015-10-02 | 2015-10-05 | 2015-10-05 | 2015-10-10 | 2015-10-10 | 2015-10-02 | 2015-10-03 | 2015-10-10 | 2015-10-10 | 2015-10-10 | 2015-10-10 | 690, Udyambag Industrial Estate, BELGAUM | 1 | 17 | 295 | M N PATIL | 07899836618 | purchase@shantiiron.net | SHANTILAL V PORWAL | - | svp@shantiiron.net | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-09-29 | 2015-09-29 | 1 |  | HEMAKSH PATIL
379 | 2017-12-08 | 4:44:36 PM | Sapl0005 | 1 | 3 | C004 | 385 | 396 | verbaloct | 35 | 0 | N0112 | 2015-10-02 | Trolley for lifting | Prajyot Genji | 19 | 2015-10-02 | 2015-10-03 | 2015-10-03 | 2015-10-07 | 2015-10-03 | 2015-10-06 | 2015-10-08 | 2015-10-08 | 2015-10-09 | 2015-10-10 | 2015-10-03 | 2015-10-06 | 2015-10-11 | 2015-10-11 | 2015-10-08 | 2015-10-08 | cil, kothrud | 1 | 21 | 405 | mohini patil | - | mohini.patil@cummins.com | mohini patil | - | mohini.patil@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2015-10-05 | 2015-10-05 | 1 |  | Prajyot Genji
381 | 2016-05-12 | 12:27:36 PM | Sapl0005 | 1 | 3 | C004 | 387 | 398 | verbwa2 | 35 | 0 | N0114 | 2015-10-02 | Modification of washing booth | HEMAKSH PATIL | 4 | 2015-10-02 | 2015-10-10 | 2015-10-12 | 2015-10-19 | 2015-10-20 | 2015-10-27 | 2015-11-04 | 2015-11-07 | 2015-11-09 | 2015-11-11 | 2015-10-27 | 2015-11-03 | 2015-11-12 | 2015-11-16 | 2015-11-09 | 2015-11-11 | CIL, PUNE | 1 | 21 | 405 | Milind Bhagwat | - | milind.v.bhagwat@cummins.com | Milind Bhagwat | - | milind.v.bhagwat@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | order not received | 2015-10-20 | 2015-10-20 | 1 |  | HEMAKSH PATIL
382 | 2017-12-08 | 4:45:13 PM | Sapl0005 | 1 | 3 | C004 | 388 | 399 | verbrol2 | 35 | 0 | N0115 | 2016-05-12 | modification of roller line | Dhananjay Sirsikar | 4 | 2016-05-12 | 2017-04-22 | 2016-05-23 | 2017-04-22 | 2016-06-01 | 2016-06-11 | 2016-06-23 | 2016-06-28 | 2016-07-01 | 2016-07-09 | 2016-06-12 | 2016-06-22 | 2016-06-23 | 2016-05-12 | 2016-06-27 | 2016-06-30 | CIL, PUNE | 1 | 21 | 405 | Milind Bhagwat | - | milind.v.bhagwat@cummins.com | Milind Bhagwat | - | milind.v.bhagwat@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2016-06-01 | 2016-06-01 | 1 |  | Dhananjay Sirsikar
393 | 2015-11-23 | 9:18:22 AM | Sapl0005 | 1 | 3 | A024 | 399 | 410 | 7015004214 | 34 | 0 | S0115 | 2015-11-05 | GUNRAIL C63 | HEMAKSH PATIL | 2 | 2015-11-05 | 2015-11-07 | 2015-11-07 | 2015-11-07 | 2015-11-07 | 2015-11-07 | 2015-11-07 | 2015-11-07 | 2015-11-07 | 2015-11-07 | 2015-11-07 | 2015-11-07 | 2015-11-07 | 2015-11-07 | 2015-11-07 | 2015-11-07 | AUTOCOMP CORPORATION PANSE PVT.LTD - DharwadPlot No. 125, Survey No. 258,Belur Industrial Area,Village-Belur,Garag Hubli,Tal : Dharwad,(Karnataka)-580011 | 1 | 17 | 304 | YOGESH SHIRSAT | +91-7387103990 | papl1.purchase@pansegroup.com | RAJGURU | - | pmrajguru@pansegroup.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-11-05 | 2015-11-05 | 1 |  | HEMAKSH PATIL
394 | 2016-02-08 | 9:51:05 AM | Sapl0005 | 1 | 3 | A031 | 400 | 411 | 2804500107 | 35 | 0 | N0120 | 2015-11-05 | Supply of Water line & Air Line - O3 Pro | HEMAKSH PATIL | 2 | 2015-11-05 | 2015-11-05 | 2015-11-05 | 2015-11-05 | 2015-11-05 | 2015-11-05 | 2015-11-05 | 2015-11-05 | 2015-11-05 | 2015-11-05 | 2015-11-05 | 2015-11-05 | 2015-11-05 | 2015-11-05 | 2015-11-05 | 2015-11-05 | ASAL, PANTNAGAR | 1 | 34 | 679 | Shadul Shaikh | - | Shadul.Shaikh@autostampings.com | mohan datir | - | Mohan.Datir@autostampings.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-11-05 | 2015-11-05 | 1 |  | HEMAKSH PATIL
395 | 2016-02-08 | 9:43:11 AM | Sapl0005 | 1 | 3 | C004 | 402 | 412 | IND3380091 | 38 | 0 | J0072 | 2015-11-16 | Fixture to wash K19/KV con rod in washing booth | HEMAKSH PATIL | 1 | 2015-11-16 | 2015-11-17 | 2015-11-17 | 2015-11-18 | 2015-11-18 | 2015-11-19 | 2015-11-22 | 2015-11-23 | 2015-11-24 | 2015-11-24 | 2015-11-19 | 2015-11-21 | 2015-11-22 | 2015-11-25 | 2015-11-25 | 2015-11-25 | Cummins India Limited:CIL_EBU_085 Kothrud:: Pune Maharashtra 411038 India | 1 | 21 | 405 | MARY VYDANI | 7720048241 | mary.vydani@cummins.com | asis sahoo | - | asiskumar.sahoo@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-11-17 | 2015-11-17 | 1 |  | HEMAKSH PATIL
397 | 2016-03-31 | 11:17:26 AM | Sapl0005 | 1 | 3 | S006 | 404 | 414 | ve19 | 34 | 0 | S0117 | 2015-11-19 | Rails C63 | HEMAKSH PATIL | 2 | 2015-11-19 | 2015-11-21 | 2015-11-22 | 2015-11-25 | 2015-11-25 | 2015-11-26 | 2015-11-29 | 2015-11-29 | 2015-11-29 | 2015-11-29 | 2015-11-26 | 2015-11-28 | 2015-11-29 | 2015-11-29 | 2015-11-29 | 2015-11-29 | sapl | 1 | 21 | 405 | - | - | sales@synergytechs.com | - | - | sales@synergytechs.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-11-25 | 2015-11-25 | 1 |  | HEMAKSH PATIL
398 | 2016-01-01 | 3:15:21 PM | Sapl0005 | 1 | 3 | J009 | 405 | 415 | JOAI/A/1500113 | 34 | 0 | S0118 | 2015-11-19 | CROSS TROLLEY -255MM LENGTH | HEMAKSH PATIL | 2 | 2015-11-19 | 2015-11-21 | 2015-11-22 | 2015-11-24 | 2015-11-24 | 2015-11-25 | 2015-11-25 | 2015-11-25 | 2015-11-25 | 2015-11-25 | 2015-11-25 | 2015-11-25 | 2015-11-25 | 2015-11-25 | 2015-11-25 | 2015-11-25 | JOAI, BANGLORE | 1 | 17 | 293 | Aradhya T.C | 9916889090 | purchase@joai.co.in | shivaprasad | - | shivaprasad@joai.co.in | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-11-25 | 2015-11-25 | 1 |  | HEMAKSH PATIL
402 | 2015-12-08 | 10:38:35 AM | Sapl0005 | 1 | 3 | J015 | 410 | 421 | 4100052492 | 36 | 0 | E0025 | 2015-12-02 | Erection & Comm. of 384 Meter Rails | HEMAKSH PATIL | 2 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | BM AUTO SYSTEM PRIVATE LIMITED, , Plot No AV-13, Bol Industrial Estate, GIDC, Sanand-II,, 382170, | 1 | 12 | 681 | Surendar Singh | 8155007778 | satyender.singh@jbm-group.com | Jitender.Yadav | - | Jitender.Yadav@jbm.co.in | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-12-02 | 2015-12-02 | 1 |  | HEMAKSH PATIL
403 | 2020-12-05 | 11:24:20 AM | sapl0313 | 1 | 3 | C004 | 411 | 422 | IND3405241 | 43 | 0 | T0021 | 2015-12-03 | Transducer Panel, Jig Boom, Panel material | Hemkash Patil | 4 | 2015-12-03 | 2016-10-03 | 2015-12-06 | 2016-10-03 | 2015-12-09 | 2015-12-15 | 2015-12-21 | 2015-12-22 | 2015-12-23 | 2015-12-23 | 2015-12-15 | 2015-12-21 | 2015-12-21 | 2016-01-26 | 2015-12-22 | 2015-12-22 | Dahanukar Colony, Kothrud, Pune 411038 | 1 | 21 | 405 | divya vasudev | 7774003358 | divya.vasudev@cummins.com | AMIT MAHADESHWAR | - | amit.m.mahadeshwar@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | WO Close | 2015-12-05 | 2015-12-05 | 1 |  | Hemkash Patil
404 | 2020-12-05 | 11:24:44 AM | sapl0313 | 1 | 3 | C004 | 412 | 423 | IND3408068 | 43 | 0 | T0022 | 2015-12-08 | Control Panel with Trolley & material | HEMAKSH PATIL | 4 | 2015-12-08 | 2016-09-27 | 2015-12-10 | 2016-09-27 | 2015-12-13 | 2015-12-15 | 2015-12-21 | 2015-12-22 | 2015-12-23 | 2015-12-23 | 2015-12-15 | 2015-12-21 | 2015-12-21 | 2015-12-26 | 2015-12-21 | 2015-12-22 | INDIRECT_085:IM1-LOC-EP KOTHRUD:: Pune Maharashtra 411038 | 1 | 21 | 405 | divya vasudev | - | divya.vasudev@cummins.com | AMIT MAHADESHWAR | - | amit.m.mahadeshwar@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | WO Close | 2015-12-12 | 2015-12-12 | 1 |  | HEMAKSH PATIL
407 | 2016-02-08 | 9:51:34 AM | Sapl0005 | 1 | 3 | N007 | 415 | 426 | VERBAL | 35 | 0 | N0123 | 2015-12-14 | POLISHING MACHINE | PRAJYOT | 2 | 2015-12-14 | 2015-12-31 | 2015-12-16 | 2015-12-31 | 2015-12-21 | 2016-01-14 | 2016-01-14 | 2016-01-20 | 2016-01-21 | 2016-01-21 | 2015-12-22 | 2016-01-21 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | SURATMAL, MANLORE | 1 | 17 | 293 | PRAJYOT | - | prajyot@synergytechs.com | - | - | prajyot@synergytechs.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | complet | 2015-12-25 | 2015-12-25 | 1 |  | PRAJYOT
408 | 2017-07-21 | 10:08:07 AM | Sapl0005 | 1 | 3 | C004 | 416 | 427 | IND3414183 | 35 | 0 | N0124 | 2015-12-15 | METALIC SKIDS FOR BW Q-60 CYLINDER BLOCK (FULL SKID) | HEMAKSH PATIL | 3 | 2015-12-15 | 2015-12-22 | 2015-12-23 | 2016-01-09 | 2016-01-10 | 2016-01-17 | 2016-01-28 | 2016-01-30 | 2016-02-01 | 2016-02-01 | 2016-01-18 | 2016-01-27 | 2016-02-02 | 2016-02-03 | 2016-02-01 | 2016-02-01 | CIL_EBU_085 Kothrud:: Pune Maharashtra 411038 | 1 | 21 | 405 | Milind Bhagwat | 9850892902 | milind.v.bhagwat@cummins.com | Milind Bhagwat | - | milind.v.bhagwat@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2016-01-01 | 2016-01-01 | 1 |  | HEMAKSH PATIL
411 | 2016-03-31 | 11:13:46 AM | Sapl0005 | 1 | 3 | A032 | 419 | 430 | 7015005345 | 34 | 0 | S0120 | 2015-12-25 | GUNRAIL C63 & TELESCOPIC RAIL | HEMAKSH PATIL | 2 | 2015-12-25 | 2015-12-28 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-31 | 2015-12-31 | 2015-12-30 | 2015-12-30 | 2015-12-29 | 2015-12-29 | 2015-12-31 | 2016-01-01 | 2015-12-30 | 2015-12-31 | AUTOCOMP CORPORATION PANSE PVT. LTD., MOSHI | 1 | 21 | 405 | YOGESH SHIRSAT | - | PAPL1@PANSEGROUP.COM | Yogesh Shirsat | - | PAPL1@PANSEGROUP.COM | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-12-26 | 2015-12-26 | 1 |  | HEMAKSH PATIL
412 | 2016-02-12 | 9:36:29 AM | Sapl0005 | 1 | 3 | C004 | 420 | 431 | IND3427191 | 38 | 0 | J0076 | 2015-12-31 | Scissor type lifter | HEMAKSH PATIL | 7 | 2015-12-31 | 2016-02-02 | 2016-01-02 | 2016-01-03 | 2016-01-03 | 2016-01-03 | 2016-01-03 | 2016-01-03 | 2016-01-04 | 2016-01-05 | 2016-01-03 | 2016-01-04 | 2016-01-03 | 2016-01-04 | 2016-01-04 | 2016-01-04 | cummins india ltd. | 1 | 21 | 405 | Asis sahoo | 8805362400 | asiskumar.sahoo@cummins.com | asis sahoo | - | asiskumar.sahoo@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | COMPLETE | 2016-01-01 | 2016-01-01 | 1 |  | HEMAKSH PATIL
414 | 2017-12-22 | 10:13:35 AM | Sapl0005 | 1 | 3 | A004 | 422 | 433 | C2_PO1516_ 003404 | 34 | 0 | S0121 | 2015-12-31 | Long rail , cross rail & trolley set | HEMAKSH PATIL | 2 | 2015-12-31 | 2016-01-02 | 2016-01-03 | 2016-01-04 | 2016-01-04 | 2016-01-04 | 2016-01-07 | 2016-01-08 | 2016-01-05 | 2016-01-05 | 2016-01-04 | 2015-12-05 | 2016-01-06 | 2016-01-08 | 2016-01-05 | 2016-01-05 | Autoline Industries Limited (C2) S No. 313, 314, 320 to 323, Nanekarwadi, Chakan, Taluka Khed,, | 1 | 21 | 405 | dnyaneshwar phalke | 9970169842 | Dnyaneshwar.Phalke@autolineind.com | atmaram.ghogare | - | atmaram.ghogare@autolineind.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | partial order cancelled by customer | 2016-01-01 | 2016-01-01 | 1 |  | HEMAKSH PATIL
415 | 2017-07-21 | 10:02:02 AM | Sapl0005 | 1 | 3 | S006 | 423 | 434 | verb1jan | 34 | 0 | S0122 | 2016-01-01 | Mechanical Car Parking | Prajyot Genji | 19 | 2016-01-01 | 2016-04-30 | 2016-01-05 | 2016-04-30 | 2016-01-10 | 2016-01-16 | 2016-01-24 | 2016-01-29 | 2016-01-30 | 2016-01-30 | 2016-01-16 | 2016-01-23 | 2016-01-24 | 2016-02-04 | 2016-01-24 | 2016-01-27 | SAPL,Pune | 1 | 21 | 405 | - | - | sales@synergytechs.com | - | - | sales@synergytechs.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 1 | COMPLETE | 2016-01-04 | 2016-01-04 | 1 |  | Prajyot Genji
416 | 2016-02-08 | 9:58:50 AM | Sapl0005 | 1 | 3 | C013 | 424 | 435 | 009 | 34 | 0 | S0123 | 2016-01-04 | Rails & load trolley | HEMAKSH PATIL | 2 | 2016-01-04 | 2016-01-05 | 2016-01-05 | 2016-01-05 | 2016-01-05 | 2016-01-05 | 2016-01-05 | 2016-01-05 | 2016-01-05 | 2016-01-05 | 2016-01-05 | 2016-01-05 | 2016-01-05 | 2016-01-05 | 2016-01-05 | 2016-01-05 | CONSULTECH ENGINEERS PVT. LTD. S. No.78, Dangat Industrial Estate, Shivne, | 1 | 21 | 405 | J. V. Ingale | 9890013871 | jvi@consultechindia.com | J. V. Ingale | - | jvi@consultechindia.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-01-05 | 2016-01-05 | 1 |  | HEMAKSH PATIL
417 | 2017-05-15 | 9:43:16 AM | Sapl0005 | 1 | 3 | N002 | 425 | 436 | LOI6jan | 35 | 0 | N0125 | 2016-01-06 | Welding fixtures for FES Project | PADMASINHA JOSHI | 3 | 2016-01-06 | 2016-08-31 | 2016-01-20 | 2016-08-31 | 2016-02-06 | 2016-02-17 | 2016-02-25 | 2016-02-29 | 2016-03-02 | 2016-03-04 | 2016-02-18 | 2016-02-25 | 2016-02-25 | 2016-03-19 | 2016-02-25 | 2016-02-27 | NMPL, Pantnagar | 1 | 34 | 679 | sanjay.dudeja | - | sanjay.dudeja@jbm.co.in | SANJAY MURGAI | - | smurgai@jbm.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2016-01-28 | 2016-01-28 | 1 |  | PADMASINHA JOSHI
418 | 2016-11-03 | 11:18:30 AM | Sapl0005 | 1 | 3 | M023 | 426 | 437 | VERB16 | 35 | 0 | N0126 | 2016-01-09 | J HOOK SPM | HEMAKSH PATIL | 2 | 2016-01-09 | 2016-01-12 | 2016-01-12 | 2016-01-16 | 2016-01-17 | 2016-01-20 | 2016-01-28 | 2016-02-02 | 2016-02-03 | 2016-02-05 | 2016-01-21 | 2016-01-28 | 2016-02-05 | 2016-02-10 | 2016-01-28 | 2016-02-02 | MI | 1 | 21 | 405 | JAGDALE | - | millennium4059@gmail.com | JAGDALE | - | millennium4059@gmail.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2016-01-13 | 2016-01-13 | 1 |  | HEMAKSH PATIL
419 | 2018-02-21 | 11:06:45 AM | Sapl0005 | 1 | 3 | N002 | 427 | 438 | verbjan18 | 35 | 0 | N0127 | 2016-01-18 | Welding Fixtures For FES | PADMASINHA JOSHI | 3 | 2016-01-06 | 2016-09-08 | 2016-01-20 | 2016-09-08 | 2016-02-06 | 2016-02-17 | 2016-02-25 | 2016-02-29 | 2016-03-02 | 2016-02-04 | 2016-02-18 | 2016-02-25 | 2016-02-25 | 2016-03-19 | 2016-02-25 | 2016-02-27 | Neel Metal Product | 1 | 34 | 679 | Ashwani Kumar | 9811498591 | ashwani.saini@jbm.co.in | anoop.sahai | - | anoop.sahai@jbm.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2016-01-28 | 2016-01-28 | 1 |  | PADMASINHA JOSHI
420 | 2016-03-31 | 10:57:30 AM | Sapl0005 | 1 | 3 | C004 | 428 | 439 | IND3441802 | 38 | 0 | J0077 | 2016-01-18 | LIFTING TACKLE A16005 | HEMAKSH PATIL | 7 | 2016-01-18 | 2016-01-20 | 2016-01-20 | 2016-01-21 | 2016-01-22 | 2016-01-23 | 2016-01-25 | 2016-01-25 | 2016-01-26 | 2016-01-27 | 2016-01-23 | 2016-01-25 | 2016-01-28 | 2016-01-29 | 2016-01-25 | 2016-01-25 | CIL, PUNE | 1 | 21 | 405 | prasad walke | 7720028701 | prasad.walke@cummins.com | deepak.s.patil | - | deepak.s.patil@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-01-22 | 2016-01-22 | 1 |  | HEMAKSH PATIL
421 | 2016-02-08 | 9:40:49 AM | Sapl0005 | 1 | 3 | A031 | 429 | 440 | 2804532536 | 36 | 0 | E0028 | 2016-01-22 | Weldeck Structure Of MCV Project | HEMAKSH PATIL | 2 | 2016-01-21 | 2016-01-21 | 2016-01-21 | 2016-01-21 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | ASAL, PANTNAGAR | 1 | 34 | 679 | Shadul Shaikh | - | Shadul.Shaikh@autostampings.com | Mohan.Datir | - | Mohan.Datir@autostampings.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-01-22 | 2016-01-22 | 1 |  | HEMAKSH PATIL
422 | 2016-02-08 | 9:41:00 AM | Sapl0005 | 1 | 3 | A031 | 430 | 441 | 2804532535 | 36 | 0 | E0029 | 2016-01-22 | labour charges -welddeck structure o3 project | HEMAKSH PATIL | 2 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | ASAL, PANTNAGAR | 1 | 34 | 679 | Shadul Shaikh | - | Shadul.Shaikh@autostampings.com | Mohan.Datir | - | Mohan.Datir@autostampings.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-01-22 | 2016-01-22 | 1 |  | HEMAKSH PATIL
423 | 2016-02-08 | 9:41:11 AM | Sapl0005 | 1 | 3 | A030 | 431 | 442 | 2802533910 | 36 | 0 | E0030 | 2016-01-22 | labour charges -welddeck structure o2 project | HEMAKSH PATIL | 2 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | ASAL, CHAKAN | 1 | 21 | 405 | Shadul Shaikh | - | Shadul.Shaikh@autostampings.com | Mohan.Datir | - | Mohan.Datir@autostampings.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-01-22 | 2016-01-22 | 1 |  | HEMAKSH PATIL
424 | 2016-02-08 | 9:41:35 AM | Sapl0005 | 1 | 3 | A007 | 432 | 443 | 2801532934 | 36 | 0 | E0031 | 2016-01-22 | labour charges -welddeck structure o2 project | HEMAKSH PATIL | 2 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 | asal Bhosari | 1 | 21 | 405 | Shadul Shaikh | - | Shadul.Shaikh@autostampings.com | Mohan.Datir | - | Mohan.Datir@autostampings.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-01-22 | 2016-01-22 | 1 |  | HEMAKSH PATIL
425 | 2016-02-08 | 9:59:14 AM | Sapl0005 | 1 | 3 | A030 | 433 | 444 | 2802500176 | 34 | 0 | S0124 | 2016-01-23 | RAILS FOR WINDSHIELD PROJECT | HEMAKSH PATIL | 2 | 2016-01-23 | 2016-01-23 | 2016-01-23 | 2016-01-23 | 2016-01-23 | 2016-01-26 | 2016-02-02 | 2016-02-02 | 2016-01-30 | 2016-01-30 | 2016-01-26 | 2016-01-29 | 2016-01-31 | 2016-02-02 | 2016-01-30 | 2016-01-30 | ASAL, CHAKAN | 1 | 21 | 405 | Shadul Shaikh | - | Shadul.Shaikh@autostampings.com | Mohan.Datir | - | Mohan.Datir@autostampings.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | complet | 2016-01-23 | 2016-01-23 | 1 |  | HEMAKSH PATIL
426 | 2016-05-12 | 12:31:08 PM | Sapl0005 | 1 | 3 | J003 | 434 | 445 | 4300021850 | 34 | 0 | S0125 | 2016-01-28 | Gunrail C63 & trolley set | HEMAKSH PATIL | 2 | 2016-01-28 | 2016-01-28 | 2016-01-28 | 2016-01-28 | 2016-01-29 | 2016-02-01 | 2016-02-03 | 2016-02-04 | 2016-02-02 | 2016-02-02 | 2016-01-29 | 2016-02-01 | 2016-02-03 | 2016-03-04 | 2016-02-02 | 2016-02-02 | JBM MA AUTOMOTIVE PVT. LTD. | 1 | 21 | 405 | vilas.kanade | - | vilas.kanade@jbmmagnetto.com | kishan.shinde | - | kishan.shinde@jbmmagnetto.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-01-28 | 2016-01-28 | 1 |  | HEMAKSH PATIL
427 | 2016-02-12 | 9:30:49 AM | Sapl0005 | 1 | 3 | J003 | 435 | 446 | 4300021980 | 34 | 0 | S0126 | 2016-02-06 | TROLLEY SET C63 | HEMAKSH PATIL | 2 | 2016-02-06 | 2016-02-06 | 2016-02-06 | 2016-02-06 | 2016-02-06 | 2016-02-06 | 2016-02-06 | 2016-02-06 | 2016-02-08 | 2016-02-08 | 2016-02-06 | 2016-02-06 | 2016-02-06 | 2016-02-06 | 2016-02-06 | 2016-02-06 | JBM MA Automotive Private Limited | 1 | 21 | 405 | vilas.kanade | 09922435918 | vilas.kanade@jbmmagnetto.com | kishan.shinde | - | kishan.shinde@jbmmagnetto.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-02-06 | 2016-02-06 | 1 |  | HEMAKSH PATIL
428 | 2016-02-12 | 9:30:29 AM | Sapl0005 | 1 | 3 | A032 | 436 | 447 | 7015006351 | 34 | 0 | S0127 | 2016-02-10 | TROLLEY SET C63 | HEMAKSH PATIL | 2 | 2016-02-10 | 2016-02-10 | 2016-02-10 | 2016-02-10 | 2016-02-10 | 2016-02-10 | 2016-02-10 | 2016-02-10 | 2016-02-10 | 2016-02-10 | 2016-02-10 | 2016-02-10 | 2016-02-10 | 2016-02-10 | 2016-02-10 | 2016-02-10 | AUTOCOMPS CORPORATION PANSE PVT LTD MOSHI-I GAT NO.219, VILLAGE-BORHADEWADI , DEHU-ALANDI ROAD , MOSHI, PUNE-412 114 | 1 | 21 | 405 | YOGESH SHIRSAT | - | papl1.purchase@pansegroup.com | Yogesh Shirsat | - | papl1.purchase@pansegroup.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-02-10 | 2016-02-10 | 1 |  | HEMAKSH PATIL
430 | 2016-11-03 | 10:23:29 AM | Sapl0005 | 1 | 3 | C004 | 438 | 449 | verbal15feb | 38 | 0 | J0078 | 2016-02-15 | A66025 & A66027 | HEMAKSH PATIL | 2 | 2016-02-15 | 2016-02-17 | 2016-02-17 | 2016-02-19 | 2016-02-19 | 2016-02-22 | 2016-02-25 | 2016-02-25 | 2016-02-26 | 2016-02-26 | 2016-02-23 | 2016-02-24 | 2016-02-26 | 2016-02-26 | 2016-02-26 | 2016-02-26 | cummins india ltd. | 1 | 21 | 405 | Asis sahoo | - | asiskumar.sahoo@cummins.com | asis sahoo | - | asiskumar.sahoo@cummins.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-02-17 | 2016-02-17 | 1 |  | HEMAKSH PATIL
431 | 2016-03-31 | 11:16:43 AM | Sapl0005 | 1 | 3 | A033 | 439 | 450 | 7015006737 | 34 | 0 | S0128 | 2016-02-24 | TELESCOPIC TROLLY SET C63 | HEMAKSH PATIL | 2 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-25 | 2016-02-25 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-25 | 2016-02-25 | AUTOCOMP CORPORATION PANSE PVT.LTD - Chennai C/O TVS LOGISTICS SERVICES LTD NO 136 B BLOCK VAIPUR ,NEAR ERAIYUR VILL. VILLAGE MATHUR SRIPERUMBUDUR, STATE - TAMILNADU 602105 | 1 | 31 | 537 | YOGESH SHIRSAT | - | papl1.purchase@pansegroup.com | Yogesh Shirsat | - | papl1.purchase@pansegroup.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-02-24 | 2016-02-24 | 1 |  | HEMAKSH PATIL
432 | 2016-03-31 | 11:16:22 AM | Sapl0005 | 1 | 3 | J003 | 440 | 451 | 4300022151 | 34 | 0 | S0129 | 2016-02-25 | Cross Rail & Trolley Set C63 | HEMAKSH PATIL | 2 | 2016-02-25 | 2016-02-25 | 2016-02-25 | 2016-02-25 | 2016-02-25 | 2016-02-25 | 2016-02-25 | 2016-02-25 | 2016-02-25 | 2016-02-25 | 2016-02-25 | 2016-02-25 | 2016-02-25 | 2016-02-25 | 2016-02-25 | 2016-02-25 | JBM MA Automotive Pvt. Limited C-1/2, Chakan MIDC Area 410501 Pune | 1 | 21 | 405 | vilas.kanade | - | vilas.kanade@jbmmagnetto.com | kishan.shinde | - | kishan.shinde@jbmmagnetto.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-02-25 | 2016-02-25 | 1 |  | HEMAKSH PATIL
433 | 2016-03-31 | 11:11:31 AM | Sapl0005 | 1 | 3 | T013 | 441 | 452 | loi27feb | 37 | 0 | P0038 | 2016-02-27 | SCISSOR LIFT HYD.CYL | HEMAKSH PATIL | 2 | 2016-02-27 | 2016-02-27 | 2016-02-27 | 2016-02-27 | 2016-02-27 | 2016-02-27 | 2016-02-27 | 2016-02-27 | 2016-02-27 | 2016-03-12 | 2016-02-27 | 2016-02-27 | 2016-02-27 | 2016-02-27 | 2016-02-27 | 2016-02-27 | TATA MOTOTRS LTD. | 1 | 17 | 304 | Sudhindra Kulkarni | 8792002445 | SNK810108@tatamotors.com | vaibhav.kulkarni2 | - | vaibhav.kulkarni2@tatamotors.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 1 |  | 1 | COMPLETE | 2016-02-27 | 2016-02-27 | 1 |  | HEMAKSH PATIL
434 | 2016-05-12 | 12:29:51 PM | Sapl0005 | 1 | 3 | T013 | 442 | 453 | 2840018590 | 37 | 0 | P0039 | 2016-03-10 | KEMPI SP003508 A001 MXF 63/65 | HEMAKSH PATIL | 4 | 2016-03-10 | 2016-03-14 | 2016-03-14 | 2016-03-14 | 2016-03-14 | 2016-03-14 | 2016-03-14 | 2016-03-14 | 2016-03-15 | 2016-03-15 | 2016-03-14 | 2016-03-14 | 2016-03-14 | 2016-03-14 | 2016-03-14 | 2016-03-14 | TATA Motors Limited, Mummigatti Post Belur Industrial Area Dharwad-580011 | 1 | 17 | 304 | kallappa.kelageri | 8095335468 | kallappa.kelageri@tatamotors.com | vaibhav.kulkarni2 | - | vaibhav.kulkarni2@tatamotors.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | order cancel | 2016-03-10 | 2016-03-10 | 1 |  | HEMAKSH PATIL
435 | 2016-03-31 | 11:16:01 AM | Sapl0005 | 1 | 3 | A030 | 443 | 454 | 2802500211 | 34 | 0 | S0130 | 2016-03-22 | rails for o2 project | HEMAKSH PATIL | 7 | 2016-03-22 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | ASAL CHAKAN | 1 | 21 | 405 | Shadul Shaikh | - | Shadul.Shaikh@autostampings.com | Mohan.Datir | - | Mohan.Datir@autostampings.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-03-22 | 2016-03-22 | 1 |  | HEMAKSH PATIL
436 | 2017-05-15 | 9:40:12 AM | Sapl0005 | 1 | 3 | N002 | 444 | 455 | verb24mar | 35 | 0 | N0129 | 2016-03-24 | Welding fixtures for FES Project | PADMASINHA JOSHI | 3 | 2016-03-24 | 2016-09-08 | 2016-03-31 | 2016-09-08 | 2016-04-01 | 2016-04-04 | 2016-04-07 | 2016-04-09 | 2016-04-11 | 2016-04-11 | 2016-04-05 | 2016-04-07 | 2016-04-07 | 2016-04-12 | 2016-04-08 | 2016-04-09 | neel metal products , pantnagar | 1 | 34 | 679 | snajay murgai | - | smurgai@jbm.co.in | Sanjay Dudeja | - | sanjay.dudeja@jbm.co.in | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2016-03-24 | 2016-03-24 | 1 |  | PADMASINHA JOSHI
437 | 2016-03-31 | 11:12:57 AM | Sapl0005 | 1 | 3 | A032 | 445 | 456 | 7015007450 | 34 | 0 | S0131 | 2016-03-25 | TROLLEY SET | HEMAKSH PATIL | 7 | 2016-03-25 | 2016-03-25 | 2016-03-25 | 2016-03-25 | 2016-03-25 | 2016-03-25 | 2016-03-25 | 2016-03-25 | 2016-03-25 | 2016-03-25 | 2016-03-25 | 2016-03-25 | 2016-03-25 | 2016-03-25 | 2016-03-25 | 2016-03-25 | GAT NO.219, VILLAGE-BORHADEWADI , DEHU-ALANDI ROAD , MOSHI, PUNE-412 114 | 1 | 21 | 405 | yogesh shirsath | - | papl1.purchase@pansegroup.com | yogesh shirsath | - | papl1.purchase@pansegroup.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-03-25 | 2016-03-25 | 1 |  | HEMAKSH PATIL
438 | 2016-03-31 | 11:34:24 AM | Sapl0005 | 1 | 3 | S027 | 446 | 457 | 313 | 34 | 0 | S0132 | 2016-03-26 | long rail, cross rail, trolley set | HEMAKSH PATIL | 7 | 2016-03-26 | 2016-03-27 | 2016-03-27 | 2016-03-28 | 2016-03-30 | 2016-03-30 | 2016-03-30 | 2016-03-30 | 2016-03-31 | 2016-03-31 | 2016-03-30 | 2016-03-30 | 2016-03-30 | 2016-03-30 | 2016-03-30 | 2016-03-30 | sakshi enterpriese | 1 | 21 | 405 | Kakade | - | info@sakshiindia.co.in | Kakade | - | info@sakshiindia.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-03-30 | 2016-03-30 | 1 |  | HEMAKSH PATIL
439 | 2016-11-03 | 10:42:29 AM | Sapl0005 | 1 | 3 | A030 | 447 | 458 | verbalmarch | 35 | 0 | N0130 | 2016-03-30 | Welddeck Structure | HEMAKSH PATIL | 2 | 2016-03-30 | 2016-03-31 | 2016-03-30 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | ASAL, CHAKAN | 1 | 21 | 405 | Shadul Shaikh | - | Shadul.Shaikh@autostampings.com | Mohan.Datir | - | Mohan.Datir@autostampings.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-03-31 | 2016-03-31 | 1 |  | HEMAKSH PATIL
440 | 2016-11-03 | 10:43:34 AM | Sapl0005 | 1 | 3 | A007 | 448 | 459 | verbmar | 35 | 0 | N0131 | 2016-03-31 | Additional welddeck work | HEMAKSH PATIL | 2 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | ASAL, BHOSARI | 1 | 21 | 405 | Shadul Shaikh | - | Shadul.Shaikh@autostampings.com | Mohan.Datir | - | Mohan.Datir@autostampings.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-03-31 | 2016-03-31 | 1 |  | HEMAKSH PATIL
441 | 2016-05-12 | 12:31:27 PM | Sapl0005 | 1 | 3 | G015 | 449 | 460 | BO/SAP/16-17/11 IV | 34 | 0 | S0133 | 2016-04-11 | CROSS RAIL C63 & TROLLEY SET C63 | HEMAKSH PATIL | 7 | 2016-04-11 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | GLORIA ENGINEERING COMPANY | 1 | 21 | 405 | MAHAJAN.D.G | - | dgmahajan2013@rediffmail.com | amit.agarwal | - | amit.agarwal@gloriagroup.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-04-13 | 2016-04-13 | 1 |  | HEMAKSH PATIL
442 | 2016-09-07 | 10:42:35 AM | Sapl0005 | 1 | 3 | B001 | 450 | 461 | 4700003748 | 34 | 0 | S0134 | 2016-04-13 | long rail, cross rail, trolley set C63 | HEMAKSH PATIL | 7 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | Badve Engg Unit 12 | 1 | 34 | 679 | vinodsingh | 9927880040 | vinodsingh@badvegroup.com | pkupadhyay | - | pkupadhyay@badvegroup.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-04-13 | 2016-04-13 | 1 |  | HEMAKSH PATIL
445 | 2016-11-03 | 10:24:09 AM | Sapl0005 | 1 | 4 | S028 | 453 | 464 | 059 | 38 | 0 | J0080 | 2016-05-07 | Fins Welding | SANJAY SHINDE | 5 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | sonal enterprises - ambegaon | 1 | 21 | 405 | mr. babar | - | sonal@gmail.com | mr. babar | - | sonal@gmail.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-05-07 | 2016-05-07 | 1 |  | SANJAY SHINDE
447 | 2016-09-07 | 10:41:39 AM | Sapl0005 | 1 | 4 | S011 | 456 | 466 | PUOR16000627 | 37 | 0 | P0041 | 2016-05-16 | BRAKE SHOE ASSY LH & RH | Dhananjay Sirsikar | 4 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | Shanti Iron & Steel 690, Udyambag Industrial Estate, BELGAUM | 1 | 17 | 295 | M.N.Patil | - | purchase@shantiiron.net | SHANTILAL PORWAL | - | svp@shantiiron.net | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-05-16 | 2016-05-16 | 1 |  | Dhananjay Sirsikar
448 | 2020-12-05 | 11:25:10 AM | sapl0313 | 1 | 4 | S006 | 457 | 467 | verbmay | 43 | 0 | T0023 | 2016-05-20 | Multicopter Drone | Amit Shedge | 4 | 2016-05-20 | 2016-05-24 | 2016-05-24 | 2016-05-26 | 2016-05-26 | 2016-05-28 | 2016-05-31 | 2016-06-02 | 2016-06-03 | 2016-06-04 | 2016-05-28 | 2016-05-30 | 2016-07-04 | 2016-06-04 | 2016-06-03 | 2016-06-03 | Synergytech Automation | 1 | 21 | 405 | - | - | sales@synergytechs.com | - | - | sales@synergytechs.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | WO Close | 2016-05-24 | 2016-05-24 | 1 |  | Amit Shedge
449 | 2016-11-03 | 10:24:26 AM | Sapl0005 | 1 | 4 | C004 | 458 | 468 | IND3587512 | 38 | 0 | J0081 | 2016-06-18 | CONNECTION,WATER INLET,3011064 | SANJAY SHINDE | 5 | 2016-06-18 | 2016-06-18 | 2016-06-18 | 2016-06-18 | 2016-06-18 | 2016-06-22 | 2016-06-27 | 2016-06-29 | 2016-06-30 | 2016-07-02 | 2016-06-23 | 2016-06-25 | 2016-06-30 | 2016-07-02 | 2016-06-29 | 2016-07-02 | cummins india ltd. | 1 | 21 | 405 | Sharma, Rajeev | 8805705300 | Rajeev.Sharma@cummins.com | asiskumar.sahoo | - | asiskumar.sahoo@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-06-20 | 2016-06-20 | 1 |  | SANJAY SHINDE
450 | 2016-11-03 | 11:13:58 AM | Sapl0005 | 1 | 4 | M013 | 459 | 469 | verbaljune16 | 35 | 0 | N0132 | 2016-08-19 | Welding Fixtures for CCB | Prajyot Genji | 3 | 2016-08-19 | 2016-09-30 | 2016-08-22 | 2016-09-30 | 2016-06-13 | 2016-06-22 | 2016-06-24 | 2016-06-25 | 2016-08-30 | 2016-08-31 | 2016-06-23 | 2016-06-24 | 2016-06-24 | 2016-09-02 | 2016-08-30 | 2016-08-31 | Mahindra & Mahindra | 1 | 21 | 405 | PUTHRAN.NITESH | - | PUTHRAN.NITESH@mahindra.com | gaur dinesh | - | GAUR.DINESH@mahindra.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2016-08-19 | 2016-08-19 | 1 |  | Prajyot Genji
452 | 2016-11-03 | 10:24:53 AM | Sapl0005 | 1 | 4 | C004 | 461 | 471 | IND3604760 | 38 | 0 | J0082 | 2016-07-07 | KTAA19 Horizontal engine parts | SANJAY SHINDE | 5 | 2016-07-07 | 2016-07-07 | 2016-07-07 | 2016-07-07 | 2016-07-07 | 2016-07-14 | 2016-07-18 | 2016-07-18 | 2016-07-18 | 2016-07-18 | 2016-07-15 | 2016-07-16 | 2016-07-18 | 2016-07-18 | 2016-07-18 | 2016-07-18 | cummins india ltd. | 1 | 21 | 405 | MARY VYDANI | 7720048241 | mary.vydani@cummins.com | Surendar Jegannathan | - | Surendar.Jegannathan@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-07-12 | 2016-07-12 | 1 |  | SANJAY SHINDE
453 | 2016-11-03 | 10:26:06 AM | Sapl0005 | 1 | 4 | C004 | 462 | 472 | IND3606025 | 38 | 0 | J0083 | 2016-07-08 | CONNNECTON WALTER INLET 3008893 | SANJAY SHINDE | 5 | 2016-07-08 | 2016-07-11 | 2016-07-11 | 2016-07-13 | 2016-07-13 | 2016-07-20 | 2016-07-27 | 2016-07-27 | 2016-07-26 | 2016-07-27 | 2016-07-20 | 2016-07-25 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | cummins india ltd. | 1 | 21 | 405 | Rajeev.Sharma | 8805705300 | Rajeev.Sharma@cummins.com | asiskumar.sahoo | - | asiskumar.sahoo@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-07-13 | 2016-07-13 | 1 |  | SANJAY SHINDE
454 | 2016-11-03 | 10:26:16 AM | Sapl0005 | 1 | 4 | C004 | 463 | 473 | IND3621011 | 38 | 0 | J0084 | 2016-07-25 | Functional Gauge to check concentricity | SANJAY SHINDE | 5 | 2016-07-27 | 2016-08-24 | 2016-07-29 | 2016-08-24 | 2016-08-01 | 2016-08-05 | 2016-08-12 | 2016-08-13 | 2016-08-10 | 2016-08-12 | 2016-08-06 | 2016-08-09 | 2016-08-12 | 2016-08-13 | 2016-08-13 | 2016-08-13 | cummins india ltd. kothrud | 1 | 21 | 405 | Asis sahoo | 8805362400 | asiskumar.sahoo@cummins.com | asis sahoo | - | asiskumar.sahoo@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 1 |  | 1 | COMPLETE | 2016-08-02 | 2016-08-02 | 1 |  | SANJAY SHINDE
455 | 2016-11-03 | 11:22:36 AM | Sapl0005 | 1 | 4 | N002 | 464 | 474 | 4300024026 | 34 | 0 | S0136 | 2016-07-27 | Long rail, cross rail & trolley set for FES Project | SANJAY SHINDE | 2 | 2016-07-27 | 2016-07-28 | 2016-08-01 | 2016-08-03 | 2016-08-03 | 2016-08-05 | 2016-08-20 | 2016-08-23 | 2016-08-10 | 2016-08-10 | 2016-08-06 | 2016-08-09 | 2016-08-23 | 2016-08-27 | 2016-08-20 | 2016-08-20 | Neel Metal Products Ltd PLOT No. 22, Sector 12, ITBT Park, IIE, SIDCUL, 263153, - Pant Nagar | 1 | 34 | 679 | Jitender.Yadav | - | Jitender.Yadav@jbm.co.in | sanjay.dudeja | - | sanjay.dudeja@jbm.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-08-02 | 2016-08-02 | 1 |  | SANJAY SHINDE
456 | 2016-11-03 | 11:29:30 AM | Sapl0005 | 1 | 4 | C004 | 465 | 475 | IND3641291 | 43 | 0 | T0024 | 2016-08-16 | Base Plate Material for Test Cell7 | Dhananjay Sirsikar | 4 | 2016-08-16 | 2016-10-06 | 2016-08-18 | 2016-10-06 | 2016-08-20 | 2016-08-22 | 2016-08-25 | 2016-08-26 | 2016-08-25 | 2016-08-25 | 2016-08-22 | 2016-08-24 | 2016-08-25 | 2016-08-27 | 2016-08-25 | 2016-08-26 | cummins india ltd., kothrud | 1 | 21 | 405 | Deshpande, Ashutosh | - | ashutosh.deshpande@cummins.com | shirkant.m.foujdar | - | shirkant.m.foujdar@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2016-08-19 | 2016-08-19 | 1 |  | Dhananjay Sirsikar
457 | 2016-11-03 | 10:26:26 AM | Sapl0005 | 1 | 4 | C004 | 466 | 476 | IND3641292 | 38 | 0 | J0085 | 2016-08-16 | Lifting, bracket | SANJAY SHINDE | 5 | 2016-08-16 | 2016-08-17 | 2016-08-17 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-20 | 2016-08-20 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | cummins india ltd., kothrud | 1 | 21 | 405 | MARY VYDANI | - | mary.vydani@cummins.com | Surendar Jegannathan | - | Surendar.Jegannathan@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-08-19 | 2016-08-19 | 1 |  | SANJAY SHINDE
458 | 2019-12-29 | 5:15:21 PM | Sapl0002 | 1 | 4 | C004 | 467 | 477 | IND3409697 | 36 | 0 | E0032 | 2016-08-20 | Transducer panel wiring work,Jig boom arm installation & Operator console panel wiring | Dhananjay Sirsikar | 4 | 2016-08-20 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-23 | 2016-08-24 | 2016-08-25 | 2016-08-26 | 2016-08-26 | 2016-08-27 | 2016-08-24 | 2016-08-25 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | cummins india ltd.,kothrud | 1 | 21 | 405 | Vasudev, Divya | - | divya.vasudev@cummins.com | shirkant.m.foujdar | - | shirkant.m.foujdar@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | complted | 2016-08-22 | 2016-08-22 | 1 |  | Dhananjay Sirsikar
459 | 2017-01-09 | 2:38:14 PM | Sapl0005 | 1 | 4 | C004 | 468 | 478 | IND3641409 | 36 | 0 | E0033 | 2016-08-20 | Labour Charges for Test Cell#7 & 8. | Dhananjay Sirsikar | 4 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | cummins india ltd., kothrud | 1 | 21 | 405 | Deshpande, Ashutosh | - | ashutosh.deshpande@cummins.com | shirkant.m.foujdar | - | shirkant.m.foujdar@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-08-20 | 2016-08-20 | 1 |  | Dhananjay Sirsikar
460 | 2016-11-03 | 10:26:35 AM | Sapl0005 | 1 | 4 | C004 | 469 | 479 | IND3642114 | 38 | 0 | J0086 | 2016-08-16 | Holding fixture for adaptor injector marking | SANJAY SHINDE | 5 | 2016-08-16 | 2016-08-18 | 2016-08-18 | 2016-08-20 | 2016-08-22 | 2016-08-23 | 2016-08-27 | 2016-08-27 | 2016-08-25 | 2016-08-27 | 2016-08-23 | 2016-08-25 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | Cummins India Ltd., Pune | 1 | 21 | 405 | Asis sahoo | - | asiskumar.sahoo@cummins.com | asiskumar.sahoo | - | asiskumar.sahoo@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-08-20 | 2016-08-20 | 1 |  | SANJAY SHINDE
461 | 2016-11-03 | 11:14:25 AM | Sapl0005 | 1 | 4 | C012 | 470 | 480 | verbal20aug | 35 | 0 | N0134 | 2016-08-16 | TOD for tilting QSK60 cylinder block | SANJAY SHINDE | 2 | 2016-08-16 | 2016-10-31 | 2016-08-24 | 2016-10-31 | 2016-08-29 | 2016-08-31 | 2016-09-05 | 2016-09-08 | 2016-09-08 | 2016-09-10 | 2016-09-01 | 2016-09-05 | 2016-09-05 | 2016-09-15 | 2016-09-07 | 2016-09-08 | Cummins Technology India Pvt. Limited, Phaltan | 1 | 21 | 405 | ramchandra.b.nimbalkar | 9922932785 | ramchandra.b.nimbalkar@cummins.com | suhas.s.bhorkar | - | suhas.s.bhorkar@cummins.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2016-08-22 | 2016-08-22 | 1 |  | SANJAY SHINDE
462 | 2017-05-15 | 9:46:06 AM | Sapl0005 | 1 | 4 | M005 | 471 | 481 | verb2016au | 35 | 0 | N0135 | 2016-08-20 | P602 End items 1 | Prajyot Genji | 3 | 2016-08-20 | 2017-01-31 | 2016-08-29 | 2017-01-31 | 2016-09-05 | 2016-09-10 | 2016-09-19 | 2016-09-22 | 2016-09-23 | 2016-09-27 | 2016-09-12 | 2016-09-17 | 2016-09-19 | 2016-09-30 | 2016-09-20 | 2016-09-23 | mahindra & mahindra chakan | 1 | 21 | 405 | PATIL.ASHOK2 | - | PATIL.ASHOK2@mahindra.com | GAVRASKAR.ANIKET | - | GAVRASKAR.ANIKET@mahindra.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2016-09-03 | 2016-09-03 | 1 |  | Prajyot Genji
463 | 2017-05-15 | 9:46:20 AM | Sapl0005 | 1 | 4 | M005 | 472 | 482 | verb22016aug | 35 | 0 | N0136 | 2016-08-20 | p602 end items2 | Prajyot Genji | 3 | 2016-08-20 | 2017-01-31 | 2016-08-29 | 2017-01-31 | 2016-09-03 | 2016-09-10 | 2016-09-17 | 2016-09-22 | 2016-09-23 | 2016-09-27 | 2016-09-10 | 2016-09-17 | 2016-09-17 | 2016-09-30 | 2016-09-17 | 2016-09-22 | mahindra & mahindra chakan | 1 | 21 | 405 | PATIL.ASHOK2 | - | PATIL.ASHOK2@mahindra.com | GAVRASKAR.ANIKET | - | GAVRASKAR.ANIKET@mahindra.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2016-09-03 | 2016-09-03 | 1 |  | Prajyot Genji
464 | 2017-05-15 | 9:46:48 AM | Sapl0005 | 1 | 4 | M005 | 473 | 483 | verb32016aug | 35 | 0 | N0137 | 2016-08-20 | p602 end items | Prajyot Genji | 3 | 2016-08-20 | 2017-01-21 | 2016-08-27 | 2017-01-21 | 2016-09-03 | 2016-09-10 | 2016-09-19 | 2016-09-23 | 2016-09-26 | 2016-09-30 | 2016-09-12 | 2016-09-17 | 2016-09-19 | 2016-10-04 | 2016-09-19 | 2016-09-23 | mahindra& mahindra chakan | 1 | 21 | 405 | PATIL.ASHOK2 | - | PATIL.ASHOK2@mahindra.com | GAVRASKAR.ANIKET | - | GAVRASKAR.ANIKET@mahindra.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2016-09-03 | 2016-09-03 | 1 |  | Prajyot Genji
465 | 2018-08-17 | 10:32:04 AM | Sapl0005 | 1 | 4 | A034 | 474 | 484 | DH_PO1617_ 000030 | 34 | 0 | S0137 | 2016-08-20 | LONG RAIL, CROSS RAIL & TROLLEY SET | Sagar Ravtale | 2 | 2016-08-20 | 2016-08-24 | 2016-08-24 | 2016-08-26 | 2016-08-26 | 2016-08-29 | 2016-09-05 | 2016-09-07 | 2016-09-01 | 2016-09-02 | 2016-08-29 | 2016-08-31 | 2016-09-05 | 2016-09-07 | 2016-09-05 | 2016-09-07 | Autoline Industries Ltd. (Dharwad) Plot No.180D A, Belur Industrial Area, Dharwad, | 1 | 17 | 304 | pravin.shinde | - | pravin.shinde@autolineind.com | Faiyaz.Kashi | - | Faiyaz.Kashi@autolineind.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | new po received for shortage | 2016-08-22 | 2016-08-22 | 1 |  | Sagar Ravtale
466 | 2018-02-01 | 2:59:02 PM | Sapl0005 | 1 | 4 | S011 | 475 | 485 | PUOR16002169 | 37 | 0 | P0042 | 2016-08-20 | BREAK COIL LIFTO HOIST | SANJAY SHINDE | 4 | 2016-08-20 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | Shanti iron & steel , belgaum | 1 | 17 | 295 | M.N.Patil | - | purchase@shantiiron.net | M.N.PATIL | - | maintenance@shantiiron.net | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-08-22 | 2016-08-22 | 1 |  | SANJAY SHINDE
468 | 2016-11-03 | 10:26:59 AM | Sapl0005 | 1 | 4 | C004 | 477 | 487 | IND3648543 | 38 | 0 | J0088 | 2016-08-24 | Dressing attachment for WMW m/c grinding wheel | SANJAY SHINDE | 5 | 2016-08-24 | 2016-08-26 | 2016-08-26 | 2016-08-29 | 2016-08-29 | 2016-08-31 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-08-31 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | Cummins India Ltd., Pune | 1 | 21 | 405 | Asis sahoo | - | asiskumar.sahoo@cummins.com | asis sahoo | - | asiskumar.sahoo@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 1 |  | 1 | COMPLETE | 2016-08-26 | 2016-08-26 | 1 |  | SANJAY SHINDE
469 | 2016-11-03 | 11:29:45 AM | Sapl0005 | 1 | 4 | C004 | 478 | 488 | verb23aug | 43 | 0 | T0025 | 2016-08-24 | Base Plate Material for Test Cell8 | Dhananjay Sirsikar | 4 | 2016-08-24 | 2016-09-08 | 2016-08-25 | 2016-09-08 | 2016-08-27 | 2016-08-27 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-27 | 2016-08-27 | 2016-08-29 | 2016-08-30 | 2016-08-29 | 2016-08-29 | Cummins India Ltd., Pune | 1 | 21 | 405 | Ashutosh S Deshpande | - | ashutosh.deshpande@cummins.com | shirkant.m.foujdar | - | shirkant.m.foujdar@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2016-08-24 | 2016-08-24 | 1 |  | Dhananjay Sirsikar
470 | 2017-07-21 | 10:00:59 AM | Sapl0005 | 1 | 4 | S006 | 479 | 489 | verb24aug | 34 | 0 | S0138 | 2016-08-24 | LONG RAIL, CROSS RAIL & TROLLEY SET | SANJAY SHINDE | 2 | 2016-08-24 | 2016-08-26 | 2016-08-26 | 2016-08-27 | 2016-08-27 | 2016-08-30 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-30 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | SAPL,Pune | 1 | 21 | 405 | sales | - | sales@synergytechs.com | sales | - | sales@synergytechs.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | COMPLETE | 2016-08-25 | 2016-08-25 | 1 |  | SANJAY SHINDE
472 | 2017-05-15 | 9:47:07 AM | Sapl0005 | 1 | 4 | M005 | 482 | 491 | verb238 | 35 | 0 | N0138 | 2016-08-31 | Welding Fixtures for P412 | Prajyot Genji | 3 | 2016-08-30 | 2017-02-09 | 2016-09-02 | 2017-02-09 | 2016-09-10 | 2016-09-13 | 2016-10-01 | 2016-10-03 | 2016-10-04 | 2016-10-07 | 2016-09-14 | 2016-09-30 | 2016-10-01 | 2016-10-11 | 2016-10-03 | 2016-10-03 | Mahindra & mahindra Ltd. | 1 | 21 | 405 | SINGH.JASPREET | - | SINGH.JASPREET4@mahindra.com | SINGH.GAGANDEEP | - | SINGH.GAGANDEEP6@mahindra.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2016-09-09 | 2016-09-09 | 1 |  | Prajyot Genji
473 | 2016-11-03 | 11:25:56 AM | Sapl0005 | 1 | 4 | A024 | 483 | 492 | 7016003473 | 34 | 0 | S0139 | 2016-09-02 | RAILS FOR BOLTABLE LOAD BODY PROJECT | Sagar Ravtale | 7 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-03 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-06 | 2016-09-06 | 2016-09-03 | 2016-09-05 | 2016-09-05 | 2016-09-09 | 2016-09-07 | 2016-09-07 | AUTOCOMP CORPORATION PANSE PVT.LTD - Dharwad Plot No. 125, Survey No. 258,Belur Industrial Area,Village-Belur,Garag Hubli,Tal : Dharwad,(Karnataka)-580011 | 1 | 17 | 304 | YOGESH SHIRSAT | 7387103990 | yjshirsat@pansegroup.com | pmrajguru | - | pmrajguru@pansegroup.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-09-02 | 2016-09-02 | 1 |  | Sagar Ravtale
474 | 2017-05-15 | 9:47:24 AM | Sapl0005 | 1 | 4 | A018 | 484 | 493 | verbalsep | 35 | 0 | N0139 | 2016-09-06 | Welding Fixtuires for Ace High Deck Body | Prajyot Genji | 3 | 2016-09-06 | 2016-11-30 | 2016-09-11 | 2016-11-30 | 2016-09-14 | 2016-09-20 | 2016-09-26 | 2016-09-28 | 2016-09-29 | 2016-10-01 | 2016-09-20 | 2016-09-26 | 2016-09-26 | 2016-10-06 | 2016-09-26 | 2016-09-28 | Autoline Industries, Pantnagar | 1 | 34 | 679 | Faiyaz.Kashi | - | Faiyaz.Kashi@autolineind.com | Satish.Satpute | - | Satish.Satpute@autolineind.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2016-09-10 | 2016-09-10 | 1 |  | Prajyot Genji
475 | 2017-07-21 | 10:15:44 AM | Sapl0005 | 1 | 4 | C004 | 485 | 494 | IND3661815 | 38 | 0 | J0089 | 2016-09-07 | TACKLE FOR V28 CYLINDER HEAD TO LIFT THE CYLINDER HEAD & ROTATE ON WASH BOOTH WORK STATION | Sagar Ravtale | 5 | 2016-09-07 | 2017-02-28 | 2016-09-12 | 2017-02-28 | 2016-09-17 | 2016-09-23 | 2016-09-30 | 2016-10-08 | 2016-10-10 | 2016-10-12 | 2016-09-23 | 2016-09-29 | 2016-09-30 | 2016-10-13 | 2016-10-10 | 2016-10-11 | cummins india ltd. | 1 | 21 | 405 | Bhagwat, Milind V, | - | milind.v.bhagwat@cummins.com | Neeta N Chavan | - | neeta.chavan@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2016-09-15 | 2016-09-15 | 1 |  | Sagar Ravtale
476 | 2016-11-03 | 10:27:11 AM | Sapl0005 | 1 | 4 | C004 | 486 | 495 | IND3663452 | 38 | 0 | J0090 | 2016-09-09 | Holding fixture to assemble & tightening of MVS assembly | SANJAY SHINDE | 5 | 2016-09-09 | 2016-09-10 | 2016-09-10 | 2016-09-12 | 2016-09-12 | 2016-09-13 | 2016-09-15 | 2016-09-15 | 2016-09-15 | 2016-09-15 | 2016-09-13 | 2016-09-14 | 2016-09-15 | 2016-09-15 | 2016-09-15 | 2016-09-15 | cummins india ltd., kothrud | 1 | 21 | 405 | Asis sahoo | - | asiskumar.sahoo@cummins.com | asiskumar.sahoo | - | asiskumar.sahoo@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 1 |  | 1 | COMPLETE | 2016-09-12 | 2016-09-12 | 1 |  | SANJAY SHINDE
478 | 2017-03-31 | 9:30:04 AM | Sapl0005 | 1 | 4 | C014 | 488 | 497 | IND3667736 | 38 | 0 | J0091 | 2016-09-14 | LIFTING TACKLE | SANJAY SHINDE | 13 | 2016-09-14 | 2016-11-30 | 2016-09-17 | 2016-11-30 | 2016-09-21 | 2016-09-24 | 2016-10-01 | 2016-10-04 | 2016-09-05 | 2016-09-05 | 2016-09-25 | 2016-09-30 | 2016-10-01 | 2016-10-06 | 2016-10-06 | 2016-10-06 | Indirect Material:IDM_ CIL DBU_017 Phaltan Plot No. A-1:MIDC, Suravadi,:Phaltan-Lonand Road Satara Maharashtra 415552 | 1 | 21 | 409 | kirankumar.waykos | 9881986931 | kirankumar.waykos@cummins.com | amit.r.umbarkar | - | amit.r.umbarkar@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 1 |  | 1 | COMPLETE | 2016-09-21 | 2016-09-21 | 1 |  | SANJAY SHINDE
479 | 2017-09-21 | 11:11:59 AM | Sapl0005 | 1 | 4 | C015 | 490 | 499 | IND3670548 | 36 | 0 | E0035 | 2016-09-17 | Transportation of roller conveyor & stand of TOD cage | SANJAY SHINDE | 2 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | Cummins Technologies India Pvt. Ltd.:Phaltan High Horsepower Plant, SEZ Unit:Plot No. B3/1, MIDC SEZ-Phaltan, Village Nandal-Surwadi, Taluka Phaltan, | 1 | 21 | 409 | Nimbalkar, Ramchandra B | 9922932785 | ramchandra.b.nimbalkar@cummins.com | suhas.s.bhorkar | - | suhas.s.bhorkar@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-09-17 | 2016-09-17 | 1 |  | SANJAY SHINDE
480 | 2017-05-15 | 9:47:41 AM | Sapl0005 | 1 | 4 | C004 | 491 | 500 | IND3671196 | 35 | 0 | N0140 | 2016-09-17 | TOD FOR K6/QSK19 CYLINDER BLOCK WITH BOTH SIDE SHUTTING TROLLY | Pooja Kadam | 3 | 2016-09-17 | 2016-12-20 | 2016-09-21 | 2016-12-20 | 2016-09-25 | 2016-09-28 | 2016-10-04 | 2016-10-05 | 2016-10-06 | 2016-10-06 | 2016-09-29 | 2016-10-03 | 2016-10-04 | 2016-10-14 | 2016-10-04 | 2016-10-05 | Cummins India Limited Kothrud:: Pune | 1 | 21 | 405 | Bhagwat, Milind V, | 9850892902 | milind.v.bhagwat@cummins.com | deepak.s.patil | - | deepak.s.patil@cummins.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2016-09-22 | 2016-09-22 | 1 |  | Pooja Kadam
482 | 2017-05-15 | 9:47:55 AM | Sapl0005 | 1 | 4 | C004 | 493 | 502 | verb199 | 35 | 0 | N0141 | 2016-09-19 | TOD FOR K6/QSK19 CYLINDER BLOCK WITH SINGLE SIDE SHUTTING TROLLY | Pooja Kadam | 3 | 2016-09-19 | 2016-11-03 | 2016-09-21 | 2016-11-03 | 2016-09-25 | 2016-09-28 | 2016-10-04 | 2016-10-05 | 2016-10-06 | 2016-10-06 | 2016-09-29 | 2016-10-03 | 2016-10-04 | 2016-10-14 | 2016-10-04 | 2016-10-05 | Cummins India Limited:CIL_EBU_085 Kothrud | 1 | 21 | 405 | milind.v.bhagwat | - | milind.v.bhagwat@cummins.com | milind.v.bhagwat | - | milind.v.bhagwat@cummins.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2016-09-22 | 2016-09-22 | 1 |  | Pooja Kadam
483 | 2017-01-09 | 2:54:35 PM | Sapl0005 | 1 | 4 | C004 | 494 | 503 | ver19sep | 35 | 0 | N0142 | 2016-09-19 | Spares for TOD | Pooja Kadam | 3 | 2016-09-19 | 2016-11-30 | 2016-09-21 | 2016-11-30 | 2016-09-25 | 2016-09-30 | 2016-10-04 | 2016-10-05 | 2016-10-06 | 2016-10-06 | 2016-10-01 | 2016-10-04 | 2016-10-04 | 2016-10-14 | 2016-10-04 | 2016-10-04 | CIL,pune | 1 | 21 | 405 | Nimbalkar, Ramchandra B | - | ramchandra.b.nimbalkar@cummins.com | milind.v.bhagwat | - | milind.v.bhagwat@cummins.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 1 |  | 1 | COMPLETE | 2016-09-22 | 2016-09-22 | 1 |  | Pooja Kadam
484 | 2016-11-03 | 11:15:03 AM | Sapl0005 | 1 | 4 | C015 | 495 | 504 | verb19se16 | 35 | 0 | N0143 | 2016-09-19 | Platform for Turn Over Device | Pooja Kadam | 3 | 2016-09-19 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-21 | 2016-10-21 | 2016-09-22 | 2016-09-22 | 2016-09-23 | 2016-09-23 | 2016-10-21 | 2016-09-21 | 2016-09-24 | 2016-09-26 | 2016-09-22 | 2016-09-22 | Cummins, Phaltan | 1 | 21 | 409 | Nimbalkar, Ramchandra B | - | ramchandra.b.nimbalkar@cummins.com | suhas.s.bhorkar | - | suhas.s.bhorkar@cummins.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-09-19 | 2016-09-19 | 1 |  | Pooja Kadam
485 | 2017-11-29 | 10:33:36 AM | Sapl0005 | 1 | 4 | N005 | 496 | 505 | 133044 | 35 | 0 | N0144 | 2016-10-10 | ECN WELDING FIXTURES MODIFICATION | PADMASINHA JOSHI | 3 | 2016-10-10 | 2016-10-17 | 2016-10-17 | 2016-10-24 | 2016-10-24 | 2016-10-29 | 2016-11-02 | 2016-11-03 | 2016-11-04 | 2016-11-04 | 2016-10-29 | 2016-11-02 | 2016-11-03 | 2016-11-04 | 2016-11-02 | 2016-11-03 | NEW HOLLAND FIAT, CHAKAN | 1 | 21 | 405 | ravi.murugadass | - | ravi.murugadass@cnhind.com | REDDY Manjunatha | - | manjunatha.reddy@cnhind.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-10-20 | 2016-10-20 | 1 |  | PADMASINHA JOSHI
488 | 2018-03-13 | 2:09:38 PM | Sapl0005 | 1 | 4 | A018 | 499 | 508 | 8nov | 35 | 0 | N0146 | 2016-11-08 | Welding fixtures for ACE Plus Load Body | Prajyot Genji | 3 | 2016-11-08 | 2018-03-31 | 2016-11-21 | 2018-03-31 | 2016-11-29 | 2016-12-07 | 2016-12-14 | 2016-12-17 | 2016-12-19 | 2016-12-23 | 2016-12-07 | 2016-12-14 | 2016-12-14 | 2016-12-31 | 2016-12-14 | 2016-12-17 | ail,pantnagar | 1 | 34 | 679 | satish.satpute | - | satish.satpute@autolineind.com | faiyaz kashi | - | Faiyaz.Kashi@autolineind.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2016-11-15 | 2016-11-15 | 1 |  | Prajyot Genji
489 | 2017-09-04 | 9:47:23 AM | Sapl0005 | 1 | 4 | M005 | 500 | 509 | 11nov2016 | 35 | 0 | N0147 | 2016-11-10 | U321 CCB prototype fixtures | PADMASINHA JOSHI | 3 | 2016-11-10 | 2017-01-31 | 2016-11-18 | 2017-01-31 | 2016-11-24 | 2016-11-30 | 2016-12-08 | 2016-12-10 | 2016-12-12 | 2016-12-14 | 2016-12-01 | 2016-12-08 | 2016-12-08 | 2016-12-17 | 2016-12-08 | 2016-12-10 | M&M CHAKAN | 1 | 21 | 405 | GAUR.DINESH | - | GAUR.DINESH@mahindra.com | NIMGAONKAR.SAMEER | - | NIMGAONKAR.SAMEER@mahindra.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 1 | COMPLETE | 2016-11-17 | 2016-11-17 | 1 |  | PADMASINHA JOSHI
490 | 2017-09-04 | 9:47:39 AM | Sapl0005 | 1 | 4 | M005 | 501 | 510 | 24nov | 35 | 0 | N0148 | 2016-11-24 | welding fixture for S101 CNG | Prajyot Genji | 3 | 2016-11-24 | 2017-03-31 | 2016-12-01 | 2017-03-31 | 2016-12-09 | 2016-12-15 | 2016-12-23 | 2016-12-30 | 2016-12-30 | 2016-12-31 | 2016-12-16 | 2016-12-22 | 2016-12-23 | 2017-01-04 | 2016-12-28 | 2016-12-30 | M&M | 1 | 21 | 405 | KALE.SATISH | - | KALE.SATISH@mahindra.com | NIMGAONKAR.SAMEER | - | NIMGAONKAR.SAMEER@mahindra.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2016-12-06 | 2016-12-06 | 1 |  | Prajyot Genji
491 | 2017-05-15 | 9:49:48 AM | Sapl0005 | 1 | 4 | C017 | 502 | 511 | IND3737279 | 35 | 0 | N0149 | 2016-11-25 | Tank Bracket Assembly station for kitting activity | Dhananjay Sirsikar | 4 | 2016-11-25 | 2017-03-31 | 2016-12-03 | 2017-03-31 | 2016-12-11 | 2016-12-17 | 2016-12-25 | 2016-12-31 | 2017-01-01 | 2017-01-05 | 2016-12-19 | 2016-12-24 | 2016-12-25 | 2017-01-11 | 2016-12-25 | 2016-12-31 | Cummins Technologies India Pvt Ltd (Division Cummins Emission Solutions):Plot No-A-1, MIDC:Suravadi Satara Maharashtra 415552 India | 1 | 21 | 409 | ajay.v.khandekar | 09850892918 | ajay.v.khandekar@cummins.com | praful.p.aole | - | praful.p.aole@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2016-12-08 | 2016-12-08 | 1 |  | Dhananjay Sirsikar
492 | 2017-01-09 | 2:50:07 PM | Sapl0005 | 1 | 4 | A032 | 503 | 512 | 7016005176 | 34 | 0 | S0142 | 2016-11-28 | telescopic rail & telescopic trolley set | Sagar Ravtale | 2 | 2016-11-28 | 2016-11-29 | 2016-11-29 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-12-01 | 2016-12-01 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | AUTOCOMPS CORPORATION PANSE PVT LTD MOSHI-I GAT NO.219, VILLAGE-BORHADEWADI , DEHU-ALANDI ROAD , MOSHI, PUNE-412 114 | 1 | 21 | 405 | YOGESH SHIRSAT | 7387103990 | yjshirsat@pansegroup.com | cvpatil | - | cvpatil@pansegroup.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-11-29 | 2016-11-29 | 1 |  | Sagar Ravtale
493 | 2017-02-15 | 1:08:31 PM | Sapl0005 | 1 | 4 | C004 | 504 | 513 | IND3754006 | 38 | 0 | J0092 | 2016-12-14 | TR25942 &TR25933 | Sagar Ravtale | 5 | 2016-12-14 | 2016-12-17 | 2016-12-17 | 2016-12-20 | 2016-12-20 | 2016-12-22 | 2016-12-23 | 2016-12-23 | 2016-12-24 | 2016-12-24 | 2016-12-22 | 2016-12-23 | 2016-12-23 | 2016-12-23 | 2016-12-23 | 2016-12-23 | cummins india ltd. | 1 | 21 | 405 | Asis sahoo | - | asiskumar.sahoo@cummins.com | Rajeev.Sharma | - | Rajeev.Sharma@cummins.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 1 | COMPLETE | 2016-12-17 | 2016-12-17 | 1 |  | Sagar Ravtale
494 | 2017-01-09 | 2:42:31 PM | Sapl0005 | 1 | 4 | C004 | 505 | 514 | IND3755266 | 38 | 0 | J0093 | 2016-12-16 | Bracket, Lifting (part no 3236118) | Sagar Ravtale | 5 | 2016-12-16 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | Cummins India Limited:CIL_EBU_085 Kothrud, pune | 1 | 21 | 405 | Jegannathan, Surendar | - | surendar.jegannathan@cummins.com | mary.vydani | - | mary.vydani@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-12-17 | 2016-12-17 | 1 |  | Sagar Ravtale
495 | 2017-01-09 | 2:50:26 PM | Sapl0005 | 1 | 4 | A004 | 506 | 515 | C2_PO16-17_003375 | 34 | 0 | S0143 | 2016-12-20 | long rail, cross rail, trolley set C63 | Sagar Ravtale | 2 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | AUTOLINE CHAKAN | 1 | 21 | 405 | dnyaneshwar phalke | - | Dnyaneshwar.Phalke@autolineind.com | atmaram ghogare | - | atmaram.ghogare@autolineind.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-12-20 | 2016-12-20 | 1 |  | Sagar Ravtale
496 | 2017-12-09 | 9:52:07 AM | Sapl0005 | 1 | 4 | C004 | 508 | 517 | IND3765303 | 35 | 0 | N0150 | 2016-12-27 | AGV TO RGV | Dhananjay Sirsikar | 4 | 2016-12-27 | 2017-11-30 | 2017-01-07 | 2017-11-30 | 2017-01-16 | 2017-01-26 | 2017-02-11 | 2017-02-15 | 2017-02-16 | 2017-02-23 | 2017-01-26 | 2017-02-10 | 2017-02-11 | 2017-02-28 | 2017-02-11 | 2017-02-15 | Cummins India Ltd., Pune | 1 | 21 | 405 | Atulsingh.Pardeshi | 9552500390 | Atulsingh.Pardeshi@cummins.com | amol.m.pophale | - | amol.m.pophale@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2017-01-17 | 2017-01-17 | 1 |  | Dhananjay Sirsikar
497 | 2019-12-29 | 5:16:07 PM | Sapl0002 | 1 | 4 | C016 | 509 | 518 | IND3765376 | 36 | 0 | E0036 | 2016-12-27 | Installation of Conveyor | Dhananjay Sirsikar | 4 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | Cummins Generator Technologies India Private Limited.:G-06, Ranjangaon MIDC,:Tal - Shirur | 1 | 21 | 405 | Yadav, Vijendra | 9031056460 | vijendra.yadav@cummins.com | ashish.save | - | ashish.save@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2016-12-27 | 2016-12-27 | 1 |  | Dhananjay Sirsikar
498 | 2017-03-13 | 10:41:39 AM | Sapl0005 | 1 | 4 | C004 | 507 | 516 | IND3762316 | 38 | 0 | J0094 | 2016-12-22 | CAC Cover to accommodate two filter | Sagar Ravtale | 5 | 2016-12-22 | 2016-12-23 | 2016-12-23 | 2016-12-23 | 2016-12-24 | 2016-12-30 | 2017-01-02 | 2017-01-02 | 2017-01-03 | 2017-01-03 | 2016-12-30 | 2017-01-02 | 2017-01-03 | 2017-01-03 | 2017-01-03 | 2017-01-03 | cummins india ltd. | 1 | 21 | 405 | Asis sahoo | - | asiskumar.sahoo@cummins.com | asis sahoo | - | asiskumar.sahoo@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-12-26 | 2016-12-26 | 1 |  | Sagar Ravtale
499 | 2017-01-09 | 2:51:59 PM | Sapl0005 | 1 | 4 | A032 | 510 | 519 | 7016005815 | 34 | 0 | S0144 | 2016-12-30 | TELESCOPIC TROLLY SET C63 | Sagar Ravtale | 2 | 2016-12-30 | 2016-12-30 | 2016-12-30 | 2016-12-30 | 2016-12-30 | 2017-01-01 | 2017-01-02 | 2017-01-02 | 2017-01-03 | 2017-01-03 | 2017-01-01 | 2017-01-02 | 2017-01-03 | 2017-01-03 | 2017-01-03 | 2017-01-03 | AUTOCOMPS CORPORATION PANSE PVT LTD MOSHI-I GAT NO.219, VILLAGE-BORHADEWADI , DEHU-ALANDI ROAD , MOSHI, PUNE-412 114 | 1 | 21 | 405 | YOGESH SHIRSAT | 91-7387103990 | yjshirsat@pansegroup.com | cvpatil | - | cvpatil@pansegroup.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2017-01-03 | 2017-01-03 | 1 |  | Sagar Ravtale
500 | 2017-03-13 | 10:41:53 AM | Sapl0005 | 1 | 4 | C004 | 511 | 520 | IND3766963 | 38 | 0 | J0095 | 2016-12-30 | TR25944 @ A606231 | Sagar Ravtale | 5 | 2016-12-30 | 2017-02-14 | 2016-12-30 | 2017-02-14 | 2016-12-31 | 2017-01-02 | 2017-01-03 | 2017-01-03 | 2017-01-04 | 2017-01-04 | 2017-01-02 | 2017-01-03 | 2017-01-03 | 2017-01-04 | 2017-01-04 | 2017-01-04 | Cummins India Ltd., Pune | 1 | 21 | 405 | Asis sahoo | - | asiskumar.sahoo@cummins.com | asis sahoo | - | asiskumar.sahoo@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 1 |  | 1 | COMPLETE | 2017-01-02 | 2017-01-02 | 1 |  | Sagar Ravtale
501 | 2017-01-23 | 2:54:29 PM | Sapl0005 | 1 | 4 | N002 | 512 | 521 | 4300026297 | 34 | 0 | S0145 | 2017-01-09 | LONG RAIL CROSS RAIL & TROLLEY SET | Sagar Ravtale | 2 | 2017-01-09 | 2017-01-10 | 2017-01-10 | 2017-01-11 | 2017-01-11 | 2017-01-12 | 2017-01-13 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-12 | 2017-01-13 | 2017-01-17 | 2017-01-17 | 2017-01-16 | 2017-01-16 | PLOT No.22 & Plot No.1A,Sector 12,ITBT Park,IIE,SIDCUL 263153 - Pant Nagar | 1 | 34 | 679 | satish.kumar | 7830002043 | satish.kumar2@jbm.co.in | SANJAY MURGAI | - | smurgai@jbm.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2017-01-11 | 2017-01-11 | 1 |  | Sagar Ravtale
502 | 2017-01-23 | 2:54:52 PM | Sapl0005 | 1 | 4 | S027 | 513 | 522 | VERBAL_JAN | 34 | 0 | S0146 | 2017-01-17 | Kemppi Machine | Dhananjay Sirsikar | 4 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | SAKSHI , CHAKAN | 1 | 21 | 405 | Kakade | - | info@sakshiindia.co.in | Kakade | - | info@sakshiindia.co.in | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2017-01-17 | 2017-01-17 | 1 |  | Dhananjay Sirsikar
503 | 2017-07-21 | 10:10:26 AM | Sapl0005 | 1 | 4 | O002 | 514 | 523 | O.L.C.I./661/2016-17 | 35 | 0 | N0151 | 2017-01-17 | UNLOADING CONVEYOR FOR HOOD | Dhananjay Sirsikar | 4 | 2017-01-17 | 2017-02-15 | 2017-01-19 | 2017-02-15 | 2017-01-23 | 2017-01-28 | 2017-02-04 | 2017-02-07 | 2017-02-07 | 2017-02-08 | 2017-01-29 | 2017-02-04 | 2017-02-04 | 2017-02-10 | 2017-02-07 | 2017-02-08 | PLOT NO. E-14, PH III NIGHOJE , CHAKAN | 1 | 21 | 405 | mayuresh.said | 9881191819 | mayuresh.said@olcieng.co.in | amit.kokane | - | amit.kokane@olcieng.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2017-01-19 | 2017-01-19 | 1 |  | Dhananjay Sirsikar
504 | 2017-07-21 | 9:58:10 AM | Sapl0005 | 1 | 4 | C004 | 515 | 524 | IND3784258 | 36 | 0 | E0037 | 2017-01-19 | Labour charges for Base plate wiring TC7 & TC8 | Dhananjay Sirsikar | 4 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | Cummins India Limited Dahanukar Colony, Kothrud, Pune 411038 | 1 | 21 | 405 | Deshpande, Ashutosh S | - | ashutosh.deshpande@cummins.com | mohini pawar | - | mohini.a.pawar@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | com | 2017-01-19 | 2017-01-19 | 1 |  | Dhananjay Sirsikar
505 | 2017-02-15 | 1:04:55 PM | Sapl0005 | 1 | 4 | G015 | 516 | 525 | G-4/BO/16-17/11VI | 34 | 0 | S0147 | 2017-01-23 | LONG RAIL CROSS RAIL & TROLLEY SET | Sagar Ravtale | 2 | 2017-01-23 | 2017-01-24 | 2017-01-24 | 2017-01-24 | 2017-01-24 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-24 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | Gloria Engineeing co Unit-4 Shelarwasti, Chikhali, Pune | 1 | 21 | 405 | SUNIL PAWAR | - | sunil.pawar@gloriagroup.co.in | deepak.verma | - | deepak.verma@gloriagroup.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2017-01-23 | 2017-01-23 | 1 |  | Sagar Ravtale
506 | 2017-02-15 | 1:09:05 PM | Sapl0005 | 1 | 4 | M025 | 517 | 526 | P6PR/00129 | 38 | 0 | J0096 | 2017-02-08 | Panels | PADMASINHA JOSHI | 3 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | MUNGI ENGINEERS PVT LTD ZHB II SURVEY NO 191,MOGDAMPALLY ROAD ZAHEERABAD - 502220 Pincode - 502220 INDIA | 1 | 46 | 692 | b.balbheem | - | b.balbheem@mungiindia.com | aggarwal.vipin | - | aggarwal.vipin@mungiindia.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2017-02-08 | 2017-02-08 | 1 |  | PADMASINHA JOSHI
507 | 2017-02-24 | 11:45:22 AM | Sapl0005 | 1 | 4 | O002 | 518 | 527 | O.L.C.I./789/2016-17 | 35 | 0 | N0152 | 2017-02-15 | SWING UNIT & DRIVE STAND | SANJAY SHINDE | 2 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | O.L.C.I. ENGINEERING CHAKAN | 1 | 21 | 405 | AMIT KOKANE | - | amit.kokane@olcieng.co.in | MAYURESH SAID | - | mayuresh.said@olcieng.co.in | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2017-02-15 | 2017-02-15 | 1 |  | SANJAY SHINDE
508 | 2017-02-24 | 11:45:39 AM | Sapl0005 | 1 | 4 | O002 | 519 | 528 | O.L.C.I./795/2016-17 | 35 | 0 | N0153 | 2017-02-16 | NYLON BRAIDED ROD | SAGAR | 2 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | OLCI, CHAKAN | 1 | 21 | 405 | AMIT KOKANE | - | AMIT.KOKANE@OLCI.COM | amit.kokane | - | AMIT.KOKANE@OLCI.COM | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2017-02-16 | 2017-02-16 | 1 |  | SAGAR
509 | 2017-03-13 | 10:40:23 AM | Sapl0005 | 1 | 4 | J012 | 520 | 529 | VERBAL_23022017 | 34 | 0 | S0148 | 2017-02-23 | LONG RAIL, CROSS RAIL & TROLLEY SET | Sagar Ravtale | 2 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-24 | 2017-02-24 | 2017-02-23 | 2017-02-23 | 2017-02-24 | 2017-02-25 | 2017-02-24 | 2017-02-24 | 624/8, Kurali, Chakan, Pune 410511 | 1 | 21 | 405 | SATISH | - | marketing@japtechind.com | SATISH | - | marketing@japtechind.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2017-02-23 | 2017-02-23 | 1 |  | Sagar Ravtale
510 | 2017-11-29 | 10:34:01 AM | Sapl0005 | 1 | 4 | M005 | 521 | 530 | verb24feb | 35 | 0 | N0154 | 2017-02-24 | PANEL ASSY SILL REAR OUTER CNG | Prajyot Genji | 3 | 2017-02-24 | 2017-04-30 | 2017-03-03 | 2017-04-30 | 2017-03-11 | 2017-03-14 | 2017-03-17 | 2017-03-19 | 2017-03-20 | 2017-03-20 | 2017-03-15 | 2017-02-17 | 2017-03-17 | 2017-03-22 | 2017-03-18 | 2017-03-19 | MAHINDRA & MAHINDRA , CHAKAN | 1 | 21 | 405 | PUTHRAN.NITESH | - | PUTHRAN.NITESH@mahindra.com | MALVADKAR.MAHENDRA | - | MALVADKAR.MAHENDRA@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2017-03-10 | 2017-03-10 | 1 |  | Prajyot Genji
512 | 2019-12-29 | 7:01:23 PM | Sapl0002 | 1 | 4 | T002 | 523 | 532 | VERBTATA | 35 | 0 | N0155 | 2017-02-24 | ASSEMBLY FIXTURE for ULTRA FRAME LINE | Prajyot Genji | 3 | 2017-02-24 | 2018-11-30 | 2017-03-10 | 2018-11-30 | 2017-03-17 | 2017-03-27 | 2017-04-07 | 2017-04-14 | 2017-04-17 | 2017-04-19 | 2017-03-27 | 2017-04-07 | 2017-04-07 | 2017-04-15 | 2017-04-07 | 2017-04-14 | TATA MOTORS, PUNE | 1 | 21 | 405 | santosh.uttekar | - | santosh.uttekar@tatamotors.com | prashant.shete | - | prashant.shete@tatamotors.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2017-03-14 | 2017-03-14 | 1 |  | Prajyot Genji
513 | 2019-12-29 | 7:02:07 PM | Sapl0002 | 1 | 4 | T002 | 524 | 533 | VERB_TATA24 | 35 | 0 | N0156 | 2017-02-24 | PICK & PLACE SYSTEM for ULTRA FRAME LINE | Prajyot Genji | 3 | 2017-02-24 | 2018-02-28 | 2017-03-10 | 2018-02-28 | 2017-03-18 | 2017-03-28 | 2017-04-07 | 2017-04-14 | 2017-04-15 | 2017-04-18 | 2017-03-28 | 2017-04-07 | 2017-04-07 | 2017-04-29 | 2017-04-07 | 2017-04-14 | TATA MOTORS, PUNE | 1 | 21 | 405 | santosh.uttekar | - | santosh.uttekar@tatamotors.com | prashant.shete | - | prashant.shete@tatamotors.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2017-03-10 | 2017-03-10 | 1 |  | Prajyot Genji
517 | 2018-08-03 | 11:38:04 AM | Sapl0005 | 1 | 4 | C004 | 528 | 537 | verb_6MAR | 35 | 0 | N0159 | 2017-03-06 | TOD | Dhananjay Sirsikar | 2 | 2017-03-06 | 2017-05-31 | 2017-03-09 | 2017-05-31 | 2017-03-11 | 2017-03-15 | 2017-03-22 | 2017-03-24 | 2017-03-25 | 2017-03-25 | 2017-03-15 | 2017-03-22 | 2017-03-22 | 2017-03-30 | 2017-03-25 | 2017-03-25 | cummins india ltd. | 1 | 21 | 405 | Milind Bhagwat | - | milind.v.bhagwat@cummins.com | Milind Bhagwat | - | milind.v.bhagwat@cummins.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2017-03-09 | 2017-03-09 | 1 |  | Dhananjay Sirsikar
519 | 2017-12-22 | 10:14:34 AM | Sapl0005 | 1 | 4 | A018 | 530 | 539 | UKD05_PO16-17_003046. | 35 | 0 | N0160 | 2017-03-09 | FIXTURES | PADMASINHA | 3 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | AUTOLINE | 1 | 34 | 679 | FAIYAZ | - | FA@ASASDASD.COM | FAIYAZ | - | FA@ASASDASD.COM | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | COMPLETE | 2017-03-09 | 2017-03-09 | 1 |  | PADMASINHA
520 | 2017-07-21 | 10:16:12 AM | Sapl0005 | 1 | 4 | C004 | 531 | 540 | IND3842388 | 38 | 0 | J0097 | 2017-03-21 | METALIC SKIDS FOR BW Q-60 CYLINDER BLOCK | Dhananjay Sirsikar | 5 | 2017-03-21 | 2017-05-31 | 2017-03-28 | 2017-05-31 | 2017-04-04 | 2017-04-30 | 2017-05-04 | 2017-05-08 | 2017-05-09 | 2017-05-10 | 2017-04-04 | 2017-05-04 | 2017-05-04 | 2017-05-10 | 2017-05-10 | 2017-05-10 | Cummins India Limited:CIL_EBU_085 Kothrud:: | 1 | 21 | 405 | Bhagwat, Milind V | - | milind.v.bhagwat@cummins.com | Bhagwat, Milind V | - | milind.v.bhagwat@cummins.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2017-03-30 | 2017-03-30 | 1 |  | Dhananjay Sirsikar
521 | 2017-07-21 | 10:15:09 AM | Sapl0005 | 1 | 4 | M025 | 532 | 541 | N/00328 | 37 | 0 | P0044 | 2017-03-25 | PLA BASE 8 PIN RELAY | Dhananjay Sirsikar | 4 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-29 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | MUNGI ENGINEERS PVT LTD ZHB II SURVEY NO 191,MOGDAMPALLY ROAD ZAHEERABAD - 502220 Pincode - 502220 INDIA | 1 | 46 | 692 | Venkatesh manne | 9866789996 | purchasezbd@munginsk.com | b.balbheem | - | b.balbheem@mungiindia.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2017-03-25 | 2017-03-25 | 1 |  | Dhananjay Sirsikar
522 | 2020-12-05 | 9:58:58 AM | sapl0313 | 1 | 4 | K009 | 533 | 542 | verbapril | 35 | 0 | N0161 | 2017-04-06 | Fixture assy for W109 Chassis | Prajyot Genji | 3 | 2017-04-06 | 2018-12-07 | 2017-04-17 | 2018-12-07 | 2017-04-24 | 2018-10-06 | 2017-05-08 | 2018-10-20 | 2017-05-15 | 2018-10-24 | 2017-04-29 | 2018-10-13 | 2017-05-08 | 2018-10-30 | 2017-05-08 | 2018-10-20 | Taal ?- ?Halol Plant Plot No?.?2014?, ? Opp?. ?Ploy Set?, ?Gidc Halol?, ?Dist?. ? Panchmahal ?389351? | 1 | 12 | 157 | yogesh.jadhav | - | yogesh.jadhav@kltgroup.net | RAJURKAR.VAIBHAV | - | RAJURKAR.VAIBHAV@mahindra.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | wo closed | 2017-04-19 | 2017-04-19 | 1 |  | Prajyot Genji
523 | 2017-07-21 | 9:58:41 AM | Sapl0005 | 1 | 4 | M020 | 534 | 543 | 3400012378 | 36 | 0 | E0038 | 2017-04-08 | service for op30 | Dhananjay Sirsikar | 4 | 2017-04-08 | 2017-04-08 | 2017-04-08 | 2017-04-08 | 2017-04-08 | 2017-04-08 | 2017-04-08 | 2017-04-08 | 2017-04-08 | 2017-04-08 | 2017-04-08 | 2017-04-08 | 2017-04-08 | 2017-04-08 | 2017-04-08 | 2017-04-08 | Mahindra CIE Automotive Limited Formerly known as Mahindra Forging Ltd (Mahindra CIEStamping Division-Zaheerabad) | 1 | 46 | 692 | Sujit kumar Sahu | 7675059192 | PURCHASE.ZBD@MAHINDRACIE.COM | UPALKAR.NIRANJAN | - | UPALKAR.NIRANJAN@MAHINDRACIE.COM | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | compl | 2017-04-08 | 2017-04-08 | 1 |  | Dhananjay Sirsikar
524 | 2017-05-15 | 9:52:07 AM | Sapl0005 | 1 | 5 | S011 | 535 | 544 | PUOR17000250 | 37 | 0 | P0045 | 2017-04-24 | Brake Shoe Assly | Dhananjay Sirsikar | 4 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-25 | 2017-04-25 | 690, Udyambag Industrial Estate, BELGAUM - 590 008 KARNATAKA - INDIA | 1 | 17 | 295 | M.N.Patil | - | purchase@shantiiron.net | maintenance | - | maintenance@shantiiron.net | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2017-04-24 | 2017-04-24 | 1 |  | Dhananjay Sirsikar
526 | 2018-07-03 | 8:58:54 AM | Sapl0005 | 1 | 5 | M028 | 537 | 546 | verb12may | 35 | 0 | N0162 | 2017-05-12 | Rotary Inversion Fixtures For Floor | Prajyot Genji | 3 | 2017-05-12 | 2017-09-15 | 2017-05-22 | 2017-09-15 | 2017-05-30 | 2017-06-10 | 2017-06-16 | 2017-06-20 | 2017-06-21 | 2017-06-23 | 2017-06-10 | 2017-06-16 | 2017-06-16 | 2017-06-27 | 2017-06-16 | 2017-06-20 | pune | 1 | 21 | 405 | ABC | - | adc@gvfd.com | ABC | - | adc@gvfd.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2017-05-23 | 2017-05-23 | 1 |  | Prajyot Genji
527 | 2018-01-11 | 1:48:44 PM | Sapl0005 | 1 | 5 | M005 | 539 | 550 | Verbal29may | 35 | 0 | N0163 | 2017-05-29 | S105 LHD & S101 RHD - Assy Pnl plenum Tucker stud welding fixture | PADMASINHA JOSHI | 3 | 2017-05-29 | 2017-10-31 | 2017-06-03 | 2017-10-31 | 2017-06-10 | 2017-06-16 | 2017-06-20 | 2017-06-23 | 2017-06-23 | 2017-06-27 | 2017-06-16 | 2017-06-20 | 2017-06-20 | 2017-07-01 | 2017-06-20 | 2017-06-23 | Mahindra & Mahindra Ltd., Chakan | 1 | 21 | 405 | KALYANKAR SUJEET | - | KALYANKAR.SUJEET@mahindra.com | AGRAWAL RITESH | - | AGRAWAL.RITESH@mahindra.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2017-06-09 | 2017-06-09 | 1 |  | PADMASINHA JOSHI
528 | 2018-02-21 | 1:30:44 PM | Sapl0005 | 1 | 5 | M001 | 540 | 551 | verbal_1jun | 35 | 0 | N0164 | 2017-06-01 | stack up conveyor | Prajyot Genji | 3 | 2017-06-01 | 2018-01-06 | 2017-06-15 | 2018-01-06 | 2017-06-28 | 2017-07-15 | 2017-07-24 | 2017-07-26 | 2017-07-28 | 2017-08-01 | 2017-07-16 | 2017-07-23 | 2017-07-24 | 2017-08-06 | 2017-07-25 | 2017-07-27 | MAHINDRA & MAHINDRA, NASHIK | 1 | 21 | 402 | YADAV.YOGESH2 | - | YADAV.YOGESH2@mahindra.com | DEOGHARE.ROOPAL | - | DEOGHARE.ROOPAL@mahindra.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2017-06-18 | 2017-06-18 | 1 |  | Prajyot Genji
529 | 2017-07-21 | 10:02:40 AM | Sapl0005 | 1 | 5 | J009 | 541 | 552 | JOAI/A/1700046 | 34 | 0 | S0152 | 2017-06-02 | LONG RAIL CROSS RAIL & TROLLEY SET | Sagar Ravtale | 2 | 2017-06-02 | 2017-06-03 | 2017-06-03 | 2017-06-03 | 2017-06-03 | 2017-06-05 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-05 | 2017-06-06 | 2017-06-08 | 2017-06-10 | 2017-06-08 | 2017-06-08 | JBM OGIHARA , BANGLORE | 1 | 17 | 293 | Aradhya T.C. | 9916889090 | purchase@joai.co.in | shivaprasad | - | shivaprasad@joai.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2017-06-02 | 2017-06-02 | 1 |  | Sagar Ravtale
530 | 2017-07-21 | 10:16:43 AM | Sapl0005 | 1 | 5 | M001 | 542 | 553 | verbal_2jun | 38 | 0 | J0098 | 2017-06-02 | LIFTER UNIT W110-TG-01 - 18F203 | Sagar Ravtale | 5 | 2017-06-01 | 2017-06-02 | 2017-06-02 | 2017-06-03 | 2017-06-03 | 2017-06-07 | 2017-06-11 | 2017-06-12 | 2017-06-12 | 2017-06-13 | 2017-06-08 | 2017-06-11 | 2017-06-13 | 2017-06-13 | 2017-06-11 | 2017-06-12 | M&M, nashik | 1 | 21 | 402 | YADAV.YOGESH2 | - | YADAV.YOGESH2@mahindra.com | AVHAD ANANT | - | AVHAD.ANANT@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2017-06-03 | 2017-06-03 | 1 |  | Sagar Ravtale
531 | 2017-09-21 | 11:08:04 AM | Sapl0005 | 1 | 5 | B001 | 543 | 554 | 4500078061 | 34 | 0 | S0153 | 2017-06-05 | TELESCOPIC RAIL & TROLLY SET C63 | Sagar Ravtale | 2 | 2017-06-05 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-08 | 2017-06-08 | 2017-06-07 | 2017-06-07 | BADVE ENGINEERING LTD.,UNIT-12 PLOT NO.52 SECTOR 11,TATAVENDOR PARK ,IIE , SIDCUL PANTNAGAR-263153,UTTARAKHAND | 1 | 34 | 679 | vinodsingh | 9927880040 | vinodsingh@badvegroup.com | pkupadhyay | - | pkupadhyay@badvegroup.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | order cancelled | 2017-06-05 | 2017-06-05 | 1 |  | Sagar Ravtale
532 | 2017-07-21 | 10:03:13 AM | Sapl0005 | 1 | 5 | A024 | 544 | 555 | 7017002089 | 34 | 0 | S0154 | 2017-06-29 | LONG RAIL & CROSS RAIL | SAGAR | 2 | 2017-06-29 | 2017-06-29 | 2017-06-29 | 2017-06-29 | 2017-06-29 | 2017-06-29 | 2017-06-29 | 2017-06-29 | 2017-06-29 | 2017-06-29 | 2017-06-29 | 2017-06-29 | 2017-06-29 | 2017-06-29 | 2017-06-29 | 2017-06-29 | AUTOCOMP PANSE,DHARWAD | 1 | 17 | 304 | MR.YOGESH SIRSAT | - | YJ@PANSE.COM | MR.RAJGURU | - | YT@PANSE.COM | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2017-06-29 | 2017-06-29 | 1 |  | SAGAR
533 | 2017-11-29 | 10:38:23 AM | Sapl0005 | 1 | 5 | M029 | 545 | 556 | Ver30 | 43 | 0 | T0026 | 2017-06-30 | GENSET | DNS | 4 | 2017-06-30 | 2017-06-30 | 2017-06-30 | 2017-06-30 | 2017-06-30 | 2017-06-30 | 2017-06-30 | 2017-06-30 | 2017-06-30 | 2017-06-30 | 2017-06-30 | 2017-06-30 | 2017-06-30 | 2017-06-30 | 2017-06-30 | 2017-06-30 | CHAKAN | 1 | 21 | 405 | MR.MANPREET | - | mackpotro2016@gmail.com | - | - | mackpotro2016@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2017-06-30 | 2017-06-30 | 1 |  | DNS
536 | 2017-09-21 | 11:08:19 AM | Sapl0005 | 1 | 5 | A024 | 548 | 559 | 7017002204 | 34 | 0 | S0155 | 2017-07-03 | TROLLEY SET C63 | Sagar Ravtale | 2 | 2017-07-03 | 2017-07-04 | 2017-07-04 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | AUTOCOMPS CORPORATION PANSE PVT LTD | 1 | 17 | 304 | YOGESH SHIRSAT | - | yjshirsat@pansegroup.com | RAJGURU | - | pmrajguru@pansegroup.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2017-07-05 | 2017-07-05 | 1 |  | Sagar Ravtale
539 | 2017-09-11 | 10:51:36 AM | Sapl0005 | 1 | 5 | C004 | 550 | 561 | IND3936183 | 35 | 0 | N0167 | 2017-07-03 | MS TRACK | Akshay bhojkar | 2 | 2017-07-03 | 2017-07-04 | 2017-07-04 | 2017-07-05 | 2017-07-06 | 2017-07-07 | 2017-07-08 | 2017-07-08 | 2017-07-09 | 2017-07-09 | 2017-07-07 | 2017-07-08 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | CUMMINS , KOTHRUD | 1 | 21 | 405 | Atulsingh.Pardeshi | - | Atulsingh.Pardeshi@cummins.com | PANKAJ KULKARNI | - | pankaj.s.kulkarni@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2017-07-05 | 2017-07-05 | 1 |  | Akshay bhojkar
541 | 2018-02-21 | 1:31:50 PM | Sapl0005 | 1 | 5 | C015 | 552 | 563 | IND3937678 | 35 | 0 | N0168 | 2017-07-03 | Fixture and Trolley to insert Cam & Crank alignment bars into QSK23 Cylinder Block | hanumant Bhilare | 2 | 2017-07-03 | 2017-09-15 | 2017-07-05 | 2017-09-15 | 2017-07-07 | 2017-07-08 | 2017-07-11 | 2017-07-12 | 2017-07-12 | 2017-07-13 | 2017-07-08 | 2017-07-10 | 2017-07-11 | 2017-07-15 | 2017-07-11 | 2017-07-12 | Cummins Technologies India Pvt. Ltd.:Phaltan High Horsepower Plant, SEZ Unit:Plot No. B3/1, MIDC SEZ-Phaltan, Village Nandal-Surwadi, Taluka Phaltan, Dist. Sata Maharashtra 415522 | 1 | 21 | 409 | ramchandra nimbalkar | - | ramchandra.b.nimbalkar@cummins.com | suhas.s.bhorkar | - | suhas.s.bhorkar@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2017-07-05 | 2017-07-05 | 1 |  | hanumant Bhilare
542 | 2018-02-01 | 2:59:45 PM | Sapl0005 | 1 | 5 | A015 | 553 | 564 | POG117000074 | 37 | 0 | P0046 | 2017-07-07 | Brake shoe assly & break coi | Dhananjay Sirsikar | 4 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | alf engg, hosur | 1 | 21 | 405 | ANIL PATIL | - | sujitnair@alfengineering.com | nitinkortikar | - | nitinkortikar@alfengineering.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2017-07-07 | 2017-07-07 | 1 |  | Dhananjay Sirsikar
543 | 2017-07-21 | 10:03:48 AM | Sapl0005 | 1 | 5 | A024 | 554 | 565 | 7017002314 | 34 | 0 | S0156 | 2017-07-10 | TROLLEY SET C63 | Sagar Ravtale | 7 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | autocomp panse dharwad | 1 | 21 | 405 | YOGESH SHIRSAT | - | yjshirsat@pansegroup.com | pmrajguru | - | pmrajguru@pansegroup.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | COMPLETE | 2017-07-10 | 2017-07-10 | 1 |  | Sagar Ravtale
544 | 2018-06-22 | 11:57:14 AM | Sapl0005 | 1 | 5 | C018 | 555 | 566 | IND3992789 | 35 | 0 | N0169 | 2017-08-29 | S4 spring wedge fitment fixture | Dhananjay Sirsikar | 4 | 2017-08-29 | 2018-02-28 | 2017-09-12 | 2018-02-28 | 2017-09-26 | 2017-09-30 | 2017-10-05 | 2017-10-10 | 2017-10-10 | 2017-10-12 | 2017-10-01 | 2017-10-05 | 2017-10-05 | 2017-10-18 | 2017-10-05 | 2017-10-10 | Cumins Generator Technologies India Private Limited.:Plot No C-33, Nagapur:MIDC Area, Ahmednagar Maharashtra 414111 India | 1 | 21 | 382 | yogesh.b.borse | - | yogesh.b.borse@cummins.com | kiran dole | - | kiran.dole@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | close | 2017-09-26 | 2017-09-26 | 1 |  | Dhananjay Sirsikar
545 | 2021-08-24 | 11:04:37 AM | Sapl0334 | 1 | 5 | C004 | 556 | 567 | IND3994074 | 35 | 0 | N0170 | 2017-08-29 | Battery Operated Rail Guided Vehicle | Dhananjay Sirsikar | 4 | 2017-08-29 | 2017-11-30 | 2017-09-05 | 2017-11-30 | 2017-09-10 | 2017-09-17 | 2017-09-21 | 2017-09-28 | 2017-09-29 | 2017-09-30 | 2017-09-15 | 2017-09-21 | 2017-09-21 | 2017-10-07 | 2017-09-21 | 2017-09-28 | kothrud | 1 | 21 | 405 | Visal, Anand V, | - | anandvisal@cummins.com | atulsingh.pardeshi | - | Atulsingh.Pardeshi@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2017-09-10 | 2017-09-10 | 1 |  | Dhananjay Sirsikar
546 | 2017-12-09 | 9:53:12 AM | Sapl0005 | 1 | 5 | A024 | 557 | 568 | Verbal_2017 | 34 | 0 | S0157 | 2017-08-31 | telescopic trolley set | Sagar Ravtale | 7 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | AUTOCOMP CORPORATION PANSE PVT.LTD - Dharwad | 1 | 17 | 304 | YOGESH SHIRSAT | - | yjshirsat@pansegroup.com | Bhatraj Patil | - | bppatil@pansegroup.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2017-08-31 | 2017-08-31 | 1 |  | Sagar Ravtale
547 | 2017-11-29 | 10:35:23 AM | Sapl0005 | 1 | 5 | C004 | 558 | 569 | IND4025818 | 35 | 0 | N0171 | 2017-10-03 | MS TRACK - 15mtr | Akshay bhojkar | 2 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-05 | 2017-10-14 | 2017-10-14 | 2017-10-11 | 2017-10-12 | 2017-10-05 | 2017-10-05 | 2017-10-14 | 2017-10-25 | 2017-10-14 | 2017-10-14 | cummins india ltd. | 1 | 21 | 405 | Visal, Anand V | - | visal.anand@cummins.com | Atulsingh.Pardesh | - | Atulsingh.Pardeshi@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2017-10-05 | 2017-10-05 | 1 |  | Akshay bhojkar
550 | 2017-12-09 | 9:52:53 AM | Sapl0005 | 1 | 5 | C004 | 561 | 572 | IND4032779 | 35 | 0 | N0174 | 2017-10-11 | MS TRACK | Akshay bhojkar | 2 | 2017-10-11 | 2017-10-13 | 2017-10-13 | 2017-10-14 | 2017-10-14 | 2017-10-14 | 2017-10-14 | 2017-10-14 | 2017-10-14 | 2017-10-14 | 2017-10-14 | 2017-10-14 | 2017-10-16 | 2017-10-17 | 2017-10-14 | 2017-10-14 | cummins india ltd | 1 | 21 | 405 | Atulsingh.Pardeshi | - | Atulsingh.Pardeshi@cummins.com | Atulsingh.Pardesh | - | Atulsingh.Pardeshi@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2017-10-11 | 2017-10-11 | 1 |  | Akshay bhojkar
551 | 2022-03-31 | 10:05:11 AM | Sapl0335 | 1 | 5 | S008 | 562 | 573 | tata12 | 35 | 0 | N0175 | 2017-12-01 | Assy Dash Board Fixture | PADMASINHA JOSHI | 3 | 2017-12-01 | 2018-10-31 | 2017-12-07 | 2018-10-31 | 2017-12-13 | 2018-01-27 | 2018-01-04 | 2018-01-05 | 2018-01-06 | 2018-01-08 | 2017-12-27 | 2018-01-03 | 2018-01-04 | 2018-01-12 | 2018-01-04 | 2018-01-05 | tata motors | 1 | 21 | 405 | santosh uttekar | - | santosh.uttekar@tatamotors.com | kanchan.pant | - | kanchan.pant@sharadaind.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | Fixture verification done | 2017-12-13 | 2017-12-13 | 1 |  | PADMASINHA JOSHI
552 | 2018-02-21 | 11:03:55 AM | Sapl0005 | 1 | 5 | A013 | 563 | 574 | POG617000422 | 37 | 0 | P0047 | 2017-12-02 | SPARES OF HOIST | Amit Shedge | 4 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | ALF ENGINEERING PVT LTD-UNIT-6 - Plot No. A-1/3, MVML Supplier Park, Phase - IV,, Village Nigoje BPuhnoer, Maharashtra, PIN : 410501 | 1 | 21 | 405 | Sunil Lokhande | - | sunillokhande@alfengineering.com | Sunil Lokhande | - | sunillokhande@alfengineering.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2017-12-02 | 2017-12-02 | 1 |  | Amit Shedge
553 | 2018-02-21 | 11:00:14 AM | Sapl0005 | 1 | 5 | A004 | 564 | 575 | C2PO1718_003592 | 34 | 0 | S0158 | 2017-12-06 | LONG RAIL, CROSS RAIL & TROLLEY SET C63 | Sagar Ravtale | 2 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-07 | 2017-12-07 | 2017-12-06 | 2017-12-06 | 2017-12-07 | 2017-12-08 | 2017-12-06 | 2017-12-06 | Autoline Industries Limited (C2) S No. 313, 314, 320 to 323, Nanekarwadi, Chakan, Taluka Khed,,Pune410501, Maharashtra,Indi a. | 1 | 21 | 405 | KETAN KADAM | - | ketan.kadam@autolineind.com | faiyaz kashi | - | Faiyaz.Kashi@autolineind.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2017-12-06 | 2017-12-06 | 1 |  | Sagar Ravtale
554 | 2019-12-29 | 7:04:14 PM | Sapl0002 | 1 | 5 | A035 | 565 | 576 | verbal8dec | 35 | 0 | N0176 | 2017-12-09 | Inversion fixture | Prajyot Genjii | 3 | 2017-12-09 | 2018-07-31 | 2017-12-16 | 2018-07-31 | 2017-12-23 | 2018-01-04 | 2018-01-10 | 2018-01-13 | 2018-01-15 | 2018-01-17 | 2018-01-04 | 2018-01-10 | 2018-01-10 | 2018-01-21 | 2018-01-10 | 2018-01-13 | ATLAS COPCO, CHAKAN | 1 | 21 | 405 | KAILASH KABRA | 9370870722 | kailash.kabra@in.atlascopco.com | KAILASH KABRA | - | kailash.kabra@in.atlascopco.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2017-12-27 | 2017-12-27 | 1 |  | Prajyot Genjii
556 | 2018-02-21 | 11:01:21 AM | Sapl0005 | 1 | 5 | C004 | 567 | 578 | IND4094964 | 43 | 0 | T0027 | 2017-12-15 | HAND SAFETY SWITCH | Amit Shedge | 4 | 2017-12-15 | 2017-12-18 | 2017-12-18 | 2017-12-20 | 2017-12-20 | 2017-12-22 | 2017-12-24 | 2017-12-25 | 2017-12-25 | 2017-12-26 | 2017-12-22 | 2017-12-23 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | cummins india ltd., kothrud | 1 | 21 | 405 | amit jogi | - | amit.jogi@cummins.com | Gudadhe, Rajesh | - | rajesh.gudadhe@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | COMPLETE | 2017-12-18 | 2017-12-18 | 1 |  | Amit Shedge
558 | 2020-12-05 | 11:25:32 AM | sapl0313 | 1 | 5 | S006 | 569 | 580 | VERB2317 | 43 | 0 | T0028 | 2017-12-23 | LIFTO | Amit Shedge | 4 | 2017-12-23 | 2018-03-01 | 2017-12-29 | 2018-03-01 | 2018-01-06 | 2018-01-13 | 2018-01-16 | 2018-01-18 | 2018-01-19 | 2018-01-19 | 2018-01-13 | 2018-01-16 | 2018-01-16 | 2018-01-20 | 2018-01-20 | 2018-01-20 | Synergytech Automation | 1 | 21 | 405 | - | - | sales@synergytechs.com | - | - | sales@synergytechs.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | WO Close | 2017-12-29 | 2017-12-29 | 1 |  | Amit Shedge
559 | 2020-12-05 | 9:56:55 AM | sapl0313 | 1 | 5 | S006 | 570 | 581 | ver26 | 38 | 0 | J0099 | 2017-12-26 | CONSUMABLES | Dhananjay Sirsikar | 5 | 2017-12-26 | 2018-01-06 | 2018-01-06 | 2018-01-13 | 2018-01-14 | 2018-01-21 | 2018-01-28 | 2018-01-31 | 2018-02-01 | 2018-02-03 | 2018-01-21 | 2018-01-28 | 2018-02-04 | 2018-02-07 | 2018-02-07 | 2018-02-10 | Synergytech Automation | 1 | 21 | 405 | - | - | sales@synergytechs.com | - | - | sales@synergytechs.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | wo closed | 2017-12-26 | 2017-12-26 | 1 |  | Dhananjay Sirsikar
560 | 2018-03-13 | 2:08:01 PM | Sapl0005 | 1 | 5 | T017 | 571 | 583 | verb9 | 38 | 0 | J0100 | 2018-01-10 | Base Frame | Sagar Ravtale | 5 | 2018-01-10 | 2018-01-12 | 2018-01-12 | 2018-01-13 | 2018-01-15 | 2018-01-20 | 2018-01-22 | 2018-01-23 | 2018-01-24 | 2018-01-24 | 2018-01-20 | 2018-01-22 | 2018-01-25 | 2018-01-25 | 2018-01-22 | 2018-01-23 | Trumech Engg LLP | 1 | 21 | 405 | Mr. Sanjay | - | trumechengg@gmail.com | Mr. Sanjay | - | trumechengg@gmail.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2018-01-13 | 2018-01-13 | 1 |  | Sagar Ravtale
561 | 2019-12-29 | 5:16:26 PM | Sapl0002 | 1 | 5 | C015 | 572 | 584 | IND4101138 | 36 | 0 | E0041 | 2018-01-11 | Installation and commissioning of 500kg Pillar mounted Jib Crane | Dhananjay Sirsikar | 3 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-13 | 2018-01-18 | 2018-01-18 | 2018-01-19 | 2018-01-19 | 2018-01-15 | 2018-01-17 | 2018-01-22 | 2018-01-24 | 2018-01-18 | 2018-01-18 | Cummins Technologies India Pvt. Ltd.: Phaltan High Horsepower Plant, SEZ Unit: Plot No. B3/1, MIDC SEZ-Phaltan, Village Nandal-Surwadi, Taluka Phaltan, Dist. Sata | 1 | 21 | 409 | priya srivastava | - | priya.srivastava@cummins.com | rajesh.m.sangar | - | rajesh.m.sangar@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | COMPLETED | 2018-01-12 | 2018-01-12 | 1 |  | Dhananjay Sirsikar
562 | 2018-03-13 | 2:07:32 PM | Sapl0005 | 1 | 5 | A018 | 573 | 585 | U5PO1718_003104 | 37 | 0 | P0048 | 2018-01-12 | BREAK COIL | Amit Shedge | 4 | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-15 | 2018-01-17 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-22 | 2018-01-22 | Autoline Industries Ltd. (Plot No.5) Plot No.05, Sector 11, (Tata Vendor Park), Sidcul, IIE, Pantnagar, Rudrapur263153, Uttarakhan, | 1 | 34 | 679 | Govindsingh | - | govind.ginwal@autolineind.com | atmaram.ghogare | - | atmaram.ghogare@autolineind.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2018-01-13 | 2018-01-13 | 1 |  | Amit Shedge
563 | 2020-12-05 | 9:59:58 AM | sapl0313 | 1 | 5 | M030 | 574 | 586 | 16jan | 35 | 0 | N0178 | 2018-01-16 | Mobile Front Working Platform | PADMASINHA JOSHI | 3 | 2018-01-16 | 2018-11-28 | 2018-01-22 | 2018-11-28 | 2018-01-30 | 2018-03-02 | 2018-02-19 | 2018-03-11 | 2018-02-22 | 2018-03-14 | 2018-02-12 | 2018-03-07 | 2018-02-19 | 2018-03-27 | 2018-02-20 | 2018-03-11 | Saharanpur | 1 | 5 | 86 | sandeep.r.kumar | - | sandeep.r.kumar@alstomgroup.com | bishnu.patnaik | - | bishnu.patnaik@alstomgroup.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | wo closed | 2018-01-30 | 2018-01-30 | 1 |  | PADMASINHA JOSHI
564 | 2019-12-29 | 7:06:30 PM | Sapl0002 | 1 | 5 | P012 | 575 | 587 | PROTOD/2017-18/-2870 | 35 | 0 | N0179 | 2018-01-19 | Drilling SPM for - 901,905,908 | PADMASINHA JOSHI | 3 | 2018-01-19 | 2018-07-31 | 2018-01-29 | 2018-07-31 | 2018-02-06 | 2018-04-07 | 2018-02-26 | 2018-04-07 | 2018-03-02 | 2018-04-07 | 2018-02-20 | 2018-04-07 | 2018-02-26 | 2018-04-07 | 2018-02-26 | 2018-04-07 | Plot No-57/357,,Waghjainagar,kharabwadi chakan,Chakan,Pune-410501,Maharashtra | 1 | 21 | 405 | Shirse Dnyanoba | - | shirse.protod@gmail.com | Dipak | - | dipak@protodengineering.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2018-04-07 | 2018-04-07 | 1 |  | PADMASINHA JOSHI
565 | 2018-08-03 | 11:39:00 AM | Sapl0005 | 1 | 5 | C015 | 576 | 588 | IND4130632 | 35 | 0 | N0180 | 2018-01-24 | Jib crane of Capacity 125 Kg | PADMASINHA JOSHI | 3 | 2018-01-24 | 2018-07-10 | 2018-01-25 | 2018-07-10 | 2018-01-30 | 2018-02-06 | 2018-02-09 | 2018-02-10 | 2018-02-10 | 2018-02-12 | 2018-02-07 | 2018-02-09 | 2018-02-09 | 2018-02-16 | 2018-02-15 | 2018-02-16 | Phaltan High Horsepower Plant, SEZ Unit: Plot No. B3/1, MIDC SEZ-Phaltan, Village Nandal-Surwadi, Taluka Phaltan, Dist. Sata | 1 | 21 | 409 | vinod.pore | - | vinod.pore@cummins.com | vijay.r.botre | - | vijay.r.botre@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2018-02-01 | 2018-02-01 | 1 |  | PADMASINHA JOSHI
566 | 2020-12-05 | 11:25:51 AM | sapl0313 | 1 | 5 | S006 | 577 | 589 | verb14feb | 43 | 0 | T0029 | 2018-02-14 | DEMO AGV | RAOSAHEB RAJALE | 4 | 2018-02-14 | 2018-02-16 | 2018-02-17 | 2018-02-20 | 2018-02-21 | 2018-03-24 | 2018-02-28 | 2018-03-01 | 2018-03-02 | 2018-02-05 | 2018-02-24 | 2018-02-27 | 2018-03-05 | 2018-03-07 | 2018-02-27 | 2018-02-28 | pune | 1 | 21 | 405 | ABC | - | sales@synergytechs.com | ABC | - | sales@synergytechs.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 1 |  | 1 | WO Close | 2018-02-27 | 2018-02-27 | 1 |  | RAOSAHEB RAJALE
567 | 2018-02-21 | 11:00:52 AM | Sapl0005 | 1 | 5 | C004 | 578 | 590 | IND4150740 | 43 | 0 | T0030 | 2018-02-15 | METAL STRIP ADJUSTMENT | Amit Shedge | 4 | 2018-02-15 | 2018-02-17 | 2018-02-17 | 2018-02-19 | 2018-02-19 | 2018-02-21 | 2018-02-23 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-21 | 2018-02-23 | 2018-02-26 | 2018-02-26 | 2018-02-26 | 2018-02-26 | kothrud | 1 | 21 | 405 | shabd.prakash | - | shabd.prakash@cummins.com | shirkant.m.foujdar | - | shirkant.m.foujdar@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2018-02-21 | 2018-02-21 | 1 |  | Amit Shedge
568 | 2018-08-29 | 10:26:04 AM | Sapl0005 | 1 | 5 | M001 | 579 | 591 | LOI17FEB | 38 | 0 | J0101 | 2018-02-17 | BWF UNITS FOR UB10 | PADMASINHA JOSHI | 3 | 2018-02-17 | 2018-03-31 | 2018-02-20 | 2018-03-31 | 2018-02-22 | 2018-02-26 | 2018-03-04 | 2018-03-06 | 2018-03-06 | 2018-03-07 | 2018-02-26 | 2018-03-03 | 2018-03-04 | 2018-03-10 | 2018-03-04 | 2018-03-06 | PLANT 2, MIDC SATPUR | 1 | 21 | 402 | YOGESH YADAV | - | YADAVYOGESH2@mahindra.com | Bodke Jagannath | - | bodkejagannath@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2018-02-21 | 2018-02-21 | 1 |  | PADMASINHA JOSHI
569 | 2020-12-05 | 11:14:04 AM | sapl0313 | 1 | 5 | C004 | 580 | 592 | IND4156755 | 37 | 0 | P0049 | 2018-02-17 | Double shuttle TOD rollers | Dhananjay Sirsikar | 3 | 2018-02-17 | 2018-02-19 | 2018-02-19 | 2018-02-20 | 2018-02-20 | 2018-02-20 | 2018-02-20 | 2018-02-20 | 2018-02-20 | 2018-02-21 | 2018-02-20 | 2018-02-20 | 2018-02-21 | 2018-02-22 | 2018-02-21 | 2018-02-21 | kothrud | 1 | 21 | 405 | ganesan.a | - | ganesan.a@cummins.com | rahul.dandgule | - | rahul.dandgule@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | WO Close | 2018-02-20 | 2018-02-20 | 1 |  | Dhananjay Sirsikar
570 | 2018-08-29 | 10:26:21 AM | Sapl0005 | 1 | 5 | M001 | 581 | 593 | VERB19FEB | 38 | 0 | J0102 | 2018-02-19 | UNITS FOR PROJECT UB20 | PADMASINHA JOSHI | 3 | 2018-02-19 | 2018-03-31 | 2018-02-21 | 2018-03-31 | 2018-02-22 | 2018-03-02 | 2018-03-06 | 2018-03-06 | 2018-03-07 | 2018-03-07 | 2018-02-28 | 2018-03-06 | 2018-03-06 | 2018-03-10 | 2018-03-06 | 2018-03-06 | PLANT 2, MIDC SATPUR | 1 | 21 | 402 | YOGESH YADAV | - | YADAVYOGESH2@mahindra.com | Bodke Jagannath | - | bodkejagannath@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2018-02-22 | 2018-02-22 | 1 |  | PADMASINHA JOSHI
571 | 2018-04-20 | 9:55:20 AM | Sapl0005 | 1 | 5 | M001 | 582 | 594 | verb1918feb | 38 | 0 | J0103 | 2018-02-19 | Fabrication of Bases with SR 18F208 | Sagar Ravtale | 5 | 2018-02-19 | 2018-03-31 | 2018-02-19 | 2018-03-31 | 2018-02-20 | 2018-02-22 | 2018-02-23 | 2018-02-23 | 2018-02-23 | 2018-02-23 | 2018-02-22 | 2018-02-23 | 2018-02-23 | 2018-02-24 | 2018-02-22 | 2018-02-22 | Plant 2, Satpur midc | 1 | 21 | 402 | KUMAR.CHANDRAMANI | - | KUMAR.CHANDRAMANI2@mahindra.com | bodke.jagannath | - | bodke.jagannath@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | c | 2018-02-20 | 2018-02-20 | 1 |  | Sagar Ravtale
572 | 2018-04-20 | 9:55:34 AM | Sapl0005 | 1 | 5 | M001 | 583 | 595 | verb22feb | 38 | 0 | J0104 | 2018-02-22 | MBA-30 Jig unit | PADMASINHA JOSHI | 3 | 2018-02-22 | 2018-03-31 | 2018-02-22 | 2018-03-31 | 2018-02-22 | 2018-02-26 | 2018-03-02 | 2018-03-02 | 2018-03-03 | 2018-03-03 | 2018-02-27 | 2018-03-01 | 2018-03-02 | 2018-03-06 | 2018-03-02 | 2018-03-02 | mahindra& mahindra, nashik | 1 | 21 | 402 | Yogesh Singh | - | YADAV.YOGESH2@mahindra.com | DEOGHARE.ROOPAL | - | DEOGHARE.ROOPAL@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | c | 2018-02-23 | 2018-02-23 | 1 |  | PADMASINHA JOSHI
574 | 2018-08-03 | 11:42:58 AM | Sapl0005 | 1 | 5 | C004 | 585 | 597 | IND4198214 | 43 | 0 | T0031 | 2018-03-30 | HEATER AND ACCESSORIES | Dhananjay Sirsikar | 4 | 2018-03-30 | 2018-05-08 | 2018-04-02 | 2018-05-08 | 2018-04-05 | 2018-04-13 | 2018-04-21 | 2018-04-30 | 2018-05-06 | 2018-05-10 | 2018-04-13 | 2018-04-20 | 2018-04-21 | 2018-05-12 | 2018-04-30 | 2018-05-05 | Cummins India Ltd., Pune | 1 | 21 | 405 | Milind Bhagwat | - | milind.v.bhagwat@cummins.com | Rahul Dandgule | - | rahul.dandgule@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2018-03-31 | 2018-03-31 | 1 |  | Dhananjay Sirsikar
575 | 2018-04-20 | 9:54:07 AM | Sapl0005 | 1 | 5 | S030 | 586 | 598 | U5BO11803000070 | 34 | 0 | S0159 | 2018-04-02 | long rail & trolley set | Sagar Ravtale | 7 | 2018-03-31 | 2018-04-02 | 2018-04-02 | 2018-04-04 | 2018-04-04 | 2018-04-05 | 2018-04-05 | 2018-04-06 | 2018-04-07 | 2018-04-07 | 2018-04-05 | 2018-04-06 | 2018-04-08 | 2018-04-09 | 2018-04-08 | 2018-04-09 | KHASRA NO. 1262SA, GOYLA INDUSTRIAL AREACHINAHAT LUCKNOW 227105 UTTAR PRADESH INDIA | 1 | 33 | 696 | KANCHAN PANT | - | kanchan@sharadaindustries.com | ranapratap.singh | - | ranapratap.singh@sharadaindustries.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | c | 2018-04-02 | 2018-04-02 | 1 |  | Sagar Ravtale
576 | 2018-05-08 | 11:01:56 AM | Sapl0005 | 1 | 6 | T016 | 587 | 599 | 05 | 34 | 0 | S0160 | 2018-05-03 | rail & load trolley | Sagar Ravtale | 7 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | Techexpert Engineering Pvt.Ltd. 78, Shivane Industrial Area, Shivane, Off NDA Road, Pune -411023 | 1 | 21 | 405 | Pankaj Jadhav | - | jvi@techexpertindia.com | ingale | - | sales@techexpertindia.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | complte | 2018-05-03 | 2018-05-03 | 1 |  | Sagar Ravtale
577 | 2018-05-21 | 9:30:14 AM | Sapl0005 | 1 | 6 | P012 | 588 | 600 | PROTOD/2018-19/-390 | 38 | 0 | J0106 | 2018-05-07 | Fabricatio n & Machining of Frame | Sagar Ravtale | 5 | 2018-05-07 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-09 | 2018-05-11 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-09 | 2018-05-10 | Plot No-57/357,,Waghjainagar,kharabwadi ,Chakan,Pune-410501,Maharashtra. | 1 | 21 | 405 | Dnyanoba shirse | - | purchase@protodengineering.com | Dnyanoba shirse | - | purchase@protodengineering.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2018-05-07 | 2018-05-07 | 1 |  | Sagar Ravtale
578 | 2018-08-03 | 12:17:10 PM | Sapl0005 | 1 | 6 | S011 | 589 | 601 | PUOR18000463 | 37 | 0 | P0050 | 2018-05-07 | BREAK COIL FOR LIFTO HOIST | Amit Shedge | 4 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 690, Udyambag Industrial Estate, BELAGAVI - 590 008 KARNATAKA - INDIA | 1 | 17 | 295 | M N PATIL | - | purchase@shantiiron.net | M N PATIL | - | stores@shantiiron.net | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2018-05-07 | 2018-05-07 | 1 |  | Amit Shedge
579 | 2018-05-18 | 8:57:51 AM | Sapl0005 | 1 | 6 | P012 | 590 | 602 | PROTOD/2018-19/-481 | 34 | 0 | S0161 | 2018-05-11 | Long rail c63, Cross Rail C63, Trolley set | Sagar Ravtale | 7 | 2018-05-11 | 2018-05-11 | 2018-05-11 | 2018-05-11 | 2018-05-12 | 2018-05-14 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-14 | 2018-05-15 | 2018-05-16 | 2018-05-17 | 2018-05-16 | 2018-05-16 | Proto D, chakan | 1 | 21 | 405 | MILIND PATIL | - | purchase@protodengineering.com | Kuldip Shinde | - | shindekuldip235@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2018-05-12 | 2018-05-12 | 1 |  | Sagar Ravtale
580 | 2020-12-05 | 10:00:25 AM | sapl0313 | 1 | 6 | C004 | 591 | 603 | IND4242546 | 35 | 0 | N0181 | 2018-05-15 | Turn Over Device for KV Cyl Block Indexing Unit without Conveyor | Prashant Suryawanshi | 3 | 2018-05-15 | 2018-11-10 | 2018-05-26 | 2018-11-10 | 2018-06-04 | 2018-06-16 | 2018-06-22 | 2018-06-27 | 2018-06-28 | 2018-06-30 | 2018-06-17 | 2018-06-22 | 2018-06-22 | 2018-07-07 | 2018-06-22 | 2018-06-27 | Cummins India Limited:CIL_EBU_085 Kothrud:: Pune Maharashtra 411038 | 1 | 21 | 405 | Milind Bhagwat | - | milind.v.bhagwat@cummins.com | Milind Bhagwat | - | milind.v.bhagwat@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | wo closed | 2018-06-04 | 2018-06-04 | 1 |  | Prashant Suryawanshi
581 | 2020-12-05 | 10:03:13 AM | sapl0313 | 1 | 6 | C004 | 592 | 604 | IND4242586 | 35 | 0 | N0182 | 2018-05-15 | Cradle Type TOD for KV Cylinder Block for Standard Rework work station | hanumant Bhilare | 2 | 2018-05-15 | 2018-11-10 | 2018-05-26 | 2018-11-10 | 2018-06-04 | 2018-06-16 | 2018-06-22 | 2018-06-27 | 2018-06-28 | 2018-06-30 | 2018-06-17 | 2018-06-22 | 2018-06-22 | 2018-07-07 | 2018-06-22 | 2018-06-27 | CUMMINS , KOTHRUD | 1 | 21 | 405 | Milind Bhagwat | - | milind.v.bhagwat@cummins.com | Milind Bhagwat | - | milind.v.bhagwat@cummins.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | wo closed | 2018-06-04 | 2018-06-04 | 1 |  | hanumant Bhilare
582 | 2020-12-05 | 9:58:19 AM | sapl0313 | 1 | 6 | M030 | 593 | 605 | verb18may | 38 | 0 | J0107 | 2018-05-18 | Manufacturing of trolley | Sagar Ravtale | 5 | 2018-05-18 | 2018-05-19 | 2018-05-19 | 2018-05-20 | 2018-05-21 | 2018-05-29 | 2018-06-03 | 2018-06-05 | 2018-06-06 | 2018-06-08 | 2018-05-29 | 2018-06-02 | 2018-06-11 | 2018-06-12 | 2018-06-04 | 2018-06-05 | madhepura | 1 | 5 | 86 | veeraragavan.parthasarathy | - | veeraragavan.parthasarathy@alstomgroup.com | veeraragavan.parthasarathy | - | veeraragavan.parthasarathy@alstomgroup.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 1 |  | 1 | wo closed | 2018-05-18 | 2018-05-18 | 1 |  | Sagar Ravtale
583 | 2018-06-11 | 9:35:15 AM | Sapl0005 | 1 | 6 | P012 | 594 | 606 | PROTOD/2018-19/-621 | 34 | 0 | S0162 | 2018-05-23 | cross Rail C63 | Sagar Ravtale | 7 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | Plot No-57/357,,Waghjainagar,kharabwadi ,Chakan,Pune-410501,Maharashtra. | 1 | 21 | 405 | MILIND PATIL | - | purchase@protodengineering.com | Kuldip Shinde | - | shindekuldip235@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2018-05-23 | 2018-05-23 | 1 |  | Sagar Ravtale
584 | 2020-12-05 | 11:15:59 AM | sapl0313 | 1 | 6 | S027 | 595 | 607 | verb24May | 34 | 0 | S0163 | 2018-05-24 | ERP SOFTWARE | MADHUR PATRIKAR | 21 | 2018-05-24 | 2018-05-26 | 2018-05-26 | 2018-05-28 | 2018-05-29 | 2018-05-31 | 2018-06-03 | 2018-06-05 | 2018-06-06 | 2018-06-08 | 2018-05-31 | 2018-06-02 | 2018-06-09 | 2018-06-11 | 2018-06-12 | 2018-06-14 | SAKSHI CHAKAN | 1 | 21 | 405 | MR. KAKADE | - | info@sakshiindia.co.in | MR. KAKADE | - | kakade01@yahoo.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | WO Close | 2018-05-24 | 2018-05-24 | 1 |  | MADHUR PATRIKAR
585 | 2020-12-05 | 11:16:25 AM | sapl0313 | 1 | 6 | P012 | 596 | 608 | VERB24 | 34 | 0 | S0164 | 2018-05-24 | ERP SYSTEM | MADHUR PATRIKAR | 21 | 2018-05-24 | 2018-05-26 | 2018-05-27 | 2018-05-29 | 2018-05-30 | 2018-06-01 | 2018-06-04 | 2018-06-06 | 2018-06-06 | 2018-06-07 | 2018-06-01 | 2018-06-03 | 2018-06-08 | 2018-06-09 | 2018-06-11 | 2018-06-12 | PROTO D | 1 | 21 | 405 | SHIRSE | - | shirse.protod@gmail.com | SHIRSE | - | shirse.protod@gmail.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | WO Close | 2018-05-24 | 2018-05-24 | 1 |  | MADHUR PATRIKAR
586 | 2018-06-25 | 10:27:31 AM | Sapl0005 | 1 | 6 | J019 | 597 | 609 | VERB2JUN | 34 | 0 | S0165 | 2018-06-04 | LONG RAIL, CROSS RAIL & TROLLEY SET | Sagar Ravtale | 7 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-05 | 2018-06-04 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-04 | 2018-06-05 | 2018-06-06 | 2018-06-07 | 2018-06-06 | 2018-06-07 | SUPERWELD | 1 | 21 | 405 | AMIT AGARWAL | - | amit.superweld@gmail.com | DEEPAK AGARWAL | - | dsagarwal@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2018-06-04 | 2018-06-04 | 1 |  | Sagar Ravtale
587 | 2018-08-17 | 11:01:13 AM | Sapl0005 | 1 | 6 | P012 | 616 | 610 | verb18jun | 38 | 0 | J0108 | 2018-06-19 | FABRICATION & MACHINING OF BASE | Sagar Ravtale | 5 | 2018-06-19 | 2018-06-20 | 2018-06-20 | 2018-06-21 | 2018-06-21 | 2018-06-23 | 2018-06-26 | 2018-06-26 | 2018-06-27 | 2018-06-27 | 2018-06-23 | 2018-06-25 | 2018-06-27 | 2018-06-27 | 2018-06-26 | 2018-06-26 | PROTO D ENGINEERING | 1 | 21 | 405 | Dnyanoba shirse | - | shirse.protod@gmail.com | MILIND | - | purchase@protodengineering.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 1 |  | 1 | close | 2018-06-20 | 2018-06-20 | 1 |  | Sagar Ravtale
588 | 2018-06-25 | 10:27:50 AM | Sapl0005 | 1 | 6 | J019 | 618 | 611 | 02 | 34 | 0 | S0166 | 2018-06-23 | LOAD TROLLEY | Sagar Ravtale | 5 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | JAPTECH ENGINEERING CORPORATION | 1 | 21 | 405 | DEEPAK AGARWAL | - | dsagarwal@gmail.com | AMIT AGARWAL | - | amit.superweld@gmail.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2018-06-23 | 2018-06-23 | 1 |  | Sagar Ravtale
589 | 2019-12-29 | 7:08:19 PM | Sapl0002 | 1 | 6 | A002 | 619 | 612 | PO_8001 | 35 | 0 | N0183 | 2018-06-25 | PICK & PLACE SYSTEM FOR ULTRA FRAME | PADMASINHA JOSHI | 2 | 2018-06-25 | 2018-11-25 | 2018-07-02 | 2018-11-25 | 2018-07-09 | 2018-08-09 | 2018-07-18 | 2018-08-16 | 2018-07-26 | 2018-08-23 | 2018-07-15 | 2018-08-13 | 2018-07-18 | 2018-09-05 | 2018-07-21 | 2018-08-18 | ANUSAYA AUTO PRESS PARTS, CHAKAN | 1 | 21 | 405 | Arun Metange | - | arunmetange@wadhokar.com | digambar.pargaonkar | - | digambar.pargaonkar@wadhokar.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | c | 2018-07-05 | 2018-07-05 | 1 |  | PADMASINHA JOSHI
590 | 2018-08-04 | 9:20:43 AM | Sapl0005 | 1 | 6 | A013 | 620 | 613 | 4100001338 | 37 | 0 | P0051 | 2018-08-03 | Brake Liner | Amit Shedge | 4 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | ALF ENGINEERING PVT. LTD., CHAKAN | 1 | 21 | 405 | ARUN PATIL | 8208876506 | arunpatil@alfengineering.com | kalidasbarne | - | kalidasbarne@alfengineering.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2018-08-03 | 2018-08-03 | 1 |  | Amit Shedge
591 | 2020-12-05 | 11:14:27 AM | sapl0313 | 1 | 6 | C004 | 621 | 614 | IND4319277 | 37 | 0 | P0052 | 2018-08-03 | PU COATED ROLLER | hanumant Bhilare | 2 | 2018-08-03 | 2018-08-08 | 2018-08-08 | 2018-08-14 | 2018-08-14 | 2018-08-20 | 2018-08-28 | 2018-08-29 | 2018-08-31 | 2018-08-31 | 2018-08-21 | 2018-08-29 | 2018-09-04 | 2018-09-06 | 2018-08-31 | 2018-09-01 | cummins india ltd. | 1 | 21 | 405 | dnyaneshwar.j.dhamal | - | dnyaneshwar.j.dhamal@cummins.com | dnyaneshwar.j.dhamal | - | dnyaneshwar.j.dhamal@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | WO Close | 2018-08-16 | 2018-08-16 | 1 |  | hanumant Bhilare
592 | 2018-08-29 | 10:24:20 AM | Sapl0005 | 1 | 6 | A002 | 622 | 615 | PO_8564 | 34 | 0 | S0167 | 2018-08-03 | LONG RAIL C63, CROSS RAILC63 & TROLLEY SET | Sagar Ravtale | 7 | 2018-08-03 | 2018-08-04 | 2018-08-04 | 2018-08-06 | 2018-08-06 | 2018-08-08 | 2018-08-16 | 2018-08-17 | 2018-08-11 | 2018-08-11 | 2018-08-08 | 2018-08-10 | 2018-08-12 | 2018-08-16 | 2018-08-16 | 2018-08-17 | Anusaya Auto Press Parts Pvt. Ltd. Pune Maharashtra | 1 | 21 | 405 | anil.bhosale | - | anil.bhosale@wadhokar.com | anil.bhosale | - | anil.bhosale@wadhokar.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2018-08-04 | 2018-08-04 | 1 |  | Sagar Ravtale
593 | 2018-08-17 | 11:00:47 AM | Sapl0005 | 1 | 6 | S011 | 623 | 616 | PUOR18001718 | 37 | 0 | P0053 | 2018-08-07 | BREAK COIL | Amit Shedge | 4 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | SHANTI IRON & STEEL | 1 | 17 | 295 | M N PATIL | - | purchase@shantiiron.net | SHANTILAL V PORWAL | - | svp@shantiiron.net | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | close | 2018-08-07 | 2018-08-07 | 1 |  | Amit Shedge
594 | 2018-09-28 | 9:06:22 AM | Sapl0005 | 1 | 6 | C004 | 624 | 617 | IND4328704 | 43 | 0 | T0032 | 2018-08-10 | CONTROL PANEL FOR SCISSOR LIFT FOR QSK60 | Amit Shedge | 4 | 2018-08-10 | 2018-08-17 | 2018-08-17 | 2018-08-24 | 2018-08-25 | 2018-09-01 | 2018-09-08 | 2018-09-14 | 2018-09-15 | 2018-09-19 | 2018-09-01 | 2018-09-08 | 2018-09-21 | 2018-09-22 | 2018-09-21 | 2018-09-22 | cummins india ltd. | 1 | 21 | 405 | RAHUL DANDGULE | - | rahul.dandgule@cummins.com | milind.v.bhagwat | - | milind.v.bhagwat@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2018-08-25 | 2018-08-25 | 1 |  | Amit Shedge
595 | 2018-09-10 | 9:10:22 AM | Sapl0005 | 1 | 6 | A034 | 474 | 618 | DHPO1819_000083 | 34 | 0 | S0168 | 2018-08-17 | TROLLEY SET C63 | Sagar Ravtale | 7 | 2018-08-17 | 2018-08-17 | 2018-08-17 | 2018-08-17 | 2018-08-17 | 2018-08-17 | 2018-08-17 | 2018-08-17 | 2018-08-17 | 2018-08-17 | 2018-08-17 | 2018-08-17 | 2018-08-17 | 2018-08-17 | 2018-08-17 | 2018-08-17 | Autoline Industries , Dharwad | 1 | 17 | 304 | girish.khanapur | - | girish.khanapur@autolineind.com | avvaneppa.asangi | - | avvaneppa.asangi@autolineind.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2018-08-17 | 2018-08-17 | 1 |  | Sagar Ravtale
596 | 2018-08-29 | 10:25:22 AM | Sapl0005 | 1 | 6 | A013 | 625 | 619 | 4100001782 | 37 | 0 | P0054 | 2018-08-18 | HOIST SPARES | Amit Shedge | 4 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | ALF ENGINEERING PVT LTD-UNIT-IV, chakan | 1 | 21 | 405 | arunpatil | - | arunpatil@alfengineering.com | kalidasbarne | - | kalidasbarne@alfengineering.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2018-08-18 | 2018-08-18 | 1 |  | Amit Shedge
597 | 2019-12-29 | 5:12:27 PM | Sapl0002 | 1 | 6 | C004 | 626 | 620 | IND4354716 | 38 | 0 | J0109 | 2018-09-07 | PU coating Roller | Prashant Suryawanshi | 2 | 2018-09-07 | 2018-09-10 | 2018-09-10 | 2018-09-12 | 2018-09-12 | 2018-10-02 | 2018-10-06 | 2018-10-06 | 2018-10-07 | 2018-10-08 | 2018-10-02 | 2018-10-06 | 2018-10-09 | 2018-10-10 | 2018-10-08 | 2018-10-08 | Cummins India Ltd., Pune | 1 | 21 | 405 | sandip.ravan | - | sandip.ravan@cummins.com | sandip.ravan | - | sandip.ravan@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2018-09-17 | 2018-09-17 | 1 |  | Prashant Suryawanshi
598 | 2020-12-05 | 10:03:45 AM | sapl0313 | 1 | 6 | K010 | 627 | 621 | verb7sep | 35 | 0 | N0184 | 2018-09-07 | TATA Motors Tooling fixtures for new Gen Load Body. | PADMASINHA JOSHI | 19 | 2019-03-04 | 2019-03-15 | 2019-03-04 | 2019-03-15 | 2019-03-08 | 2019-03-15 | 2019-03-08 | 2019-03-15 | 2019-03-08 | 2019-03-15 | 2019-03-08 | 2019-03-15 | 2019-03-08 | 2019-03-15 | 2019-03-08 | 2019-03-15 | kailash Vahan Udyog | 1 | 21 | 405 | Samir Bhanarkar | - | samir@kvul.in | shivam.arren | - | shivam.arren@kvul.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | wo closed | 2019-03-15 | 2019-03-15 | 1 |  | PADMASINHA JOSHI
599 | 2020-12-05 | 10:04:26 AM | sapl0313 | 1 | 6 | S029 | 628 | 622 | 10094166 | 35 | 0 | N0185 | 2018-09-07 | Cross belt sampler | PADMASINHA JOSHI | 2 | 2018-09-28 | 2018-12-04 | 2018-10-11 | 2018-12-17 | 2018-10-12 | 2019-01-08 | 2018-11-29 | 2019-01-17 | 2018-12-25 | 2019-01-19 | 2018-10-29 | 2019-01-15 | 2018-12-26 | 2019-01-21 | 2018-11-14 | 2019-01-22 | SGS India Private Limited | 1 | 17 | 293 | Gangadhar.Udnur | - | Gangadhar.Udnur@sgs.com | Sunil.Samay | - | Sunil.Samay@sgs.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | wo closed | 2018-10-20 | 2018-10-08 | 1 |  | PADMASINHA JOSHI
600 | 2018-09-25 | 8:39:33 AM | Sapl0005 | 1 | 6 | P012 | 629 | 623 | PROTOD/2018-19/-2004 | 34 | 0 | S0169 | 2018-09-10 | TROLLEY SET | Sagar Ravtale | 7 | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-11 | 2018-09-11 | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-10 | Proto D Engineering (Chakan) | 1 | 21 | 405 | MILIND PATIL | - | purchase@protodengineering.com | vikas | - | vikas@protodengineering.co.in | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2018-09-10 | 2018-09-10 | 1 |  | Sagar Ravtale
601 | 2020-12-05 | 11:26:14 AM | sapl0313 | 1 | 6 | S033 | 630 | 626 | verbalsep12 | 43 | 0 | T0033 | 2018-09-14 | cables | Amit Shedge | 4 | 2018-09-14 | 2018-09-14 | 2018-09-14 | 2018-09-14 | 2018-09-14 | 2018-09-14 | 2018-09-14 | 2018-09-14 | 2018-09-14 | 2018-09-14 | 2018-09-14 | 2018-09-14 | 2018-09-14 | 2018-09-14 | 2018-09-14 | 2018-09-14 | suman electrical | 1 | 21 | 405 | xyz | - | xyz@gmail.com | xyz | - | xyz@gmail.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | WO Close | 2018-09-14 | 2018-09-14 | 1 |  | Amit Shedge
602 | 2019-12-29 | 7:05:34 PM | Sapl0002 | 1 | 6 | J020 | 631 | 627 | 4300035047 | 34 | 0 | S0170 | 2018-10-10 | LONG RAIL C63, CROSS RAILC63, TROLLEY SET | Dhananjay Sirsikar | 7 | 2018-10-10 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11 | JBM AUTO LIMITED | 1 | 21 | 402 | BIJAY AGARWAL | 9881907992 | bijay.agrawal@jbmgroup.com | vinayak.kale | - | vinayak.kale@jbmgroup.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | c | 2018-10-10 | 2018-10-10 | 1 |  | Dhananjay Sirsikar
604 | 2018-10-15 | 3:39:18 PM | Sapl0005 | 1 | 6 | S011 | 633 | 629 | PUOR18002586 | 37 | 0 | P0055 | 2018-10-11 | BREAK COIL | Amit Shedge | 4 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 690, Udyambag Industrial Estate, BELAGAVI - 590 008 KARNATAKA - INDIA | 1 | 17 | 295 | M N PATIL | - | purchase@shantiiron.net | M N PATIL | - | purchase@shantiiron.net | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2018-10-11 | 2018-10-11 | 1 |  | Amit Shedge
605 | 2020-12-05 | 11:16:48 AM | sapl0313 | 1 | 6 | J017 | 634 | 630 | 4300035195 | 34 | 0 | S0171 | 2018-10-11 | SLIDO RAILS & TROLLEY SET | Dhananjay Sirsikar | 7 | 2018-10-11 | 2018-10-13 | 2018-10-13 | 2018-10-15 | 2018-10-15 | 2018-10-16 | 2018-10-17 | 2018-10-17 | 2018-10-18 | 2018-10-18 | 2018-10-16 | 2018-10-17 | 2018-10-23 | 2018-10-26 | 2018-10-22 | 2018-10-22 | JBM Auto Limited, Pithampur, | 1 | 20 | 689 | pradeep.boharpi | - | pradeep.boharpi@jbmgroup.com | shashank.agone | - | shashank.agone@jbmgroup.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | WO Close | 2018-10-15 | 2018-10-15 | 1 |  | Dhananjay Sirsikar
607 | 2020-12-05 | 10:53:50 AM | sapl0313 | 1 | 6 | A035 | 636 | 633 | PNEDL04736 | 35 | 0 | N0186 | 2018-11-29 | Frame fixture for 9097227701_9097424501 | MS. SONALI | 3 | 2018-11-22 | 2019-01-05 | 2018-11-26 | 2019-01-13 | 2018-12-04 | 2019-01-23 | 2018-12-14 | 2019-01-27 | 2018-12-25 | 2019-02-04 | 2018-12-13 | 2019-01-24 | 2018-12-14 | 2019-02-09 | 2018-12-22 | 2019-02-04 | Atlas Copco (India) Ltd. S.No.65/2B, Gat No.133,134/1.134/2,139,141,145,146, Village Mahalunge, Taluka-Khed, Chakan, Pune 410501, Maharashtra, INDIA GST No.-27AAACA4074D1Z2 PAN: AAACA4074D | 1 | 21 | 405 | MR SATISH KAKADE | 9822614720 | satish.kakade@in.atlascopco.com | - | - | sanjay.shinde@in.atlascopco.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | WO Close | 2018-12-13 | 2018-11-13 | 1 |  | MS. SONALI
608 | 2020-12-05 | 10:54:14 AM | sapl0313 | 1 | 6 | C015 | 637 | 634 | IND4418734 | 35 | 0 | N0187 | 2018-12-06 | Tool load assist for loading of cutting tool in CNC Mazak machine. | Prashant Suryawanshi | 3 | 2018-12-05 | 2018-12-10 | 2018-12-10 | 2019-01-15 | 2018-12-14 | 2018-12-25 | 2018-12-31 | 2019-01-01 | 2019-01-02 | 2019-02-04 | 2018-12-26 | 2018-12-29 | 2018-12-31 | 2019-01-30 | 2019-03-05 | 2019-03-06 | CUMMINS TECHNOLOGIES INDIA, PVT. LTD, PHALTAN | 1 | 21 | 405 | MR. MAHESH JEDHE | 7720043716 | mahesh.jedhe@cummins.com | S D SHINDE | - | sdshinde@synergytechs.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | WO Close | 2019-01-18 | 2019-01-18 | 1 |  | Prashant Suryawanshi
609 | 2019-12-29 | 5:18:02 PM | Sapl0002 | 1 | 6 | A013 | 638 | 635 | 4100003461 | 38 | 0 | J0110 | 2018-12-13 | - | - | 1 | 2018-12-01 | 2018-12-13 | 2018-12-01 | 2018-12-13 | 2018-12-01 | 2018-12-13 | 2018-12-01 | 2018-12-13 | 2018-12-01 | 2018-12-13 | 2018-12-01 | 2018-12-13 | 2018-12-01 | 2018-12-13 | 2018-12-01 | 2018-12-13 | Plot No. A-1/3, MVML Supplier Park, Phase IV, Chakan, Pune, PIN : 410501. Maharashtra,India | 1 | 21 | 405 | ARUN PATIL | - | arunpatil@alfengineering.com | - | - | Arunpatil@alfengineering.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | complted | 2018-12-13 | 2018-12-13 | 1 |  | -
610 | 2020-12-05 | 10:54:38 AM | sapl0313 | 1 | 6 | A002 | 639 | 637 | Verbalsep13 | 35 | 0 | N0188 | 2018-12-18 | unloading arrangement for long members | PADMASINHA JOSHI | 3 | 2018-12-13 | 2018-12-17 | 2018-12-18 | 2018-12-21 | 2018-12-22 | 2019-01-05 | 2019-01-06 | 2019-01-08 | 2018-12-24 | 2018-12-26 | 2019-01-05 | 2019-01-08 | 2019-01-09 | 2019-01-12 | 2019-01-14 | 2019-01-15 | ANUSAYA AUTO PRESS PARTS, CHAKAN | 1 | 21 | 405 | Arun Metange | - | arunmetange@wadhokar.com | digambar.pargaonkar | - | digambar.pargaonkar@wadhokar.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | WO Close | 2018-12-18 | 2018-12-17 | 1 |  | PADMASINHA JOSHI
613 | 2020-12-05 | 10:55:05 AM | sapl0313 | 1 | 6 | O002 | 642 | 640 | PN00090 | 35 | 0 | N0189 | 2018-12-22 | Turning devices and mounting fixtures | PADMASINHA JOSHI | 3 | 2018-12-21 | 2018-12-23 | 2018-12-24 | 2018-12-25 | 2018-12-26 | 2019-02-02 | 2019-01-06 | 2019-01-06 | 2019-01-07 | 2018-12-07 | 2019-01-03 | 2019-01-05 | 2019-01-06 | 2018-12-08 | 2018-12-10 | 2018-12-10 | Plot No?. ?E?-?14?,?Chakan Industrial ? Area Ph?-?Iii?, ?Village ?- ?Nighoje?, ? Taluka ?- ?Khed Pune ?410501? | 1 | 21 | 405 | Subhash Tapkir | - | subhash.tapkir@olcieng.co.in | AMIT KOKANE | - | amit.kokane@olcieng.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | WO Close | 2019-01-01 | 2018-12-31 | 1 |  | PADMASINHA JOSHI
615 | 2020-12-05 | 10:55:55 AM | sapl0313 | 1 | 6 | S008 | 644 | 642 | u3cG11901000001 | 35 | 0 | N0191 | 2019-01-02 | ADDLTIONAL WELDING FIXTURE DUE TO ECN | Sonali kadam | 3 | 2019-01-01 | 2019-01-01 | 2019-01-01 | 2019-01-01 | 2019-01-01 | 2019-01-01 | 2019-01-01 | 2019-01-01 | 2019-01-01 | 2019-01-01 | 2019-01-01 | 2019-01-01 | 2019-01-01 | 2019-01-01 | 2019-01-01 | 2019-01-01 | SHARADA INDUSTRIES F II Block Plot No. 30/10/2 pimpri industrial A. 411018 | 1 | 21 | 405 | Shivanand | 9552503533 | shivanand.pattan@sharadaindustries.com | Sd shinde | - | sbshinde@synergytechs.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | WO Close | 2019-01-01 | 2019-01-01 | 1 |  | Sonali kadam
616 | 2020-12-05 | 10:56:22 AM | sapl0313 | 1 | 6 | C019 | 643 | 641 | verbal638 | 35 | 0 | N0192 | 2019-01-07 | Common welding & fabrication fixtures sets | PADMASINHA JOSHI | 3 | 2019-01-01 | 2019-01-04 | 2019-01-04 | 2019-02-04 | 2019-01-07 | 2019-02-08 | 2019-02-08 | 2019-02-09 | 2019-02-08 | 2019-02-10 | 2019-02-11 | 2019-02-15 | 2019-02-08 | 2019-02-07 | 2019-02-11 | 2019-02-14 | CEPL H?/?INJEWADI? S NO?.?239?/?240? NEAR RAJIV GANDHI IT PARK?, ? TAL?- ?MULSHI?, ?HINJEWADI?, ?PUNE?.? 411057? | 1 | 21 | 405 | RAVINDRA CHAPHEKAR | 9518507008 | ravindra@chaphekarengg.com | Sd shinde | - | sbshinde@synergytechs.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | WO Close | 2019-02-04 | 2019-02-04 | 1 |  | PADMASINHA JOSHI
617 | 2020-12-05 | 10:56:43 AM | sapl0313 | 1 | 6 | S029 | 646 | 645 | 10097809 | 35 | 0 | N0193 | 2019-01-23 | Vibro Motors for Belt Samplers | Prashant Suryavanshi | 3 | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-01-23 | SGS India Private Limited No.23, Siva, Arcade, 29th Main, BTM 1st Stage Bangalore, Karnataka (29) Karnataka (29) 560068 India | 1 | 17 | 293 | SMITA HUMNE | - | smita.humne@sgs.com | sdshinde | - | sdshinde@synergytechs.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | WO Close | 2019-01-23 | 2019-01-23 | 1 |  | Prashant Suryavanshi
618 | 2020-12-05 | 10:57:07 AM | sapl0313 | 1 | 6 | S029 | 647 | 646 | 10098109 | 35 | 0 | N0194 | 2019-01-23 | Paint removing and repainting of Cross Belt Sampler | Prashant Suryavanshi | 3 | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-01-23 | SGS India Private Limited Ahmed Plaza, No.38/1 and 38/2, Beretena Agrahara,Begur Hobli, Hosur Main Road,Bangalore – 560 100, Karnataka(19) Karnataka (29) 560100 India | 1 | 17 | 293 | SMITA HUMNE | - | smita.humne@sgs.com | sdshinde | - | sdshinde@synergytechs.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | WO Close | 2019-01-23 | 2019-01-23 | 1 |  | Prashant Suryavanshi
619 | 2020-12-05 | 11:18:01 AM | sapl0313 | 1 | 6 | J009 | 648 | 647 | 1800040 | 34 | 0 | S0174 | 2019-01-24 | CROSS TROLLEY | Prashant Suryavanshi | 3 | 2019-01-24 | 2019-01-24 | 2019-01-24 | 2019-01-24 | 2019-01-24 | 2019-01-24 | 2019-01-24 | 2019-01-24 | 2019-01-25 | 2019-01-25 | 2019-01-24 | 2019-01-24 | 2019-01-24 | 2019-01-24 | 2019-01-24 | 2019-01-24 | Building No:6,Onsite Supplier Park,Plot No 1,Toyota Kirloskar Motors Pvt Ltd. Bidadi Industrial Area,Ramanagaram District,Bangalore-562109. | 1 | 17 | 293 | Aradhya T.C. | - | purchase.joai@jbmgroup.com | sdshinde | - | sdshinde@synergytechs.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | WO Close | 2019-01-24 | 2019-01-24 | 1 |  | Prashant Suryavanshi
620 | 2020-12-05 | 11:18:25 AM | sapl0313 | 1 | 6 | M001 | 650 | 648 | 3101474878 | 34 | 0 | S0175 | 2019-03-15 | - | - | 1 | 2019-03-15 | 2019-03-15 | 2019-03-15 | 2019-03-15 | 2019-03-15 | 2019-03-15 | 2019-03-15 | 2019-03-15 | 2019-03-15 | 2019-03-15 | 2019-03-15 | 2019-03-15 | 2019-03-15 | 2019-03-15 | 2019-03-15 | 2019-03-15 | TOOL & Die plant, 80, M.I.D.C. Satpur nashik | 1 | 21 | 402 | - | - | www.0000@gmail.com | - | - | www.0000@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 1 | WO Close | 2019-03-13 | 2019-03-14 | 1 |  | -
622 | 2019-12-29 | 5:18:54 PM | Sapl0002 | 1 | 6 | M001 | 651 | 649 | PO_3101479697 | 38 | 0 | J0112 | 2019-03-18 | W501 MB 20 UNITS | MR.PRASHANT SURYAWANSHI | 3 | 2019-03-18 | 2019-03-18 | 2019-03-18 | 2019-03-18 | 2019-03-20 | 2019-03-25 | 2019-03-25 | 2019-03-26 | 2019-03-27 | 2019-03-27 | 2019-03-26 | 2019-03-26 | 2019-03-30 | 2019-03-30 | 2019-03-31 | 2019-03-31 | PLANT - 2,80 - MIDC,Satpur, Nashik,Maharashtra, India. | 1 | 21 | 402 | Mr.udhav lokhande | - | LOKHANDE.UDHAV@mahindra.com | - | - | www.0000@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | complted | 2019-03-19 | 2019-03-22 | 1 |  | MR.PRASHANT SURYAWANSHI
623 | 2020-12-05 | 10:57:40 AM | sapl0313 | 1 | 6 | C015 | 652 | 650 | IND4418734 | 35 | 0 | N0195 | 2019-01-01 | tool assist | MR.PRASHANT SURYAWANSHI | 1 | 2019-03-31 | 2019-03-31 | 2019-03-31 | 2019-03-31 | 2019-03-31 | 2019-03-31 | 2019-03-31 | 2019-03-31 | 2019-03-31 | 2019-03-31 | 2019-03-31 | 2019-03-31 | 2019-03-31 | 2019-03-31 | 2019-03-31 | 2019-03-31 | C/O Cummins Technologies India Pvt.Ltd. Phaltan High Horsepower plant, village nandal-surwadi, taluka-phaltan | 1 | 21 | 409 | Mr.mahesh jedhe | 7720043716 | www.0000@gmail.com | - | - | www.0000@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | WO Close | 2018-12-19 | 2019-02-14 | 1 |  | MR.PRASHANT SURYAWANSHI
624 | 2020-12-05 | 10:58:02 AM | sapl0313 | 1 | 6 | C015 | 652 | 650 | IND4418734 | 35 | 0 | N0196 | 2019-03-31 | tool assist | MR.PRASHANT SURYAWANSHI | 1 | 2019-03-29 | 2019-03-29 | 2019-03-29 | 2019-03-29 | 2019-03-29 | 2019-03-29 | 2019-03-29 | 2019-03-29 | 2019-03-29 | 2019-03-29 | 2019-03-29 | 2019-03-29 | 2019-03-29 | 2019-03-29 | 2019-03-29 | 2019-03-29 | C/O Cummins technologies India pvt.ltd Village nandal-surwadi taluka phaltan | 1 | 21 | 409 | Mr.mahesh jedhe | 7720043716 | www.0000@gmail.com | - | - | www.0000@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | WO Close | 2018-12-14 | 2018-12-29 | 1 |  | MR.PRASHANT SURYAWANSHI
625 | 2020-12-05 | 10:58:26 AM | sapl0313 | 1 | 7 | S011 | 653 | 651 | PUOR18004387 | 35 | 0 | N0197 | 2019-04-02 | BREAK COIL | MR.PRASHANT SURYAWANSHI | 1 | 2019-03-02 | 2019-03-02 | 2019-04-12 | 2019-04-12 | 2019-04-12 | 2019-04-12 | 2019-04-12 | 2019-04-12 | 2019-04-12 | 2019-04-12 | 2019-04-12 | 2019-04-12 | 2019-04-12 | 2019-04-12 | 2019-04-12 | 2019-04-12 | 690?, ?Udyambag?,?Industrial Estate?,? Belgaum?, ?Karnataka?, ?India ?- -.? | 1 | 17 | 295 | Mr.shantilal V Porwal | - | svp@shantiiron.net | - | - | www.0000@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | WO Close | 2019-03-15 | 2019-03-30 | 1 |  | MR.PRASHANT SURYAWANSHI
626 | 2020-12-05 | 10:58:50 AM | sapl0313 | 1 | 7 | A013 | 654 | 652 | 4100005381 | 35 | 0 | N0198 | 2019-02-13 | BREAK COIL | MR.PRASHANT SURYAWANSHI | 1 | 2019-02-13 | 2019-04-12 | 2019-04-12 | 2019-04-12 | 2019-04-12 | 2019-04-12 | 2019-04-12 | 2019-04-12 | 2019-04-12 | 2019-04-12 | 2019-04-12 | 2019-04-12 | 2019-04-12 | 2019-04-12 | 2019-04-12 | 2019-04-12 | Plot No?.?A?-?1?/?3?,?Mvml Supplier Park?,?Phase?-?Iv?,?Village?-?Nigoje?,?Midc?-?Chakan? Pune?, ?Maharashtra?, ?India ?- ?413 105?.? | 1 | 21 | 405 | Mr.Arun Patil | - | arunpatil@alfengineering.com | - | - | www.0000@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | WO Close | 2019-02-14 | 2019-03-20 | 1 |  | MR.PRASHANT SURYAWANSHI
627 | 2020-12-05 | 11:18:53 AM | sapl0313 | 1 | 7 | T016 | 655 | 653 | SME-0087/18-19 | 34 | 0 | S0176 | 2019-04-19 | slido rail | MR.PRASHANT SURYAWANSHI | 1 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | S.No. 78/1, Shivane Industrial Area, NDA Road, Near Hindustan Bekry, Shivane, Pune-411023 Mr Pankaj Jadhav (9160688340) | 1 | 21 | 405 | Mr Pankaj Jadhav | - | www@0000.com | - | - | www@0000.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | WO Close | 2019-03-01 | 2019-03-31 | 1 |  | MR.PRASHANT SURYAWANSHI
628 | 2020-12-05 | 11:19:17 AM | sapl0313 | 1 | 7 | T016 | 655 | 654 | 0008/1803/18-19 | 34 | 0 | S0177 | 2019-04-19 | slido rail | MR.PRASHANT SURYAWANSHI | 1 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | S.No. 78/1, Shivane Industrial Area, NDA Road, Near Hindustan Bekry, Shivane, Pune-411023 | 1 | 21 | 405 | Mr Pankaj Jadhav | - | www@0000.com | - | - | www@0000.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | WO Close | 2019-03-14 | 2019-04-01 | 1 |  | MR.PRASHANT SURYAWANSHI
630 | 2020-12-05 | 11:14:48 AM | sapl0313 | 1 | 7 | C004 | 657 | 656 | IND6050005 | 37 | 0 | P0056 | 2019-05-06 | SWING CLAMP | MR.PRASHANT SURYAWANSHI | 1 | 2019-01-30 | 2019-02-20 | 2019-05-06 | 2019-05-06 | 2019-05-06 | 2019-05-06 | 2019-05-06 | 2019-05-06 | 2019-05-06 | 2019-05-06 | 2019-05-06 | 2019-05-06 | 2019-05-06 | 2019-05-06 | 2019-05-06 | 2019-05-06 | kothrud | 1 | 21 | 405 | Mr.Milind Bhagwat | - | www.0000@gmail.com | - | - | www.0000@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | WO Close | 2019-02-05 | 2019-02-25 | 1 |  | MR.PRASHANT SURYAWANSHI
631 | 2020-12-05 | 10:59:15 AM | sapl0313 | 1 | 7 | C015 | 658 | 657 | IND6157276 | 35 | 0 | N0199 | 2019-05-06 | Rails | MR.PRASHANT SURYAWANSHI | 1 | 2019-05-03 | 2019-05-03 | 2019-05-03 | 2019-05-03 | 2019-05-03 | 2019-05-03 | 2019-05-03 | 2019-05-03 | 2019-05-03 | 2019-05-03 | 2019-05-03 | 2019-05-03 | 2019-05-03 | 2019-05-03 | 2019-05-03 | 2019-05-03 | SEZ Unit:Plot No. B3/1, PHP/IEBU (MEGASITE Phaltan),Village Surwadi Nandal-, Taluka Phaltan,, Satara,Maharashtra, | 1 | 21 | 409 | Miss.Shweta Nagarale | - | www.0000@gmail.com | - | - | www.0000@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | WO Close | 2019-05-03 | 2019-05-03 | 1 |  | MR.PRASHANT SURYAWANSHI
632 | 2020-12-05 | 11:20:15 AM | sapl0313 | 1 | 7 | T016 | 659 | 658 | 0005/1902/19-20Rev1 | 34 | 0 | S0179 | 2019-05-03 | Rails | MR.PRASHANT SURYAWANSHI | 1 | 2019-05-01 | 2019-05-01 | 2019-05-01 | 2019-05-01 | 2019-05-01 | 2019-05-01 | 2019-05-01 | 2019-05-01 | 2019-05-01 | 2019-05-01 | 2019-05-01 | 2019-05-01 | 2019-05-01 | 2019-05-01 | 2019-05-01 | 2019-05-01 | 78?, ?Shivane Industrial Area?, ?Shivane?,?Off Nda Road?, ?Pune ? -?411023?,? Pune?, ?Maharashtra | 1 | 21 | 405 | Mr.pankaj jadhav | 9160688340 | www.0000@gmail.com | - | - | www.0000@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | WO Close | 2019-04-30 | 2019-04-30 | 1 |  | MR.PRASHANT SURYAWANSHI
634 | 2019-12-29 | 5:19:15 PM | Sapl0002 | 1 | 7 | C004 | 661 | 660 | IND6170666 | 38 | 0 | J0113 | 2019-05-21 | service support TOD reinstallationfrom OEM-Synergytech | MR.PRASHANT SURYAWANSHI | 1 | 2019-05-21 | 2019-05-21 | 2019-05-21 | 2019-05-21 | 2019-05-21 | 2019-05-21 | 2019-05-21 | 2019-05-21 | 2019-05-21 | 2019-05-21 | 2019-05-21 | 2019-05-21 | 2019-05-21 | 2019-05-21 | 2019-05-21 | 2019-05-21 | kothrud | 1 | 21 | 405 | Mr.Milind Bhagwat | - | www.0000@gmail.com | - | - | www.0000@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | COMPLETED | 2019-05-21 | 2019-05-21 | 1 |  | MR.PRASHANT SURYAWANSHI
635 | 2019-12-29 | 5:19:48 PM | Sapl0002 | 1 | 7 | C004 | 662 | 661 | IND6173672 | 38 | 0 | J0114 | 2019-05-23 | service support TOD reinstallationfrom OEM-Synergytech | MR.PRASHANT SURYAWANSHI | 1 | 2019-05-23 | 2019-05-23 | 2019-05-23 | 2019-05-23 | 2019-05-23 | 2019-05-23 | 2019-05-23 | 2019-05-23 | 2019-05-23 | 2019-05-23 | 2019-05-23 | 2019-05-23 | 2019-05-23 | 2019-05-23 | 2019-05-23 | 2019-05-23 | kothrud | 1 | 21 | 405 | Mr.Milind Bhagwat | - | milind.v.bhagwat@cummins.com | - | - | www.0000@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | COMPLETED | 2019-05-23 | 2019-05-23 | 1 |  | MR.PRASHANT SURYAWANSHI
636 | 2019-12-29 | 5:20:10 PM | Sapl0002 | 1 | 7 | O002 | 664 | 664 | Verbal664 | 38 | 0 | J0115 | 2019-06-08 | Weld Structure | Mr. Pravin Choughule | 5 | 2019-06-08 | 2019-06-08 | 2019-06-08 | 2019-06-08 | 2019-06-08 | 2019-06-22 | 2019-06-22 | 2019-06-24 | 2019-06-28 | 2019-06-28 | 2019-06-28 | 2019-06-28 | 2019-06-22 | 2019-06-28 | 2019-06-27 | 2019-06-27 | Plot No?. ?E?-?14?,?Chakan Industrial ? Area Ph?-?Iii?, ?Village ?- ?Nighoje?, ? Taluka ?- ?Khed Pune ?410501? | 1 | 21 | 405 | Subhash Tapkir | 8007020509 | subhash.tapkir@olcieng.co.in | AMIT KOKANE | - | amit.kokane@olcieng.co.in | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | COMPLETED | 2019-06-14 | 2019-06-15 | 1 |  | Mr. Pravin Choughule
637 | 2020-12-05 | 11:00:05 AM | sapl0313 | 1 | 7 | A013 | 663 | 662 | 4100007316 | 35 | 0 | N0201 | 2019-06-08 | BREAK COIL | MR.PRASHANT SURYAWANSHI | 1 | 2019-06-08 | 2019-06-08 | 2019-06-08 | 2019-06-08 | 2019-06-08 | 2019-06-08 | 2019-06-08 | 2019-06-08 | 2019-06-08 | 2019-06-08 | 2019-06-08 | 2019-06-08 | 2019-06-08 | 2019-06-08 | 2019-06-08 | 2019-06-08 | ALF Engineering Pvt Ltd, Chakan Plot No-A-1/3,MVML Supplier Park, Phase-IV,Vil | 1 | 21 | 405 | Mayur Deshpande | - | mayurdeshpande@alfengineering.com | - | - | www.0000@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | WO Close | 2019-06-08 | 2019-06-08 | 1 |  | MR.PRASHANT SURYAWANSHI
674 | 2020-12-05 | 11:10:29 AM | sapl0313 | 1 | 7 | N002 | 703 | 705 | DummyWO0218 | 35 | 0 | N0220 | 2020-03-08 | FES BS6 Maunal Welding Fixtures | Mr. Aniruddha Raut | 3 | 2020-03-01 | 2020-03-07 | 2020-03-01 | 2020-03-07 | 2020-03-02 | 2020-03-24 | 2020-03-20 | 2020-03-28 | 2020-03-28 | 2020-04-01 | 2020-04-06 | 2020-04-13 | 2020-04-10 | 2020-04-20 | 2020-04-20 | 2020-04-25 | Neel Metal Products Limited, PLOT No.22 & Plot No.1A,Sector 12,ITBT Park,IIE,SIDCUL,263153, - Pantnagar | 1 | 34 | 679 | - | - | rahul.mishra@jbmgroup.com | - | - | rahul.mishra@jbmgroup.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | WO Close | 2020-03-24 | 2020-03-20 | 1 |  | Mr. Aniruddha Raut
675 | 2021-06-09 | 10:24:17 AM | Sapl0331 | 1 | 7 | P013 | 704 | 706 | DummyWO0219 | 35 | 0 | N0221 | 2020-03-08 | FES BS6 Maunal Welding Fixtures | Mr. Aniruddha Raut | 3 | 2020-03-02 | 2020-03-14 | 2020-03-07 | 2020-03-14 | 2020-03-03 | 2020-03-24 | 2020-03-20 | 2020-03-28 | 2020-03-28 | 2020-03-31 | 2020-04-07 | 2020-04-11 | 2020-04-10 | 2020-04-21 | 2020-04-21 | 2020-04-25 | Sipcot-1, B12A & B14, Sidco Industrial Estate, Hosur 635 126 Tamil Nadu India 04344 - 279848, 276001 prabhaengineers@eth.net | 1 | 31 | 680 | - | - | anandraj@prabhaengineers.com | - | - | senthil.s@prabhaengineers.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | DONE WITH PO | 2020-03-24 | 2020-03-15 | 1 |  | Mr. Aniruddha Raut
677 | 2020-12-05 | 11:11:13 AM | sapl0313 | 1 | 7 | N002 | 706 | 708 | TPL_Neel_Prabha | 35 | 0 | N0222 | 2020-03-14 | TPL for FES BS6 Maunal Welding Fixtures | Mr. Aniruddha Raut | 3 | 2020-03-14 | 2020-03-15 | 2020-03-15 | 2020-03-15 | 2020-03-16 | 2020-03-29 | 2020-03-25 | 2020-03-29 | 2020-03-29 | 2020-03-31 | 2020-04-06 | 2020-04-20 | 2020-03-25 | 2020-04-18 | 2020-04-20 | 2020-04-27 | Neel Metal & Prabha Automotive | 1 | 34 | 679 | Mr Anand Raj | - | anandraj@prabhaengineers.com | Mr Rahul Mishra | - | rahul.mishra@jbmgroup.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 1 |  | 1 | WO Close | 2020-03-25 | 2020-03-20 | 1 |  | Mr. Aniruddha Raut
678 | 2020-12-05 | 11:11:37 AM | sapl0313 | 1 | 7 | N002 | 707 | 709 | TPL_Neel_Prabha | 35 | 0 | N0223 | 2020-03-14 | FES BS6 Maunal Welding Fixtures | Mr. Aniruddha Raut | 3 | 2020-03-14 | 2020-03-21 | 2020-03-14 | 2020-03-21 | 2020-03-14 | 2020-03-25 | 2020-03-26 | 2020-03-30 | 2020-03-28 | 2020-03-31 | 2020-04-06 | 2020-04-11 | 2020-03-26 | 2020-04-23 | 2020-04-23 | 2020-04-25 | Neel Prabha | 1 | 34 | 679 | Mr Anand Raj | - | anandraj@prabhaengineers.com | Mr Rahul Mishra | - | rahul.mishra@jbmgroup.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 1 |  | 1 | WO Close | 2020-03-25 | 2020-03-20 | 1 |  | Mr. Aniruddha Raut
679 | 2020-12-05 | 11:12:02 AM | sapl0313 | 1 | 7 | N002 | 708 | 710 | TPL_Neel_Prabha | 35 | 0 | N0224 | 2020-03-16 | FES BS6 Maunal Welding Fixtures | Mr. Aniruddha Raut | 3 | 2020-03-16 | 2020-03-28 | 2020-03-16 | 2020-03-28 | 2020-03-16 | 2020-03-28 | 2020-03-16 | 2020-03-28 | 2020-03-16 | 2020-03-28 | 2020-03-16 | 2020-03-28 | 2020-03-16 | 2020-03-28 | 2020-03-16 | 2020-03-28 | Neel Metal, Prabha Auto | 1 | 34 | 679 | Mr Anand Raj | - | anandraj@prabhaengineers.com | Mr Rahul Mishra | - | rahul.mishra@jbmgroup.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 1 |  | 1 | WO Close | 2020-03-20 | 2020-03-20 | 1 |  | Mr. Aniruddha Raut
680 | 2020-12-05 | 11:12:23 AM | sapl0313 | 1 | 7 | N002 | 709 | 711 | TPL_Neel_Prabha | 35 | 0 | N0225 | 2020-03-16 | FES BS6 Maunal Welding Fixtures | Mr. Aniruddha Raut | 3 | 2020-03-16 | 2020-03-28 | 2020-03-16 | 2020-03-28 | 2020-03-16 | 2020-03-28 | 2020-03-16 | 2020-03-28 | 2020-03-16 | 2020-03-28 | 2020-03-16 | 2020-03-28 | 2020-03-16 | 2020-03-28 | 2020-03-16 | 2020-03-28 | Neel Metal, Prabha Auto | 1 | 34 | 679 | Mr Anand Raj | - | anandraj@prabhaengineers.com | Mr Rahul Mishra | - | rahul.mishra@jbmgroup.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | WO Close | 2020-03-28 | 2020-03-20 | 1 |  | Mr. Aniruddha Raut
719 | 2021-08-24 | 10:54:42 AM | Sapl0334 | 1 | 8 | G016 | 748 | 751 | Verble NMC15022021 | 35 | 0 | N0234 | 2021-02-15 | Gloria Structure | Mahesh Durgale | 5 | 2021-02-15 | 2021-02-15 | 2021-02-15 | 2021-02-15 | 2021-02-16 | 2021-02-19 | 2021-02-18 | 2021-02-19 | 2021-02-20 | 2021-02-21 | 2021-02-19 | 2021-02-20 | 2021-02-21 | 2021-02-22 | 2021-02-20 | 2021-02-20 | Gat No?.?1326?, ?Shelarwasti?,?Dehu Alandi Road?.? Pune?, ?Maharashtra?, ?India ?- ?412 114?.? | 1 | 21 | 405 | S.K.Kadam | - | purchase@gloriagroup.co.in | - | - | purchase@gloriagroup.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 1 | COMPLETED | 2021-02-16 | 2021-02-18 | 1 |  | Mahesh Durgale
720 | 2021-08-24 | 11:01:23 AM | Sapl0334 | 1 | 8 | T018 | 749 | 752 | 272054 | 38 | 0 | J0138 | 2021-02-13 | Tube Stand 1300LG*850HT | Mahesh Durgale | 5 | 2021-02-10 | 2021-02-11 | 2021-02-11 | 2021-02-11 | 2021-02-13 | 2021-02-20 | 2021-02-20 | 2021-02-20 | 2021-02-21 | 2021-02-22 | 2021-02-20 | 2021-02-21 | 2021-02-20 | 2021-02-23 | 2021-02-20 | 2021-02-20 | Gat no ?3?(?part?)?, ?243?(?part?)?, ?5?(?part?)?, ?Kasurdi ?(?Kheba?)? Tal?: ?Bhor Dist?: ?Pune PIN?: ?412205 ?Ph?: ?02113 305 ? 222?/?38?/?48? 222/?38/48 | 1 | 21 | 405 | Sandesh Udhane | 9999999999 | purchasem@tepl.co.in | - | - | purchasem@tepl.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2021-02-13 | 2021-02-15 | 1 |  | Mahesh Durgale
726 | 2022-02-11 | 10:29:12 AM | Sapl0335 | 1 | 8 | G016 | 756 | 758 | GP/20 21/22-IV | 35 | 0 | N0235 | 2021-03-10 | Material Handling System? Complete structure with railing system and Electric hoist?.? | Mahesh Durgale | 5 | 2021-03-08 | 2021-03-09 | 2021-03-08 | 2021-03-09 | 2021-03-10 | 2021-03-15 | 2021-03-15 | 2021-03-16 | 2021-03-16 | 2021-03-17 | 2021-03-16 | 2021-03-16 | 2021-03-18 | 2021-03-19 | 2021-03-15 | 2021-03-16 | Gat No?.?1326?, ?Shelarwasti?,?Dehu ? Alandi Road?.? | 1 | 21 | 405 | S.K.Kadam | - | purchase@gloriagroup.co.in | - | - | purchase@gloriagroup.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | - | 2021-03-10 | 2021-03-10 | 1 |  | Mahesh Durgale
727 | 2021-08-24 | 10:43:05 AM | Sapl0334 | 1 | 8 | C020 | 757 | 759 | IND6709125 | 36 | 0 | E0048 | 2021-03-10 | Temperature boom installation | Vinod Kumar | 22 | 2021-03-02 | 2021-03-04 | 2021-03-04 | 2021-03-05 | 2021-03-05 | 2021-03-09 | 2021-03-09 | 2021-03-09 | 2021-03-10 | 2021-03-10 | 2021-03-09 | 2021-03-10 | 2021-03-10 | 2021-03-13 | 2021-03-09 | 2021-03-10 | CTCI Kothrud | 1 | 21 | 405 | Rashmi Naik | 8669998744 | rashmi.naik@cummins.com | - | - | rashmi.naik@cummins.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2021-03-02 | 2021-03-03 | 1 |  | Vinod Kumar
780 | 2022-09-29 | 11:11:05 AM | Sapl0335 | 1 | 9 | G020 | 801 | 815 | 5804019559 | 34 | 0 | S0204 | 2022-03-20 | New supply of pallets | Mr Mayur | 2 | 2022-03-20 | 2022-03-20 | 2022-03-20 | 2022-03-21 | 2022-03-20 | 2022-03-24 | 2022-03-24 | 2022-03-26 | 2022-03-23 | 2022-03-27 | 2022-03-26 | 2022-03-28 | 2022-03-28 | 2022-03-30 | 2022-03-30 | 2022-03-31 | E?1 ?(?Part?)?,?Chakan Midc Road?, ?Phase?-?Iii?,?Kharabwadi?, ?Chakan?, ?Talegaon Chakan Road?, ?Mahalunge ? Ingale?, ?Maharashtra? Pune?, ?Maharashtra?, ?India ?- ?410501? | 1 | 21 | 405 | sunil kokate | 9090909090 | xyz@gmail.com | - | - | a@a.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | Dispatch completed | 2022-03-20 | 2022-03-20 | 1 |  | Mr Mayur
538 | 2022-07-18 | 4:06:09 PM | sapl0001 | 1 | 5 | C004 | 549 | 560 | IND3932559 | 35 | 0 | N0166 | 2017-07-03 | SCISSOR LIFT & PLATFORM | Akshay bhojkar | 2 | 2017-07-03 | 2018-04-30 | 2017-07-15 | 2018-04-30 | 2017-07-26 | 2017-08-12 | 2017-08-24 | 2017-08-26 | 2017-08-26 | 2017-08-29 | 2017-08-12 | 2017-08-24 | 2017-08-24 | 2017-09-02 | 2017-08-26 | 2017-08-29 | CUMMINS, KOTHRUD | 1 | 21 | 405 | Milind Bhagwat | - | milind.v.bhagwat@cummins.com | Milind Bhagwat | - | milind.v.bhagwat@cummins.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 | - | 2017-07-20 | 2017-07-20 | 1 |  | Akshay bhojkar
555 | 2022-07-18 | 2:20:58 PM | Sapl0335 | 1 | 5 | C015 | 566 | 577 | IND4092465 | 35 | 0 | N0177 | 2017-12-09 | Pillar mounted 500 kg Jib crane with electrical hoist | Akshay bhojkar | 2 | 2017-12-09 | 2018-02-10 | 2017-12-16 | 2018-02-10 | 2017-12-20 | 2017-12-23 | 2017-12-26 | 2017-12-28 | 2017-12-29 | 2017-12-29 | 2017-12-24 | 2017-12-26 | 2017-12-26 | 2018-01-03 | 2017-12-26 | 2017-12-28 | Cummins Technologies India Pvt. Ltd.: Phaltan High Horsepower Plant, SEZ Unit: Plot No. B3/1, MIDC SEZ-Phaltan, Village Nandal-Surwadi, Taluka Phaltan, Dist. Sata | 1 | 21 | 409 | priya.srivastava | 9130083734 | priya.srivastava@cummins.com | rajesh.m.sangar | - | rajesh.m.sangar@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 1 | 1 |  | 0 | for design verification | 2017-12-20 | 2017-12-20 | 1 |  | Akshay bhojkar
718 | 2021-02-12 | 11:21:50 AM | Sapl0334 | 1 | 8 | F008 | 747 | 750 | Verbal NMC | 35 | 0 | N0233 | 2021-02-12 | Storage Trolley | Mahesh Durgale | 1 | 2021-02-18 | 2021-02-22 | 2021-02-14 | 2021-02-28 | 2021-03-03 | 2021-03-20 | 2021-03-20 | 2021-03-21 | 2021-03-27 | 2021-03-28 | 2021-03-10 | 2021-03-23 | 2021-03-20 | 2021-04-07 | 2021-03-10 | 2021-03-20 | Gat No 54, Pune Nashik Highway, Kuruli, behind Hotel Sai Sagar, Chakan, Maharashtra 410501 | 1 | 21 | 405 | - | - | a@a.com | - | - | a@a.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2021-03-01 | 2021-03-01 | 1 |  | Mahesh Durgale
729 | 2021-03-31 | 1:46:47 PM | Sapl0334 | 1 | 8 | J019 | 759 | 761 | Verbal_NMC_31/03/2021 | 35 | 0 | N0237 | 2021-03-31 | Riveting trunnion Fixture | Mahesh Durgale | 5 | 2021-03-30 | 2021-03-31 | 2021-03-30 | 2021-03-31 | 2021-04-01 | 2021-04-02 | 2021-04-02 | 2021-04-02 | 2021-04-03 | 2021-04-03 | 2021-04-02 | 2021-04-02 | 2021-04-04 | 2021-04-04 | 2021-04-02 | 2021-04-02 | Plot No?.?55?, ?Gat No?. ?444?/?2 ? Success Industrial Park?, ? Opposite Mahindra ?& ?Mahindra ? Vehicle Gate No?. ?8?, ?Nighoje?, ? Chakan ?- ?410501? | 1 | 21 | 405 | - | - | a@a.com | - | - | a@a.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2021-04-01 | 2021-04-01 | 1 |  | Mahesh Durgale
730 | 2022-01-28 | 4:45:59 PM | sapl0001 | 1 | 8 | G020 | 760 | 762 | Verble | 38 | 0 | J0143 | 2021-04-07 | Pallet madification | Mahesh Durgale | 5 | 2021-04-03 | 2021-04-04 | 2021-04-04 | 2021-04-06 | 2021-04-07 | 2021-04-12 | 2021-04-12 | 2021-04-13 | 2021-04-13 | 2021-04-14 | 2021-04-12 | 2021-04-12 | 2021-04-14 | 2021-04-14 | 2021-04-11 | 2021-04-12 | E1 (Part),Chakan MIDC Road, Phase-III,Kharabwadi, Chakan, Talegaon Chakan Road, Mahalunge Ingale, Maharashtra, Pune, Maharashtra, India. | 1 | 21 | 405 | - | - | gaipl@in.gestamp.com | - | - | gaipl@in.gestamp.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 0 | For PO Purpose | 2021-04-07 | 2021-04-07 | 1 |  | Mahesh Durgale
731 | 2021-03-31 | 1:58:08 PM | Sapl0334 | 1 | 8 | G016 | 761 | 763 | Verble_NMC_09.04.2021 | 43 | 0 | T0036 | 2021-04-09 | Linear Welding SPM | Mahesh Durgale | 22 | 2021-03-27 | 2021-03-31 | 2021-03-30 | 2021-04-06 | 2021-04-08 | 2021-04-15 | 2021-04-16 | 2021-04-20 | 2021-04-20 | 2021-04-21 | 2021-04-18 | 2021-04-19 | 2021-04-22 | 2021-04-22 | 2021-04-21 | 2021-04-21 | GAT NO.1326, SHELARWASTI,DEHU ALANDI ROAD029624. | 1 | 21 | 405 | SUNIL PAWAR | 7757029624 | Sunil.pawar@gloria.com | - | - | Sunil.pawar@gloria.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2021-04-09 | 2021-04-09 | 1 |  | Mahesh Durgale
734 | 2021-04-12 | 11:18:48 AM | Sapl0334 | 1 | 8 | G020 | 764 | 768 | 5804019016 | 38 | 0 | J0144 | 2021-05-14 | Supply of Pallets | Vinod Kumar | 5 | 2021-04-24 | 2021-04-25 | 2021-04-25 | 2021-04-27 | 2021-04-28 | 2021-05-25 | 2021-05-10 | 2021-05-25 | 2021-05-10 | 2021-05-30 | 2021-05-08 | 2021-05-25 | 2021-05-28 | 2021-05-30 | 2021-05-08 | 2021-05-25 | E1 (Part),Chakan MIDC Road, Phase-III,Kharabwadi, Chakan, Talegaon Chakan Road, Mahalunge Ingale, Maharashtra | 1 | 21 | 405 | Mr. Sunil Kokate | +91-9673334857 | gaipl@in.gestamp.com | - | - | gaipl@in.gestamp.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2021-04-28 | 2021-04-29 | 1 |  | Vinod Kumar
735 | 2021-04-30 | 5:00:51 PM | Sapl0334 | 1 | 8 | C004 | 765 | 769 | IND6753931 | 34 | 0 | S0194 | 2021-04-30 | Baterry Operated Rail Guided Vehicle | Mahesh Durgale | 5 | 2021-04-30 | 2021-05-02 | 2021-05-03 | 2021-05-04 | 2021-05-05 | 2021-05-20 | 2021-05-21 | 2021-05-26 | 2021-05-26 | 2021-05-27 | 2021-05-21 | 2021-05-25 | 2021-05-28 | 2021-06-01 | 2021-05-23 | 2021-05-25 | Cummins India Limited, Kothrud | 1 | 21 | 405 | Anita Sharma | - | KD238@cummins.com | - | - | KD238@cummins.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2021-05-03 | 2021-05-03 | 1 |  | Mahesh Durgale
738 | 2021-06-11 | 5:21:03 PM | Sapl0334 | 1 | 9 | F009 | 767 | 772 | 4300049968 | 34 | 0 | S0195 | 2021-06-11 | I- BEAM STRUCTURE AND RAIL | Vinod Kumar | 5 | 2021-06-13 | 2021-06-14 | 2021-06-13 | 2021-06-16 | 2021-06-17 | 2021-06-19 | 2021-06-19 | 2021-06-21 | 2021-06-22 | 2021-06-24 | 2021-06-24 | 2021-06-28 | 2021-06-28 | 2021-06-30 | 2021-07-01 | 2021-07-02 | FJM Cylinder pvt ltd Opp-24 Milestone SH-7 vithalapur Taluka-mandal ahmedabad | 1 | 12 | 142 | - | - | a@a.com | - | - | a@a.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2021-06-12 | 2021-06-12 | 1 |  | Vinod Kumar
745 | 2021-08-20 | 4:42:32 PM | sapl0003 | 1 | 9 | G018 | 771 | 782 | GME/SGS/2021/ VEDANTACPP/ ORDER/4840/06 | 37 | 0 | P0067 | 2021-08-20 | - | - | 1 | 2021-06-16 | 2021-07-01 | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-08-20 | - | 1 | 26 | 460 | - | - | www@ca.com | - | - | www@ca.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 0 |  | 0 |  | 2021-07-28 | 2021-07-28 | 1 |  | -
746 | 2021-08-20 | 4:58:07 PM | sapl0003 | 1 | 9 | G018 | 771 | 783 | GME/SGS/2021/ VEDANTACPP/ ORDER/4841/07 | 37 | 0 | P0068 | 2021-07-26 | - | - | 1 | 2021-07-26 | 2021-08-01 | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-08-20 | - | 1 | 26 | 460 | - | - | www@ca.com | - | - | www@ca.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 0 |  | 0 |  | 2021-07-30 | 2021-08-01 | 1 |  | -
748 | 2021-08-21 | 5:23:29 PM | sapl0003 | 1 | 9 | G018 | 773 | 785 | GME/SGS/2021/06 | 37 | 0 | P0069 | 2021-07-28 | auger spares | - | 1 | 2021-07-26 | 2021-08-03 | 2021-08-21 | 2021-08-21 | 2021-08-21 | 2021-08-21 | 2021-08-21 | 2021-08-21 | 2021-08-21 | 2021-08-21 | 2021-08-21 | 2021-08-21 | 2021-08-21 | 2021-08-21 | 2021-08-21 | 2021-08-21 | - | 1 | 26 | 460 | - | - | www@ca.com | - | - | www@ca.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 0 |  | 0 |  | 2021-08-21 | 2021-08-21 | 1 |  | -
760 | 2021-10-10 | 3:08:31 PM | sapl0003 | 1 | 9 | S035 | 783 | 796 | Verbal 6.10.2021 | 37 | 0 | P0072 | 2021-10-06 | - | - | 1 | 2021-10-04 | 2021-10-06 | 2021-10-04 | 2021-10-06 | 2021-10-04 | 2021-10-06 | 2021-10-04 | 2021-10-06 | 2021-10-04 | 2021-10-06 | 2021-10-04 | 2021-10-06 | 2021-10-04 | 2021-10-06 | 2021-10-04 | 2021-10-06 | - | 1 | 21 | 405 | - | - | xyz@gmail.com | - | - | xyz@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 0 |  | 0 |  | 2021-10-04 | 2021-10-04 | 1 |  | -
765 | 2021-11-24 | 9:34:49 AM | sapl0003 | 1 | 9 | S035 | 788 | 801 | Verbal 23.11.2021 | 37 | 0 | P0073 | 2021-11-10 | Auger Parts | - | 1 | 2021-11-17 | 2021-11-19 | 2021-11-18 | 2021-11-19 | 2021-11-19 | 2021-11-19 | 2021-11-19 | 2021-11-20 | 2021-11-22 | 2021-11-22 | 2021-11-10 | 2021-11-12 | 2021-11-21 | 2021-11-21 | 2021-11-22 | 2021-11-22 | - | 1 | 21 | 405 | - | - | www@ps.com | - | - | www@ps.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 0 |  | 0 |  | 2021-11-03 | 2021-11-05 | 1 |  | -
772 | 2022-02-11 | 11:09:14 AM | Sapl0335 | 1 | 9 | N003 | 794 | 808 | 4500464525 | 37 | 0 | P0074 | 2022-02-11 | Gun rail spare part | vinodkumar | 5 | 2022-02-11 | 2022-02-12 | 2022-02-12 | 2022-02-13 | 2022-02-13 | 2022-02-16 | 2022-02-16 | 2022-02-17 | 2022-02-18 | 2022-02-19 | 2022-02-20 | 2022-02-22 | 2022-02-22 | 2022-02-25 | 2022-02-25 | 2022-02-26 | Neel Metal Products Limited?,? Plot No?.-?1?,?2?,?5?&?6?,?TVS Industrial ? Estate?,?Harita?,,?635109?,?Hosur? | 1 | 31 | 680 | MR. N.SATISH | 8220007523 | sathish.narashiman@jbm-group.com | - | - | a@a.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2022-02-14 | 2022-02-16 | 1 |  | vinodkumar
773 | 2022-02-11 | 11:18:14 AM | Sapl0335 | 1 | 9 | N003 | 793 | 807 | 4300053631 | 37 | 0 | P0075 | 2022-02-11 | Gun rail spare part | vinodkumar | 5 | 2022-02-11 | 2022-02-12 | 2022-02-12 | 2022-02-13 | 2022-02-14 | 2022-02-17 | 2022-02-17 | 2022-02-18 | 2022-02-18 | 2022-02-20 | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-25 | 2022-02-25 | 2022-02-26 | Neel Metal Products Limited?,? Plot No?.-?1?,?2?,?5?&?6?,?TVS Industrial ? Estate?,?Harita?,,?635109?,?Hosur? | 1 | 31 | 680 | MR. N.SATISH | 8220007523 | sathish.narashiman@jbm-group.com | - | - | a@a.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2022-02-13 | 2022-02-14 | 1 |  | vinodkumar
774 | 2022-02-20 | 5:29:11 PM | Sapl0335 | 1 | 9 | S036 | 795 | 809 | Verbal_DNS_20-feb-22 | 44 | 0 | A0001 | 2022-02-20 | Agriculture product | Supriya acharya | 22 | 2022-02-20 | 2022-02-21 | 2022-02-21 | 2022-02-22 | 2022-02-24 | 2022-02-27 | 2022-03-01 | 2022-03-03 | 2022-03-04 | 2022-02-16 | 2022-03-25 | 2022-03-31 | 2022-03-31 | 2022-03-31 | 2022-03-31 | 2022-03-31 | Synergytech automation pvt ltd pune kasudi | 1 | 21 | 405 | vinodkumar | 9156465854 | vinodkumar.kadepure@synergytechs.com | - | - | a@a.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2022-02-23 | 2022-02-25 | 1 |  | Supriya acharya
775 | 2022-02-25 | 11:58:41 AM | Sapl0335 | 1 | 9 | A013 | 796 | 810 | 4100026760 | 37 | 0 | P0076 | 2022-02-25 | Sapre parts | vinodkumar | 23 | 2022-02-25 | 2022-02-25 | 2022-02-25 | 2022-02-26 | 2022-02-25 | 2022-02-25 | 2022-02-25 | 2022-02-26 | 2022-02-26 | 2022-02-26 | 2022-02-25 | 2022-02-26 | 2022-02-26 | 2022-02-26 | 2022-02-26 | 2022-02-26 | ALF Engineering Pvt Ltd, Chakan Plot No-A-1/3,MVML Supplier Park, Phase-IV,Village-Chakan 410501 | 1 | 21 | 405 | Mayur Deshpande | 9860194709 | mayurdeshpande@alfengineering.com | - | - | a@a.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 0 |  | 2022-02-25 | 2022-02-25 | 1 |  | vinodkumar
778 | 2022-03-18 | 11:13:22 AM | Sapl0335 | 1 | 9 | J009 | 799 | 813 | 4300054309 | 34 | 0 | S0202 | 2022-03-15 | Gun rail spare part | Mr.mayur todkar | 5 | 2022-03-15 | 2022-03-16 | 2022-03-16 | 2022-03-17 | 2022-03-17 | 2022-03-26 | 2022-03-27 | 2022-03-29 | 2022-03-29 | 2022-04-02 | 2022-04-02 | 2022-04-07 | 2022-03-27 | 2022-04-11 | 2022-04-12 | 2022-04-13 | Supplier Park ?- ?Building No ?- ?6?,?Toyota Kirloskar Motors Pvt?.?Ltd?.?,?Plot No?.?1?, ?Bidadi Industrial ? Area?,?Ramnagardistt?, ?Bidadi? Bangalore?, ?Karnataka?, ?India ?- ?562109 | 1 | 17 | 293 | Vijay tomar | 7836972511 | purchase@joai.co.in | - | - | a@a.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2022-03-18 | 2022-03-20 | 1 |  | Mr.mayur todkar
789 | 2022-05-18 | 7:49:05 PM | Sapl0335 | 1 | 10 | F009 | 806 | 823 | Verbal_NMC_16-05-2022 | 35 | 0 | N0252 | 2022-05-16 | Assembly stand platfrom | Mr.mayur todkar | 5 | 2022-05-16 | 2022-05-16 | 2022-05-16 | 2022-05-16 | 2022-05-16 | 2022-05-17 | 2022-05-17 | 2022-05-18 | 2022-05-18 | 2022-05-19 | 2022-05-20 | 2022-05-20 | 2022-05-17 | 2022-05-23 | 2022-05-24 | 2022-05-23 | Opp ?24?Th ? Milestone?,?Sh?-?7?,?Village?-?Vithala? pur?, ?382130?,?Tq?-?Mandal ? ,?Ahmedabad St Code?-?24 | 1 | 12 | 142 | Dharam Pal Yadav | 9992500769 | purchase@fjmcylinders.com | - | - | a@a.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 0 |  | 2022-05-16 | 2022-05-17 | 1 |  | Mr.mayur todkar
799 | 2022-09-08 | 9:40:06 AM | Sapl0335 | 1 | 10 | G017 | 812 | 833 | Verbal_NMC_14-06-2022 | 35 | 0 | N0260 | 2022-06-14 | Screen Printing Machine | Mr.mayur todkar | 5 | 2022-06-14 | 2022-06-14 | 2022-06-14 | 2022-06-15 | 2022-06-15 | 2022-07-02 | 2022-07-02 | 2022-07-04 | 2022-06-04 | 2022-07-10 | 2022-07-14 | 2022-07-15 | 2022-07-02 | 2022-07-18 | 2022-07-18 | 2022-07-18 | Plant, Pirojshanagar Wikhroli, Mumbai 400079 | 1 | 21 | 398 | Gajendrasingh J Bhadauria | 9820225024 | gjb@godrej.com | - | - | a@a.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2022-06-17 | 2022-06-18 | 1 |  | Mr.mayur todkar
801 | 2022-09-12 | 3:47:11 PM | Sapl0335 | 1 | 10 | F009 | 814 | 835 | NMC_verbal_11/07/22 | 35 | 0 | N0261 | 2022-07-11 | JIB CRANE | MR. MADAN KUMBAR | 5 | 2022-07-13 | 2022-07-15 | 2022-07-11 | 2022-07-13 | 2022-07-14 | 2022-07-22 | 2022-07-26 | 2022-07-26 | 2022-07-22 | 2022-07-25 | 2022-07-28 | 2022-07-28 | 2022-07-26 | 2022-08-05 | 2022-08-06 | 2022-08-06 | FJM CYLINDERS PVT. LTD, Plot No-20 & 21-P,Bidadi Industrial Area,Phase-II,,562109, Sector-1,Shanumangala,Bidadi,Ramanagara | 1 | 17 | 293 | - | - | fjmcyliners@gmail.com | - | - | a@a.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2022-07-15 | 2022-07-21 | 1 |  | MR. MADAN KUMBAR
802 | 2022-07-12 | 1:34:31 PM | Sapl0335 | 1 | 10 | E003 | 815 | 836 | NMC_verbal_12/07/22 | 35 | 0 | N0262 | 2022-07-12 | SCISSOR LIFT FOR BATTERY ASSEMBLY | MR. MADAN KUMBAR | 5 | 2022-07-14 | 2022-07-15 | 2022-07-12 | 2022-07-13 | 2022-07-13 | 2022-07-22 | 2022-07-25 | 2022-07-26 | 2022-07-22 | 2022-07-25 | 2022-07-27 | 2022-07-28 | 2022-08-02 | 2022-08-05 | 2022-08-05 | 2022-08-06 | Euler Motors Sheikh Sarai Phase 1, Sheikh Sarai, New Delhi, Delhi 110017 | 1 | 10 | 133 | abcd | 9090909090 | abcd@gmail.com | - | - | a@a.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2022-07-16 | 2022-07-20 | 1 |  | MR. MADAN KUMBAR
803 | 2022-07-16 | 10:47:00 AM | Sapl0335 | 1 | 10 | T002 | 816 | 837 | 2410272344 | 37 | 0 | P0079 | 2022-07-16 | Eletrical Spare parts | MR. VINODKUMAR KADEPURE | 13 | 2022-07-16 | 2022-07-16 | 2022-07-17 | 2022-07-17 | 2022-07-17 | 2022-07-17 | 2022-07-17 | 2022-07-18 | 2022-07-18 | 2022-07-18 | 2022-07-17 | 2022-07-18 | 2022-07-18 | 2022-07-19 | 2022-07-20 | 2022-07-20 | SERVO DRIVE 80VD100PD.C000-14 B&R | 1 | 21 | 405 | Omprakash shaw | 9090909090 | ops524362@tatamotor.com | - | - | a@a.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 0 |  | 2022-07-18 | 2022-07-18 | 1 |  | MR. VINODKUMAR KADEPURE
826 | 2022-10-03 | 1:57:58 PM | sapl0003 | 1 | 10 | E004 | 839 | 860 | 2348 | 35 | 0 | N0277 | 2022-10-03 | LOAD BODY TROLLEY FOR PAINT SHOP | - | 1 | 2022-09-28 | 2022-09-29 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 2022-10-01 | 2022-10-01 | 2022-10-01 | 2022-10-01 | 2022-10-01 | 2022-10-01 | 2022-10-01 | 2022-10-01 | 2022-10-01 | 2022-10-01 | Euler Palwal Topline Logistics Park Private Limited At village Aurangabad, Mitnol & Dighot Palwal District,Tehsil Hodal Haryana-Haryana 121105 | 1 | 13 | 173 | - | - | www@000.com | - | - | www@000.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 0 |  | 2022-09-30 | 2022-09-30 | 1 |  | -
63 | 2013-08-28 | 10:39:17 AM | Sapl0005 | 1 | 1 | P001 | 66 | 77 | Email | 34 | 0 | S0014 | 2013-05-27 | Gunrail | Mr. Rajkumar Jagtap | 2 | 2013-05-27 | 2013-05-27 | 2013-05-27 | 2013-05-27 | 2013-05-27 | 2013-05-27 | 2013-05-27 | 2013-05-27 | 2013-05-28 | 2013-05-28 | 2013-05-28 | 2013-05-28 | 2013-05-27 | 2013-05-28 | 2013-05-28 | 2013-05-28 | F-19,?KATPHAL ROAD?, ? MIDC AREA?,?BARAMATI? | 1 | 21 | 405 | SAGAR DEOKAR | 02112-2304382 | SAGAR.DEOKAR@piaggio.co.in | - | - | SAGAR.DEOKAR@piaggio.co.in | - | - | - | - | 0 | 0 | 0 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-05-28 | 2013-05-28 | 1 |  | Mr. Rajkumar Jagtap
356 | 2015-06-13 | 4:46:27 PM | Sapl0005 | 1 | 3 | M020 | 361 | 372 | 3400002289 | 36 | 0 | E0022 | 2015-03-03 | ECN for P601 | MANOJ SHINDE | 3 | 2015-03-03 | 2015-03-03 | 2015-03-03 | 2015-03-03 | 2015-03-03 | 2015-03-03 | 2015-03-03 | 2015-03-03 | 2015-03-03 | 2015-03-03 | 2015-03-03 | 2015-03-03 | 2015-03-03 | 2015-03-03 | 2015-03-03 | 2015-03-03 | mahindra CIE automotive | 1 | 46 | 692 | mishra | - | MISHRA.SATYAPRAKASH@MAHINDRACIE.COM | Sujit Barge | - | BARGE.SUJIT@MAHINDRACIE.COM | - | - | - | - | 0 | 0 | 0 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-03-03 | 2015-03-03 | 1 |  | MANOJ SHINDE
357 | 2015-07-13 | 10:51:18 AM | Sapl0005 | 1 | 3 | C004 | 362 | 373 | IND3210473 | 36 | 0 | E0023 | 2015-06-13 | LABOR CHARGES FOR PANEL REPAIRING | HEMAKSH PATIL | 4 | 2015-06-13 | 2015-06-13 | 2015-06-13 | 2015-06-13 | 2015-06-13 | 2015-06-13 | 2015-06-13 | 2015-06-13 | 2015-06-13 | 2015-06-13 | 2015-06-13 | 2015-06-13 | 2015-06-13 | 2015-06-13 | 2015-06-13 | 2015-06-13 | CIL, PUNE | 1 | 21 | 405 | archana karande | - | archana.karande@cummins.com | archana.karande | - | archana.karande@cummins.com | - | - | - | - | 0 | 0 | 0 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-06-13 | 2015-06-13 | 1 |  | HEMAKSH PATIL
359 | 2015-07-24 | 11:36:13 AM | Sapl0005 | 1 | 3 | S011 | 364 | 375 | PUOR15001116 | 36 | 0 | E0024 | 2015-06-16 | RAIL I&C | RAJKUMAR JAGTAP | 2 | 2015-06-26 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 2015-06-30 | 690, Udyambag Industrial Estate, BELGAUM - 590 008 KARNATAKA - INDIA | 1 | 17 | 295 | SUNEEL NAGATHAN | - | projects@shantiiron.net | SUNEEL NAGATHAN | - | projects@shantiiron.net | - | - | - | - | 0 | 0 | 0 | - | - |  | 0 | 0 | 0 |  | 1 | compl | 2015-06-30 | 2015-06-30 | 1 |  | RAJKUMAR JAGTAP
399 | 2017-07-21 | 10:07:43 AM | Sapl0005 | 1 | 3 | S006 | 407 | 418 | nov24 | 35 | 0 | N0121 | 2015-11-24 | Hydraulic Car Parking System | HEMAKSH PATIL | 2 | 2015-11-24 | 2015-12-01 | 2015-12-01 | 2015-12-05 | 2015-12-07 | 2015-12-14 | 2015-12-21 | 2015-12-26 | 2015-12-28 | 2015-12-28 | 2015-12-14 | 2015-12-21 | 2015-12-21 | 2015-12-31 | 2015-12-31 | 2015-12-31 | sapl, pune | 1 | 21 | 405 | - | - | sales@synergytechs.com | - | - | sales@synergytechs.com | - | - | - | - | 0 | 0 | 0 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2015-11-24 | 2015-11-24 | 1 |  | HEMAKSH PATIL
400 | 2018-06-22 | 11:00:33 AM | Sapl0005 | 1 | 3 | A029 | 408 | 419 | MH_PO15-16_001324 | 35 | 0 | N0122 | 2015-11-24 | Modification of fixtures | Prajyot Genji | 3 | 2015-11-24 | 2015-11-26 | 2015-11-26 | 2015-11-28 | 2015-11-28 | 2015-11-30 | 2015-12-07 | 2015-12-09 | 2015-12-03 | 2015-12-05 | 2015-12-01 | 2015-12-03 | 2015-12-07 | 2015-12-09 | 2015-12-08 | 2015-12-09 | autoline unit iii, chakan | 1 | 21 | 405 | Sujeet Chaskar | - | sujeet.chaskar@autolineind.com | Faiyaz.Kashi | - | Faiyaz.Kashi@autolineind.com | - | - | - | - | 0 | 0 | 0 | - | - |  | 0 | 0 | 0 |  | 1 | close | 2015-11-26 | 2015-11-26 | 1 |  | Prajyot Genji
406 | 2019-12-29 | 5:14:41 PM | Sapl0002 | 1 | 3 | C004 | 414 | 425 | IND3409695 | 36 | 0 | E0026 | 2015-12-09 | I&C of console operator panel | HEMAKSH PATIL | 4 | 2015-12-09 | 2015-12-25 | 2015-12-25 | 2015-12-25 | 2015-12-25 | 2015-12-25 | 2015-12-25 | 2015-12-25 | 2015-12-25 | 2015-12-25 | 2015-12-25 | 2015-12-25 | 2015-12-23 | 2015-12-25 | 2015-12-25 | 2015-12-25 | cil, kothrud | 1 | 21 | 405 | divya vasudev | 7774003358 | divya.vasudev@cummins.com | amit.m.mahadeshwar | - | amit.m.mahadeshwar@cummins.com | - | - | - | - | 0 | 0 | 0 | - | - |  | 1 | 1 | 0 |  | 1 | COMPLETE | 2015-12-16 | 2015-12-17 | 1 |  | HEMAKSH PATIL
471 | 2017-01-09 | 2:38:55 PM | Sapl0005 | 1 | 4 | C004 | 480 | 490 | IND3650651 | 36 | 0 | E0034 | 2016-08-25 | Labour Charges for reconnection of Test Cell7 & 8 to field instrument | Dhananjay Sirsikar | 4 | 2016-08-25 | 2016-08-26 | 2016-08-26 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-29 | 2016-08-31 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-29 | 2016-08-31 | 2016-08-29 | 2016-08-31 | Cummins India Ltd., Pune | 1 | 21 | 405 | Deshpande, Ashutosh | - | ashutosh.deshpande@cummins.com | shirkant.m.foujdar | - | shirkant.m.foujdar@cummins.com | - | - | - | - | 0 | 0 | 0 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-08-25 | 2016-08-25 | 1 |  | Dhananjay Sirsikar
486 | 2017-01-09 | 2:49:45 PM | Sapl0005 | 1 | 4 | A024 | 497 | 506 | 7016004399 | 34 | 0 | S0141 | 2016-10-15 | telescopic trolley set | SANJAY SHINDE | 2 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | AUTOCOMPS CORPORATION PANSE PVT LTD Plot No. 125, Survey No. 258, Belur Industrial, Area,Village - Belur, Garag Hobli,Tal Dharwad,Karnataka : 580011 | 1 | 17 | 304 | YOGESH SHIRSAT | - | yjshirsat@pansegroup.com | pmrajguru@pansegroup.com | - | pmrajguru@pansegroup.com | - | - | - | - | 0 | 0 | 0 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-10-15 | 2016-10-15 | 1 |  | SANJAY SHINDE
534 | 2018-02-19 | 4:25:04 PM | Sapl0005 | 1 | 5 | M001 | 546 | 557 | 3400274331 | 36 | 0 | E0039 | 2017-07-03 | INSTALLATION OF EC Conveyor S201 | Prajyot Genji | 2 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | Mahindra & Mahindra | 1 | 21 | 402 | avhad anant | - | AVHAD.ANANT@mahindra.com | YADAV.YOGESH2 | - | YADAV.YOGESH2@mahindra.com | - | - | - | - | 0 | 0 | 0 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2017-07-03 | 2017-07-03 | 1 |  | Prajyot Genji
540 | 2017-12-09 | 9:50:43 AM | Sapl0005 | 1 | 5 | C004 | 551 | 562 | IND3936184 | 36 | 0 | E0040 | 2017-07-03 | channel to be weld below rail and installation | Akshay bhojkar | 2 | 2017-07-05 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | CUMMINS, KOTHRUD | 1 | 21 | 405 | Atulsingh.Pardeshi | - | Atulsingh.Pardeshi@cummins.com | Atulsingh.Pardesh | - | Atulsingh.Pardeshi@cummins.com | - | - | - | - | 0 | 0 | 0 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2017-07-03 | 2017-07-03 | 1 |  | Akshay bhojkar
548 | 2018-02-21 | 1:32:43 PM | Sapl0005 | 1 | 5 | A035 | 559 | 570 | verb9oct | 35 | 0 | N0172 | 2017-10-09 | DESIGN CHARGES FOR FIXTURES | Prajyot Genji | 19 | 2017-10-09 | 2017-10-12 | 2017-10-12 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | ATLAS COPCO | 1 | 21 | 405 | nipun.mahanta | - | nipun.mahanta@in.atlascopco.com | rajesh.khetrapal | - | rajesh.khetrapal@in.atlascopco.com | - | - | - | - | 0 | 0 | 0 | - | - |  | 0 | 0 | 1 |  | 1 | COMPLETE | 2017-10-13 | 2017-10-13 | 1 |  | Prajyot Genji
549 | 2018-04-19 | 8:45:16 AM | Sapl0005 | 1 | 5 | C004 | 560 | 571 | IND4032260 | 35 | 0 | N0173 | 2017-10-09 | Up gradation of AGV trolley to RGV trolley | Akshay bhojkar | 2 | 2017-10-09 | 2018-04-07 | 2017-10-15 | 2018-04-07 | 2017-10-21 | 2017-10-29 | 2017-11-05 | 2017-11-10 | 2017-11-11 | 2017-11-14 | 2017-10-29 | 2017-11-04 | 2017-11-05 | 2017-11-18 | 2017-11-09 | 2017-11-11 | cummins india ltd. | 1 | 21 | 405 | Atulsingh.Pardeshi | - | Atulsingh.Pardeshi@cummins.com | praful aole | - | praful.p.aole@cummins.com | - | - | - | - | 0 | 0 | 0 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2017-10-18 | 2017-10-18 | 1 |  | Akshay bhojkar
573 | 2018-03-13 | 2:08:56 PM | Sapl0005 | 1 | 5 | M001 | 584 | 596 | 3101184049 | 38 | 0 | J0105 | 2018-02-28 | MACHINING OF BASES 18F208 | Sagar Ravtale | 5 | 2018-02-28 | 2018-03-31 | 2018-02-28 | 2018-03-31 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | M&M, nashik | 1 | 21 | 405 | KUMAR.CHANDRAMANI | - | KUMAR.CHANDRAMANI2@mahindra.com | YADAV YOGESH | - | YADAV.YOGESH2@mahindra.com | - | - | - | - | 0 | 0 | 0 | - | - |  | 1 | 0 | 0 |  | 1 | COMPLETE | 2018-02-28 | 2018-02-28 | 1 |  | Sagar Ravtale
603 | 2019-12-29 | 5:16:42 PM | Sapl0002 | 1 | 6 | J020 | 632 | 628 | 4100106865 | 36 | 0 | E0042 | 2018-10-10 | INSTALLATION OF Rails | Dhananjay Sirsikar | 7 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | JBM AUTO LTD. | 1 | 21 | 402 | bijay.agrawal | - | bijay.agrawal@jbmgroup.com | vinayak.kale | - | vinayak.kale@jbmgroup.com | - | - | - | - | 0 | 0 | 0 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2018-10-13 | 2018-10-13 | 1 |  | Dhananjay Sirsikar
606 | 2020-12-05 | 11:17:12 AM | sapl0313 | 1 | 6 | A002 | 635 | 632 | PO_9887 | 34 | 0 | S0172 | 2018-10-24 | - | - | 1 | 2018-10-24 | 2018-10-24 | 2018-10-24 | 2018-10-24 | 2018-10-24 | 2018-10-24 | 2018-10-24 | 2018-10-24 | 2018-10-24 | 2018-10-24 | 2018-10-24 | 2018-10-24 | 2018-10-24 | 2018-10-24 | 2018-10-24 | 2018-10-24 | - | 1 | 21 | 405 | - | - | a@a.com | - | - | a@a.com | - | - | - | - | 0 | 0 | 0 | - | - |  | 0 | 0 | 0 |  | 1 | WO Close | 2018-10-24 | 2018-10-24 | 1 |  | -
629 | 2020-12-05 | 11:19:51 AM | sapl0313 | 1 | 7 | T016 | 655 | 655 | 0016/1802/18-19 | 34 | 0 | S0178 | 2019-04-19 | slido rail | MR.PRASHANT SURYAWANSHI | 1 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | 2019-04-19 | Techexpert Engineering Pvt Ltd S.No. 78/1, Shivane Industrial Area, NDA Road, Near Hindustan Bekry, Shivane, Pune-411023 | 1 | 21 | 405 | Mr Pankaj Jadhav | - | www@0000.com | - | - | www@0000.com | - | - | - | - | 1 | 1 | 0 | - | - |  | 1 | 0 | 0 |  | 1 | WO Close | 2019-03-09 | 2019-04-15 | 1 |  | MR.PRASHANT SURYAWANSHI
685 | 2020-12-05 | 10:50:51 AM | sapl0313 | 1 | 7 | T018 | 714 | 716 | 256362 | 38 | 0 | J0125 | 2020-08-23 | SS304 CON STAND | Mr. Pravin Chougule | 5 | 2020-08-23 | 2020-08-23 | 2020-08-23 | 2020-08-23 | 2020-08-23 | 2020-08-24 | 2020-08-24 | 2020-08-25 | 2020-08-25 | 2020-08-25 | 2020-08-25 | 2020-08-25 | 2020-08-26 | 2020-08-26 | 2020-08-26 | 2020-08-26 | Gat no. 3(part, 243(part), 5(part) Kasurdi(Kheba), Tal.- Bhor, Dist.-Pune, PIN- 412205 | 1 | 21 | 405 | - | - | purchase@technofor.com | - | - | purchase@technofor.com | - | - | - | - | 1 | 0 | 0 | - | - |  | 1 | 0 | 0 |  | 1 | WO Close | 2020-08-25 | 2020-08-25 | 1 |  | Mr. Pravin Chougule
340 | 2016-01-01 | 3:12:57 PM | Sapl0005 | 1 | 2 | Y002 | 345 | 356 | 2015500032 | 35 | 0 | N0101 | 2015-03-25 | 3D AND 2D DESIGN+ SIMULATION | AMIT POTDAR | 19 | 2015-03-25 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2015-03-30 | 2015-03-30 | YASKAWA ITALIA SRL STRADA DEL PORTONE, 75/A 10137 TORINO ITALIA | 4 | 41 | 693 | DONATO ABBATTISTA | - | Donato.Abbattista@yaskawa.eu.com | Giorgia.Senetta | - | Giorgia.Senetta@yaskawa.eu.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-03-25 | 2015-03-25 | 1 |  | AMIT POTDAR
537 | 2017-07-03 | 2:04:27 PM |  | 0 | 0 | C004 | 549 | 560 | IND3932559 | 35 | 0 | N0165 | 2017-07-03 | SCISSOR LIFT & PLATFORM | Akshay bhojkar | 2 | 2017-07-03 | 2017-07-20 | 2017-07-20 | 2017-07-31 | 2017-07-31 | 2017-08-12 | 2017-08-26 | 2017-08-28 | 2017-08-28 | 2017-08-31 | 2017-08-12 | 2017-08-26 | 2017-09-01 | 2017-09-04 | 2017-08-26 | 2017-08-28 | CUMMINS INDIA , KOTHRUD | 1 | 21 | 405 | Milind Bhagwat | - | milind.v.bhagwat@cummins.com | Milind Bhagwat | - | milind.v.bhagwat@cummins.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 0 |  | 2017-07-20 | 2017-07-20 | 1 |  | Akshay bhojkar
660 | 2020-12-05 | 11:15:37 AM | sapl0313 | 1 | 7 | A018 | 688 | 691 | U5PO1920_000332 | 37 | 0 | P0058 | 2019-11-27 | Spares_Magnetic Plungers | Mr. S. D. Shinde | 15 | 2019-11-27 | 2019-11-27 | 2019-11-27 | 2019-11-27 | 2019-11-27 | 2019-11-27 | 2019-11-27 | 2019-11-27 | 2019-11-27 | 2019-11-27 | 2019-11-27 | 2019-11-27 | 2019-11-27 | 2019-11-27 | 2019-11-27 | 2019-11-27 | Autoline Industries Ltd. Plot No.05, Sector 11, (Tata Vendor Park), Sidcul, IIE, Pantnagar, Rudrapur, PIN-263153, Uttarakhand. | 1 | 34 | 679 | Govindsingh Chandansingh Ginwal | - | govind.ginwal@autolineind.com | Govindsingh Chandansingh Ginwal | - | govind.ginwal@autolineind.com | - | - | - | - | 0 | 1 | 1 | - | SAPL Scope of Packing & Forwarding |  | 1 | 0 | 0 |  | 1 | WO Close | 2019-11-27 | 2019-11-27 | 1 |  | Mr. S. D. Shinde
690 | 2020-12-05 | 10:51:14 AM | sapl0313 | 1 | 8 | T018 | 719 | 721 | 258764 | 38 | 0 | J0126 | 2020-09-25 | SS304 MD CONV STAND ASS SET - 3rd Set | Mr. Pravin Chougule | 5 | 2020-09-22 | 2020-09-23 | 2020-09-23 | 2020-09-28 | 2020-09-23 | 2020-09-28 | 2020-09-26 | 2020-09-28 | 2020-09-28 | 2020-09-28 | 2020-09-28 | 2020-09-28 | 2020-09-26 | 2020-09-28 | 2020-09-28 | 2020-09-28 | Technofour Electronics Pvt Ltd Gat no 3(part), 243(part), 5(part), Kasurdi (Kheba) Tal: Bhor Dist: Pune PIN: 412205 | 1 | 21 | 405 | - | - | purchase@technofor.com | Mr Pawar | - | purchase@technofor.com | - | - | - | - | 1 | 1 | 1 | - | Packing with Bubble Sheets |  | 1 | 1 | 1 |  | 1 | WO Close | 2020-09-28 | 2020-09-28 | 1 |  | Mr. Pravin Chougule
691 | 2020-12-05 | 10:51:40 AM | sapl0313 | 1 | 8 | T018 | 720 | 722 | 259228 | 38 | 0 | J0127 | 2020-09-26 | SS 304 MD CONV STAND ASSEMBLY 4TH SET | Mr. Pravin Chougule | 5 | 2020-09-26 | 2020-09-26 | 2020-09-26 | 2020-09-26 | 2020-09-28 | 2020-09-30 | 2020-09-30 | 2020-09-30 | 2020-10-01 | 2020-10-01 | 2020-10-01 | 2020-10-01 | 2020-10-01 | 2020-10-01 | 2020-10-01 | 2020-10-01 | Technofour Electronics Pvt Ltd Gat no 3(part), 243(part), 5(part), Kasurdi (Kheba) Tal: Bhor Dist: Pune PIN: 412205 Ph: 02113 305 222/38/48 | 1 | 21 | 405 | Mr. Satish Kalekar | - | storem@tepl.co.in | Mr. Nitin Bhole | - | storem@tepl.co.i | - | - | - | - | 1 | 1 | 1 | - | Packing with Bubble Sheets |  | 1 | 1 | 1 |  | 1 | WO Close | 2020-09-29 | 2020-09-28 | 1 |  | Mr. Pravin Chougule
638 | 2019-12-29 | 5:20:28 PM | Sapl0002 | 1 | 7 | O002 | 665 | 665 | Verbal 665 | 38 | 0 | J0116 | 2019-06-15 | ROBOT PEDESTAL | Mr. Pravin Choughule | 5 | 2019-06-14 | 2019-06-14 | 2019-06-15 | 2019-06-15 | 2019-06-20 | 2019-06-20 | 2019-06-20 | 2019-06-20 | 2019-06-21 | 2019-06-21 | 2019-06-21 | 2019-06-21 | 2019-06-21 | 2019-06-21 | 2019-06-21 | 2019-06-21 | Plot no. A-22/1/1, MIDC Chakan Phase II, Tal. Khed, Dist. Pune, 410501 | 1 | 21 | 405 | DHEERAJ PRASAD | 9607959793 | dheeraj.prasad@olcieng.co.in | AMIT KOKANE | - | amit.kokane@olcieng.co.in | - | - | - | - | 0 | 0 | 1 | Only Polythene wrapping. | - |  | 1 | 0 | 0 |  | 1 | COMPLETED | 2019-06-15 | 2019-06-15 | 1 |  | Mr. Pravin Choughule
641 | 2019-12-29 | 6:58:57 PM | Sapl0002 | 1 | 7 | O002 | 669 | 668 | Verbal 669 | 38 | 0 | J0117 | 2019-06-25 | Weld Structure 8 nos. | Mr. Pravin Choughule | 5 | 2019-06-25 | 2019-06-25 | 2019-06-26 | 2019-06-26 | 2019-06-26 | 2019-07-09 | 2019-07-10 | 2019-07-10 | 2019-07-12 | 2019-07-12 | 2019-07-12 | 2019-07-12 | 2019-07-12 | 2019-07-12 | 2019-07-12 | 2019-07-12 | Plot No. A-22 A/1/1, MIDC Chakan, Phase -II, Khalumbre Khed, Pune - 410501 | 1 | 21 | 405 | DHEERAJ PRASAD | 9922941202 | dheeraj.prasad@olcieng.co.in | AMIT KOKANE | - | amit.kokane@olcieng.co.in | - | - | - | - | 0 | 0 | 1 | Packing by Wrapping sheet | Door Delivery |  | 1 | 1 | 0 |  | 1 | COMPLETED | 2019-06-28 | 2019-06-26 | 1 |  | Mr. Pravin Choughule
643 | 2020-12-05 | 11:00:41 AM | sapl0313 | 1 | 7 | O002 | 666 | 666 | PO/2019/000910 | 35 | 0 | N0202 | 2019-06-29 | Operator Platform 800Kg. | Mr. S Shinde | 3 | 2019-07-22 | 2019-07-27 | 2019-07-22 | 2019-07-29 | 2019-07-22 | 2019-08-05 | 2019-08-05 | 2019-08-17 | 2019-08-20 | 2019-08-24 | 2019-08-24 | 2019-08-24 | 2019-08-24 | 2019-08-24 | 2019-08-24 | 2019-08-24 | Plot no. A-22/1/1, MIDC Chakan Phase II, Tal. Khed, Dist. Pune, 410501 | 1 | 21 | 405 | Subhash Tapkir | 8007020509 | subhash.tapkir@olcieng.co.in | AMIT KOKANE | - | amit.kokane@olcieng.co.in | - | - | - | - | 1 | 1 | 1 | Packing by Wrapping sheet and Base Wooden Pallet. | Not Applicable |  | 1 | 1 | 1 |  | 1 | WO Close | 2019-08-05 | 2019-08-14 | 1 |  | Mr. S Shinde
688 | 2021-08-24 | 10:47:22 AM | Sapl0334 | 1 | 8 | G015 | 717 | 719 | GP/20-21/12-IV | 35 | 0 | N0230 | 2020-09-22 | Structure and Material Handling System | Mr. Aniruddha Raut | 3 | 2020-09-22 | 2020-09-25 | 2020-09-26 | 2020-09-26 | 2020-09-28 | 2020-10-16 | 2020-10-16 | 2020-10-17 | 2020-10-16 | 2020-10-16 | 2020-10-17 | 2020-10-19 | 2020-10-17 | 2020-10-19 | 2020-10-20 | 2020-10-20 | Gloria Engineering Company Factory Address – Gloria Eng. Co., Gat No. 1326, shelar wasti, chikhali, Pune-412114 | 1 | 21 | 405 | Mr. Deepak Verma | 9370925004 | deepak.verma@gloriagroup.co.in | Mr Pawar | - | sunilpawar071@gmail.com | - | - | - | - | 1 | 1 | 1 | Reports to submit | Packing with Bubble Sheets |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2020-10-10 | 2020-10-08 | 1 |  | Mr. Aniruddha Raut
12 | 2013-08-28 | 10:48:33 AM | Sapl0005 | 1 | 1 | C012 | 16 | 21 | IND2350830 | 35 | 0 | N0003 | 2013-04-09 | MANUAL TOD REQUIRED IN CYLINDER HEAD LINE FOR VALVE ASSEMBLY | RAJKUMAR JAGTAP | 2 | 2012-12-15 | 2012-12-30 | 2012-12-31 | 2013-01-08 | 2013-01-09 | 2013-01-22 | 2013-02-01 | 2013-02-07 | 2013-02-08 | 2013-02-20 | 2013-01-23 | 2013-01-31 | 2013-02-26 | 2013-02-28 | 2013-02-02 | 2013-02-08 | PLOT NO. A-1, MIDC SURWADI, - PHALTAN-LONAND ROAD - PHALTAN - 415522, MAHARASHTRA, INDIA | 1 | 21 | 405 | SARANG PATEKAR | +91 8888848018 | sarang.patekar@cummins.com | - | - | SDAD@REDF.IN | +91-02138-399098 | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-01-10 | 2013-01-10 | 1 |  | RAJKUMAR JAGTAP
59 | 2018-01-11 | 1:46:16 PM | Sapl0005 | 1 | 1 | M001 | 62 | 73 | LOI | 35 | 0 | N0014 | 2013-05-22 | BWF Units | Mr. Manoj Shinde | 3 | 2013-05-08 | 2013-05-08 | 2013-05-08 | 2013-05-08 | 2013-05-08 | 2013-05-08 | 2013-05-08 | 2013-05-08 | 2013-05-08 | 2013-05-08 | 2013-05-08 | 2013-05-08 | 2013-05-08 | 2013-05-08 | 2013-05-08 | 2013-05-08 | Mahindra & Mahindra Ltd. Plant- 2, 80 M.I.D.C. Satpur | 1 | 21 | 402 | Snehal Malge | +91 253 6613052 | MALGE.SNEHAL@mahindra.com | Snehal Malge | +91 253 6613052 | MALGE.SNEHAL@mahindra.com | +91 253 2353320 | - | - | - | 0 | 0 | 0 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-05-08 | 2013-05-08 | 1 |  | Mr. Manoj Shinde
273 | 2014-11-28 | 11:43:05 AM | Sapl0005 | 1 | 2 | C002 | 276 | 285 | 60010975 | 36 | 0 | E0014 | 2014-08-02 | FENCE ADDITIONAL WORK CHARGES. | MR. SANJAY D. SHINDE | 18 | 2014-08-11 | 2014-08-11 | 2014-08-12 | 2014-08-12 | 2014-08-16 | 2014-08-16 | 2014-08-18 | 2014-08-18 | 2014-08-19 | 2014-08-19 | 2014-08-20 | 2014-08-20 | 2014-08-21 | 2014-08-21 | 2014-08-22 | 2014-08-22 | COMAU INDIA PVT. LTD., GAT NO. 1394, 1395, 1397, VILLAGE SHIKRAPUR, TALUKA SHIRUR, 412208, PUNE, INDIA. | 1 | 21 | 405 | MR. SUJEET KULKARNI | 9923200755 | sujeet.kulkarni@comau.com | MR. UMESH WARE | 8411957778 | umesh.ware@comau.com | 2066002865 | - | - | - | 1 | 1 | 1 | NA | NA |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-08-07 | 2014-08-08 | 1 |  | MR. SANJAY D. SHINDE
733 | 2021-04-06 | 7:00:24 PM | Sapl0334 | 1 | 8 | C004 | 763 | 767 | IND6712742 | 34 | 0 | S0193 | 2021-04-20 | PU Coated Rollers | Vinod Kumar | 5 | 2021-04-08 | 2021-04-09 | 2021-04-09 | 2021-04-11 | 2021-04-22 | 2021-04-26 | 2021-04-26 | 2021-05-08 | 2021-05-10 | 2021-05-11 | 2021-05-09 | 2021-05-09 | 2021-05-11 | 2021-05-11 | 2021-05-09 | 2021-05-10 | Cummins India Limited KOTHRUD 411038 India | 1 | 21 | 405 | Prajapati Sunil | 999999999 | OD189@cummins.com | - | 999999999 | OD189@cummins.com | --- | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2021-04-21 | 2021-04-21 | 1 |  | Vinod Kumar
737 | 2022-01-21 | 8:53:48 AM | sapl0001 | 1 | 8 | G020 | 766 | 771 | 5804019069 | 38 | 0 | J0146 | 2021-05-15 | NEW PALLET MANUFACTURING | Vinod Kumar | 5 | 2021-05-05 | 2021-05-10 | 2021-05-09 | 2021-05-11 | 2021-05-16 | 2021-07-02 | 2021-05-31 | 2021-07-02 | 2021-06-10 | 2021-07-06 | 2021-06-07 | 2021-07-05 | 2021-06-13 | 2021-07-08 | 2021-06-05 | 2021-07-05 | E?1 ?(?Part?)?,?Chakan Midc Road?, ?Phase?-?Iii?,?Kharabwadi?, ?Chakan?, ?Talegaon Chakan Road?, ?Mahalunge ? Ingale?, ?Maharashtra? | 1 | 21 | 405 | Mr. Sunil Kokate | +91-9673334857 | gaipl@in.gestamp.com | Mr. Omprakash | 9673337705 | gaipl@in.gestamp.com | --- | - | - | - | 1 | 1 | 1 | -- | - |  | 0 | 1 | 1 |  | 0 | OPEN FOR PO | 2021-05-16 | 2021-05-16 | 1 |  | Vinod Kumar
845 | 2023-02-09 | 11:22:16 AM | Sapl0335 | 1 | 10 | P017 | 861 | 879 | PPAPL200012 | 35 | 0 | N0292 | 2023-02-09 | Robotic fixture | Mr.mayur todkar | 5 | 2023-02-09 | 2023-02-09 | 2023-02-09 | 2023-02-10 | 2023-02-10 | 2023-02-13 | 2023-02-13 | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-14 | 2023-02-15 | 2023-02-17 | 2023-02-18 | 2023-02-18 | 2023-02-18 | Gut.No. 40, Plot No 01, Karodi, M.I.D.C. Waluj, Aurangabad 431136 | 1 | 21 | 385 | Nikhil Khandelwal | 9834586024 | mailto:purchase@planetrobotics.in | Rahul jhadhvo | 9834586024 | mailto:rahul.jadhao@planetrobotics.in | -- | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 0 |  | 2023-02-09 | 2023-02-10 | 1 |  | Mr. vinodkumar
847 | 2023-06-20 | 4:35:24 PM | Sapl0335 | 1 | 10 | S040 | 863 | 881 | DNS_verbal_27-03-23 | 35 | 0 | N0293 | 2023-03-27 | Robotic fixture | Mr.Vinodkumar | 5 | 2023-03-24 | 2023-03-29 | 2023-03-28 | 2023-04-01 | 2023-04-01 | 2023-04-07 | 2023-04-13 | 2023-04-14 | 2023-04-16 | 2023-04-17 | 2023-04-08 | 2023-04-12 | 2023-04-13 | 2023-04-19 | 2023-04-18 | 2023-04-18 | B-5, M.I.D.C. SATPUR, NASIK-07. Phone: 0253-2350988, Fax – 0253-6614154. Email- smi22@rediffmail.com | 1 | 21 | 405 | Anil patil | 9090909090 | smi22@rediffmail.com | Anil patil | 9090909090 | smi22@rediffmail.com | -- | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 0 |  | 2023-03-27 | 2023-03-27 | 1 |  | Mr.Vinodkumar
849 | 2023-05-02 | 11:57:19 AM | Sapl0335 | 1 | 11 | S042 | 866 | 884 | 232400958 | 34 | 0 | S0215 | 2023-05-02 | GUN RAIL | Mr.mayur todkar | 5 | 2023-05-01 | 2023-05-02 | 2023-05-02 | 2023-05-02 | 2023-05-02 | 2023-05-03 | 2023-05-02 | 2023-05-03 | 2023-05-03 | 2023-05-03 | 2023-05-03 | 2023-05-04 | 2023-05-04 | 2023-05-05 | 2023-05-04 | 2023-05-05 | Survey 342 Plot 690 Udyambag Industrial Estate, Karnataka 590008 | 1 | 17 | 295 | SANJAY | 7899836619 | purchase@shantifoumach.com | SANJAY | 7899836619 | purchase@shantifoumach.com | --- | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 0 |  | 0 |  | 2023-05-02 | 2023-05-02 | 1 |  | Mr.Vinodkumar
850 | 2023-06-06 | 3:34:15 PM | Sapl0335 | 1 | 11 | A036 | 864 | 882 | 7622000200 | 35 | 0 | N0295 | 2023-06-06 | Robotic cell integration | Mr.Sourabh Kamlbe | 5 | 2023-05-27 | 2023-05-29 | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-06-04 | 2023-06-09 | 2023-06-09 | 2023-06-09 | 2023-06-10 | 2023-06-08 | 2023-06-09 | 2023-06-10 | 2023-06-15 | 2023-06-16 | 2023-06-17 | A21/1, Chakan Industrial Area Phase - II, Village Khalumbare, Taluk : Khed,,Dist: Pune Pin-410501,Maharashtra,India Tel No. +91-020-27130658 Fax No. +91-020-27130321 | 1 | 21 | 405 | Pramod Tathe | 8446410903 | acppl1.development@pansegroup.com | Pramod Tathe | 8446410903 | acppl1.development@pansegroup.com | --- | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 0 |  | 2023-06-06 | 2023-06-06 | 1 |  | Mr. Joshi
852 | 2023-06-09 | 12:03:14 PM | Sapl0335 | 1 | 11 | S040 | 871 | 888 | SSPPL/ 2022-23/80 | 35 | 0 | N0296 | 2023-06-09 | Fixture and cmm stand | Mr.Sourabh Kamlbe | 5 | 2023-06-01 | 2023-06-02 | 2023-06-02 | 2023-06-03 | 2023-06-03 | 2023-06-06 | 2023-06-09 | 2023-06-10 | 2023-06-09 | 2023-06-09 | 2023-06-08 | 2023-06-08 | 2023-06-09 | 2023-06-10 | 2023-06-10 | 2023-06-12 | D-92, M.I.D.C. SATPUR, NASIK-07. Phone: 0253-2350988, Fax – 0253-6614154. | 1 | 21 | 402 | Anil patil | 9090909090 | smi22@rediffmail.com | Anil patil | 9090909090 | smi22@rediffmail.com | --- | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 0 |  | 2023-06-09 | 2023-06-09 | 1 |  | Mr. Joshi
853 | 2023-06-10 | 9:12:18 AM | Sapl0335 | 1 | 11 | S043 | 872 | 889 | SMI/ 2023-24/16 | 35 | 0 | N0297 | 2023-06-09 | Checking gauge | Mr.Sourabh Kamlbe | 5 | 2023-06-03 | 2023-06-05 | 2023-06-08 | 2023-06-14 | 2023-06-15 | 2023-06-22 | 2023-06-19 | 2023-06-20 | 2023-06-23 | 2023-06-24 | 2023-06-19 | 2023-06-23 | 2023-06-19 | 2023-06-27 | 2023-06-28 | 2023-06-29 | B-5, M.I.D.C. SATPUR, NASIK-07. Phone: 0253-2350988, Fax – 0253-6614154. | 1 | 21 | 402 | Anil patil | 9090909090 | smi22@rediffmail.com | Anil patil | 9090909090 | smi22@rediffmail.com | --- | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 0 |  | 2023-06-09 | 2023-06-09 | 1 |  | Mr. Joshi
858 | 2023-06-23 | 11:41:48 AM | Sapl0335 | 1 | 11 | S043 | 874 | 893 | SMI/ 2023-24/27 | 35 | 0 | N0298 | 2023-06-23 | Robotic fixture | Mr.Vinodkumar | 2 | 2023-06-01 | 2023-06-03 | 2023-06-03 | 2023-06-06 | 2023-06-06 | 2023-06-13 | 2023-06-18 | 2023-06-19 | 2023-06-23 | 2023-06-23 | 2023-06-13 | 2023-06-17 | 2023-06-22 | 2023-06-24 | 2023-06-24 | 2023-06-26 | B-5, M.I.D.C. SATPUR, NASIK-07. Phone: 0253-2350988, Fax – 0253-6614154. Email- smi22@rediffmail.com | 1 | 21 | 402 | Anil patil | 9090909090 | smi22@rediffmail.com | Anil patil | 9090909090 | smi22@rediffmail.com | --- | - | - | - | 1 | 1 | 1 | -- | - |  | 0 | 0 | 0 |  | 0 |  | 2023-06-23 | 2023-06-23 | 1 |  | Mr. Joshi
863 | 2023-09-15 | 1:59:05 PM | Sapl0335 | 1 | 11 | T019 | 877 | 897 | Verbal_nmc_9-8-23 | 35 | 0 | N0301 | 2023-08-09 | Robotic cell installtion | Mr.Vinodkumar | 5 | 2023-08-09 | 2023-08-15 | 2023-08-16 | 2023-08-20 | 2023-08-20 | 2023-08-31 | 2023-09-07 | 2023-09-08 | 2023-09-08 | 2023-09-09 | 2023-09-01 | 2023-09-06 | 2023-09-07 | 2023-09-22 | 2023-08-22 | 2023-08-23 | A1/4 Mvml vendor park ,chakan phase iv,, MIDC, Bhosari, Pimpri-Chinchwad, Maharashtra 410501, Pune,Maharashtra, India. 410501 | 1 | 21 | 405 | Rahul Agnihotri | 8010420497 | rahul.agnihotri@trackcomponents.in | Rahul Agnihotri | 8010420497 | rahul.agnihotri@trackcomponents.in | --- | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 0 |  | 2023-08-09 | 2023-08-09 | 1 |  | Mr.Joshi
644 | 2019-10-04 | 11:10:08 AM | sapl0001 | 1 | 7 | J003 | 671 | 670 | Verbal 671 | 35 | 0 | N0203 | 2019-07-02 | Tube Piercing SPM | Mr. S Shinde | 3 | 2019-07-10 | 2019-07-15 | 2019-07-15 | 2019-07-20 | 2019-07-20 | 2019-08-20 | 2019-08-21 | 2019-08-28 | 2019-08-29 | 2019-08-31 | 2019-09-02 | 2019-09-03 | 2019-09-04 | 2019-09-05 | 2019-09-05 | 2019-09-07 | Plot No. C-1/2, Mahalunge, Near Bajaj Ltd., Chakan MIDC, Pune | 1 | 21 | 405 | Mr. Tanaji Chavan | 9767896389 | tanaji.chavan@synergytechs.com | Mr. Rajaram Bhosale | 8888809426 | rajaram.bhosale@jbmmagnetto.com | - | - | - | - | 1 | 1 | 1 | Packing by Wrapping sheet and Base Wooden Pallet. | Not Applicable |  | 0 | 0 | 1 |  | 1 | order cancel | 2019-08-05 | 2019-08-15 | 1 |  | Mr. S Shinde
646 | 2019-12-29 | 6:59:14 PM | Sapl0002 | 1 | 7 | O002 | 674 | 673 | Verbal 674 | 38 | 0 | J0118 | 2019-07-22 | CBS OP02 | Mr. Aniruddha Raut | 5 | 2019-07-22 | 2019-07-23 | 2019-07-23 | 2019-07-23 | 2019-07-23 | 2019-08-05 | 2019-08-03 | 2019-08-05 | 2019-08-05 | 2019-08-07 | 2019-08-07 | 2019-08-07 | 2019-08-07 | 2019-08-07 | 2019-08-07 | 2019-08-07 | Plot No. A-22-A/1/1, MIDC Chakan, Phase-II, Khalumbre, Tal.-Khed, Dist. Pune, PIN- 410501 | 1 | 21 | 405 | DHEERAJ PRASAD | 9922941202 | dheeraj.prasad@olcieng.co.in | AMIT KOKANE | 8888809426 | amit.kokane@olcieng.co.in | - | - | - | - | 1 | 1 | 1 | Only Polythene wrapping. | Not Applicable |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2019-08-01 | 2019-08-01 | 1 |  | Mr. Aniruddha Raut
647 | 2020-12-05 | 10:48:27 AM | sapl0313 | 1 | 7 | O002 | 675 | 674 | Verbal 675 | 38 | 0 | J0119 | 2019-07-31 | CP 01 | Mr. S Shinde | 5 | 2019-07-31 | 2019-07-31 | 2019-07-31 | 2019-07-31 | 2019-07-31 | 2019-08-08 | 2019-08-08 | 2019-08-09 | 2019-08-09 | 2019-08-10 | 2019-08-10 | 2019-08-10 | 2019-08-10 | 2019-08-10 | 2019-08-10 | 2019-08-10 | Plot No. A-22-A/1/1, MIDC Chakan, Phase- II, Khalumbre, Tal.-Khed, Dist.-Pune, Pin-410501 | 1 | 21 | 405 | DHEERAJ PRASAD | 9922941202 | dheeraj.prasad@olcieng.co.in | AMIT KOKANE | 8888809426 | amit.kokane@olcieng.co.in | - | - | - | - | 1 | 1 | 1 | Packing by Wrapping sheet and Base Wooden Pallet. | Door Delivery |  | 1 | 1 | 1 |  | 1 | WO Close | 2019-08-07 | 2019-08-04 | 1 |  | Mr. S Shinde
654 | 2020-12-05 | 11:02:24 AM | sapl0313 | 1 | 7 | C015 | 682 | 683 | IND6310582 | 35 | 0 | N0207 | 2019-10-17 | Nut Runner & Hoist Parking Mwechanism | Mr. Sanjay D Shinde | 3 | 2019-10-17 | 2019-10-18 | 2019-10-18 | 2019-10-22 | 2019-10-22 | 2019-11-04 | 2019-10-28 | 2019-10-31 | 2019-11-04 | 2019-11-06 | 2019-11-06 | 2019-11-08 | 2019-11-06 | 2019-11-08 | 2019-11-06 | 2019-11-08 | CTIL_QSK_894:CTIL_QSK_894 C/O Cummins Technologies India Pvt. Ltd. Phaltan High Horsepower Plant, SEZ Unit Plot No. B3/1, MIDC SEZ-Phaltan, 415522 | 1 | 21 | 405 | Miss Shweta Nagarale | 7447426367 | shweta.nagarale@cummins.com | Miss Shweta Nagarale | 7447426367 | shweta.nagarale@cummins.com | - | - | - | - | 1 | 1 | 1 | To supply separately 3. Limit Switch (Teknic Make) – 01 no. | Not aplicablle |  | 1 | 1 | 1 |  | 1 | WO Close | 2019-11-02 | 2019-11-02 | 1 |  | Mr. Sanjay D Shinde
655 | 2020-12-05 | 11:02:46 AM | sapl0313 | 1 | 7 | A004 | 683 | 686 | LOI 151019 | 35 | 0 | N0208 | 2019-10-19 | WELDING FIXTURES FOR NEXON ELECTRIC VEHICLE | Mr. Sanjay D Shinde | 3 | 2019-10-22 | 2019-10-26 | 2019-10-26 | 2019-11-03 | 2019-11-03 | 2019-11-19 | 2019-11-19 | 2019-11-21 | 2019-11-21 | 2019-11-23 | 2019-11-23 | 2019-11-26 | 2019-11-26 | 2019-11-28 | 2019-11-26 | 2019-11-28 | Autoline Industries Ltd. Plant-II Nanekarwad, Chakan MIDC, Tal.- Khed, Dist.-Pune | 1 | 21 | 405 | Mr. Pankaj Deore | 7249466691 | pankaj.deore@autolineind.com | Mr. Amit Hange | 9960024484 | Amit.Hange@autolineind.com | - | - | - | - | 1 | 1 | 1 | Packing with Bubble Sheet and Transport, installation and commissioning in SAPL Scope. | Not aplicablle |  | 1 | 1 | 1 |  | 1 | WO Close | 2019-11-19 | 2019-10-12 | 1 |  | Mr. Sanjay D Shinde
658 | 2020-12-05 | 11:03:55 AM | sapl0313 | 1 | 7 | A004 | 686 | 689 | LOI-12112019 | 35 | 0 | N0211 | 2019-11-16 | Manual Spot Weld Fixture of Part no - 6115AAD00200N | Mr. Sanjay D Shinde | 3 | 2019-11-16 | 2019-11-23 | 2019-11-23 | 2019-11-25 | 2019-11-25 | 2019-12-07 | 2019-12-07 | 2019-12-11 | 2019-12-13 | 2019-12-14 | 2019-12-16 | 2019-12-18 | 2019-12-17 | 2019-12-19 | 2019-12-18 | 2019-12-19 | Autoline Industries Ltd. ( Unit-2) Gat No.313-314, Nanekarwadi, Chakan, Pune-410501 | 1 | 21 | 405 | Vinod Ambulkar | 7588185633 | vinod.ambulkar@autolineind.com | Mr. Pankaj Deore | 7249466691 | pankaj.deore@autolineind.com | - | - | - | - | 1 | 1 | 1 | Painting, Packing & Transport in Our Scope | Bubble Sheet Wrapping |  | 1 | 1 | 1 |  | 1 | WO Close | 2019-12-12 | 2019-12-07 | 1 |  | Mr. Sanjay D Shinde
659 | 2020-12-05 | 11:04:25 AM | sapl0313 | 1 | 7 | A004 | 687 | 690 | LOI14112019 | 35 | 0 | N0212 | 2019-11-16 | Inspection Gauges of 4 Assy. Parts-Electric Vehicle | Mr. Sanjay D Shinde | 3 | 2019-11-16 | 2019-11-21 | 2019-11-21 | 2019-11-23 | 2019-11-24 | 2020-01-15 | 2019-12-06 | 2020-01-15 | 2019-12-08 | 2020-01-15 | 2019-12-09 | 2020-01-16 | 2019-12-06 | 2020-01-17 | 2019-12-09 | 2020-01-18 | Auto-line Industries Ltd. ( Unit-2) Gat No.313-314, Nanekarwadi, Chakan, Pune-410501 | 1 | 21 | 405 | Mr. Amit Hange | 9960024484 | Amit.Hange@autolineind.com | Mr. Pankaj Deore | 7249466691 | pankaj.deore@autolineind.com | - | - | - | - | 1 | 1 | 1 | Painting, Packing & Transport in Our Scope | Not aplicablle |  | 1 | 1 | 1 |  | 1 | WO Close | 2020-01-15 | 2020-01-15 | 1 |  | Mr. Sanjay D Shinde
661 | 2019-12-29 | 6:59:47 PM | Sapl0002 | 1 | 7 | O002 | 689 | 692 | LOI02122019 | 38 | 0 | J0121 | 2019-12-02 | Job Work-Interface Eloco | Mr. S. D. Shinde | 5 | 2019-12-02 | 2019-12-02 | 2019-11-25 | 2019-12-02 | 2019-12-02 | 2019-12-04 | 2019-12-04 | 2019-12-05 | 2019-12-05 | 2019-12-06 | 2019-12-06 | 2019-12-06 | 2019-12-06 | 2019-12-06 | 2019-12-06 | 2019-12-06 | OLCI Engineering Pvt. Ltd. | 1 | 21 | 405 | Mr. Dheeraj Prasad | 9922941202 | dheeraj.prasad@olcieng.co.in | Mr. Amit kokane | 8308361607 | amit.kokane@olcieng.co.in | - | - | - | - | 1 | 1 | 1 | - | SAPL Scope of Packing & Forwarding |  | 1 | 0 | 0 |  | 1 | COMPLETED | 2019-12-04 | 2019-12-03 | 1 |  | Mr. S. D. Shinde
663 | 2020-12-05 | 11:04:47 AM | sapl0313 | 1 | 7 | A004 | 691 | 694 | C2TRPO1920_000928 | 35 | 0 | N0213 | 2019-12-06 | Handy Fixture and Fixture Modification | Mr. S. D. Shinde | 3 | 2019-12-06 | 2019-12-11 | 2019-12-09 | 2019-12-11 | 2019-12-09 | 2020-01-16 | 2019-12-14 | 2020-01-16 | 2019-12-14 | 2020-01-16 | 2019-12-16 | 2020-01-16 | 2019-12-14 | 2020-01-16 | 2019-12-16 | 2020-01-17 | Autoline Industries Ltd. 313/314,320 to 323,Nanekarwadi,Chakan, Pune410501, Maharashtra, India. CIN No.: L34300PN1996PLC104510 | 1 | 21 | 405 | Mr. Pankaj Deore | 7249466691 | pankaj.deore@autolineind.com | Mr. Satish Satpute | 9890030485 | Satish.Satpute@autolineind.com | - | - | - | - | 1 | 1 | 1 | Packing with Bubble Sheet | SAPL Scope of Packing & Forwarding |  | 1 | 1 | 1 |  | 1 | WO Close | 2020-01-15 | 2020-01-15 | 1 |  | Mr. S. D. Shinde
664 | 2020-12-05 | 11:05:18 AM | sapl0313 | 1 | 7 | S019 | 692 | 695 | U1RPM1920000195 | 35 | 0 | N0214 | 2019-12-11 | Handy Fixture and Fixture Modification 267462100111 | Mr. S. D. Shinde | 3 | 2019-12-12 | 2019-12-16 | 2019-12-13 | 2019-12-16 | 2019-12-14 | 2020-01-15 | 2019-12-21 | 2020-01-15 | 2019-12-23 | 2020-01-15 | 2019-12-24 | 2020-01-15 | 2019-12-21 | 2020-01-15 | 2019-12-26 | 2020-01-15 | SHARADA INDUSTRIES, W-199, S Block , - MIDC Bhosari UNIT-1 PUNE - 411026 | 1 | 21 | 405 | Mr. Vishvanath karale | 9146009830 | vishvanath.karale@sharadaindustries.com | Mr. Vishvanath karale | 9146009830 | vishvanath.karale@sharadaindustries.com | - | - | - | - | 1 | 1 | 1 | Packing with Bubble Sheet | SAPL Scope of Packing & Forwarding |  | 1 | 1 | 1 |  | 1 | WO Close | 2020-01-14 | 2020-01-14 | 1 |  | Mr. S. D. Shinde
666 | 2020-12-05 | 11:05:44 AM | sapl0313 | 1 | 7 | A002 | 694 | 697 | LOI27122019 | 35 | 0 | N0215 | 2019-12-29 | Wall Clamp Bending & Riveting SPMs 2 Nos. | Mr. S. D. Shinde | 3 | 2019-12-30 | 2020-01-06 | 2020-01-03 | 2020-01-17 | 2020-01-03 | 2020-01-25 | 2020-01-20 | 2020-01-24 | 2020-01-24 | 2020-01-25 | 2020-01-27 | 2020-01-28 | 2020-01-20 | 2020-01-30 | 2020-01-31 | 2020-01-31 | Gat No.388 , Village Mahalunge , Chakan_Talegaon Road, Next to Bajaj Auto , Tal_Khed, Dist_ Pune - 410501 ( Maharashtra) | 1 | 21 | 405 | Mr. Digambar Pargaonkar | 9881700985 | digambar.pargaonkar@wadhokar.com | Mr. Sushil Wadhokar | 9881700985 | sushil@wadhokar.com | - | - | - | - | 1 | 1 | 1 | Packing with Bubble Sheet | SAPL Scope of Packing & Forwarding |  | 1 | 1 | 0 |  | 1 | WO Close | 2020-01-25 | 2020-01-25 | 1 |  | Mr. S. D. Shinde
667 | 2020-12-05 | 11:06:12 AM | sapl0313 | 1 | 7 | O002 | 695 | 698 | LOI02012020 | 35 | 0 | N0216 | 2020-01-03 | Multi Utility Trolleys with Caster Wheel Assy Set -06 Nos. | Mr. S. D. Shinde | 3 | 2020-01-03 | 2020-01-04 | 2020-01-04 | 2020-01-04 | 2020-01-04 | 2020-01-18 | 2020-01-20 | 2020-01-20 | 2020-01-21 | 2020-01-21 | 2020-01-21 | 2020-01-20 | 2020-01-21 | 2020-01-21 | 2020-01-21 | 2020-01-21 | O.L.C.I. Engineering Pvt. Ltd. E-14. Chakan Industrial Area, Phase-III, Nighoje, Khed, Pune- 410501 | 1 | 21 | 405 | Avinash Ambad | 9607959792 | avinash.ambad@olcieng.co.in | Mr. Amit kokane | 8308361607 | amit.kokane@olcieng.co.in | - | - | - | - | 1 | 1 | 1 | Packing with Bubble Sheet | SAPL Scope of Packing & Forwarding |  | 1 | 1 | 1 |  | 1 | WO Close | 2020-01-16 | 2020-01-10 | 1 |  | Mr. S. D. Shinde
668 | 2020-12-05 | 11:09:22 AM | sapl0313 | 1 | 7 | S034 | 696 | 699 | LOI24122019 | 35 | 0 | N0217 | 2020-01-08 | Welding Line for MBP BIW Assy Fixtures | Mr. Joshi | 3 | 2019-12-26 | 2020-01-11 | 2020-01-10 | 2020-03-15 | 2020-01-10 | 2020-03-07 | 2020-02-25 | 2020-03-10 | 2020-03-02 | 2020-03-10 | 2020-03-10 | 2020-03-12 | 2020-02-25 | 2020-03-15 | 2020-03-12 | 2020-03-15 | Sitarganj, Uttarakhand. | 1 | 34 | 650 | Mr. Nandi | 7022788094 | nandi@surinauto.com | Mr. Nandi | 7022788094 | nandi@surinauto.com | - | - | - | - | 1 | 1 | 1 | Packing with Bubble Sheet | SAPL Scope of Packing & Forwarding |  | 1 | 1 | 1 |  | 1 | WO Close | 2020-01-28 | 2020-01-25 | 1 |  | Mr. Joshi
669 | 2020-12-05 | 10:49:21 AM | sapl0313 | 1 | 7 | O002 | 697 | 700 | LOI17012020 | 38 | 0 | J0122 | 2020-01-17 | Lifting Tackles-04 Nos. | Mr. Pravin Chougule | 5 | 2020-01-17 | 2020-01-17 | 2020-01-17 | 2020-01-17 | 2020-01-17 | 2020-01-22 | 2020-01-22 | 2020-01-22 | 2020-01-22 | 2020-01-22 | 2020-01-22 | 2020-01-22 | 2020-01-22 | 2020-01-22 | 2020-01-22 | 2020-01-22 | Plot No. A-22-A-/1/1, MIDC Chakan, Phase-II, Khalumbre Khed, Pune-410501 | 1 | 21 | 405 | Mr. Dheeraj Prasad | 9922941202 | dheeraj.prasad@olcieng.co.in | Mr. Amit kokane | 8308361607 | amit.kokane@olcieng.co.in | - | - | - | - | 1 | 1 | 1 | Packing with Bubble Sheet | SAPL Scope of Packing & Forwarding |  | 1 | 1 | 1 |  | 1 | WO Close | 2020-01-21 | 2020-01-21 | 1 |  | Mr. Pravin Chougule
670 | 2020-12-05 | 10:49:59 AM | sapl0313 | 1 | 7 | O002 | 699 | 701 | LOI30012020 | 38 | 0 | J0123 | 2020-02-01 | Safety Fence | Mr. Prashant Suryawanshi | 5 | 2020-01-31 | 2020-01-31 | 2020-01-31 | 2020-01-31 | 2020-02-01 | 2020-02-15 | 2020-02-15 | 2020-02-15 | 2020-02-15 | 2020-02-15 | 2020-02-15 | 2020-02-15 | 2020-02-15 | 2020-02-15 | 2020-02-08 | 2020-02-14 | Plot No. E-14, Chakan Industrial Area, Phase III, Nighoje, Khed, Pune, Pin-410501 | 1 | 21 | 405 | Avinash Ambad | 9607959792 | avinash.ambad@olcieng.co.in | Mr. Amit kokane | 8308361607 | amit.kokane@olcieng.co.in | - | - | - | - | 1 | 1 | 1 | Packing with Bubble Sheet | SAPL Scope of Packing & Forwarding |  | 1 | 1 | 1 |  | 1 | WO Close | 2020-02-14 | 2020-02-07 | 1 |  | Mr. Prashant Suryawanshi
671 | 2020-12-05 | 11:22:35 AM | sapl0313 | 1 | 7 | N002 | 700 | 702 | 4300043614 | 34 | 0 | S0186 | 2020-02-17 | Railing System | Mr. Prashant Suryawanshi | 2 | 2020-02-17 | 2020-02-17 | 2020-02-17 | 2020-02-17 | 2020-02-21 | 2020-02-21 | 2020-02-22 | 2020-02-22 | 2020-02-22 | 2020-02-22 | 2020-03-07 | 2020-03-10 | 2020-03-07 | 2020-03-10 | 2020-03-09 | 2020-03-09 | Neel Metal Products Limited, PLOT No.22 & Plot No.1A,Sector 12,ITBT Park,IIE,SIDCUL,263153, - Pantnagar | 1 | 34 | 679 | Abhishek Painuly | 7830002048 | abhishek.painuly@jbmgroup.com | Abhishek Painuly | 7830002048 | abhishek.painuly@jbmgroup.com | - | - | - | - | 1 | 1 | 1 | Packing with Bubble Sheet | Not Applicable |  | 1 | 0 | 0 |  | 1 | WO Close | 2020-02-22 | 2020-02-19 | 1 |  | Mr. Prashant Suryawanshi
672 | 2020-12-05 | 11:09:41 AM | sapl0313 | 1 | 7 | N002 | 701 | 703 | 4300043061 | 35 | 0 | N0218 | 2020-03-01 | MBP FES BIW Assy Welding Fixtures | Mr. Aniruddha Raut | 3 | 2020-03-01 | 2020-03-14 | 2020-03-01 | 2020-03-14 | 2020-03-02 | 2020-03-24 | 2020-03-20 | 2020-03-28 | 2020-03-28 | 2020-03-31 | 2020-04-06 | 2020-04-13 | 2020-04-10 | 2020-04-15 | 2020-04-15 | 2020-04-20 | Neel Metal Products Ltd. Plot no. 22 & 1A, Sector 12, ITBT park, IIE, SIDCUL, Pantnagar- 263153 | 1 | 34 | 679 | Manoj Joshi | 7060036876 | manoj.joshi@jbmgroup.com | Anand Garg | 7060302014 | anand.garg@jbmgroup.com | - | - | - | - | 1 | 1 | 1 | Packing & Supply | Packing with Bubble Sheets |  | 1 | 1 | 1 |  | 1 | N0218 | 2020-03-25 | 2020-03-15 | 1 |  | Mr. Aniruddha Raut
673 | 2020-12-05 | 11:10:04 AM | sapl0313 | 1 | 7 | P013 | 702 | 704 | 2011004 | 35 | 0 | N0219 | 2020-03-03 | MBP FES BIW Assy Welding Fixtures- 28 nos. | Mr. Aniruddha Raut | 3 | 2020-03-03 | 2020-03-14 | 2020-03-03 | 2020-03-14 | 2020-03-04 | 2020-03-25 | 2020-03-25 | 2020-03-29 | 2020-03-30 | 2020-03-31 | 2020-04-07 | 2020-04-11 | 2020-03-25 | 2020-04-26 | 2020-04-27 | 2020-04-30 | Sipcot-1, B12A & B14, Sidco Industrial Estate, Hosur 635 126 Tamil Nadu India 04344 - 279848, 276001 prabhaengineers@eth.net | 1 | 31 | 680 | Mr. Anand Raj | 9597954949 | anandraj@prabhaengineers.com | Mr. Senthil Kumar | 9790160288 | senthil.s@prabhaengineers.com | - | - | - | - | 1 | 1 | 1 | Packing with Bubble Sheet | Not Applicable |  | 1 | 1 | 0 |  | 1 | WO Close | 2020-03-24 | 2020-03-15 | 1 |  | Mr. Aniruddha Raut
683 | 2020-08-05 | 5:10:34 PM | sapl0313 | 1 | 7 | S006 | 712 | 714 | LOI 05 Aug 2020 | 35 | 0 | N0228 | 2020-08-05 | Rail Guided Vehicle | Mr. Amit Shedge | 3 | 2020-08-05 | 2020-08-14 | 2020-08-14 | 2020-08-18 | 2020-08-18 | 2020-09-05 | 2020-09-06 | 2020-09-12 | 2020-09-13 | 2020-09-16 | 2020-09-18 | 2020-09-21 | 2020-09-22 | 2020-09-26 | 2020-09-26 | 2020-09-29 | Gut No.205,Kasurdi,Khed Shivapur, Off Pune Bangalore Highway, Pune - 412 205 | 1 | 21 | 405 | Mr. Narendra Chaudhary | 9822314833 | narendra@synergytechs.com | Mr. Dhananjay Sirsikar | 9822614720 | dhananjay@synergytechs.com | - | - | - | - | 1 | 1 | 1 | Required | Not required |  | 0 | 1 | 1 |  | 0 |  | 2020-09-05 | 2020-09-02 | 1 |  | Mr. Amit Shedge
684 | 2020-12-05 | 11:22:56 AM | sapl0313 | 1 | 7 | N003 | 713 | 715 | 4300045356 | 34 | 0 | S0187 | 2020-08-08 | Railing System | Mr. Aniruddha Raut | 4 | 2020-08-08 | 2020-08-08 | 2020-08-08 | 2020-08-08 | 2020-08-08 | 2020-08-14 | 2020-08-14 | 2020-08-14 | 2020-08-14 | 2020-08-14 | 2020-08-14 | 2020-08-14 | 2020-08-19 | 2020-08-19 | 2020-08-21 | 2020-08-21 | Neel Metal Products Ltd. Plt No. 1,2,5 & 6, TVS Industrial Estate, Harita, 635109, Hosur | 1 | 31 | 680 | Mr. Nishanth Bolar | 09307780598 | nishanth.bolar@jbmgroup.com | Mr. Sathish Narashiman | 08220007523 | sathish.narashiman@jbmgroup.com | - | - | - | - | 1 | 1 | 1 | Required | Not required |  | 1 | 0 | 0 |  | 1 | WO Close | 2020-08-12 | 2020-08-10 | 1 |  | Mr. Aniruddha Raut
689 | 2020-12-05 | 11:23:15 AM | sapl0313 | 1 | 8 | A004 | 718 | 720 | C1PO2021_000175 | 34 | 0 | S0189 | 2020-09-24 | Gun Rail System | Mr. Aniruddha Raut | 4 | 2020-09-01 | 2020-09-01 | 2020-09-03 | 2020-09-03 | 2020-09-04 | 2020-09-12 | 2020-09-12 | 2020-09-12 | 2020-09-14 | 2020-09-14 | 2020-09-15 | 2020-09-16 | 2020-09-14 | 2020-09-16 | 2020-09-14 | 2020-09-16 | Autoline Industries Ltd Gat No.291,Nanekarwadi,Chakan, Pune410501, Maharashtra, India. | 1 | 21 | 405 | Mr. Atmaram Ghogare | - | atmaram.ghogare@autolineind.com | Mr. Satish Satpute | 9890030485 | Satish.Satpute@autolineind.com | - | - | - | - | 1 | 1 | 1 | - | Packing with Bubble Sheets |  | 1 | 0 | 0 |  | 1 | WO Close | 2020-09-11 | 2020-09-07 | 1 |  | Mr. Aniruddha Raut
692 | 2020-12-05 | 11:23:40 AM | sapl0313 | 1 | 8 | A004 | 721 | 723 | C1PO2021_000283 | 34 | 0 | S0190 | 2020-10-05 | Gun Rail System | Mr. Aniruddha Raut | 4 | 2020-10-03 | 2020-10-03 | 2020-10-03 | 2020-10-03 | 2020-10-05 | 2020-10-08 | 2020-10-08 | 2020-10-08 | 2020-10-09 | 2020-10-09 | 2020-10-09 | 2020-10-10 | 2020-10-10 | 2020-10-10 | 2020-10-10 | 2020-10-10 | Autoline Industries Ltd. Gat No. 291 to 296, Nanekarwadi, Chakan, Pune410501, Maharashtra, India. | 1 | 21 | 405 | Mr. Satish Satpute | 9890030485 | satish.satpute@autolineind.com | Mr. Satish Satpute | 9890030485 | Satish.Satpute@autolineind.com | - | - | - | - | 1 | 1 | 1 | - | Packing with Bubble Sheets |  | 1 | 0 | 0 |  | 1 | WO Close | 2020-10-08 | 2020-10-06 | 1 |  | Mr. Aniruddha Raut
693 | 2020-12-19 | 10:19:32 AM | sapl0313 | 1 | 8 | T018 | 722 | 724 | 259834 | 38 | 0 | J0128 | 2020-10-06 | Cabinet Assembly | Mr. Amit Shedge | 22 | 2020-10-05 | 2020-10-05 | 2020-10-06 | 2020-10-06 | 2020-10-07 | 2020-10-10 | 2020-10-12 | 2020-10-12 | 2020-10-12 | 2020-10-12 | 2020-10-12 | 2020-10-13 | 2020-10-13 | 2020-10-13 | 2020-10-14 | 2020-10-14 | Gat no 3(part), 243(part), 5(part), Kasurdi (Kheba) Tal: Bhor Dist: Pune PIN: 412205 Ph: 02113 305 222/38/48 | 1 | 21 | 405 | Mr. Sandesh Udhane | 8888831614 | purchasem@tepl.co.in | Mr. Sandesh Udhane | 8888831614 | purchasem@tepl.co.in | - | - | - | - | 1 | 1 | 1 | - | Packing with Bubble Sheets |  | 0 | 1 | 1 |  | 0 | To get TPL | 2020-10-10 | 2020-10-07 | 1 |  | Mr. Amit Shedge
108 | 2013-08-28 | 5:06:09 PM | Sapl0005 | 1 | 1 | C002 | 109 | 120 | 10307781 | 38 | 0 | J0032 | 2013-07-17 | ROBO PEDESTALS | MILIND TERAWDE | 13 | 2013-07-13 | 2013-07-17 | 2013-07-18 | 2013-07-19 | 2013-07-20 | 2013-07-23 | 2013-07-24 | 2013-07-24 | 2013-07-25 | 2013-07-25 | 2013-07-22 | 2013-07-23 | 2013-07-26 | 2013-07-26 | 2013-07-23 | 2013-07-24 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | MANISH RAVAL | - | manish.raval@comau.com | SUJEET KULKARNI | 91206678036 | sujeet.kulkarni@comau.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-07-17 | 2013-07-17 | 1 |  | MILIND TERAWDE
157 | 2014-11-28 | 11:42:00 AM | Sapl0005 | 1 | 1 | C011 | 158 | 168 | IND2599029 | 36 | 0 | E0004 | 2013-09-17 | Installation & commissioning for 3rd line | HEMAKSH PATIL | 4 | 2013-09-17 | 2013-09-17 | 2013-09-17 | 2013-09-17 | 2013-09-17 | 2013-09-17 | 2013-09-17 | 2013-09-17 | 2013-09-17 | 2013-09-17 | 2013-09-17 | 2013-09-17 | 2013-09-17 | 2013-09-17 | 2013-09-17 | 2013-09-17 | Plot No.B-2 , Phaltan SEZ Industrial Area , Village-Nandal and Surawadi , Tal-Phaltan , Dist-Satara , 415523 , Maharashtra , India | 1 | 21 | 405 | SANDIP BHADANE | 9922434636 | sandip.v.bhadane@cummins.com | SANDIP BHADANE | 9922434636 | sandip.v.bhadane@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2013-09-17 | 2013-09-17 | 1 |  | HEMAKSH PATIL
190 | 2014-01-21 | 9:34:25 AM | Sapl0005 | 1 | 1 | S011 | 191 | 201 | PUOR13004311 | 34 | 0 | S0039 | 2014-01-04 | LONG RAIL C75, CROSS RAIL C75 & TROLLEY SET | RAJKUMAR JAGTAP | 2 | 2014-01-04 | 2014-01-06 | 2014-01-06 | 2014-01-11 | 2014-01-11 | 2014-01-11 | 2014-01-11 | 2014-01-11 | 2014-01-13 | 2014-01-13 | 2014-01-11 | 2014-01-11 | 2014-01-15 | 2014-01-17 | 2014-01-15 | 2014-01-15 | 690,, Udyambag,, Belgaum., Belgaum, PIN : . Karnataka, India | 1 | 17 | 295 | AMIT | 9844577876 | amit.k@shantiiron.net | M.N.PATIL | 831 4218328 | purchase@shantiiron.net | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2014-01-06 | 2014-01-06 | 1 |  | RAJKUMAR JAGTAP
198 | 2015-01-21 | 11:13:07 AM | Sapl0005 | 1 | 1 | T009 | 199 | 209 | 9000026913 | 35 | 0 | N0064 | 2014-01-18 | BodyTransfer Wagon for Super Ace & Venture | RAJKUMAR JAGTAP | 2 | 2014-01-18 | 2014-01-31 | 2014-02-01 | 2014-02-08 | 2014-02-08 | 2014-02-21 | 2014-03-08 | 2014-03-09 | 2014-03-10 | 2014-03-10 | 2014-02-21 | 2014-03-07 | 2014-03-17 | 2014-03-22 | 2014-03-07 | 2014-03-09 | TATA MOTORS LTD., PANTNAGAR | 1 | 34 | 679 | Mr. Anil Kumar Khan | 09258069747 | anil.khan@tatamotors.com | Mr. Naveen Kumar Singh | 9258072908 | naveen.singh@tatamotors.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-02-08 | 2014-02-08 | 1 |  | RAJKUMAR JAGTAP
201 | 2014-03-31 | 5:32:14 PM | Sapl0005 | 1 | 1 | A004 | 202 | 212 | C2_PO1314_ 002852 | 34 | 0 | S0042 | 2014-01-31 | LONG RAIL C63 & CROSS RAIL C63 | RAJKUMAR JAGTAP | 2 | 2014-01-31 | 2014-02-13 | 2014-02-13 | 2014-02-15 | 2014-02-15 | 2014-02-15 | 2014-02-15 | 2014-02-15 | 2014-02-15 | 2014-02-15 | 2014-02-15 | 2014-02-15 | 2014-02-15 | 2014-02-15 | 2014-02-15 | 2014-02-15 | Autoline Industries Limited (C2) S No. 313, 314, 320 to 323, Nanekarwadi, Chakan, Taluka Khed,, Pune410501, Maharastra, | 1 | 21 | 405 | Mr. Dnyaneshwar Phalke | 9970169842 | Dnyaneshwar.Phalke@autolineind.com | Mr. Arjun Patil | 9970399502 | Arjun.Patil@autolineind.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-02-05 | 2014-02-05 | 1 |  | RAJKUMAR JAGTAP
204 | 2017-07-21 | 10:01:31 AM | Sapl0005 | 1 | 1 | A004 | 205 | 215 | verbfeb | 34 | 0 | S0043 | 2014-02-10 | LONG RAIL C63 & CROSS RAIL C63 | RAJKUMAR JAGTAP | 2 | 2014-02-10 | 2014-02-12 | 2014-02-12 | 2014-02-13 | 2014-02-13 | 2014-02-13 | 2014-02-15 | 2014-02-15 | 2014-02-15 | 2014-02-15 | 2014-02-15 | 2014-02-15 | 2014-02-15 | 2014-02-17 | 2014-02-16 | 2014-02-16 | Autoline Industries Limited (C2) S No. 313, 314, 320 to 323, Nanekarwadi, Chakan, Taluka Khed,, Pune410501, Maharastra, | 1 | 21 | 405 | Arjun.Patil | 9970399502 | Arjun.Patil@autolineind.com | Dnyaneshwar.Phalke | 91 9970169842 | Dnyaneshwar.Phalke@autolineind.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | COMPLETE | 2014-02-12 | 2014-02-12 | 1 |  | RAJKUMAR JAGTAP
205 | 2014-03-31 | 5:35:16 PM | Sapl0005 | 1 | 1 | M019 | 206 | 216 | PO-MAS-2013-14-Q4-234R2 | 34 | 0 | S0044 | 2014-02-19 | LONG RAIL C75 & CROSS RAIL C75 | RAJKUMAR JAGTAP | 2 | 2014-02-19 | 2014-02-19 | 2014-02-20 | 2014-02-20 | 2014-02-20 | 2014-02-20 | 2014-02-20 | 2014-02-20 | 2014-02-21 | 2014-02-21 | 2014-02-20 | 2014-02-20 | 2014-02-22 | 2014-02-22 | 2014-02-21 | 2014-02-21 | S.No-30/8, Saraswati Ind. Estate,Shop No.-31 Dhayari Narhe Road,Near Prabhat Press,Dhayari,Pune – 411041, INDIA. | 1 | 21 | 405 | V. R. Bhanage | 09850068554 | purchase@micromatic.co.in | Santosh | 09767414253 | purchase@micromatic.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | COMPLETED | 2014-02-19 | 2014-02-19 | 1 |  | RAJKUMAR JAGTAP
228 | 2014-05-06 | 2:33:03 PM | Sapl0005 | 1 | 1 | A002 | 229 | 239 | Con¦2013¦04465 | 34 | 0 | S0048 | 2014-04-05 | Cable Balncer Trolley & Gun bal Hanging trolly | RAJKUMAR JAGTAP | 2 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | Anusaya Auto Press Parts Pvt. Ltd. Gat No.288,village-Mahalunge,Talegaon-Chakan Road Chakan ,Pune-410501 | 1 | 21 | 405 | Pudake S.N. | 09881700821 | snpudake@wadhokar.com | Pudake S.N. | 09881700821 | snpudake@wadhokar.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-04-05 | 2014-04-05 | 1 |  | RAJKUMAR JAGTAP
229 | 2014-05-06 | 2:33:51 PM | Sapl0005 | 1 | 1 | A002 | 230 | 240 | Con¦2013¦04464 | 34 | 0 | S0049 | 2014-04-05 | Cross rail C63 & Trolley Set | RAJKUMAR JAGTAP | 2 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 | Gat No.288,village-Mahalunge ,Talegaon-Chakan Road Chakan ,Pune-410501 | 1 | 21 | 405 | Pudake S.N. | 09881700821 | snpudake@wadhokar.com | Pudake S.N. | 09881700821 | snpudake@wadhokar.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | COMPLETE | 2014-04-05 | 2014-04-05 | 1 |  | RAJKUMAR JAGTAP
245 | 2014-06-03 | 4:55:26 PM | Sapl0005 | 1 | 2 | A028 | 247 | 256 | 7014000591 | 34 | 0 | S0055 | 2014-05-19 | LONG RAIL C63, CROSS RAIL C63 & TROLLEY SET | RAJKUMAR JAGTAP | 2 | 2014-05-19 | 2014-05-21 | 2014-05-21 | 2014-05-21 | 2014-05-21 | 2014-05-21 | 2014-05-21 | 2014-05-21 | 2014-05-21 | 2014-05-21 | 2014-05-21 | 2014-05-21 | 2014-05-21 | 2014-05-21 | 2014-05-21 | 2014-05-21 | AUTOCOMPS CORPORATION PANSE PVT LTD PlotNo.3/3, F-II Block, Pimpri Pune-411018. | 1 | 21 | 405 | YOGESH SHIRSAT | 7387103990 | papl1.purchase2@pansegroup.com | Yogesh Shirsat | 7387103990 | papl1.purchase2@pansegroup.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | COMPLETE | 2014-05-20 | 2014-05-20 | 1 |  | RAJKUMAR JAGTAP
246 | 2016-01-06 | 1:51:26 PM | Sapl0005 | 1 | 2 | A025 | 248 | 257 | alfverb | 35 | 0 | N0074 | 2014-05-19 | WELDING FIXTURES FOR REVA PROJECT | Kiran Kadam | 3 | 2014-05-19 | 2015-06-30 | 2014-06-05 | 2015-06-30 | 2014-06-16 | 2015-01-15 | 2014-06-30 | 2014-07-05 | 2014-07-05 | 2014-11-30 | 2014-06-23 | 2014-06-30 | 2014-06-30 | 2014-07-31 | 2014-06-30 | 2014-07-05 | ALF ENGINEERING PVT. LTD., HOSUR | 1 | 31 | 680 | VIVEK PATIL | - | vivekpatil@alfengineering.com | DINESH RAUT | 09325379844 | dineshraut@alfengineering.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-06-05 | 2014-06-05 | 1 |  | Kiran Kadam
255 | 2014-08-30 | 12:02:54 PM | Sapl0005 | 1 | 2 | J006 | 257 | 266 | 4300014490 | 34 | 0 | S0057 | 2014-06-12 | LONG RAIL C63 & CROSS RAIL C63 | RAJKUMAR JAGTAP | 2 | 2014-06-12 | 2014-06-24 | 2014-06-26 | 2014-06-26 | 2014-06-26 | 2014-06-26 | 2014-06-26 | 2014-06-26 | 2014-06-26 | 2014-06-26 | 2014-06-26 | 2014-06-26 | 2014-06-26 | 2014-06-26 | 2014-06-26 | 2014-06-26 | Jay Bharat Maruti Limited ( Plant -1) Plot No.5, Maruti Joint Venture Complex, Gurgaon. | 1 | 13 | 171 | jcpathak | - | jcpathak@jbm.co.in | JRS YADAV | 09891895554 | jyadav@jbm.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | COMPLETE | 2014-06-26 | 2014-06-26 | 1 |  | RAJKUMAR JAGTAP
258 | 2014-11-29 | 9:38:41 AM | Sapl0005 | 1 | 2 | C008 | 261 | 269 | IND2862851 | 37 | 0 | P0026 | 2014-06-18 | LAPP MAKE CABLE/ WIRE OF 1 SQ MM | HEMAKSH PATIL | 4 | 2014-06-18 | 2014-06-30 | 2014-07-01 | 2014-07-10 | 2014-07-10 | 2014-07-10 | 2014-07-10 | 2014-07-10 | 2014-08-12 | 2014-08-12 | 2014-07-10 | 2014-07-10 | 2014-07-10 | 2014-07-10 | 2014-08-12 | 2014-08-12 | CTIL, DTC, PUNE 411004 | 1 | 21 | 405 | SUJATA RANADE | +91 9552512174 | sujata.v.ranade@cummins.com | AMITKUMAR GURAV | +91 8378976291 | amitkumar.gurav@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-06-30 | 2014-06-30 | 1 |  | HEMAKSH PATIL
259 | 2014-11-29 | 9:39:04 AM | Sapl0005 | 1 | 2 | C008 | 262 | 270 | IND2863285 | 37 | 0 | P0027 | 2014-06-18 | LAPP MAKE CABLE/ WIRE OF 1 SQ MM & 0.75 SQ MM | HEMAKSH PATIL | 4 | 2014-06-18 | 2014-06-30 | 2014-07-01 | 2014-07-18 | 2014-07-18 | 2014-07-18 | 2014-07-18 | 2014-07-18 | 2014-08-12 | 2014-08-12 | 2014-07-18 | 2014-07-18 | 2014-07-18 | 2014-07-18 | 2014-08-12 | 2014-08-12 | CTIL, DTC , PUNE | 1 | 21 | 405 | SUJATA RANADE | +91 9552512174 | sujata.v.ranade@cummins.com | AMITKUMAR GURAV | +91 8378976291 | amitkumar.gurav@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-07-18 | 2014-07-18 | 1 |  | HEMAKSH PATIL
296 | 2014-12-08 | 2:29:39 PM | Sapl0005 | 1 | 2 | S011 | 299 | 308 | PUOR14003576 | 37 | 0 | P0030 | 2014-11-07 | BREAK COIL | HEMAKSH PATIL | 4 | 2014-11-07 | 2014-11-08 | 2014-11-08 | 2014-11-08 | 2014-11-08 | 2014-11-08 | 2014-11-08 | 2014-11-08 | 2014-11-08 | 2014-11-08 | 2014-11-08 | 2014-11-08 | 2014-11-08 | 2014-11-08 | 2014-11-08 | 2014-11-08 | 690, Udyambag Industrial Estate, BELGAUM - 590 008 KARNATAKA - INDIA | 1 | 17 | 295 | M.N.Patil | +91 831 4218328 | purchase@shantiiron.net | MULLA MOHAMMEDZEM M | 0831-2440972 | purchase@shantiiron.net | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-11-08 | 2014-11-08 | 1 |  | HEMAKSH PATIL
300 | 2015-03-05 | 2:52:14 PM | Sapl0005 | 1 | 2 | J017 | 303 | 312 | 4100039814 | 36 | 0 | E0017 | 2014-11-28 | Erection & Commissioning of Rail | RAJKUMAR JAGTAP | 2 | 2014-11-28 | 2014-11-28 | 2014-11-28 | 2014-11-28 | 2014-11-28 | 2014-11-28 | 2014-11-28 | 2014-11-28 | 2014-11-28 | 2014-11-28 | 2014-11-28 | 2014-11-28 | 2014-11-28 | 2014-11-28 | 2014-11-28 | 2014-11-28 | JBM Auto Limited 454775 Pithampur Distt. Dhar INDIA | 1 | 20 | 347 | amit.raghav | 8109075174 | amit.raghav@jbm.co.in | ROHIT RAKHEJA | 09999702774 | rohit.rakheja@jbm.co.in | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-11-28 | 2014-11-28 | 1 |  | RAJKUMAR JAGTAP
301 | 2015-03-05 | 2:52:19 PM | Sapl0005 | 1 | 2 | J017 | 304 | 313 | 4100039893 | 36 | 0 | E0018 | 2014-11-28 | Erection & Commissioning of Rail 195m | RAJKUMAR JAGTAP | 2 | 2014-11-28 | 2014-11-28 | 2014-11-28 | 2014-11-28 | 2014-11-28 | 2014-11-28 | 2014-11-28 | 2014-11-28 | 2014-11-28 | 2014-11-28 | 2014-11-28 | 2014-11-28 | 2014-11-28 | 2014-11-28 | 2014-11-28 | 2014-11-28 | JBM Auto Limited 454775 Pithampur Distt. Dhar INDIA | 1 | 20 | 347 | amit.raghav | 8109075174 | amit.raghav@jbm.co.in | ROHIT RAKHEJA | 09999702774 | rohit.rakheja@jbm.co.in | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-11-28 | 2014-11-28 | 1 |  | RAJKUMAR JAGTAP
302 | 2014-12-08 | 2:22:29 PM | Sapl0005 | 1 | 2 | A003 | 305 | 314 | 7014003001 | 34 | 0 | S0079 | 2014-12-01 | LONG RAIL C63, CROSS RAIL C63 & TROLLEY SET | RAJKUMAR JAGTAP | 2 | 2014-12-01 | 2014-12-04 | 2014-12-04 | 2014-12-04 | 2014-12-04 | 2014-12-04 | 2014-12-04 | 2014-12-04 | 2014-12-04 | 2014-12-04 | 2014-12-04 | 2014-12-04 | 2014-12-05 | 2014-12-05 | 2014-12-04 | 2014-12-04 | AUTOCOMPS CORPORATION PANSE PVT LTD UNIT-I GAT NO 392/2 CHAKAN TALEGOAN ROAD , TAL-KHED DIST-PUNE | 1 | 21 | 405 | sagar.jadhav | - | sagar.jadhav@pansegroup.com | YOGESH J. SHIRSAT | 7387103990 | papl1.purchase@pansegroup.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-12-02 | 2014-12-02 | 1 |  | RAJKUMAR JAGTAP
308 | 2017-07-21 | 10:04:39 AM | Sapl0005 | 1 | 2 | T002 | 311 | 321 | 2410191080 | 34 | 0 | S0080 | 2014-12-18 | RAIL TROLLY 565 X 125 FOR TCF LINE | RAJKUMAR JAGTAP | 2 | 2014-12-18 | 2014-12-23 | 2014-12-23 | 2014-12-25 | 2014-12-25 | 2014-12-30 | 2014-12-31 | 2015-01-01 | 2015-01-01 | 2015-01-02 | 2014-12-30 | 2014-12-31 | 2015-01-03 | 2015-01-05 | 2015-01-03 | 2015-01-03 | tata motors ltd., pune | 1 | 21 | 405 | ravindra.takawane | 8237008336 | ravindra.takawane@tatamotors.com | ravindra.takawane | 8237008336 | ravindra.takawane@tatamotors.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-12-20 | 2014-12-20 | 1 |  | RAJKUMAR JAGTAP
310 | 2015-02-28 | 10:22:33 AM | Sapl0005 | 1 | 2 | T002 | 313 | 323 | 9000028682 | 34 | 0 | S0082 | 2014-12-29 | 2T Hoist for Frame Inversion System at E6 Storme Frame Line | RAJKUMAR JAGTAP | 2 | 2014-12-29 | 2014-12-30 | 2014-12-31 | 2014-12-31 | 2014-12-31 | 2015-01-01 | 2015-01-02 | 2015-01-02 | 2015-01-02 | 2015-01-02 | 2014-12-31 | 2014-12-31 | 2015-01-03 | 2015-01-03 | 2015-01-02 | 2015-01-02 | tata motors ltd., pune | 1 | 21 | 405 | Nagesh Kulkarni | 9028097910 | nagesh.kulkarni@tatamotors.com | abhijit.medhekar | 020-6613 2426 | abhijit.medhekar@tatamotors.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-12-30 | 2014-12-30 | 1 |  | RAJKUMAR JAGTAP
314 | 2015-02-28 | 10:22:57 AM | Sapl0005 | 1 | 2 | A002 | 317 | 327 | Veranusaya | 34 | 0 | S0084 | 2015-01-07 | LONG RAIL & HOIST TROLLEY | RAJKUMAR JAGTAP | 2 | 2015-01-07 | 2015-01-24 | 2015-01-10 | 2015-01-24 | 2015-01-10 | 2015-01-10 | 2015-01-10 | 2015-01-10 | 2015-01-10 | 2015-01-10 | 2015-01-10 | 2015-01-10 | 2015-01-10 | 2015-01-10 | 2015-01-11 | 2015-01-11 | ANUSAYA AUTO PRESS PARTS , CHAKAN | 1 | 21 | 405 | HIREMATH | 9881700801 | marulesh2002@gmail.com | HIREMATH | 9881700801 | marulesh2002@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2015-01-07 | 2015-01-07 | 1 |  | RAJKUMAR JAGTAP
323 | 2016-11-03 | 10:38:10 AM | Sapl0005 | 1 | 2 | N005 | 326 | 336 | NH1 | 35 | 0 | N0094 | 2015-02-12 | C Class Fixtures Phase 2 | PADMASINHA JOSHI | 3 | 2015-02-05 | 2016-08-31 | 2015-02-15 | 2016-08-31 | 2015-02-26 | 2015-03-30 | 2015-03-20 | 2015-04-25 | 2015-04-15 | 2015-04-30 | 2015-03-10 | 2015-04-20 | 2015-03-20 | 2015-04-30 | 2015-03-20 | 2015-04-25 | New Holland Fiat India Pvt Ltd, Chakan | 1 | 21 | 405 | Manjunatha Reddy | 8130694938 | manjunatha.reddy@cnh.com | Devendra Pandey | 07722046658 | devendrakumar.pandey@cnhind.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2015-02-20 | 2015-02-20 | 1 |  | PADMASINHA JOSHI
324 | 2015-02-28 | 10:23:30 AM | Sapl0005 | 1 | 2 | A021 | 327 | 337 | 7014003719 | 34 | 0 | S0088 | 2015-02-13 | Trolley Set C75 | RAJKUMAR JAGTAP | 2 | 2015-02-13 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | GAT NO.198/200, VILLAGE-BORHADEWADI , DEHU-ALANDI ROAD , MOSHI, PUNE-412 114 | 1 | 21 | 405 | YOGESH SHIRSAT | 7387103990 | papl1.purchase@pansegroup.com | Yogesh Shirsat | 7387103990 | papl1.purchase@pansegroup.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-02-13 | 2015-02-13 | 1 |  | RAJKUMAR JAGTAP
325 | 2015-02-28 | 10:23:42 AM | Sapl0005 | 1 | 2 | A002 | 328 | 338 | Con¦2013¦0446\10 | 34 | 0 | S0089 | 2015-02-14 | long rail & trolley set | RAJKUMAR JAGTAP | 2 | 2015-02-14 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | Gat No.388,village-Mahalunge, Talegaon-Chakan Road Chakan ,Pune-410501 | 1 | 21 | 405 | M. S, Hiremath | 9881700801 | mshiremath@wadhokar.com | santosh pudake | 09881700821 | snpudake@wadhokar.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | COMPLETE | 2015-02-14 | 2015-02-14 | 1 |  | RAJKUMAR JAGTAP
326 | 2015-02-28 | 10:23:58 AM | Sapl0005 | 1 | 2 | A002 | 329 | 339 | Con¦2013¦0446/11 | 34 | 0 | S0090 | 2015-02-14 | Beam Clam & Joint Coupler | RAJKUMAR JAGTAP | 2 | 2015-02-14 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | 2015-02-16 | Gat No.388,village-Mahalunge, Talegaon-Chakan Road Chakan ,Pune-410501 | 1 | 21 | 405 | M.S. Hiremath | - | mshiremath@wadhokar.com | santosh pudake | 09881700821 | snpudake@wadhokar.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2015-02-16 | 2015-02-16 | 1 |  | RAJKUMAR JAGTAP
332 | 2015-04-24 | 9:41:32 AM | Sapl0005 | 1 | 2 | C004 | 335 | 345 | IND3107471 | 38 | 0 | J0067 | 2015-02-21 | TROLLEY | MILIND TERAWDE | 7 | 2015-02-21 | 2015-02-25 | 2015-02-26 | 2015-02-28 | 2015-03-01 | 2015-03-07 | 2015-03-11 | 2015-03-12 | 2015-03-13 | 2015-02-17 | 2015-03-07 | 2015-03-10 | 2015-03-18 | 2015-03-20 | 2015-03-18 | 2015-03-18 | CUMMINS INDIA LIMITED: CIL_EBU_085, KOTHRUD PUNE | 1 | 21 | 405 | MARY VYDANI | 7720048241 | mary.vydani@cummins.com | MARY VYDANI | 7720048241 | mary.vydani@cummins.com | - | - | - | - | 0 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-02-26 | 2015-02-26 | 1 |  | MILIND TERAWDE
360 | 2016-01-01 | 3:11:20 PM | Sapl0005 | 1 | 3 | C004 | 366 | 377 | IND3223769 | 38 | 0 | J0070 | 2015-06-17 | TACKLE FOR KV CYLINDER BLOCK FOR LIFTING KV BLOCK | RAJKUMAR JAGTAP | 2 | 2015-06-17 | 2015-06-22 | 2015-06-22 | 2015-06-26 | 2015-06-26 | 2015-06-29 | 2015-07-03 | 2015-07-07 | 2015-07-07 | 2015-07-09 | 2015-06-29 | 2015-07-03 | 2015-07-03 | 2015-07-11 | 2015-07-06 | 2015-07-09 | CUMMINS INDIA LTD., | 1 | 21 | 405 | Milind Bhagwat | 9850892902 | milind.v.bhagwat@cummins.com | PARAG PAWAR | 020-25385435 | parag.p.pawar@cummins.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2015-06-22 | 2015-06-22 | 1 |  | RAJKUMAR JAGTAP
362 | 2015-07-24 | 11:41:42 AM | Sapl0005 | 1 | 3 | J009 | 368 | 379 | JOAI/A/1500034 | 34 | 0 | S0098 | 2015-06-29 | LONG RAIL, CROSS RAIL & TROLLEY SET FOR C63 | RAJKUMAR JAGTAP | 2 | 2015-06-29 | 2015-07-01 | 2015-07-01 | 2015-07-01 | 2015-07-01 | 2015-07-01 | 2015-07-01 | 2015-07-01 | 2015-07-01 | 2015-07-01 | 2015-07-01 | 2015-07-01 | 2015-07-01 | 2015-07-01 | 2015-07-01 | 2015-07-01 | JOAI, BANGLORE | 1 | 17 | 293 | SHIVAPRASAD | 8066701050 | shivaprasad@joai.co.in | ARADHYE | 9916889090 | purchase@joai.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-07-01 | 2015-07-01 | 1 |  | RAJKUMAR JAGTAP
364 | 2016-11-03 | 11:20:27 AM | Sapl0005 | 1 | 3 | S011 | 370 | 381 | PUOR15001770 | 37 | 0 | P0035 | 2015-07-21 | BRAKE SHOE ASSY LH & RH | HEMAKSH PATIL | 4 | 2015-07-21 | 2015-07-21 | 2015-07-21 | 2015-07-21 | 2015-07-21 | 2015-07-21 | 2015-07-21 | 2015-07-21 | 2015-07-21 | 2015-07-21 | 2015-07-21 | 2015-07-21 | 2015-07-21 | 2015-07-21 | 2015-07-21 | 2015-07-21 | 690, Udyambag Industrial Estate, BELGAUM - 590 008 KARNATAKA - INDIA | 1 | 17 | 295 | M.N.Patil | 07899836618 | purchase@shantiiron.net | M.N.PATIL | 07899836618 | projects@shantiiron.net | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2015-07-21 | 2015-07-21 | 1 |  | HEMAKSH PATIL
377 | 2015-11-23 | 9:17:51 AM | Sapl0005 | 1 | 3 | V006 | 383 | 394 | PO/116283 | 34 | 0 | S0108 | 2015-10-02 | LONG RAIL CROSS RAIL, TROLLEY SET C75 | HEMAKSH PATIL | 2 | 2015-10-02 | 2015-10-05 | 2015-10-05 | 2015-10-21 | 2015-10-21 | 2015-10-21 | 2015-10-28 | 2015-10-29 | 2015-10-22 | 2015-10-22 | 2015-10-21 | 2015-10-21 | 2015-10-27 | 2015-10-28 | 2015-10-26 | 2015-10-26 | VCIPL, GAZIABAD | 1 | 34 | 611 | Sanket Goyal | 9599600584 | vcipl2000@gmail.com | Mohit Khatri | 9968939314 | vciplpurchase@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-10-05 | 2015-10-05 | 1 |  | HEMAKSH PATIL
378 | 2016-09-07 | 10:38:51 AM | Sapl0005 | 1 | 3 | M021 | 384 | 395 | MHEPL/MMP/3200099456 | 35 | 0 | N0111 | 2015-10-02 | Cutter Lifter Manipulator | HEMAKSH PATIL | 4 | 2015-10-02 | 2015-12-31 | 2015-10-10 | 2015-12-31 | 2015-10-28 | 2015-11-06 | 2015-11-14 | 2015-11-19 | 2015-11-20 | 2015-11-20 | 2015-11-06 | 2015-11-14 | 2015-11-14 | 2015-11-26 | 2015-11-16 | 2015-11-19 | mahindra heavy engine pvt. ltd. | 1 | 21 | 405 | PARTE.MAHENDRA | 022- 28849647 | PARTE.MAHENDRA@mahindra.com | CHANDA.RAM1 | 7768874094 | CHANDA.RAM1@mahindra.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2015-10-28 | 2015-10-28 | 1 |  | HEMAKSH PATIL
380 | 2018-08-03 | 11:37:38 AM | Sapl0005 | 1 | 3 | C004 | 386 | 397 | verboct2 | 35 | 0 | N0113 | 2016-05-12 | TOD for QSK & KV cylinder block | Dhananjay Sirsikar | 4 | 2016-05-12 | 2017-04-30 | 2016-05-16 | 2017-04-30 | 2016-05-20 | 2016-05-25 | 2016-05-31 | 2016-06-04 | 2016-06-06 | 2016-06-09 | 2016-05-25 | 2016-05-30 | 2016-05-31 | 2016-06-15 | 2016-05-31 | 2016-06-04 | Cummins India Ltd., Pune | 1 | 21 | 405 | Milind Bhagwat | 9850892902 | milind.v.bhagwat@cummins.com | Milind Bhagwat | 9850892902 | milind.v.bhagwat@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2016-05-21 | 2016-05-21 | 1 |  | Dhananjay Sirsikar
383 | 2015-11-16 | 11:44:20 AM | Sapl0005 | 1 | 3 | A031 | 389 | 400 | loi19SEP | 35 | 0 | N0116 | 2015-10-06 | Welddeck & Water / Air Pipe line for Magic Close Van | HEMAKSH PATIL | 2 | 2015-10-06 | 2015-10-31 | 2015-10-06 | 2015-10-31 | 2015-10-11 | 2015-10-14 | 2015-11-09 | 2015-11-13 | 2015-10-29 | 2015-10-29 | 2015-10-14 | 2015-10-14 | 2015-11-09 | 2015-11-08 | 2015-10-31 | 2015-10-31 | ASAL, PANTNAGAR | 1 | 34 | 679 | Shadul Shaikh | 7507263821 | Shadul.Shaikh@autostampings.com | Mohan.Datir | 9552550418 | Mohan.Datir@autostampings.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 1 |  | 1 | COMPLETE | 2015-10-06 | 2015-10-06 | 1 |  | HEMAKSH PATIL
384 | 2015-11-16 | 11:44:39 AM | Sapl0005 | 1 | 3 | A031 | 390 | 401 | loi30SEP | 35 | 0 | N0117 | 2015-10-06 | Welddeck & Water / Air Pipe line for O3 PROJECT | HEMAKSH PATIL | 2 | 2015-10-06 | 2015-10-30 | 2015-10-14 | 2015-10-31 | 2015-10-19 | 2015-10-23 | 2015-11-09 | 2015-11-13 | 2015-10-28 | 2015-10-29 | 2015-10-24 | 2015-10-27 | 2015-11-09 | 2015-11-08 | 2015-11-02 | 2015-11-02 | ASAL, PANTNAGAR | 1 | 34 | 679 | Shadul Shaikh | 7507263821 | Shadul.Shaikh@autostampings.com | Mohan.Datir | 9552550418 | Mohan.Datir@autostampings.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 1 |  | 1 | COMPLETE | 2015-10-07 | 2015-10-07 | 1 |  | HEMAKSH PATIL
385 | 2016-05-12 | 12:33:41 PM | Sapl0005 | 1 | 3 | A030 | 391 | 402 | VERBALSEP19 | 35 | 0 | N0118 | 2015-10-06 | WELDDECK FOR O2 Project | HEMAKSH PATIL | 2 | 2015-10-06 | 2015-10-31 | 2015-10-12 | 2015-10-31 | 2015-10-20 | 2015-10-26 | 2015-11-05 | 2015-11-07 | 2015-10-29 | 2015-10-29 | 2015-10-27 | 2015-10-28 | 2015-11-05 | 2015-11-04 | 2015-11-01 | 2015-12-02 | ASAL, CHAKAN | 1 | 21 | 405 | Shadul Shaikh | 7507263821 | Shadul.Shaikh@autostampings.com | Mohan.Datir | 9552550418 | Mohan.Datir@autostampings.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 1 |  | 1 | COMPLETE | 2015-10-06 | 2015-10-06 | 1 |  | HEMAKSH PATIL
386 | 2015-11-16 | 11:45:04 AM | Sapl0005 | 1 | 3 | A007 | 392 | 403 | VERBALSEP192 | 35 | 0 | N0119 | 2015-10-06 | WELDDECK FOR O2 Project, BHOSARI | HEMAKSH PATIL | 2 | 2015-10-06 | 2015-10-31 | 2015-10-11 | 2015-10-31 | 2015-10-21 | 2015-10-24 | 2015-11-05 | 2015-11-07 | 2015-10-28 | 2015-10-29 | 2015-10-25 | 2015-10-27 | 2015-11-05 | 2015-11-05 | 2015-10-31 | 2015-11-01 | ASAL, BHOSARI | 1 | 21 | 405 | Shadul Shaikh | 7507263821 | Shadul.Shaikh@autostampings.com | Mohan.Datir | 9552550418 | Mohan.Datir@autostampings.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 1 |  | 1 | COMPLETE | 2015-10-06 | 2015-10-06 | 1 |  | HEMAKSH PATIL
387 | 2015-11-23 | 9:19:04 AM | Sapl0005 | 1 | 3 | A007 | 393 | 404 | verbalrail | 34 | 0 | S0109 | 2015-10-08 | Gunrail system for welddeck O2 project, Bhosari | HEMAKSH PATIL | 2 | 2015-10-08 | 2015-10-10 | 2015-10-11 | 2015-10-14 | 2015-10-15 | 2015-10-17 | 2015-10-30 | 2015-10-31 | 2015-10-21 | 2015-10-22 | 2015-10-18 | 2015-10-20 | 2015-10-30 | 2015-10-29 | 2015-10-22 | 2015-10-22 | ASAL, BHOSARI | 1 | 21 | 405 | Shadul Shaikh | 7507263821 | Shadul.Shaikh@autostampings.com | Mohan.Datir | 9552550418 | Mohan.Datir@autostampings.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-10-08 | 2015-10-08 | 1 |  | HEMAKSH PATIL
388 | 2016-02-08 | 9:56:12 AM | Sapl0005 | 1 | 3 | A030 | 394 | 405 | VEROCT9 | 34 | 0 | S0110 | 2015-10-09 | RAILS FOR WINDSHIELD PROJECT | HEMAKSH PATIL | 2 | 2015-10-09 | 2015-10-13 | 2015-10-13 | 2015-10-16 | 2015-10-16 | 2015-10-19 | 2015-10-30 | 2015-10-31 | 2015-10-24 | 2015-10-27 | 2015-10-19 | 2015-10-23 | 2015-10-28 | 2015-10-30 | 2015-10-27 | 2015-10-27 | ASAL, CHAKAN | 1 | 21 | 405 | Shadul Shaikh | 7507263821 | Shadul.Shaikh@autostampings.com | Mohan.Datir | 9552550418 | Mohan.Datir@autostampings.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-10-13 | 2015-10-13 | 1 |  | HEMAKSH PATIL
389 | 2015-11-23 | 9:19:34 AM | Sapl0005 | 1 | 3 | A030 | 395 | 406 | VEROCT1 | 34 | 0 | S0111 | 2015-10-09 | RAILS FOR O2 PROJECT CHAKAN | HEMAKSH PATIL | 2 | 2015-10-09 | 2015-10-12 | 2015-10-13 | 2015-10-15 | 2015-10-16 | 2015-10-19 | 2015-10-29 | 2015-10-31 | 2015-10-22 | 2015-10-24 | 2015-10-19 | 2015-10-21 | 2015-10-27 | 2015-10-30 | 2015-10-26 | 2015-10-26 | ASAL CHAKAN | 1 | 21 | 405 | Shadul Shaikh | 7507263821 | Shadul.Shaikh@autostampings.com | Mohan.Datir | 9552550418 | Mohan.Datir@autostampings.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-10-14 | 2015-10-14 | 1 |  | HEMAKSH PATIL
390 | 2016-02-08 | 9:55:27 AM | Sapl0005 | 1 | 3 | A031 | 396 | 407 | verbalrailOCT2 | 34 | 0 | S0112 | 2015-10-09 | Gunrail system for welddeck O3 project, | HEMAKSH PATIL | 2 | 2015-10-09 | 2015-10-12 | 2015-10-13 | 2015-10-15 | 2015-10-16 | 2015-10-19 | 2015-10-30 | 2015-10-31 | 2015-10-24 | 2015-10-26 | 2015-10-20 | 2015-10-23 | 2015-10-27 | 2015-10-30 | 2015-10-26 | 2015-10-26 | ASAL, PANTNAGAR | 1 | 34 | 679 | Shadul Shaikh | 7507263821 | Shadul.Shaikh@autostampings.com | Mohan.Datir | 9552550418 | Mohan.Datir@autostampings.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-10-09 | 2015-10-09 | 1 |  | HEMAKSH PATIL
391 | 2015-11-23 | 9:20:26 AM | Sapl0005 | 1 | 3 | A031 | 397 | 408 | verbalrailOCT3 | 34 | 0 | S0113 | 2015-10-09 | RAILS FOR MAGIC CLOSE VAN PROJECT | HEMAKSH PATIL | 2 | 2015-10-09 | 2015-10-12 | 2015-10-12 | 2015-10-14 | 2015-10-14 | 2015-10-17 | 2015-10-30 | 2015-10-31 | 2015-10-22 | 2015-10-23 | 2015-10-19 | 2015-10-21 | 2015-10-27 | 2015-10-30 | 2015-10-26 | 2015-10-26 | ASAL, PANTNAGAR | 1 | 34 | 679 | Shadul Shaikh | 7507263821 | Shadul.Shaikh@autostampings.com | Mohan.Datir | 9552550418 | Mohan.Datir@autostampings.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-10-09 | 2015-10-09 | 1 |  | HEMAKSH PATIL
392 | 2016-02-08 | 9:56:50 AM | Sapl0005 | 1 | 3 | A030 | 398 | 409 | VERB34 | 34 | 0 | S0114 | 2015-10-09 | Gunrail system for X104 BIW project, CHAKAN | HEMAKSH PATIL | 2 | 2015-10-09 | 2015-10-12 | 2015-10-12 | 2015-10-14 | 2015-10-14 | 2015-10-16 | 2015-10-29 | 2015-10-31 | 2015-10-20 | 2015-10-22 | 2015-10-16 | 2015-10-19 | 2015-10-24 | 2015-10-29 | 2015-10-23 | 2015-10-23 | Asal , chakan | 1 | 34 | 679 | Shadul Shaikh | 7507263821 | Shadul.Shaikh@autostampings.com | Mohan.Datir | 9552550418 | Mohan.Datir@autostampings.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-10-09 | 2015-10-09 | 1 |  | HEMAKSH PATIL
396 | 2016-03-31 | 11:14:31 AM | Sapl0005 | 1 | 3 | J014 | 403 | 413 | 4300021014 | 34 | 0 | S0116 | 2015-11-17 | Rails & trolley set C63 | HEMAKSH PATIL | 7 | 2015-11-17 | 2015-11-19 | 2015-11-19 | 2015-11-20 | 2015-11-20 | 2015-11-21 | 2015-11-23 | 2015-11-23 | 2015-11-23 | 2015-11-23 | 2015-11-21 | 2015-11-22 | 2015-11-24 | 2015-11-25 | 2015-11-24 | 2015-11-24 | JBM AUTO LIMITED Plot No:SP1-891,RIICO Ind. Area, 303107 Pathredi (Alwar-Rajasthan) INDIA | 1 | 29 | 500 | jaswant.singh | 7728884956 | jaswant.singh1@jbm.co.in | Jitender.Yadav | 9899143035 | Jitender.Yadav@jbm.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-11-17 | 2015-11-17 | 1 |  | HEMAKSH PATIL
401 | 2015-12-08 | 10:34:36 AM | Sapl0005 | 1 | 3 | N006 | 409 | 420 | NPES/15-16/001 | 34 | 0 | S0119 | 2015-12-01 | C63 RAILS & TROLLEY SET | HEMAKSH PATIL | 7 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-02 | 2015-12-02 | 2015-12-01 | 2015-12-01 | 2015-12-04 | 2015-12-04 | 2015-12-04 | 2015-12-04 | Peenya Indl. Area, near NTTF, Peenya 4th phase, BENGALOORU-560058. | 1 | 17 | 293 | RAYBAGI | 918722248998. | npenggservices@yahoo.com | RAYBAGI | 919448048998 | npenggservices@yahoo.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-12-01 | 2015-12-01 | 1 |  | HEMAKSH PATIL
405 | 2016-02-08 | 9:43:37 AM | Sapl0005 | 1 | 3 | C004 | 413 | 424 | IND3409729 | 38 | 0 | J0073 | 2015-12-09 | Fixture for con rod | HEMAKSH PATIL | 2 | 2015-12-09 | 2015-12-10 | 2015-12-10 | 2015-12-11 | 2015-12-11 | 2015-12-14 | 2015-12-18 | 2015-12-18 | 2015-12-18 | 2015-12-18 | 2015-12-15 | 2015-12-17 | 2015-12-18 | 2015-12-18 | 2015-12-18 | 2015-12-18 | Dahanukar Colony, Kothrud, Pune 411038 | 1 | 21 | 405 | Asis sahoo | 8805362400 | asiskumar.sahoo@cummins.com | mary.vydani | 7720048241 | mary.vydani@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | cmplete | 2015-12-10 | 2015-12-10 | 1 |  | HEMAKSH PATIL
409 | 2016-02-08 | 10:04:50 AM | Sapl0005 | 1 | 3 | M022 | 417 | 428 | PO/2015-16/002/432 | 38 | 0 | J0074 | 2015-12-17 | Machining Parts Thermo forming machine | HEMAKSH PATIL | 7 | 2015-12-17 | 2015-12-31 | 2015-12-18 | 2015-12-31 | 2015-12-18 | 2015-12-31 | 2015-12-18 | 2015-12-31 | 2015-12-19 | 2015-12-31 | 2015-12-18 | 2015-12-31 | 2015-12-18 | 2015-12-31 | 2015-12-18 | 2015-12-31 | Mirhae Engineering India Pvt Ltd S.No.79, Besides ICD Dighi, Pune Alandi Road, Pune-411015. | 1 | 21 | 405 | Atul Kulkarni | 8408883798 | kulkarni.a@mirhaeindia.com | Iqbal S Sayyad | 8554983599 | iqbal.s@mirhaeindia.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2015-12-31 | 2015-12-31 | 1 |  | HEMAKSH PATIL
410 | 2016-05-12 | 12:22:30 PM | Sapl0005 | 1 | 3 | M022 | 418 | 429 | PO/2015-16/002/449 | 38 | 0 | J0075 | 2015-12-17 | MACHINING PARTS | HEMAKSH PATIL | 7 | 2015-12-17 | 2015-12-31 | 2015-12-18 | 2015-12-31 | 2015-12-20 | 2015-12-31 | 2015-12-22 | 2015-12-31 | 2015-12-23 | 2015-12-31 | 2015-12-22 | 2015-12-31 | 2015-12-22 | 2015-12-31 | 2015-12-23 | 2015-12-31 | S.No.79, Besides ICD Dighi, Pune Alandi Road, Pune-411015. | 1 | 21 | 405 | iqbal.s | 8554983599 | iqbal.s@mirhaeindia.com | atul.k | 8408883798 | atul.k@mirhaeindia.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | 2 jobs cancelled | 2015-12-18 | 2015-12-18 | 1 |  | HEMAKSH PATIL
413 | 2016-01-01 | 3:08:25 PM | Sapl0005 | 1 | 3 | J014 | 421 | 432 | 4100053625 | 36 | 0 | E0027 | 2015-12-31 | I&C of rails | HEMAKSH PATIL | 2 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | JBM AUTO LTD., Plot No:SP1-891,RIICO Ind. Area, 303107 Pathredi (Alwar-Rajasthan) | 1 | 29 | 500 | jaswant singh | +91-7728884956 | jaswant.singh1@jbm.co.in | jaswant singh | +91-7728884956 | jaswant.singh1@jbm.co.in | - | - | - | - | 0 | 0 | 0 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2015-12-31 | 2015-12-31 | 1 |  | HEMAKSH PATIL
429 | 2017-07-21 | 10:14:09 AM | Sapl0005 | 1 | 3 | A029 | 437 | 448 | MH_PO1516_ 001835 | 35 | 0 | N0128 | 2016-02-11 | Welding Fixture for Y1 Project | HEMAKSH PATIL | 3 | 2016-02-11 | 2016-04-30 | 2016-02-18 | 2016-04-30 | 2016-02-23 | 2016-02-27 | 2016-03-06 | 2016-03-11 | 2016-03-12 | 2016-03-16 | 2016-02-28 | 2016-03-05 | 2016-03-06 | 2016-03-23 | 2016-03-07 | 2016-03-10 | Autoline Industries Limited (MH) Gat No . 613/2 , Chakan Talegaon Road, Mahalunge , Tal Khed | 1 | 21 | 405 | sujeet.chaskar | 9561086430 | sujeet.chaskar@autolineind.com | Faiyaz.Kashi | 98 90 675845 | Faiyaz.Kashi@autolineind.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2016-02-22 | 2016-02-22 | 1 |  | HEMAKSH PATIL
443 | 2016-11-03 | 10:23:57 AM | Sapl0005 | 1 | 4 | C004 | 451 | 462 | IND3545856 | 38 | 0 | J0079 | 2016-05-04 | HOLDING FIXTURE | Milind Terwade | 5 | 2016-05-04 | 2016-05-14 | 2016-05-06 | 2016-05-14 | 2016-05-09 | 2016-05-10 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-09 | 2016-05-10 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | kothrud | 1 | 21 | 405 | Asis sahoo | 8805362400 | asiskumar.sahoo@cummins.com | mary.vydani | 7720048241 | mary.vydani@cummins.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 1 | COMPLETE | 2016-05-07 | 2016-05-07 | 1 |  | Milind Terwade
444 | 2016-05-12 | 12:30:07 PM | Sapl0005 | 1 | 4 | A015 | 452 | 463 | PO116000135 | 37 | 0 | P0040 | 2016-05-06 | Brake Coil | Dhananjay Sirsikar | 4 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | ALF ENGINEERING PVT LTD-UNIT-1 Plot No. E-60/61/62,, MIDC,, Ambad,, Nasik, PIN : 422010. | 1 | 21 | 402 | ANIL PATIL | 0253-66228831 | sujitnair@alfengineering.com | ANIL PATIL | 0253-66228831 | sujitnair@alfengineering.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-05-06 | 2016-05-06 | 1 |  | Dhananjay Sirsikar
446 | 2016-09-07 | 10:43:01 AM | Sapl0005 | 1 | 4 | A019 | 454 | 465 | 7016000952 | 34 | 0 | S0135 | 2016-05-11 | TROLLEY SET C63 | Dhananjay Sirsikar | 7 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-13 | 2016-05-13 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | Autocomp Corporation Panse Pvt. Ltd Plot No 38-39 Sector 11,IIE Pantnagar,Udham Shingh Nagar,(Rudrapur) Ut tarakhand-263153 | 1 | 34 | 679 | adyadav | 9557790780 | adyadav@pansegroup.com | sandeep | 9557790934 | skarya@pansegroup.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-05-11 | 2016-05-11 | 1 |  | Dhananjay Sirsikar
451 | 2017-07-21 | 10:13:44 AM | Sapl0005 | 1 | 4 | K008 | 460 | 470 | 4200004894 | 35 | 0 | N0133 | 2016-08-19 | Welding Fixtures For GM tavera | Prajyot Genji | 3 | 2016-08-19 | 2016-10-31 | 2016-08-22 | 2016-10-31 | 2016-08-25 | 2016-08-30 | 2016-09-05 | 2016-09-07 | 2016-09-08 | 2016-09-10 | 2016-08-31 | 2016-09-03 | 2016-09-05 | 2016-09-15 | 2016-09-07 | 2016-09-10 | KLT Automotive & Tubular Products Ltd.TAAL - Halol Plant Plot No.2014 389351 | 1 | 12 | 157 | tushar.mane | 9167620197 | tushar.mane@kltgroup.net | Jaydeep Vora | 7878240005 | project.halol@kltgroup.net | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 1 | COMPLETE | 2016-08-19 | 2016-08-19 | 1 |  | Prajyot Genji
467 | 2016-11-03 | 10:26:46 AM | Sapl0005 | 1 | 4 | C004 | 476 | 486 | IND3648524 | 38 | 0 | J0087 | 2016-08-24 | Machining services of MS bracket | SANJAY SHINDE | 5 | 2016-08-24 | 2016-08-25 | 2016-08-25 | 2016-08-26 | 2016-08-26 | 2016-08-30 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-08-30 | 2016-09-01 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | cummins india, kothrud | 1 | 21 | 405 | MARY VYDANI | 7720048241 | mary.vydani@cummins.com | MARY VYDANI | 7720048241 | mary.vydani@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-08-26 | 2016-08-26 | 1 |  | SANJAY SHINDE
481 | 2016-11-03 | 11:26:14 AM | Sapl0005 | 1 | 4 | N008 | 492 | 501 | 4300024944 | 34 | 0 | S0140 | 2016-09-19 | Long Rail C63 , Cross Rail C63 & Trolley Set C63 | Sagar Ravtale | 7 | 2016-09-19 | 2016-09-19 | 2016-09-20 | 2016-09-20 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | Neel Metal Product Limited Sector-36, Mohmmedpur Jharsa 122001 Gurgaon | 1 | 13 | 171 | Dinesh.Kumar-NMPL | 9999189678 | Dinesh.Kumar-NMPL@Jbm.co.in | Dinesh.Kumar-NMPL | 9999189678 | Dinesh.Kumar-NMPL@Jbm.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2016-09-20 | 2016-09-20 | 1 |  | Sagar Ravtale
487 | 2017-03-13 | 10:52:46 AM | Sapl0005 | 1 | 4 | C016 | 498 | 507 | IND3707946 | 35 | 0 | N0145 | 2016-10-26 | Powerised Roller Conveyor & Hydraulic tilter | Tanaji Sawant | 2 | 2016-10-26 | 2016-12-31 | 2016-11-03 | 2016-12-31 | 2016-11-06 | 2016-11-11 | 2016-11-17 | 2016-11-19 | 2016-11-21 | 2016-11-25 | 2016-11-11 | 2016-11-16 | 2016-11-17 | 2016-11-30 | 2016-11-21 | 2016-11-25 | Cummins Generator Technologies India Private Limited.:G-06, Ranjangaon MIDC,:Tal - Shirur, Pune Maharashtra 412220 India | 1 | 21 | 405 | Lovepreet Gumber | - | ns818@cummins.com | vijendra.yadav | 722092596 | vijendra.yadav@cummins.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2016-11-04 | 2016-11-04 | 1 |  | Tanaji Sawant
514 | 2021-01-05 | 11:50:16 AM | Sapl0331 | 1 | 4 | S029 | 525 | 534 | verb_28 | 35 | 0 | N0157 | 2017-02-28 | Auger sampling system (primary sampling) | Prajyot Genji | 3 | 2017-02-28 | 2017-12-30 | 2017-03-11 | 2017-12-30 | 2017-03-27 | 2017-04-15 | 2017-04-24 | 2017-04-27 | 2017-05-05 | 2017-05-05 | 2017-04-06 | 2017-04-24 | 2017-04-24 | 2017-05-25 | 2017-04-24 | 2017-04-27 | Ahmed Plaza,No 38/1 & 38/2, Bertenna Agrahara, Hosur Road (Next to Metro Cash & Carry) Begur Hobli,Bangalore - 560 100, Karnataka, India | 1 | 17 | 293 | Mahantesh Ghivari | 9620 73 22 29 | Mahantesh.Ghivari@sgs.com | Jagannath.Nilwani | 7738392831 | Jagannath.Nilwani@sgs.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | close | 2017-03-27 | 2017-03-27 | 1 |  | Prajyot Genji
515 | 2021-01-05 | 11:50:35 AM | Sapl0331 | 1 | 4 | S029 | 526 | 535 | verb_28feb | 35 | 0 | N0158 | 2017-02-28 | Sample Preparation Unit | Prajyot Genji | 3 | 2017-02-28 | 2017-12-30 | 2017-03-11 | 2017-12-30 | 2017-03-27 | 2017-04-15 | 2017-04-24 | 2017-04-27 | 2017-05-05 | 2017-05-05 | 2017-04-06 | 2017-04-24 | 2017-04-24 | 2017-05-25 | 2017-04-24 | 2017-04-27 | Ahmed Plaza,No 38/1 & 38/2, Bertenna Agrahara, Hosur Road (Next to Metro Cash & Carry) Begur Hobli,Bangalore - 560 100, Karnataka, India | 1 | 17 | 293 | Mahantesh Ghivari | 9620 73 22 29 | Mahantesh.Ghivari@sgs.com | Jagannath.Nilwani | 7738392831 | Jagannath.Nilwani@sgs.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | close | 2017-03-27 | 2017-03-27 | 1 |  | Prajyot Genji
516 | 2017-03-13 | 10:40:45 AM | Sapl0005 | 1 | 4 | T016 | 527 | 536 | 12 | 34 | 0 | S0150 | 2017-03-01 | Long rail c63 & load trolley | Sagar Ravtale | 2 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | Techexpert Engineering Pvt.Ltd. 78, Shivane Industrial Area, Shivane, Off NDA Road, Pune -411023 | 1 | 21 | 405 | JV Ingale | 9890013871 | jvi@techexpertindia.com | Pankaj Jadhav | 9168608340 | info@techexpertindia.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2017-03-01 | 2017-03-01 | 1 |  | Sagar Ravtale
518 | 2017-03-13 | 10:33:39 AM | Sapl0005 | 1 | 4 | A015 | 529 | 538 | PO116001451 | 37 | 0 | P0043 | 2017-03-08 | HOIST SPARES | Amit Shedge | 4 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | Plot No. E-60/61/62,, MIDC,, Ambad,, Nasik, PIN : 422010. Maharashtra, India | 1 | 21 | 402 | ANIL PATIL | 0253-6628831 | sujitnair@alfengineering.com | ANIL PATIL | 0253-6628831 | sujitnair@alfengineering.com | - | - | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2017-03-08 | 2017-03-08 | 1 |  | Amit Shedge
525 | 2017-09-21 | 11:07:17 AM | Sapl0005 | 1 | 5 | T002 | 536 | 545 | 2410221089 | 34 | 0 | S0151 | 2017-04-29 | RAIL TROLLY 565 X 125 FOR TCF LINE | Sagar Ravtale | 2 | 2017-04-29 | 2017-05-05 | 2017-05-05 | 2017-05-12 | 2017-05-13 | 2017-05-20 | 2017-05-27 | 2017-05-30 | 2017-05-31 | 2017-05-31 | 2017-05-20 | 2017-05-26 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | CV PUN Auto Maint Tata Motors Ltd. Pune | 1 | 21 | 405 | sachin.surve | 91 7276097552 | sachin.surve@tatamotors.com | Nita.Patil | 91 20 6613 3003 | Nita.Patil@tatamotors.com | - | - | - | - | 0 | 0 | 0 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2017-05-06 | 2017-05-06 | 1 |  | Sagar Ravtale
611 | 2019-12-29 | 5:18:37 PM | Sapl0002 | 1 | 6 | C004 | 640 | 638 | IND4398340 | 38 | 0 | J0111 | 2018-12-21 | SS Tray for Cradle Type TOD for KV Cylinder Block for Standard Rework work station | PADMASINHA JOSHI | 3 | 2018-12-03 | 2018-12-05 | 2018-12-06 | 2018-12-08 | 2018-12-10 | 2018-12-17 | 2018-12-21 | 2018-12-22 | 2018-12-24 | 2018-12-25 | 2018-12-17 | 2018-12-20 | 2018-12-21 | 2018-12-26 | 2018-12-27 | 2018-12-27 | CIL KOTHRUD:: Pune Maharashtra 411038 India | 1 | 21 | 405 | Milind v Bhagwat | 9850892902 | milind.v.bhagwat@cummins.com | S D SHINDE | 9850997209 | sdshinde@synergytechs.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2018-12-14 | 2018-12-15 | 1 |  | PADMASINHA JOSHI
612 | 2020-12-05 | 11:17:39 AM | sapl0313 | 1 | 6 | N003 | 641 | 639 | 4300036525 | 34 | 0 | S0173 | 2018-12-21 | Railing Sapres | PADMASINHA JOSHI | 3 | 2018-12-19 | 2018-12-20 | 2018-12-20 | 2018-12-22 | 2018-12-24 | 2018-12-31 | 2019-01-05 | 2019-01-06 | 2019-01-07 | 2019-01-08 | 2019-01-01 | 2019-01-04 | 2019-01-10 | 2019-01-10 | 2019-01-11 | 2019-01-11 | Neel auto pvt ltd. 789/1 anekal road, poonapalli village houser Belagondapalli Post Krishnagiri. | 1 | 21 | 405 | Nishanth Bolar | 9003342354 | naplhub.purchase1@jbmgroup.com | S D SHINDE | 9850997209 | sdshinde@synergytechs.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | WO Close | 2018-12-27 | 2018-12-26 | 1 |  | PADMASINHA JOSHI
633 | 2020-12-05 | 10:59:43 AM | sapl0313 | 1 | 7 | C015 | 660 | 659 | IND6172003 | 35 | 0 | N0200 | 2019-05-21 | Draw Bridge for test cell | MR.PRASHANT SURYAWANSHI | 5 | 2019-05-21 | 2019-06-22 | 2019-06-24 | 2019-06-26 | 2019-06-26 | 2019-07-10 | 2019-07-10 | 2019-07-13 | 2019-07-15 | 2019-07-17 | 2019-07-17 | 2019-07-17 | 2019-07-17 | 2019-07-17 | 2019-07-17 | 2019-07-17 | Cummins Technologies India Pvt. Ltd.: Phaltan High Horsepower Plant, SEZ Unit:Plot No. B3/1, MIDC SEZ-Phaltan | 1 | 21 | 405 | Mr.Rajesh Sangar | 020 30233677 | rajesh.m.sangar@cummins.com | Mr.Rajesh Sangar | 020 30233677 | rajesh.m.sangar@cummins.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | WO Close | 2019-07-04 | 2019-07-05 | 1 |  | MR.PRASHANT SURYAWANSHI
645 | 2020-12-05 | 11:15:10 AM | sapl0313 | 1 | 7 | O002 | 673 | 671 | PO/2019/001073 | 37 | 0 | P0057 | 2019-07-03 | Spares Hardware | Mr. S Shinde | 15 | 2019-07-03 | 2019-07-03 | 2019-07-03 | 2019-07-03 | 2019-07-03 | 2019-07-03 | 2019-07-03 | 2019-07-03 | 2019-07-03 | 2019-07-03 | 2019-07-03 | 2019-07-03 | 2019-07-03 | 2019-07-03 | 2019-07-03 | 2019-07-03 | OLCI | 1 | 21 | 405 | Subhash Tapkir | 8007020509 | subhash.tapkir@olcieng.co.in | AMIT KOKANE | 8888809426 | amit.kokane@olcieng.co.in | - | - | - | - | 0 | 0 | 0 | - | - |  | 1 | 0 | 0 |  | 1 | WO Close | 2019-07-03 | 2019-07-03 | 1 |  | Mr. S Shinde
652 | 2020-12-05 | 11:01:32 AM | sapl0313 | 1 | 7 | C015 | 680 | 681 | IND6283279 | 35 | 0 | N0205 | 2019-09-25 | Modification in Rigging and De Rigging Stations | Mr. Sanjay D Shinde | 3 | 2019-09-23 | 2019-09-26 | 2019-09-26 | 2019-09-27 | 2019-09-27 | 2019-10-20 | 2019-10-04 | 2019-10-21 | 2019-10-07 | 2019-10-24 | 2019-10-07 | 2019-10-24 | 2019-10-02 | 2019-10-25 | 2019-09-02 | 2019-10-19 | Cummins Technologies India Pvt. Ltd. Phaltan High Horsepower Plant, SEZ Unit Plot No. B3/1, MIDC SEZ-Phaltan | 1 | 21 | 405 | Mr. Rajesh Sangar | 9881151559 | rajesh.m.sangar@cummins.com | - | 9881151559 | rajesh.m.sangar@cummins.com | - | - | - | - | 1 | 1 | 1 | Painting, Packing with Bubble sheets & Transport in Our Scope | - |  | 1 | 0 | 1 |  | 1 | WO Close | 2019-10-05 | 2019-10-05 | 1 |  | Mr. Sanjay D Shinde
653 | 2020-12-05 | 11:01:55 AM | sapl0313 | 1 | 7 | C015 | 681 | 682 | IND6288991 | 35 | 0 | N0206 | 2019-09-25 | Safety wire ropes with suitable clamps with Installation and prove out | Mr. Sanjay D Shinde | 2 | 2019-09-26 | 2019-09-26 | 2019-09-26 | 2019-09-26 | 2019-09-26 | 2019-09-28 | 2019-09-30 | 2019-10-02 | 2019-09-30 | 2019-09-30 | 2019-09-30 | 2019-10-05 | 2019-09-30 | 2019-10-05 | 2019-09-30 | 2019-10-05 | Cummins Technologies India Pvt. Ltd.: Phaltan High Horsepower Plant, SEZ Unit: Plot No. B3/1, MIDC SEZ-Phaltan | 1 | 21 | 405 | Mr. Vinod Pore | 9552048487 | vinod.pore@cummins.com | Mr. Vinod Pore | 9552048487 | vinod.pore@cummins.com | - | - | - | - | 1 | 1 | 1 | Packing with Bubble Sheet and Transport, installation and commissioning in SAPL Scope. | - |  | 1 | 0 | 1 |  | 1 | WO Close | 2019-09-26 | 2019-09-27 | 1 |  | Mr. Sanjay D Shinde
656 | 2020-12-05 | 11:03:06 AM | sapl0313 | 1 | 7 | C004 | 684 | 687 | IND6206730 | 35 | 0 | N0209 | 2019-11-04 | Assy. Guide Rollers | Mr. Sanjay D Shinde | 3 | 2019-11-04 | 2019-11-05 | 2019-11-05 | 2019-11-06 | 2019-11-06 | 2019-11-11 | 2019-11-11 | 2019-11-11 | 2019-11-11 | 2019-11-12 | 2019-11-11 | 2019-11-12 | 2019-11-12 | 2019-11-12 | 2019-11-12 | 2019-11-13 | Cummins India Ltd. Kothrud, Pune-411038, Maharashtra, India | 1 | 21 | 405 | Mr. Gautam Kolgaonkar | 9011943971 | gautam.kolgaonkar@cummins.com | Mr. Nadaf | 9146060045 | mahamadhanif.nadaf@cummins.com | - | - | - | - | 1 | 1 | 0 | Packing with Bubble Sheet and Transport in SAPL Scope. | - |  | 1 | 0 | 1 |  | 1 | WO Close | 2019-11-11 | 2019-11-09 | 1 |  | Mr. Sanjay D Shinde
657 | 2022-07-18 | 1:46:38 PM | Sapl0335 | 1 | 7 | C015 | 685 | 688 | IND6319788IND6319789 | 35 | 0 | N0210 | 2019-11-04 | Sypply of missing material, installation & prove out of existing 500 kg pillar mounted jib crane | Mr. Sanjay D Shinde | 3 | 2019-11-04 | 2019-11-05 | 2019-11-05 | 2019-11-06 | 2019-11-06 | 2020-01-18 | 2019-11-14 | 2020-01-18 | 2019-11-18 | 2020-01-18 | 2019-11-19 | 2020-01-24 | 2019-11-14 | 2020-01-24 | 2019-11-19 | 2020-01-24 | Phaltan High Horsepower Plant Cummins Technologies India Pvt. Ltd. Phaltan, Maharashtra, India. | 1 | 21 | 405 | Mr. Amit Kumar | 9130083046 | amit.r.kumar@cummins.com | Ramchandra B Nimbalkar | 9922932785 | ramchandra.b.nimbalkar@cummins.com | - | - | - | - | 1 | 1 | 1 | Packing with Bubble Sheet and Transport, installation and commissioning in SAPL Scope. | - |  | 1 | 1 | 1 |  | 1 | NA | 2020-01-17 | 2020-01-17 | 1 |  | Mr. Sanjay D Shinde
665 | 2020-12-05 | 11:22:14 AM | sapl0313 | 1 | 7 | N003 | 693 | 696 | 4300042513 | 34 | 0 | S0185 | 2019-12-23 | Standard Product - Channel Support | Mr. S. D. Shinde | 5 | 2019-12-23 | 2019-12-23 | 2019-12-23 | 2019-12-23 | 2019-12-23 | 2019-12-25 | 2019-12-25 | 2019-12-25 | 2019-12-25 | 2019-12-25 | 2019-12-25 | 2019-12-25 | 2019-12-25 | 2019-12-25 | 2019-12-25 | 2019-12-25 | Neel Metal Products Limited (HUB) 789/1, Anekal Road, Poonapalli Village, Hosur, Tamilnadu | 1 | 31 | 680 | Mr. Neeshanth Bolar | 9003342354 | nishanth.bolar@jbmgroup.com | Mr. Neeshanth Bolar | 9003342354 | nishanth.bolar@jbmgroup.com | - | - | - | - | 1 | 1 | 1 | Packing with Bubble Sheet | - |  | 1 | 0 | 0 |  | 1 | WO Close | 2019-12-24 | 2019-12-24 | 1 |  | Mr. S. D. Shinde
676 | 2020-12-05 | 10:50:25 AM | sapl0313 | 1 | 7 | O002 | 705 | 707 | LOI13032020 | 38 | 0 | J0124 | 2020-03-13 | Mahindra Trolleys- 08 nos. | Mr. Aniruddha Raut | 3 | 2020-03-13 | 2020-03-17 | 2020-03-13 | 2020-03-17 | 2020-03-14 | 2020-03-30 | 2020-03-30 | 2020-03-31 | 2020-03-30 | 2020-03-31 | 2020-03-30 | 2020-04-04 | 2020-03-30 | 2020-04-10 | 2020-04-06 | 2020-04-11 | Plot no. A-22- A/1/1, MIDC Chakan Industrial Area, Phase-II, Khalumbre, Khed, Pune-410501, Maharashtra | 1 | 21 | 405 | Mr. Dheeraj Prasad | 9922941202 | dheeraj.prasad@olcieng.co.in | Mr. Amit kokane | 8308361607 | amit.kokane@olcieng.co.in | - | - | - | - | 1 | 1 | 1 | Packing by Bubble Sheets | - |  | 1 | 1 | 1 |  | 1 | WO Close | 2020-03-20 | 2020-03-17 | 1 |  | Mr. Aniruddha Raut
681 | 2020-12-05 | 11:12:47 AM | sapl0313 | 1 | 7 | T002 | 710 | 712 | 9300023508 | 35 | 0 | N0226 | 2020-05-29 | Installation and Commissioning of ILCV BS6 Frame Line | Mr. Aniruddha Raut | 3 | 2020-05-29 | 2020-06-02 | 2020-06-03 | 2020-06-03 | 2020-06-03 | 2020-06-06 | 2020-06-06 | 2020-06-25 | 2020-06-25 | 2020-06-25 | 2020-06-25 | 2020-06-25 | 2020-06-06 | 2020-06-25 | 2020-06-20 | 2020-06-25 | Tata Motors Ltd. Pimpri | 1 | 21 | 405 | Mr. Nagesh Kulkarni | 9028097910 | nagesh.kulkarni@tatamotors.com | Mr. Abhijeet Selukar | 7276098909 | ABHIJEET.SELUKAR2@tatamotors.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | WO Close | 2020-06-06 | 2020-06-06 | 1 |  | Mr. Aniruddha Raut
682 | 2020-12-05 | 11:13:10 AM | sapl0313 | 1 | 7 | S006 | 711 | 713 | LOI Aug 2020 | 35 | 0 | N0227 | 2020-08-05 | Auto Guided Vehicle | Mr. Dhananjay Sirsikar | 3 | 2020-08-06 | 2020-08-15 | 2020-08-16 | 2020-08-19 | 2020-08-20 | 2020-09-10 | 2020-09-10 | 2020-09-21 | 2020-09-21 | 2020-09-25 | 2020-09-25 | 2020-09-28 | 2020-09-28 | 2020-09-29 | 2020-09-30 | 2020-09-30 | Gut No.205,Kasurdi,Khed Shivapur, Off Pune Bangalore Highway, Pune - 412 205 | 1 | 21 | 405 | Mr. Narendra Chaudhary | 9822314833 | narendra@synergytechs.com | Mr. Dhananjay Sirsikar | 9822614720 | dhananjay@synergytechs.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 1 |  | 1 | WO Close | 2020-09-04 | 2020-08-28 | 1 |  | Mr. Dhananjay Sirsikar
686 | 2020-08-31 | 2:53:32 PM | sapl0313 | 1 | 8 | S006 | 715 | 717 | Verbal by DNS | 34 | 0 | S0188 | 2020-08-31 | Maintain Inventory of Gun Rail Parts | Mr. Aniruddha Raut | 4 | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-09-05 | 2020-09-05 | 2020-09-07 | 2020-09-07 | 2020-09-08 | 2020-09-08 | 2020-09-10 | 2020-09-10 | 2020-09-12 | 2020-09-12 | 2020-09-12 | 2020-09-12 | Synergytech Automation Pvt.Ltd. Gut No.205,Kasurdi,Khed Shivapur, Off Pune Bangalore Highway, Pune - 412 205 | 1 | 21 | 405 | Mr. Dhananjay Sirsikar | 9822614720 | dhananjay@synergytechs.com | Mr. Narendra Chaudhary | 9822314833 | narendra@synergytechs.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2020-09-05 | 2020-09-02 | 1 |  | Mr. Aniruddha Raut
687 | 2020-09-22 | 11:21:20 AM | sapl0313 | 1 | 8 | S006 | 716 | 718 | Verbal by NMC | 35 | 0 | N0229 | 2020-09-22 | Welding SPM and Tooling for Technofour Assembly Production | Mr. Pravin Chougule | 5 | 2020-09-19 | 2020-09-24 | 2020-09-21 | 2020-09-25 | 2020-09-23 | 2020-10-10 | 2020-10-09 | 2020-10-13 | 2020-10-13 | 2020-10-14 | 2020-10-14 | 2020-10-14 | 2020-10-15 | 2020-10-15 | 2020-10-15 | 2020-10-15 | Synergytech Automation Pvt. Ltd. Gut No.205,Kasurdi,Khed Shivapur, Off Pune Bangalore Highway, Pune - 412 205 | 1 | 21 | 405 | Mr. Dhananjay Sirsikar | 9822614720 | dhananjay@synergytechs.com | Mr. Narendra Chaudhary | 9822314833 | narendra@synergytechs.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2020-10-07 | 2020-09-04 | 1 |  | Mr. Pravin Chougule
694 | 2020-12-05 | 10:52:28 AM | sapl0313 | 1 | 8 | T018 | 723 | 725 | LOI14102020 | 38 | 0 | J0129 | 2020-10-15 | SS 304 MD CONV STAND ASSEMBLY SIZE 1065X540X590MM WITH SS ASSEMBLY PART SET(PR ) WITH DT & POLISHING | Mr. Aniruddha Raut | 5 | 2020-10-14 | 2020-10-15 | 2020-10-15 | 2020-10-15 | 2020-10-15 | 2020-10-18 | 2020-10-19 | 2020-10-19 | 2020-10-20 | 2020-10-20 | 2020-10-20 | 2020-10-20 | 2020-10-20 | 2020-10-20 | 2020-10-20 | 2020-10-20 | Technofour | 1 | 21 | 405 | Mr | 0 | u@r.com | Mr | 0 | u@r.com | - | - | - | - | 1 | 1 | 1 | Packing with Polythene | - |  | 1 | 1 | 1 |  | 1 | WO Close | 2020-10-15 | 2020-10-17 | 1 |  | Mr. Aniruddha Raut
695 | 2021-08-24 | 10:40:11 AM | Sapl0334 | 1 | 8 | C004 | 724 | 726 | IND6590000 | 36 | 0 | E0043 | 2020-10-19 | Refurbishment of 2 Conveyors on Site | Mr. Aniruddha Raut | 2 | 2020-10-22 | 2020-10-24 | 2020-10-26 | 2020-10-27 | 2020-10-28 | 2020-11-12 | 2020-11-12 | 2020-11-12 | 2020-11-13 | 2020-11-13 | 2020-11-16 | 2020-11-19 | 2020-11-19 | 2020-11-19 | 2020-11-20 | 2020-11-20 | Cummins India Limited Dahanukar Colony, Kothrud, Pune 411038 | 1 | 21 | 405 | Anagha Mandar | 1111111111 | LN836@cummins.com | Gaurav | 1111111111 | LN836@cummins.com | - | - | - | - | 1 | 1 | 1 | Wrap with Bubble Sheet. | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2020-11-10 | 2020-11-10 | 1 |  | Mr. Aniruddha Raut
696 | 2020-12-05 | 11:24:01 AM | sapl0313 | 1 | 8 | A004 | 725 | 727 | C1PO2021_000316 | 34 | 0 | S0191 | 2020-10-20 | Telescopic Cross Rails | Mr. Aniruddha Raut | 2 | 2020-10-19 | 2020-10-20 | 2020-10-20 | 2020-10-20 | 2020-10-20 | 2020-10-23 | 2020-10-23 | 2020-10-23 | 2020-10-24 | 2020-10-24 | 2020-10-24 | 2020-10-26 | 2020-10-26 | 2020-10-26 | 2020-10-27 | 2020-10-27 | Gat No. 291 to 296, Nanekarwadi, Chakan, Pune410501, Maharashtra, India. | 1 | 21 | 405 | Miss Priyanka Patil | 9890030485 | priyanka.patil@autolineind.com | Mr. Satish Satpute | 9890030485 | Satish.Satpute@autolineind.com | - | - | - | - | 1 | 1 | 1 | Wrap with Bubble Sheet. | - |  | 1 | 0 | 1 |  | 1 | WO Close | 2020-10-22 | 2020-10-22 | 1 |  | Mr. Aniruddha Raut
697 | 2021-08-24 | 10:43:55 AM | Sapl0334 | 1 | 8 | C004 | 726 | 729 | IND6596337 | 38 | 0 | J0130 | 2020-10-26 | Supply of Electrical Power Supply for PM Chamber at PSBU TCs | Mr. Amit Shedge | 22 | 2020-10-26 | 2020-10-27 | 2020-10-27 | 2020-10-27 | 2020-10-27 | 2020-10-29 | 2020-10-29 | 2020-10-29 | 2020-10-30 | 2020-10-30 | 2020-10-31 | 2020-10-31 | 2020-10-31 | 2020-10-31 | 2020-10-31 | 2020-10-31 | cummins india ltd., kothrud | 1 | 21 | 405 | Mr. Naik | 9999999999 | naik@cummins.com | Mrs. Rashmi Shankar | 9999999999 | rashmi@cummmins.com | - | - | - | - | 1 | 1 | 1 | Wrap with Bubble Sheet. | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2020-10-27 | 2020-10-28 | 1 |  | Mr. Amit Shedge
698 | 2021-08-24 | 10:42:39 AM | Sapl0334 | 1 | 8 | C004 | 727 | 728 | IND6596338 | 36 | 0 | E0044 | 2020-10-19 | Installataion and commissioning of Supply of Electrical Power to PM chamber at PSBU | Mr. Amit Shedge | 22 | 2020-10-26 | 2020-10-26 | 2020-10-26 | 2020-10-27 | 2020-10-28 | 2020-10-30 | 2020-10-30 | 2020-10-31 | 2020-10-30 | 2020-10-31 | 2020-10-30 | 2020-10-31 | 2020-10-30 | 2020-10-31 | 2020-10-31 | 2020-10-31 | kothrud | 1 | 21 | 405 | Mr. Naik | 9999999999 | naik@cummins.com | Mrs. Rashmi Shankar | 9999999999 | rashmi@cummmins.com | - | - | - | - | 1 | 1 | 1 | Wrap with Bubble Sheet. | - |  | 1 | 0 | 0 |  | 1 | COMPLETED | 2020-10-28 | 2020-10-30 | 1 |  | Mr. Amit Shedge
699 | 2020-12-05 | 5:01:31 PM | sapl0313 | 1 | 8 | C015 | 728 | 730 | IND6319789 | 36 | 0 | E0045 | 2019-10-23 | Installation and commissioning of existing 500 kg Jib crane | Mr. Aniruddha Raut | 2 | 2019-11-01 | 2019-11-04 | 2019-11-05 | 2019-11-07 | 2020-11-06 | 2019-11-16 | 2019-11-18 | 2019-11-19 | 2019-11-19 | 2019-11-23 | 2019-11-25 | 2019-11-29 | 2019-11-29 | 2019-11-30 | 2019-11-29 | 2019-11-29 | IM2-LOC-QSK:IM2-LOC-QSK Cummins Technologies India Pvt. Ltd. Phaltan High Horsepower Plant, SEZ Unit Plot No. B3/1, MIDC SEZ-Phaltan | 1 | 21 | 405 | ramchandra nimbalkar | 9922932785 | ramchandra.b.nimbalkar@cummins.com | Amit Kumar | 9130083046 | mit.r.kumar@cummins.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | WO Close | 2019-11-13 | 2019-11-15 | 1 |  | Mr. Aniruddha Raut
700 | 2020-12-12 | 8:06:13 PM | sapl0313 | 1 | 8 | A004 | 729 | 731 | C1PO2021_000392 | 34 | 0 | S0192 | 2020-11-09 | Gun Rail Trolleys | Mr. Aniruddha Raut | 2 | 2020-11-09 | 2020-11-09 | 2020-11-09 | 2020-11-09 | 2020-11-10 | 2020-11-10 | 2020-11-10 | 2020-11-10 | 2020-11-10 | 2020-11-10 | 2020-11-10 | 2020-11-10 | 2020-11-10 | 2020-11-10 | 2020-11-10 | 2020-11-10 | Gat No.291,Nanekarwadi,Chakan, Pune410501, Maharashtra, India. | 1 | 21 | 405 | Miss Priyanka Patil | 9860292859 | priyanka.patil@autolineind.com | Mr. Satish Satpute | 9890030485 | Satish.Satpute@autolineind.com | - | - | - | - | 1 | 1 | 1 | Wrap with Bubble Sheet. | - |  | 1 | 0 | 0 |  | 1 | Order Closed | 2020-11-09 | 2020-11-09 | 1 |  | Mr. Aniruddha Raut
701 | 2021-08-24 | 10:59:19 AM | Sapl0334 | 1 | 8 | T018 | 730 | 732 | 263888 | 38 | 0 | J0131 | 2020-12-01 | SS304 SQ TUBE STAND ASSEMBLY | Mr. Aniruddha Raut | 5 | 2020-12-01 | 2020-12-01 | 2020-12-01 | 2020-12-01 | 2020-12-01 | 2020-12-04 | 2020-12-03 | 2020-12-04 | 2020-12-04 | 2020-12-04 | 2020-12-04 | 2020-12-04 | 2020-12-05 | 2020-12-05 | 2020-12-05 | 2020-12-05 | Technofour Electronics Pvt Ltd Gat no 3(part), 243(part), 5(part), Kasurdi (Kheba) Tal: Bhor Dist: Pune PIN: 412205 Ph: 02113 305 222/38/48 | 1 | 21 | 405 | Satish Kalkar | 9999999999 | storem@tepl.co.in | Navnath Bhogle | 1111111111 | nbhogale@tepl.co.in | - | - | - | - | 1 | 1 | 1 | Wrap with Bubble Sheet. | - |  | 1 | 0 | 0 |  | 1 | COMPLETED | 2020-12-03 | 2020-12-02 | 1 |  | Mr. Aniruddha Raut
702 | 2021-08-24 | 10:47:57 AM | Sapl0334 | 1 | 8 | G017 | 731 | 733 | GodrejLOI30112020 | 35 | 0 | N0231 | 2020-12-08 | Roof Finalization Fixture | Mr. Aniruddha Raut | 3 | 2020-12-08 | 2020-12-12 | 2020-12-08 | 2020-12-12 | 2020-12-09 | 2021-01-07 | 2021-01-07 | 2021-01-09 | 2021-01-11 | 2021-01-12 | 2021-01-13 | 2021-01-19 | 2021-01-14 | 2021-01-19 | 2021-01-20 | 2021-01-22 | Godrej & Boyce Mfg. Co, Ltd. Plant 7, Pirojshanagar, Vikhroli, Mumbai 400079, India | 1 | 21 | 398 | Mr. Gajendra Bhadauria | 9820225024 | gjb@godrej.com | Mr. Narayan Masurkar | 9820389211 | masurkar@godrej.com | - | - | - | - | 1 | 1 | 1 | Wrap with Bubble Sheet. | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2020-12-25 | 2020-12-20 | 1 |  | Mr. Aniruddha Raut
703 | 2020-12-12 | 8:01:52 PM | sapl0313 | 1 | 8 | C020 | 732 | 734 | IND6629023 | 36 | 0 | E0046 | 2020-12-12 | Test bed automation and control system hardware dismantling, refurbishment, shifting & re-installation & storage | Mr. Amit Shedge | 22 | 2021-01-20 | 2021-01-20 | 2021-01-20 | 2021-01-20 | 2021-01-20 | 2021-01-20 | 2021-01-20 | 2021-01-20 | 2021-01-20 | 2021-01-21 | 2021-01-20 | 2021-02-15 | 2021-01-20 | 2021-02-15 | 2021-02-15 | 2021-02-15 | Cummins Technologies India Pvt Ltd India Technical Centre Division Dahanukar Colony, Kothrud | 1 | 21 | 405 | Mrs. Rashmi Naik | 08669998744 | rashmi.naik@cummins.com | Mr. Varawadekar | 1111111111 | vaeawadekar@cummins.com | - | - | - | - | 1 | 1 | 1 | Wrap with Bubble Sheet. | - |  | 0 | 1 | 0 |  | 0 |  | 2021-01-20 | 2021-01-15 | 1 |  | Mr. Amit Shedge
704 | 2020-12-12 | 8:18:08 PM | sapl0313 | 1 | 8 | C020 | 733 | 735 | IND6629020 | 36 | 0 | E0047 | 2020-12-12 | Endurance Test cell Relocation: Automation & control system supply scope | Mr. Amit Shedge | 22 | 2020-12-15 | 2020-12-15 | 2020-12-15 | 2020-12-19 | 2020-12-21 | 2021-01-09 | 2021-01-09 | 2021-01-09 | 2021-01-11 | 2021-01-11 | 2021-01-11 | 2021-02-15 | 2021-01-11 | 2021-02-15 | 2021-02-15 | 2021-02-15 | Cummins Technologies India Pvt Ltd India Technical Centre Division Dahanukar Colony, Kothrud | 1 | 21 | 405 | Mrs. Rashmi Naik | 08669998744 | rashmi.naik@cummins.com | Mr. Varawadekar | 1111111111 | vaeawadekar@cummins.com | - | - | - | - | 1 | 1 | 1 | Wrap with Bubble Sheet. | - |  | 0 | 1 | 1 |  | 0 |  | 2021-01-05 | 2021-01-05 | 1 |  | Mr. Amit Shedge
705 | 2020-12-14 | 11:31:28 AM | sapl0313 | 1 | 8 | T018 | 734 | 736 | VerbalNMC10122020 | 43 | 0 | T0034 | 2020-12-14 | STD HMI CABINET(JBE08) AND PANEL(JAF20) MECH AND ELECTRONICS ASSEMBLY | Mr. Amit Shedge | 22 | 2020-12-11 | 2020-12-11 | 2020-12-12 | 2020-12-12 | 2020-12-14 | 2020-12-26 | 2020-12-28 | 2020-12-30 | 2020-12-30 | 2020-12-31 | 2020-12-30 | 2020-12-31 | 2020-12-31 | 2020-12-31 | 2021-01-01 | 2021-01-01 | Gat no 3(part), 243(part), 5(part), Kasurdi (Kheba) Tal: Bhor Dist: Pune PIN: 412205 Ph: 02113 305 222/38/48 | 1 | 21 | 405 | Sandesh Udhane | 8888831614 | purchasem@tepl.co.in | Sandesh Udhane | 8888831614 | purchasem@tepl.co.in | - | - | - | - | 1 | 1 | 1 | Wrap with Bubble Sheet. | - |  | 0 | 1 | 1 |  | 0 |  | 2020-12-23 | 2020-12-19 | 1 |  | Mr. Amit Shedge
706 | 2021-08-24 | 10:59:24 AM | Sapl0334 | 1 | 8 | T018 | 735 | 737 | LOIFrame01 | 38 | 0 | J0132 | 2020-12-17 | SS304 SQ TUBE STAND ASSEMBLY | Mr. Aniruddha Raut | 5 | 2020-12-15 | 2020-12-15 | 2020-12-15 | 2020-12-15 | 2020-12-16 | 2020-12-16 | 2020-12-17 | 2020-12-19 | 2020-12-21 | 2020-12-21 | 2020-12-22 | 2020-12-22 | 2020-12-22 | 2020-12-22 | 2020-12-22 | 2020-12-22 | Gat no 3(part), 243(part), 5(part), Kasurdi (Kheba) Tal: Bhor Dist: Pune PIN: 412205 Ph: 02113 305 222/38/48 Bill to: Technofour Electronics Pvt Ltd, 45 Dr Ambedkar Rd, Pune 411001 | 1 | 21 | 405 | Sandesh Udhane | 08669998744 | storem@tepl.co.in | Sandesh Udhane | 08669998744 | storem@tepl.co.in | - | - | - | - | 1 | 1 | 1 | Wrap with Bubble Sheet. | - |  | 1 | 0 | 1 |  | 1 | COMPLETED | 2020-12-19 | 2020-12-18 | 1 |  | Mr. Aniruddha Raut
707 | 2020-12-21 | 3:21:35 PM | sapl0313 | 1 | 8 | A013 | 736 | 738 | 4100018002 | 37 | 0 | P0059 | 2020-12-21 | Break Coil Transformer | Mr. Amit Shedge | 15 | 2020-12-21 | 2020-12-21 | 2020-12-21 | 2020-12-21 | 2020-12-21 | 2020-12-21 | 2020-12-21 | 2020-12-21 | 2020-12-22 | 2020-12-24 | 2020-12-24 | 2020-12-24 | 2020-12-24 | 2020-12-24 | 2020-12-25 | 2020-12-25 | ALF Engineering Pvt Ltd, Chakan Plot No-A-1/3,MVML Supplier Park, Phase-IV,Village-Chakan 410501 | 1 | 21 | 405 | Mayur Deshpande | 9860194709 | mayurdeshpande@alfengineering.com | Mayur Deshpande | 9860194709 | mayurdeshpande@alfengineering.com | - | - | - | - | 1 | 1 | 1 | Wrap with Bubble Sheet. | - |  | 0 | 1 | 0 |  | 0 |  | 2020-12-23 | 2020-12-23 | 1 |  | Mr. Amit Shedge
708 | 2021-08-24 | 10:59:30 AM | Sapl0334 | 1 | 8 | T018 | 737 | 739 | VerbalNMC291220 | 38 | 0 | J0133 | 2020-12-31 | SS304 SQ TUBE STAND ASSEMBLY | Mr. Aniruddha Raut | 5 | 2020-12-30 | 2020-12-30 | 2020-12-31 | 2020-12-31 | 2020-12-31 | 2021-01-05 | 2021-01-05 | 2021-01-05 | 2021-01-06 | 2021-01-06 | 2021-01-06 | 2021-01-06 | 2021-01-05 | 2021-01-06 | 2021-01-07 | 2021-01-07 | Technofour Electronics Pvt Ltd Gat no 3(part), 243(part), 5(part), Kasurdi (Kheba) Tal: Bhor Dist: Pune PIN: 412205 Ph: 02113 305 222/38/48 Bill to: Technofour Electronics Pvt Ltd, 45 Dr Ambedkar Rd, Pune 411001 | 1 | 21 | 405 | Sandesh Udhane | 8888831614 | purchasem@tepl.co.in | Sandesh Udhane | 8888831614 | storem@tepl.co.in | - | - | - | - | 1 | 1 | 1 | Wrap with Bubble Sheet. | - |  | 1 | 0 | 1 |  | 1 | COMPLETED | 2020-12-31 | 2021-01-01 | 1 |  | Mr. Aniruddha Raut
709 | 2021-08-24 | 10:48:31 AM | Sapl0334 | 1 | 8 | C004 | 738 | 740 | VerbalNMC301220 | 35 | 0 | N0232 | 2020-12-30 | KBK Rail for RGV | Mr. Aniruddha Raut | 3 | 2020-12-30 | 2020-12-31 | 2020-12-31 | 2021-01-01 | 2021-01-02 | 2021-01-05 | 2021-01-05 | 2021-01-05 | 2021-01-05 | 2021-01-05 | 2021-01-06 | 2021-01-06 | 2021-01-06 | 2021-01-06 | 2021-01-06 | 2021-01-06 | CIL_EBU_085:Cummins India Limited Kothrud | 1 | 21 | 405 | - | 1111111111 | naik@cummins.com | - | 1111111111 | naik@cummins.com | - | - | - | - | 1 | 1 | 1 | Wrap with Bubble Sheet. | - |  | 1 | 0 | 1 |  | 1 | COMPLETED | 2021-01-02 | 2021-01-04 | 1 |  | Mr. Aniruddha Raut
710 | 2021-08-24 | 11:00:20 AM | Sapl0334 | 1 | 8 | T018 | 740 | 741 | Verbal050121 | 38 | 0 | J0134 | 2021-01-07 | GF-200 STAND FOR COMPACT FLAP | Mr. Aniruddha Raut | 5 | 2021-01-05 | 2021-01-05 | 2021-01-06 | 2021-01-06 | 2021-01-06 | 2021-01-12 | 2021-01-12 | 2021-01-12 | 2021-01-13 | 2021-01-13 | 2021-01-13 | 2021-01-13 | 2021-01-12 | 2021-01-13 | 2021-01-13 | 2021-01-13 | Gat no 3(part), 243(part), 5(part), Kasurdi (Kheba) Tal: Bhor Dist: Pune PIN: 412205 Ph: 02113 305 222/38/48 | 1 | 21 | 405 | Sandesh Udhane | 9999999999 | purchasem@tepl.co.in | Navnath Bhogle | 1111111111 | purchasem@tepl.co.in | - | - | - | - | 1 | 1 | 1 | Wrap with Bubble Sheet. | - |  | 1 | 0 | 1 |  | 1 | COMPLETED | 2021-01-09 | 2021-01-09 | 1 |  | Mr. Aniruddha Raut
712 | 2021-08-01 | 11:44:58 AM | sapl0001 | 1 | 8 | G018 | 743 | 743 | GME/SGS/2021/VEDANTA/ORDER/01 | 37 | 0 | P0060 | 2021-01-15 | Spares Order 1 for SGS Auger | Mr. Amit Shedge | 13 | 2021-01-15 | 2021-01-15 | 2021-01-16 | 2021-01-16 | 2021-01-18 | 2021-02-13 | 2021-02-13 | 2021-02-13 | 2021-02-15 | 2021-02-16 | 2021-02-16 | 2021-02-16 | 2021-02-17 | 2021-02-17 | 2021-02-17 | 2021-02-17 | Plot no 2 – A/5. IDCO Industrial Estate, P.O: Industrial Estate. Dist Jharsuguda – Odisha, Pin Code – 768203. E-mail ID: gme_uni@yahoo.co.in | 1 | 26 | 460 | - | 9999999999 | gme_uni@yahoo.co.in | - | 1111111111 | gme_uni@yahoo.co.in | - | - | - | - | 1 | 1 | 1 | Wrap with Bubble Sheet. | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2021-02-12 | 2021-02-10 | 1 |  | Mr. Amit Shedge
713 | 2021-08-01 | 11:45:18 AM | sapl0001 | 1 | 8 | G018 | 742 | 742 | GME/SGS/2021/VEDANTA/ORDER/02 | 37 | 0 | P0061 | 2021-01-15 | Spares Order 2 for SGS Auger | Mr. Amit Shedge | 13 | 2021-01-15 | 2021-01-15 | 2021-01-16 | 2021-01-16 | 2021-01-18 | 2021-02-12 | 2021-02-13 | 2021-02-15 | 2021-02-15 | 2021-02-16 | 2021-02-17 | 2021-02-17 | 2021-02-17 | 2021-02-17 | 2021-02-17 | 2021-02-17 | Plot no 2 – A/5. IDCO Industrial Estate P.O: Industrial Estate. Dist: Jharsuguda Pin Code – 768203, Odisha | 1 | 26 | 460 | - | 9999999999 | gme_uni@yahoo.co.in | - | 1111111111 | gme_uni@yahoo.co.in | - | - | - | - | 1 | 1 | 1 | Wrap with Bubble Sheet. | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2021-02-11 | 2021-02-05 | 1 |  | Mr. Amit Shedge
714 | 2021-08-24 | 11:00:24 AM | Sapl0334 | 1 | 8 | T018 | 744 | 745 | 269476 | 38 | 0 | J0135 | 2021-01-11 | SS304 Conv Stsand Assy | Mr. Aniruddha Raut | 5 | 2021-01-08 | 2021-01-08 | 2021-01-09 | 2021-01-09 | 2021-01-11 | 2021-01-15 | 2021-01-15 | 2021-01-15 | 2021-01-16 | 2021-01-16 | 2021-01-18 | 2021-01-18 | 2021-01-15 | 2021-01-18 | 2021-01-18 | 2021-01-18 | Gat no 3(part), 243(part), 5(part), Kasurdi (Kheba) Tal: Bhor Dist: Pune PIN: 412205 Ph: 02113 305 222/38/48 | 1 | 21 | 405 | Sandesh Udhane | 9999999999 | purchasem@tepl.co.in | Navnath Bhogle | 1111111111 | storem@tepl.co.in | - | - | - | - | 1 | 1 | 1 | Wrap with Bubble Sheet. | - |  | 1 | 0 | 1 |  | 1 | COMPLETED | 2021-01-11 | 2021-01-14 | 1 |  | Mr. Aniruddha Raut
715 | 2021-08-24 | 11:00:30 AM | Sapl0334 | 1 | 8 | T018 | 745 | 746 | VerbalNMC120121 | 38 | 0 | J0136 | 2021-01-12 | SS304 Conv Stsand Assy | Mr. Aniruddha Raut | 5 | 2021-01-12 | 2021-01-12 | 2021-01-13 | 2021-01-13 | 2021-01-13 | 2021-01-18 | 2021-01-18 | 2021-01-18 | 2021-01-18 | 2021-01-18 | 2021-01-19 | 2021-01-19 | 2021-01-19 | 2021-01-19 | 2021-01-19 | 2021-01-19 | Gat no 3(part), 243(part), 5(part), Kasurdi (Kheba) Tal: Bhor Dist: Pune PIN: 412205 Ph: 02113 305 222/38/48 | 1 | 21 | 405 | Sandesh Udhane | 9999999999 | purchasem@tepl.co.in | Sandesh Udhane | 1111111111 | storem@tepl.co.in | - | - | - | - | 1 | 1 | 1 | Wrap with Bubble Sheet. | - |  | 1 | 0 | 1 |  | 1 | COMPLETED | 2021-01-18 | 2021-01-16 | 1 |  | Mr. Aniruddha Raut
716 | 2021-08-24 | 11:01:18 AM | Sapl0334 | 1 | 8 | T018 | 745 | 747 | 269884 | 38 | 0 | J0137 | 2021-02-04 | SS304 Conv Stsand Assy | Mr. Aniruddha Raut | 5 | 2021-02-04 | 2021-02-04 | 2021-02-04 | 2021-02-04 | 2021-02-04 | 2021-02-04 | 2021-02-04 | 2021-02-04 | 2021-02-04 | 2021-02-04 | 2021-02-04 | 2021-02-04 | 2021-02-04 | 2021-02-04 | 2021-02-04 | 2021-02-04 | Gat no 3(part), 243(part), 5(part), Kasurdi (Kheba) Tal: Bhor Dist: Pune PIN: 412205 Ph: 02113 305 222/38/48 Bill to: Technofour Electronics Pvt Ltd, 45 Dr Ambedkar Rd, Pune 411001 | 1 | 21 | 405 | Sandesh Udhane | 9999999999 | purchasem@tepl.co.in | Navnath Bhogle | 1111111111 | storem@tepl.co.in | - | - | - | - | 0 | 0 | 0 | - | - |  | 0 | 0 | 1 |  | 1 | COMPLETED | 2021-02-04 | 2021-02-04 | 1 |  | Mr. Aniruddha Raut
717 | 2021-02-09 | 3:08:07 PM | Sapl0334 | 1 | 8 | G019 | 746 | 749 | 290003817 | 43 | 0 | T0035 | 2021-02-09 | Semi Automated Grinding System | Mahesh Durgale | 1 | 2021-03-05 | 2021-03-11 | 2021-03-11 | 2021-03-18 | 2021-02-05 | 2021-02-25 | 2021-03-30 | 2021-04-26 | 2021-04-28 | 2021-05-10 | 2021-05-11 | 2021-05-12 | 2021-05-13 | 2021-05-24 | 2021-05-25 | 2021-05-31 | GERE_IN7_LM POWER BLADES BANGALORE LM Power Blades (India) Private Ltd. Plot No-85, KIADB Industrial Area-Phase II, Dabaspet, Nelamangala Taluk BANGLORE(RURAL DIST.), KARNATAKA 562111 India | 1 | 17 | 294 | Mr. Makrand Ratnaparkhi | 9663157191 | makrand.ratnaparkhi@ge.com | Mr. Purushotam | 9663157191 | PurushothKumar.P@lmwindpower.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2021-03-05 | 2021-02-13 | 1 |  | Mahesh Durgale
721 | 2021-08-24 | 11:01:33 AM | Sapl0334 | 1 | 8 | C004 | 750 | 753 | Verbal DNS | 38 | 0 | J0139 | 2021-02-23 | Jig Boom Refurbishment | Mahesh Durgale | 5 | 2021-02-21 | 2021-02-22 | 2021-02-23 | 2021-02-23 | 2021-02-24 | 2021-02-26 | 2021-02-26 | 2021-02-27 | 2021-02-28 | 2021-03-01 | 2021-02-26 | 2021-02-27 | 2021-03-02 | 2021-02-04 | 2021-02-28 | 2021-02-28 | CTCI Kothrud | 1 | 21 | 405 | Rashmi Naik | 8669998744 | rashmi.naik@cummins.com | - | 8669998744 | rashmi.naik@cummins.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2021-02-23 | 2021-02-23 | 1 |  | Mahesh Durgale
722 | 2021-08-24 | 10:58:06 AM | Sapl0334 | 1 | 8 | T018 | 752 | 754 | Verble NMC24022021 | 38 | 0 | J0140 | 2021-02-24 | Conveyor stand 750HT 1800LG 310 DEPTH COIL | Mahesh Durgale | 5 | 2021-02-22 | 2021-02-23 | 2021-02-23 | 2021-02-23 | 2021-02-24 | 2021-02-27 | 2021-02-27 | 2021-02-27 | 2021-02-28 | 2021-02-28 | 2021-02-27 | 2021-02-27 | 2021-03-01 | 2021-03-01 | 2021-02-27 | 2021-02-27 | Gat?. ?No?. ?3?(?Part?)?, ?243?(?Part?)?, ? 5?(?Part?)?, ?Kasurdi ?(?Kheba?)?,?Tal?.? -?Bhor?, ?Dist?.-?Pune?, ?Pin?- ? 412205 | 1 | 21 | 405 | - | 02113 305 222/38/48 | purchase@technofour.com | - | 02113 305 222/38/48 | purchase@technofour.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 1 | COMPLETED | 2021-02-24 | 2021-02-24 | 1 |  | Mahesh Durgale
723 | 2022-01-28 | 4:34:34 PM | sapl0001 | 1 | 8 | G020 | 753 | 755 | 5810000932 | 38 | 0 | J0141 | 2021-02-27 | Container Tail gate Outer upper | Mahesh Durgale | 5 | 2021-02-20 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-08 | 2021-03-09 | 2021-03-11 | 2021-03-12 | 2021-03-09 | 2021-03-10 | 2021-03-12 | 2021-03-13 | 2021-03-10 | 2021-03-11 | E?1 ?(?Part?)?,?Chakan Midc Road?, ? Phase?-?Iii?,?Kharabwadi?, ?Chakan?, ? Talegaon Chakan Road?, ? Mahalunge Ingale?, ? Maharashtra? | 1 | 21 | 405 | Mr. Sunil Kokate | 91-9673334857 | gaipl@in.gestamp.com | - | 91-9673334857 | gaipl@in.gestamp.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 | For PO Purpose | 2021-03-02 | 2021-03-02 | 1 |  | Mahesh Durgale
724 | 2021-02-27 | 9:52:08 AM | Sapl0334 | 1 | 8 | G020 | 754 | 756 | 5810000928 | 38 | 0 | J0142 | 2021-02-27 | Container Modification 6RG827105A to 6JM827105 PQ to MQB | Mahesh Durgale | 5 | 2021-02-22 | 2021-02-24 | 2021-02-23 | 2021-02-24 | 2021-03-03 | 2021-03-10 | 2021-03-10 | 2021-03-11 | 2021-03-11 | 2021-03-12 | 2021-03-10 | 2021-03-11 | 2021-03-12 | 2021-03-12 | 2021-03-10 | 2021-03-11 | E?1 ?(?Part?)?,?Chakan Midc Road?, ? Phase?-?Iii?,?Kharabwadi?, ? Chakan?, ?Talegaon Chakan ? Road?, ?Mahalunge Ingale?, ? Maharashtra | 1 | 21 | 405 | Mr. Sunil Kokate | 9673334857 | gaipl@in.gestamp.com | - | 91-9673334857 | gaipl@in.gestamp.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2021-03-02 | 2021-03-02 | 1 |  | Mahesh Durgale
725 | 2021-08-24 | 10:55:49 AM | Sapl0334 | 1 | 8 | G018 | 755 | 757 | Verble NMC02/03/2021 | 37 | 0 | P0062 | 2021-03-02 | GM ENGINEERS SPARES | Mahesh Durgale | 13 | 2021-03-02 | 2021-03-02 | 2021-03-03 | 2021-03-03 | 2021-03-08 | 2021-03-15 | 2021-03-16 | 2021-03-17 | 2021-03-21 | 2021-03-22 | 2021-03-18 | 2021-03-20 | 2021-03-23 | 2021-03-23 | 2021-03-19 | 2021-03-20 | Plot no ?2 ?– A?/?5?. ?IDCO Industrial Estate? P?.?O?: ?Industrial Estate?. ?Dist?: ?Jharsuguda? Pin Code – ?768203?, ?Odisha | 1 | 26 | 460 | - | 999999999 | gme_uni@yahoo.co.in | - | 999999999 | gme_uni@yahoo.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2021-03-04 | 2021-03-04 | 1 |  | Mahesh Durgale
728 | 2021-03-22 | 4:20:52 PM | Sapl0334 | 1 | 8 | G017 | 758 | 760 | 1800/1DR026470/CA1018386 | 35 | 0 | N0236 | 2021-03-22 | Roof Finalization Fixture RRTS | Mahesh Durgale | 5 | 2021-03-23 | 2021-03-25 | 2021-03-18 | 2021-03-25 | 2021-03-29 | 2021-04-10 | 2021-04-10 | 2021-04-13 | 2021-04-15 | 2021-04-16 | 2021-04-08 | 2021-04-13 | 2021-04-21 | 2021-04-28 | 2021-03-08 | 2021-03-10 | Plant ?7?, ?Pirojshanagar?, ?Wikhroli?, ?Mumbai ?400079? Mumbai?, ?Maharashtra?, ?India ?- ?400079?.? | 1 | 21 | 398 | Mr. Gajendra Bhadauria | 9820225024 | gjb@godrej.com | Mr. Narayan Masurkar | 9820389211 | masurkar@godrej.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2021-03-26 | 2021-03-26 | 1 |  | Mahesh Durgale
732 | 2021-08-24 | 10:56:02 AM | Sapl0334 | 1 | 8 | G018 | 755 | 766 | GME/SGS/2021/VEDANTA/03 | 37 | 0 | P0063 | 2021-03-31 | GM ENGINEERS SPARES | Mahesh Durgale | 13 | 2021-03-25 | 2021-03-26 | 2021-03-10 | 2021-03-20 | 2021-03-19 | 2021-03-27 | 2021-03-18 | 2021-03-28 | 2021-03-04 | 2021-03-18 | 2021-03-24 | 2021-03-27 | 2021-03-16 | 2021-03-26 | 2021-03-18 | 2021-03-19 | Plot no ?2 ?– A?/?5?. ?IDCO Industrial Estate? P?.?O?: ?Industrial Estate?. ?Dist?: ?Jharsuguda? | 1 | 26 | 460 | - | 9999999999 | gme_uni@yahoo.co.in | - | 999999999 | gme_uni@yahoo.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2021-03-31 | 2021-03-31 | 1 |  | Mahesh Durgale
736 | 2022-01-28 | 4:46:21 PM | sapl0001 | 1 | 8 | G020 | 766 | 770 | 5804019069 | 38 | 0 | J0145 | 2021-05-15 | Container Modification | Vinod Kumar | 5 | 2021-05-01 | 2021-05-05 | 2021-05-05 | 2021-05-08 | 2021-05-16 | 2021-06-30 | 2021-05-25 | 2021-06-30 | 2021-06-20 | 2021-06-30 | 2021-05-31 | 2021-06-30 | 2021-07-01 | 2021-07-05 | 2021-05-31 | 2021-06-30 | E1 (Part),Chakan MIDC Road, Phase-III,Kharabwadi, Chakan, Talegaon Chakan Road, Mahalunge Ingale, Maharashtra, Pune, Maharashtra, India. | 1 | 21 | 405 | Mr. Sunil Kokate | +91-9673334857 | gaipl@in.gestamp.com | Mr. Omprakash | 9673337705 | gaipl@in.gestamp.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 | For PO Purpose | 2021-05-16 | 2021-05-16 | 1 |  | Vinod Kumar
739 | 2021-07-13 | 1:49:03 PM | sapl0001 | 1 | 9 | G018 | 755 | 773 | GME/SGS/2021/VEDANTA/ORDER/1804/04 | 37 | 0 | P0064 | 2021-06-30 | GM ENGINEERS SPARES | Mahesh Durgale | 5 | 2021-06-30 | 2021-07-02 | 2021-07-07 | 2021-07-09 | 2021-07-05 | 2021-07-24 | 2021-07-12 | 2021-07-10 | 2021-07-05 | 2021-07-09 | 2021-07-13 | 2021-07-13 | 2021-07-05 | 2021-07-08 | 2021-07-18 | 2021-07-13 | Plot no 2 – A?/?5. IDCO Industrial Estate? P?.?O??: ??Industrial Estate??. ?Dist??: ?Jharsuguda?? Pin Code – 768203?, ??Odisha? | 1 | 26 | 460 | - | 99999999999 | gme_uni@yahoo.co.in | - | 9999999999 | gme_uni@yahoo.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2021-07-13 | 2021-07-13 | 1 |  | Mahesh Durgale
740 | 2021-07-13 | 1:52:04 PM | sapl0001 | 1 | 9 | G018 | 755 | 774 | GME/SGS/2021/VEDANTACPP/ORDER/1881/05 | 37 | 0 | P0065 | 2021-07-01 | GM ENGINEERS SPARES | Mahesh Durgale | 5 | 2021-07-01 | 2021-07-16 | 2021-07-06 | 2021-07-16 | 2021-07-13 | 2021-07-16 | 2021-07-04 | 2021-07-10 | 2021-07-12 | 2021-07-09 | 2021-07-06 | 2021-07-30 | 2021-07-27 | 2021-07-31 | 2021-06-28 | 2021-07-24 | Plot no ?2 ?– A???/???5?. ?IDCO Industrial Estate??? P???.???O????: ????Industrial Estate????. ???Dist????: ???Jharsuguda???? Pin Code – ?768203??, ???Odisha??? | 1 | 26 | 460 | - | 9999999999 | gme_uni@yahoo.co.in | - | 9999999999 | gme_uni@yahoo.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2021-07-01 | 2021-07-01 | 1 |  | Mahesh Durgale
741 | 2021-07-23 | 10:05:44 AM | Sapl0334 | 1 | 9 | C004 | 768 | 775 | IND6800321 | 43 | 0 | T0037 | 2021-07-23 | Tilting arrangement with Ball cage plate | Mahesh Durgale | 5 | 2021-07-01 | 2021-07-05 | 2021-07-05 | 2021-07-25 | 2021-07-15 | 2021-08-10 | 2021-08-10 | 2021-07-17 | 2021-08-18 | 2021-08-18 | 2021-08-10 | 2021-08-18 | 2021-08-21 | 2021-08-24 | 2021-08-15 | 2021-08-17 | CIL Kothrud | 1 | 21 | 405 | Anagha Shende | 9527160500 | anagha.shende@cummins.com | Anagha Shende | 9527160500 | anagha.shende@cummins.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2021-07-25 | 2021-07-25 | 1 |  | Mahesh Durgale
742 | 2021-07-23 | 10:16:17 AM | Sapl0334 | 1 | 9 | C004 | 769 | 776 | IND6800326 | 43 | 0 | T0038 | 2021-07-23 | Appender Tilting arrangement | Mahesh Durgale | 5 | 2021-07-01 | 2021-07-10 | 2021-07-05 | 2021-07-20 | 2021-07-25 | 2021-08-20 | 2021-08-15 | 2021-08-25 | 2021-08-25 | 2021-08-28 | 2021-08-15 | 2021-08-25 | 2021-08-28 | 2021-09-04 | 2021-08-15 | 2021-07-25 | CIL Kotrhud | 1 | 21 | 405 | Anagha Shende | 9527160500 | anagha.shende@cummins.com | Anagha Shende | 9527160500 | anagha.shende@cummins.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2021-07-31 | 2021-08-01 | 1 |  | Mahesh Durgale
743 | 2021-07-25 | 3:41:58 PM | sapl0001 | 1 | 9 | G018 | 755 | 777 | NMC_VERBAL_25/07/2021 | 37 | 0 | P0066 | 2021-07-25 | GM ENGINEERS SPARES | Mahesh Durgale | 5 | 2021-07-25 | 2021-08-07 | 2021-07-25 | 2021-08-06 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-07-31 | 2021-07-25 | 2021-08-06 | 2021-07-25 | 2021-07-25 | 2021-07-25 | 2021-08-07 | 2021-07-25 | 2021-07-29 | Plot no 2 – A?/?5. IDCO Industrial Estate? P?.?O??: ??Industrial Estate. | 1 | 26 | 460 | - | 9999999999 | gme_uni@yahoo.co.in | - | 9999999999 | gme_uni@yahoo.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2021-07-25 | 2021-07-25 | 1 |  | Mahesh Durgale
744 | 2021-08-24 | 10:52:56 AM | Sapl0334 | 1 | 9 | F009 | 770 | 781 | VERBAL_FJM | 34 | 0 | S0196 | 2021-08-17 | I- BEAM STRUCTURE AND RAIL | Vinod Kumar | 5 | 2021-08-13 | 2021-08-20 | 2021-08-13 | 2021-09-03 | 2021-08-06 | 2021-09-04 | 2021-08-13 | 2021-08-28 | 2021-08-13 | 2021-08-28 | 2021-08-13 | 2021-08-28 | 2021-08-12 | 2021-09-04 | 2021-08-12 | 2021-08-17 | FJM Cylinder pvt ltd Opp-24 Milestone SH-7 vithalapur Taluka-mandal ahmedabad | 1 | 12 | 142 | A | 1234567892 | a@a.com | - | 1234569854 | a@a.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2021-09-04 | 2021-09-04 | 1 |  | Vinod Kumar
747 | 2022-01-28 | 4:46:52 PM | sapl0001 | 1 | 9 | G020 | 772 | 784 | 5804019439 | 38 | 0 | J0147 | 2021-08-21 | VW-SUV TAIL-GATE UPPER | Mahesh Durgale | 5 | 2021-08-21 | 2021-08-22 | 2021-08-22 | 2021-08-23 | 2021-08-24 | 2021-08-31 | 2021-08-31 | 2021-09-04 | 2021-09-10 | 2021-08-14 | 2021-07-30 | 2021-09-04 | 2021-09-05 | 2021-09-12 | 2021-09-12 | 2021-09-19 | Chakan midc road kharabwadi chakan talegoan chakan road mahalunge maharashtra | 1 | 21 | 405 | sunil kokate | 91-9673334857 | gaipl@in.gestamp.com | - | 91-9673334857 | gaipl@in.gestamp.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 | For PO Purpose | 2021-08-21 | 2021-08-24 | 1 |  | Mahesh Durgale
749 | 2021-10-02 | 2:36:24 PM | Sapl0334 | 1 | 9 | C004 | 774 | 786 | IND6781325 | 37 | 0 | P0070 | 2021-08-22 | CUMMINS SPARE PARTS | Mahesh Durgale | 2 | 2021-08-22 | 2021-08-23 | 2021-08-23 | 2021-08-25 | 2021-08-25 | 2021-09-01 | 2021-09-01 | 2021-09-03 | 2021-09-03 | 2021-09-05 | 2021-09-05 | 2021-09-07 | 2021-09-01 | 2021-09-10 | 2021-09-11 | 2021-09-12 | KOTHRUDE | 1 | 21 | 405 | - | 1111111111 | abc@gmail.com | - | 1111111111 | xyz@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2021-08-22 | 2021-08-22 | 1 |  | Mahesh Durgale
750 | 2021-08-28 | 1:51:53 PM | sapl0001 | 1 | 9 | G018 | 773 | 787 | GME/SGS/2021/VEDANTACPP/ORDER/3997/5241/08 | 37 | 0 | P0071 | 2021-08-28 | GM ENGINEERS SPARES | Mahesh Durgale | 5 | 2021-07-31 | 2021-09-04 | 2021-08-04 | 2021-09-04 | 2021-07-29 | 2021-09-04 | 2021-07-29 | 2021-09-04 | 2021-08-05 | 2021-09-04 | 2021-08-05 | 2021-10-09 | 2021-08-10 | 2021-08-28 | 2021-08-24 | 2021-09-04 | Plot no ?2 ?– A??/??5?. ?IDCO Industrial Estate P?.??O??: ?Industrial Estate?.? | 1 | 26 | 460 | - | 9999999999 | gme_uni@yahoo.co.in | - | 9999999999 | gme_uni@yahoo.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 0 |  | 0 | open | 2021-09-04 | 2021-09-04 | 1 |  | Mahesh Durgale
751 | 2021-09-05 | 3:23:30 PM | Sapl0334 | 1 | 9 | S034 | 775 | 788 | SUTK\REPM\2122\00062 | 34 | 0 | S0197 | 2021-09-05 | BULK HEAD STRUCTURE | Mahesh Durgale | 5 | 2021-09-05 | 2021-09-05 | 2021-09-07 | 2021-09-07 | 2021-09-09 | 2021-09-13 | 2021-09-14 | 2021-09-17 | 2021-09-21 | 2021-09-24 | 2021-09-18 | 2021-09-22 | 2021-09-14 | 2021-09-28 | 2021-09-29 | 2021-09-30 | Surin Automotive Pvt?. ?Ltd?. ?Sitarganj?, ?Uttarakhand? Sitapur?, ?Uttarakhand?, ?India ? | 1 | 21 | 405 | Vaibhav kumar singh | 9675307323 | npd.utk@surinauto.com | Vaibhav kumar singh | 9675307323 | npd.utk@surinauto.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 0 |  | 0 |  | 2021-09-10 | 2021-09-10 | 1 |  | Mahesh Durgale
752 | 2021-09-05 | 3:54:19 PM | Sapl0334 | 1 | 9 | S034 | 775 | 788 | SUTK\REPM\2122\00062 | 35 | 0 | N0238 | 2021-09-05 | ? BULK HEAD STRUCTURE | Mahesh Durgale | 5 | 2021-09-06 | 2021-09-10 | 2021-09-11 | 2021-09-16 | 2021-09-17 | 2021-09-20 | 2021-09-21 | 2021-09-25 | 2021-09-26 | 2021-09-30 | 2021-10-01 | 2021-10-06 | 2021-09-21 | 2021-10-10 | 2021-10-11 | 2021-09-14 | A - 194 Phase I, Eldeco Sidcul Industrial Park Sitarganj - Distt. Udham Singh Nagar Uttrakhand - India | 1 | 34 | 650 | Vaibhav kumar singh | 9675307323 | npd.utk@surinauto.com | Vaibhav kumar singh | 9675307323 | npd.utk@surinauto.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2021-09-10 | 2021-09-10 | 1 |  | Mahesh Durgale
753 | 2021-09-16 | 1:38:28 PM | Sapl0335 | 1 | 9 | S034 | 776 | 789 | SUTK\PO\2122\00204 | 35 | 0 | N0239 | 2021-09-16 | NEW BULK HEAD OUTRIGGER | Mahesh Durgale | 5 | 2021-09-18 | 2021-09-22 | 2021-09-20 | 2021-09-23 | 2021-09-24 | 2021-09-30 | 2021-10-01 | 2021-09-06 | 2021-09-07 | 2021-09-10 | 2021-09-11 | 2021-09-14 | 2021-10-14 | 2021-09-20 | 2021-09-20 | 2021-09-22 | A ?- ?194 ?Phase I?, ?Eldeco Sidcul Industrial Park? Sitarganj ?- ?Distt?. ?Udham Singh Nagar? Uttrakhand ?- ?India? | 1 | 34 | 650 | Vaibhav kumar singh | 9675307323 | npd.utk@surinauto.com | Vaibhav kumar singh | 9675307323 | npd.utk@surinauto.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2021-09-21 | 2021-09-22 | 1 |  | Mahesh Durgale
754 | 2021-09-20 | 1:28:26 PM | Sapl0335 | 1 | 9 | G020 | 777 | 790 | 5804019559 | 38 | 0 | J0148 | 2021-09-20 | modification pallets manufacturing | Mahesh Durgale | 5 | 2021-09-10 | 2021-09-11 | 2021-09-12 | 2021-09-14 | 2021-09-24 | 2021-10-02 | 2021-09-24 | 2021-09-28 | 2021-10-26 | 2021-11-24 | 2021-09-30 | 2021-10-08 | 2021-09-30 | 2021-10-30 | 2021-10-09 | 2021-11-11 | E1 MIDC Industrial Area (PH III), Chakan 410501 Pune - Maharashtra (INDIA) | 1 | 21 | 405 | sunil kokate | 91-9673334857 | gaipl@in.gestamp.com | sunil kokate | 91-9673334857 | gaipl@in.gestamp.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2021-09-22 | 2021-09-23 | 1 |  | Mahesh Durgale
755 | 2021-09-22 | 6:27:49 PM | Sapl0334 | 1 | 9 | P013 | 778 | 791 | 22100457 | 35 | 0 | N0240 | 2021-09-22 | BULK HEAD STRUCTURE | Mahesh Durgale | 5 | 2021-09-10 | 2021-09-16 | 2021-09-17 | 2021-09-19 | 2021-09-30 | 2021-10-15 | 2021-10-16 | 2021-10-19 | 2021-10-20 | 2021-10-23 | 2021-10-26 | 2021-10-30 | 2021-10-16 | 2021-11-06 | 2021-11-06 | 2021-10-10 | Sipcot-1, Plot No. B12A & B14, Sidco Industrial Estate, Sipcot - I, Hosur 635126 Tamil Nadu India | 1 | 31 | 680 | S.Senthil Kumar | 04344 - 279848, 276001 | prabhaengineers@eth.net | S.Senthil Kumar | 04344 - 279848, 276001 | prabhaengineers@eth.net | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 0 |  | 0 |  | 2021-09-30 | 2021-09-30 | 1 |  | Mahesh Durgale
756 | 2021-09-22 | 6:50:26 PM | Sapl0335 | 1 | 9 | P013 | 779 | 792 | 22100457 | 35 | 0 | N0241 | 2021-09-22 | NEW BULK HEAD OUTRIGGER | Mahesh Durgale | 5 | 2021-09-07 | 2021-09-11 | 2021-09-12 | 2021-09-17 | 2021-09-20 | 2021-10-12 | 2021-09-22 | 2021-10-23 | 2021-10-20 | 2021-09-30 | 2021-10-27 | 2021-10-30 | 2021-11-01 | 2021-10-05 | 2021-10-07 | 2021-11-10 | Sipcot-1, Plot No. B12A & B14, Sidco Industrial Estate, Sipcot - I, Hosur 635126 Tamil Nadu India | 1 | 31 | 680 | S.Senthil Kumar | 04344 - 279848, 276001 | prabhaengineers@eth.net | S.Senthil Kumar | 04344 - 279848, 276001 | prabhaengineers@eth.net | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 0 |  | 0 |  | 2021-09-29 | 2021-09-30 | 1 |  | Mahesh Durgale
757 | 2021-10-01 | 12:04:35 PM | Sapl0335 | 1 | 9 | N002 | 780 | 793 | verbal_nmc_01/10/21 | 35 | 0 | N0242 | 2021-10-01 | BULK HEAD STRUCTURE | Mahesh Durgale | 5 | 2021-10-01 | 2021-10-04 | 2021-10-04 | 2021-10-06 | 2021-10-07 | 2021-10-10 | 2021-10-10 | 2021-10-13 | 2021-10-12 | 2021-10-15 | 2021-10-15 | 2021-10-19 | 2021-10-19 | 2021-10-21 | 2021-10-21 | 2021-10-23 | Plot No?. ?22?,?Secot ?- ?12?,?Itbt ? Park?,?Sidcul?, ?Pant ? Nagar?,?Udham Singh Nagar?,?Pantnagar Uttarakhand India | 1 | 34 | 679 | Santosh Sisodia | 9927715666 | hgv@dsfgb.gb | Santosh Sisodia | 9927715666 | hgv@dsfgb.gb | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 0 |  | 0 |  | 2021-11-08 | 2021-11-09 | 1 |  | Mahesh Durgale
758 | 2021-10-02 | 12:02:14 PM | Sapl0335 | 1 | 9 | N002 | 781 | 794 | verbal_nmc_01/10/21 | 35 | 0 | N0243 | 2021-10-02 | NEW BULK HEAD OUTRIGGER | Mahesh Durgale | 5 | 2021-09-18 | 2021-10-19 | 2021-09-25 | 2021-10-26 | 2021-11-03 | 2021-10-06 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-11 | 2021-10-15 | 2021-10-17 | 2021-10-21 | 2021-10-22 | 2021-10-25 | Plot No?. ?22?,?Secot ?- ?12?,?Itbt ? Park?,?Sidcul?, ?Pant ? Nagar?,?Udham Singh Nagar?,?Pantnagar Uttarakhand India | 1 | 34 | 679 | Santosh Sisodia | 9927715666 | hgv@dsfgb.gb | Santosh Sisodia | 9927715666 | hgv@dsfgb.gb | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 0 |  | 0 |  | 2021-10-08 | 2021-10-09 | 1 |  | Mahesh Durgale
759 | 2022-01-19 | 11:58:21 AM | Sapl0335 | 1 | 9 | G020 | 782 | 795 | 5804019642 | 38 | 0 | J0149 | 2021-10-06 | pallets supply | Mahesh Durgale | 5 | 2021-10-01 | 2021-10-02 | 2021-10-03 | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-11 | 2021-10-15 | 2021-10-08 | 2021-10-22 | 2021-10-23 | 2021-10-26 | E1 MIDC Industrial Area (PH III), Chakan 410501 Pune - Maharashtra (INDIA) | 1 | 21 | 405 | Mr. Sunil Kokate | 91-9673334857 | gaipl@in.gestamp.com | Mr. Sunil Kokate | 91-9673334857 | gaipl@in.gestamp.com | - | - | - | - | 1 | 1 | 1 | 43Nos body side modification TPL done in J0145 | - |  | 1 | 1 | 1 |  | 1 | Dispatched | 2021-10-07 | 2021-10-09 | 1 |  | Mahesh Durgale
761 | 2021-10-23 | 2:29:01 PM | sapl0001 | 1 | 9 | G020 | 784 | 797 | 5810001077 | 38 | 0 | J0150 | 2021-10-23 | New tail gate supply | Mahesh Durgale | 5 | 2021-10-13 | 2021-10-15 | 2021-10-15 | 2021-10-18 | 2021-10-24 | 2021-11-04 | 2021-11-07 | 2021-11-09 | 2021-11-11 | 2021-11-17 | 2021-11-17 | 2021-11-19 | 2021-11-07 | 2021-11-29 | 2021-11-28 | 2021-11-30 | GE STAMP AUTOMOTIVE INDIA PVT LTD E?1 ?MIDC Industrial Area ?(?PH III?)?, ?Chakan? 410501 ?Pune ?- ?Maharashtra ?(?INDIA?)? | 1 | 21 | 405 | sunil kokate | 91-9673334857 | gaipl@in.gestamp.com | sunil kokate | 91-9673334857 | gaipl@in.gestamp.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2021-10-26 | 2021-10-27 | 1 |  | Mahesh Durgale
762 | 2022-01-30 | 9:46:51 AM | sapl0001 | 1 | 9 | G020 | 785 | 798 | 5810001086 | 38 | 0 | J0151 | 2021-10-23 | Supply of Pallets | Mahesh Durgale | 5 | 2021-10-11 | 2021-10-15 | 2021-10-15 | 2021-10-16 | 2021-10-22 | 2021-11-16 | 2021-11-17 | 2021-11-22 | 2021-11-21 | 2021-11-26 | 2021-11-26 | 2021-11-29 | 2021-11-17 | 2021-11-30 | 2021-11-30 | 2021-12-02 | E1 (Part),Chakan Midc Road, Phase-Iii,Kharabwadi, Chakan, Talegaon Chakan Road, Mahalunge Ingale, Maharashtra Pune, Maharashtra, India - 410501. | 1 | 21 | 405 | sunil kokate | 91-9673334857 | gaipl@in.gestamp.com | sunil kokate | 91-9673334857 | gaipl@in.gestamp.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2021-10-26 | 2021-10-28 | 1 |  | Mahesh Durgale
763 | 2021-10-29 | 10:47:21 AM | Sapl0335 | 1 | 9 | S036 | 786 | 799 | verbal_nmc_29/10/21 | 43 | 0 | T0039 | 2021-10-29 | AGV WITH MECANUM WHEEL | Mahesh Durgale | 5 | 2021-10-31 | 2021-11-09 | 2021-11-09 | 2021-11-12 | 2021-11-12 | 2021-11-19 | 2021-11-20 | 2021-11-27 | 2021-11-27 | 2021-11-30 | 2021-11-24 | 2021-11-27 | 2021-11-28 | 2021-11-30 | 2021-11-25 | 2021-12-01 | Gut ?205?, ?Kasurdi?,?Khed Shivapur ? Off Pune?-?Bangalore Highway ? Tal?.?Bhor?, ?Pune ?412205? | 1 | 21 | 405 | MAHESH | 9156476626 | mahesh@synergytyechs.com | MAHESH | 9156476626 | mahesh@synergytyechs.com | - | - | - | - | 1 | 1 | 1 | -- | - |  | 0 | 1 | 0 |  | 0 |  | 2021-11-09 | 2021-11-16 | 1 |  | Mahesh Durgale
764 | 2021-10-29 | 3:47:57 PM | Sapl0335 | 1 | 9 | D007 | 787 | 800 | DZ/07/2021 | 38 | 0 | J0152 | 2021-10-29 | Design, Supply & Assembly for Troll Ball Assembly | Mahesh Durgale | 5 | 2021-10-29 | 2021-11-06 | 2021-11-06 | 2021-10-11 | 2021-11-11 | 2021-11-23 | 2021-11-23 | 2021-11-25 | 2021-11-25 | 2021-11-26 | 2021-11-26 | 2021-11-28 | 2021-11-28 | 2021-11-30 | 2021-12-01 | 2021-12-02 | Flat No?.?2001?, ?B Wing?, ?Shubh ? Kalyan Society?, ?Nanded City ? Sinhgad Road?, ?Pune?-?411041? | 1 | 21 | 405 | Mr. Amit Kokane | +91 7798464040 | amitkokane2036@gmail.com | Mr. Amit kokane | +91 7798464040 | amitkokane2036@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 0 |  | 0 |  | 2021-11-11 | 2021-11-16 | 1 |  | Mahesh Durgale
767 | 2022-01-25 | 11:46:02 AM | Sapl0334 | 1 | 9 | G020 | 789 | 803 | 5810001144 | 34 | 0 | S0198 | 2022-01-24 | New container supply of Body side notch back pallets LH & RH | Mr Vinodkumar Kadepure | 5 | 2022-01-24 | 2022-01-27 | 2022-01-27 | 2022-01-29 | 2022-01-29 | 2022-02-20 | 2022-02-20 | 2022-02-27 | 2022-02-25 | 2022-02-27 | 2022-02-21 | 2022-02-26 | 2022-02-20 | 2022-03-01 | 2022-03-02 | 2022-03-04 | E????1 ???(???Part????)??,??Chakan Midc Road?, ? Phase????-???III?,??Kharabwadi?, ??Chakan??, ? Talegaon Chakan Road??, ? Mahalunge Ingale??, ? Maharashtra??? | 1 | 21 | 405 | Mr sunil kokate | 99224333407 | gaipl@in.gestamp.com | - | 99224333407 | gaipl@in.gestamp.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2022-01-29 | 2022-02-10 | 1 |  | Mr Vinodkumar Kadepure
768 | 2022-01-24 | 2:50:25 PM | Sapl0335 | 1 | 9 | G020 | 790 | 804 | 5804019559 | 34 | 0 | S0199 | 2022-01-24 | Modification tail gate outer lower pallets manufacturing | Mr Vinodkumar Kadepure | 5 | 2022-01-24 | 2022-01-28 | 2022-01-28 | 2022-01-29 | 2022-01-29 | 2022-02-28 | 2022-02-28 | 2022-03-02 | 2022-02-02 | 2022-03-05 | 2022-02-28 | 2022-03-02 | 2022-03-03 | 2022-03-05 | 2022-03-03 | 2022-02-05 | E???1 ???(???Part???)??,??Chakan Midc Road??, ? ??Phase???-???Iii??,??Kharabwadi??, ??Chakan??, ??Talegaon ? Chakan Road??, ??Mahalunge ??? Ingale??, ??Maharashtra??? | 1 | 21 | 405 | Mr sunil kokate | 99224333407 | gaipl@in.gestamp.com | Mr sunil kokate | 99224333407 | gaipl@in.gestamp.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2022-01-29 | 2022-01-31 | 1 |  | Mr Vinodkumar Kadepure
769 | 2022-01-24 | 4:36:39 PM | Sapl0335 | 1 | 9 | G020 | 791 | 805 | 5810001086 | 34 | 0 | S0200 | 2022-01-24 | Supply of new tail gate outer upper pallets | Mr Vinodkumar Kadepure | 5 | 2022-01-24 | 2022-01-28 | 2022-01-28 | 2022-01-29 | 2022-01-29 | 2022-02-28 | 2022-02-28 | 2022-03-02 | 2022-03-02 | 2022-03-05 | 2022-02-28 | 2022-03-02 | 2022-03-05 | 2022-03-08 | 2022-03-08 | 2022-03-10 | E???1 ???(???Part???)??,??Chakan Midc Road??, ? ??Phase???-???Iii??,??Kharabwadi??, ??Chakan??, ??Talegaon ? Chakan Road??, ??Mahalunge ??? Ingale??, ??Maharashtra??? Pune??, ??Maharashtra??, ??India ???- ???410501???.?? | 1 | 21 | 405 | Mr sunil kokate | 99224333407 | gaipl@in.gestamp.com | Mr sunil kokate | 99224333407 | gaipl@in.gestamp.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2022-01-28 | 2022-01-31 | 1 |  | Mr Vinodkumar Kadepure
770 | 2022-03-09 | 3:12:06 PM | Sapl0331 | 1 | 9 | G020 | 792 | 806 | 5810001077 | 34 | 0 | S0201 | 2022-01-24 | Supply of new tail gate outer upper pallets | Mr Vinodkumar Kadepure | 5 | 2022-01-24 | 2022-01-28 | 2022-01-28 | 2022-01-29 | 2022-01-29 | 2022-02-20 | 2022-02-20 | 2022-02-22 | 2022-02-22 | 2022-02-26 | 2022-01-30 | 2022-02-20 | 2022-02-20 | 2022-03-01 | 2022-03-02 | 2022-03-05 | E1 (Part),Chakan Midc Road, Phase-Iii,Kharabwadi, Chakan, Talegaon Chakan Road, Mahalunge Ingale, Maharashtra | 1 | 21 | 405 | Mr sunil kokate | 99224333407 | gaipl@in.gestamp.com | Mr sunil kokate | 99224333407 | gaipl@in.gestamp.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2022-01-25 | 2022-01-31 | 1 |  | Mr Vinodkumar Kadepure
804 | 2022-08-04 | 11:09:36 AM | Sapl0335 | 1 | 10 | T019 | 818 | 838 | verbal_NMC_22-07-22 | 43 | 0 | T0042 | 2022-07-22 | Cross member assy body mount | Mr.gurunath | 5 | 2022-07-21 | 2022-07-22 | 2022-07-22 | 2022-07-23 | 2022-07-23 | 2022-08-05 | 2022-08-05 | 2022-08-06 | 2022-08-19 | 2022-08-20 | 2022-08-10 | 2022-08-18 | 2022-08-05 | 2022-08-26 | 2022-07-27 | 2022-08-28 | PLOT A-1/4, PHASE IV, MVML VENDOR PARK CHAKAN,M.I.D.C CHAKAN | 1 | 21 | 405 | Rahul Agnihotri | 9090909090 | rahul.agnihotri@trackcomponents.in | Rahul Agnihotri | 9090909090 | rahul.agnihotri@trackcomponents.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2022-07-22 | 2022-07-22 | 1 |  | Mr.Vinodkumar
805 | 2022-07-23 | 1:50:20 PM | Sapl0335 | 1 | 10 | E003 | 819 | 839 | 1214 | 35 | 0 | N0263 | 2022-07-23 | TROLLEY | Mr.Madan kumbarkar | 5 | 2022-07-23 | 2022-07-24 | 2022-07-24 | 2022-07-25 | 2022-07-25 | 2022-07-30 | 2022-08-01 | 2022-08-03 | 2022-08-06 | 2022-08-07 | 2022-08-04 | 2022-08-06 | 2022-08-09 | 2022-08-11 | 2022-08-11 | 2022-08-11 | Euler Motors? A?-?39 ?Mohan Co?-?Operative ? Ind?.?Estate Near Mohan Estate ? Metro Station New Delhi?, ?Delhi ? 110017? | 1 | 10 | 133 | abcd | 9090909090 | xyz@gmail.com | abcd | 9090909090 | xyz@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 0 |  | 2022-07-23 | 2022-07-23 | 1 |  | Mr.Vinodkumar
806 | 2022-07-23 | 2:41:47 PM | Sapl0335 | 1 | 10 | E004 | 820 | 840 | 1218 | 34 | 0 | S0205 | 2022-07-23 | Railing work | Mr.pravin | 5 | 2022-07-23 | 2022-07-24 | 2022-07-24 | 2022-07-25 | 2022-07-26 | 2022-07-30 | 2022-08-01 | 2022-08-03 | 2022-08-04 | 2022-08-06 | 2022-08-01 | 2022-08-03 | 2022-08-05 | 2022-08-13 | 2022-08-13 | 2022-08-15 | Topline Logistic Park Pvt Ltd At ? Village Aurangabad Mitnol ? &?Dighot Palwal Haryana ?121105? | 1 | 13 | 173 | abcd | 9090909090 | xyz@gmail.com | abcd | 9090909090 | xyz@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 0 |  | 2022-07-23 | 2022-07-23 | 1 |  | Mr.Vinodkumar
807 | 2022-10-17 | 1:56:21 PM | Sapl0335 | 1 | 10 | F007 | 821 | 841 | verbal_NMC_27-07-22 | 35 | 0 | N0264 | 2022-07-27 | Diabolla Roller Chain drive Conveyor | Mr.Madan kumbhar | 5 | 2022-07-30 | 2022-07-30 | 2022-07-31 | 2022-08-05 | 2022-08-04 | 2022-08-20 | 2022-08-26 | 2022-08-28 | 2022-08-30 | 2022-08-30 | 2022-08-20 | 2022-08-25 | 2022-08-26 | 2022-09-06 | 2022-09-06 | 2022-09-08 | Plot-360, Sector 3, Industrial Model Twp, Bawal, Haryana 123501 | 1 | 13 | 183 | Tushar | 06072708690 | purchase@fjmcylinders.com | TUSHAR | 06072708690 | purchase@fjmcylinders.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2022-07-27 | 2022-07-27 | 1 |  | Mr.Gurunath Jamdar
808 | 2022-08-03 | 2:53:44 PM | Sapl0335 | 1 | 10 | E004 | 822 | 842 | verbal_NMC_2-08-22 | 34 | 0 | S0206 | 2022-08-02 | Gun rail set | Mr.Sanket raut | 5 | 2022-08-03 | 2022-08-03 | 2022-08-03 | 2022-08-05 | 2022-08-05 | 2022-08-12 | 2022-08-15 | 2022-08-17 | 2022-08-20 | 2022-08-20 | 2022-08-10 | 2022-08-15 | 2022-08-15 | 2022-08-26 | 2022-08-26 | 2022-08-29 | Topline Logistic Park Pvt Ltd At ? Village Aurangabad Mitnol ? &?Dighot Palwal Haryana ?121105? | 1 | 13 | 173 | acbd | 9090909090 | xyz@gmail.com | abcd | 9090909090 | xyz@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2022-08-04 | 2022-08-05 | 1 |  | Mr.Gurunath Jamdar
809 | 2022-08-17 | 3:39:37 PM | Sapl0335 | 1 | 10 | E004 | 823 | 843 | verbal_NMC_17-08-22 | 34 | 0 | S0207 | 2022-08-17 | Gunrail assembly | Mr.Sanket raut | 5 | 2022-08-03 | 2022-08-03 | 2022-08-05 | 2022-08-05 | 2022-08-05 | 2022-08-12 | 2022-08-16 | 2022-08-17 | 2022-08-19 | 2022-08-20 | 2022-08-12 | 2022-08-15 | 2022-08-23 | 2022-08-26 | 2022-08-27 | 2022-08-27 | Topline Logistic Park Pvt Ltd At ??? Village Aurangabad Mitnol ??? &??Dighot Palwal Haryana ???121105 | 1 | 13 | 173 | abcd | 9090909090 | xyz@gmail.com | abcd | 9090909090 | xyz@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 0 |  | 2022-08-18 | 2022-08-18 | 1 |  | Mr.Gurunath Jamdar
810 | 2022-09-02 | 10:43:27 AM | Sapl0335 | 1 | 10 | G020 | 824 | 844 | verbal_NMC_2-9-22 | 35 | 0 | N0265 | 2022-09-02 | Blue blanking pallets | Mr.mayur todkar | 5 | 2022-09-01 | 2022-09-02 | 2022-09-02 | 2022-09-03 | 2022-09-03 | 2022-09-07 | 2022-09-07 | 2022-09-10 | 2022-09-10 | 2022-09-11 | 2022-09-09 | 2022-09-10 | 2022-09-12 | 2022-09-13 | 2022-09-13 | 2022-09-13 | E?1 ?(?Part?)?,?Chakan Midc Road?, ? Phase?-?Iii?,?Kharabwadi?, ?Chakan?, ? Talegaon Chakan Road?, ? Mahalunge Ingale?, ? Maharashtra | 1 | 21 | 405 | sunil kokate | 9090909090 | gaipl@in.gestamp.com | sunil kokate | 9090909090 | gaipl@in.gestamp.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 0 |  | 2022-09-02 | 2022-09-02 | 1 |  | Mr.sanket raut
811 | 2022-09-07 | 4:49:48 PM | Sapl0335 | 1 | 10 | E004 | 825 | 845 | 1912 | 35 | 0 | N0266 | 2022-09-02 | TROLLEY | Mr.Sanket raut | 5 | 2022-09-02 | 2022-09-03 | 2022-09-04 | 2022-09-04 | 2022-09-05 | 2022-09-09 | 2022-09-10 | 2022-09-12 | 2022-09-12 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-10 | 2022-09-16 | 2022-09-17 | 2022-09-17 | EMAX engineering system pvt ltd. Pplot no.746 sector 69 imt faridabaad 121004, | 1 | 13 | 173 | abcd | 9090909090 | xyz@gmail.com | abcd | 9090909090 | xyz@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 0 |  | 2022-09-02 | 2022-09-02 | 1 |  | Mr.Vinodkumar
812 | 2022-10-15 | 4:00:17 PM | Sapl0335 | 1 | 10 | G017 | 826 | 846 | verbal_NMC_2-9-22 | 35 | 0 | N0267 | 2022-09-02 | CHUCK WHEEL | Mr.Sanket raut | 5 | 2022-09-02 | 2022-09-03 | 2022-09-03 | 2022-09-03 | 2022-09-04 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-10 | 2022-09-11 | 2022-09-12 | 2022-09-12 | 2022-09-07 | 2022-09-13 | 2022-09-13 | 2022-09-14 | Plant ?7?, ?Pirojshanagar?, ?Wikhroli?, ? Mumbai ?400079? | 1 | 21 | 398 | Gajendrasingh J Bhadauria | 9820389211 | gjb@godrej.com | Gajendrasingh J Bhadauria | 9820389211 | gjb@godrej.com | - | - | - | - | 1 | 1 | 1 | -- | - |  | 0 | 0 | 1 |  | 0 |  | 2022-09-02 | 2022-09-02 | 1 |  | Mr.Vinodkumar
813 | 2022-09-06 | 11:28:15 AM | Sapl0335 | 1 | 10 | E004 | 827 | 847 | verbal_NMC_6-9-22 | 35 | 0 | N0268 | 2022-09-06 | Materials | vinodkumar | 5 | 2022-09-02 | 2022-09-03 | 2022-09-04 | 2022-09-05 | 2022-09-07 | 2022-09-08 | 2022-09-08 | 2022-09-09 | 2022-09-08 | 2022-09-10 | 2022-09-10 | 2022-09-10 | 2022-09-10 | 2022-09-10 | 2022-09-11 | 2022-09-11 | Topline Logistic Park Pvt Ltd At ? Village Aurangabad Mitnol ? &?Dighot Palwal Haryana ?121105? | 1 | 13 | 173 | abcd | 9090909090 | xyz@gmail.com | abcd | 9090909090 | xyz@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 0 |  | 2022-09-08 | 2022-09-06 | 1
815 | 2022-09-11 | 9:54:15 AM | Sapl0335 | 1 | 10 | C004 | 828 | 849 | IND7175229 | 35 | 0 | N0270 | 2022-09-11 | RGV modification | Mr.gurunath | 2 | 2022-09-01 | 2022-09-02 | 2022-09-03 | 2022-09-03 | 2022-09-03 | 2022-09-04 | 2022-09-04 | 2022-09-05 | 2022-09-05 | 2022-09-05 | 2022-09-12 | 2022-09-12 | 2022-09-13 | 2022-09-13 | 2022-09-14 | 2022-09-15 | Dhanukar Colony Kothrud Pune Maharashtra 411038 India | 1 | 21 | 405 | Prajakta | 9075564236 | adesh.a.sheth@cummins.com | Prajakta | 9075564236 | adesh.a.sheth@cummins.com | - | - | - | - | 1 | 1 | 1 | -- | - |  | 0 | 0 | 0 |  | 0 |  | 2022-09-08 | 2022-09-08 | 1 |  | Mr.Vinodkumar
816 | 2022-09-11 | 4:11:01 PM | Sapl0335 | 1 | 10 | E004 | 829 | 850 | verbal_dns_09-11 | 35 | 0 | N0271 | 2022-09-11 | Materials | Mr.mayur todkar | 5 | 2022-09-10 | 2022-09-11 | 2022-09-11 | 2022-09-12 | 2022-09-11 | 2022-09-12 | 2022-09-11 | 2022-09-13 | 2022-09-13 | 2022-09-14 | 2022-09-14 | 2022-09-14 | 2022-09-15 | 2022-09-15 | 2022-09-16 | 2022-09-17 | Topline Logistic Park Pvt Ltd At ? Village Aurangabad Mitnol ? &?Dighot Palwal Haryana ?121005? | 1 | 13 | 173 | abcd | 9090909090 | xyz@gmail.com | abcd | 9090909090 | xyz@gmail.com | - | - | - | - | 1 | 1 | 1 | -- | - |  | 0 | 0 | 0 |  | 0 |  | 2022-09-11 | 2022-09-11 | 1 |  | Mr.sanket raut
817 | 2022-09-12 | 12:20:14 PM | Sapl0335 | 1 | 10 | T002 | 830 | 851 | 9300024898 | 35 | 0 | N0272 | 2022-09-12 | I&C_Frame Fixtures Modification for Phas | Mr.Madan kumbarkar | 5 | 2022-08-25 | 2022-08-26 | 2022-08-27 | 2022-08-28 | 2022-09-01 | 2022-09-05 | 2022-09-07 | 2022-09-08 | 2022-09-14 | 2022-09-15 | 2022-09-15 | 2022-09-16 | 2022-09-16 | 2022-09-28 | 2022-09-28 | 2022-09-30 | Mplp Pimpri Plant | 1 | 21 | 405 | abcd | 9090909090 | xyz@gmail.com | abcd | 9090909090 | xyz@gmail.com | - | - | - | - | 1 | 1 | 1 | --- | - |  | 0 | 0 | 0 |  | 0 |  | 2022-09-08 | 2022-09-09 | 1 |  | Mr.Vinodkumar
818 | 2022-09-12 | 2:04:26 PM | Sapl0335 | 1 | 10 | T002 | 831 | 852 | 9000036686 | 35 | 0 | N0273 | 2022-09-12 | ILCV Frame line fixtures | Mr.mayur todkar | 5 | 2022-09-01 | 2022-09-02 | 2022-09-02 | 2022-09-03 | 2022-09-03 | 2022-09-07 | 2022-09-07 | 2022-09-10 | 2022-09-11 | 2022-09-14 | 2022-09-14 | 2022-09-19 | 2022-09-19 | 2022-09-30 | 2022-09-30 | 2022-10-04 | Mplp Pimpri Plant | 1 | 21 | 405 | GOPICHAND KUNDNANI | 9028097908 | xyz@gmail.com | GOPICHAND KUNDNANI | 9028097908 | xyz@gmail.com | - | - | - | - | 1 | 1 | 1 | -- | - |  | 0 | 0 | 0 |  | 0 |  | 2022-09-13 | 2022-09-13 | 1 |  | Mr.Vinodkumar
822 | 2022-09-17 | 2:35:11 PM | Sapl0335 | 1 | 10 | G020 | 835 | 856 | verbal_nmc_17-09-22 | 34 | 0 | S0208 | 2022-09-17 | Modification pallets for SK-SUV & NOTCH BACK | Mr.Sanket raut | 5 | 2022-09-15 | 2022-09-16 | 2022-09-16 | 2022-09-17 | 2022-09-17 | 2022-09-27 | 2022-09-28 | 2022-09-30 | 2022-09-30 | 2022-10-06 | 2022-10-07 | 2022-10-12 | 2022-10-12 | 2022-10-20 | 2022-10-20 | 2022-10-20 | E?1 ?(?Part?)?,?Chakan Midc Road?, ? Phase?-?Iii?,?Kharabwadi?, ?Chakan?, ? Talegaon Chakan Road?, ? Mahalunge Ingale?, ? Maharashtra? | 1 | 21 | 405 | Mr. Niroop | 9119480205 | gaipl@in.gestamp.com | Mr. Niroop | 9119480205 | gaipl@in.gestamp.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2022-09-17 | 2022-09-17 | 1 |  | Mr.Vinodkumar
824 | 2022-09-23 | 3:14:21 PM | Sapl0335 | 1 | 10 | E004 | 837 | 858 | verbal_nmc_23-9-2022 | 34 | 0 | S0210 | 2022-09-23 | Rails | Mr.Sanket raut | 5 | 2022-09-22 | 2022-09-23 | 2022-09-23 | 2022-09-24 | 2022-09-24 | 2022-09-25 | 2022-09-25 | 2022-09-26 | 2022-09-26 | 2022-09-27 | 2022-09-26 | 2022-09-28 | 2022-09-28 | 2022-09-29 | 2022-09-30 | 2022-09-30 | Topline Logistic Park Pvt Ltd At ? Village Aurangabad Mitnol ? &?Dighot Palwal Haryana ?121005? | 1 | 13 | 173 | abcd | 900900900 | xyz@gmail.com | abcd | 900900900 | xyz@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 0 |  | 2022-09-23 | 2022-09-23 | 1 |  | Mr.mayur todkar
827 | 2022-10-14 | 4:20:24 PM | sapl0325 | 1 | 10 | E004 | 840 | 861 | 2527 | 34 | 0 | S0211 | 2022-10-14 | CROSS RAIL&LONG RAIL | vinodkumar | 5 | 2022-10-07 | 2022-10-08 | 2022-10-09 | 2022-10-10 | 2022-10-11 | 2022-10-18 | 2022-10-19 | 2022-10-20 | 2022-10-21 | 2022-10-22 | 2022-10-18 | 2022-10-20 | 2022-10-23 | 2022-10-26 | 2022-10-25 | 2022-10-28 | Topline Logistic Park Pvt Ltd ? At Village Aurangabad Mitnol ? &?Dighot Palwal Haryana ? 121005 | 1 | 13 | 173 | abcd | 9090909090 | xyz@gmail.com | xyz | 9090909090 | xyz@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 0 |  | 2022-10-10 | 2022-10-18 | 1 |  | Sanket
828 | 2022-10-21 | 5:21:27 PM | sapl0325 | 1 | 10 | S041 | 841 | 862 | verbal_nmc_21-10-2022 | 35 | 0 | N0278 | 2022-10-20 | Trolley assembly | Mr.Sanket raut | 5 | 2022-10-01 | 2022-10-02 | 2022-10-03 | 2022-10-04 | 2022-10-04 | 2022-10-11 | 2022-10-11 | 2022-10-13 | 2022-10-13 | 2022-10-18 | 2022-10-10 | 2022-10-17 | 2022-10-17 | 2022-10-18 | 2022-10-19 | 2022-10-21 | Sr No ?38?/?1?, ?Khedekar Industrial ? Estate?, ?Narhe?-?Dhayari Road?, ? Narhegaon?, ?Tal ?- ?Haveli?, ?Dist ?- ? Pune ?411041? | 1 | 21 | 405 | Sameer Pilane | 9822112841 | sales@samrudhiengg.com | Sameer Pilane | 9822112841 | sales@samrudhiengg.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 0 |  | 0 |  | 2022-10-03 | 2022-10-06 | 1 |  | Mr.Vinodkumar
831 | 2022-11-08 | 12:36:09 PM | Sapl0335 | 1 | 10 | C004 | 845 | 865 | IND7230900 | 35 | 0 | N0281 | 2022-11-08 | RGV modification | Mr.gurunath | 2 | 2022-11-08 | 2022-11-09 | 2022-11-09 | 2022-11-09 | 2022-11-09 | 2022-11-21 | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-05 | 2022-11-18 | 2022-11-28 | 2022-12-07 | 2022-12-08 | 2022-12-07 | 2022-12-09 | Dhanukar Colony Kothrud Pune Maharashtra 411038 India | 1 | 21 | 405 | Prajakta S Brahme | 9075564236 | prajakta.brahme@cummins.com | Prajakta S Brahme | 9075564236 | prajakta.brahme@cummins.com | - | - | - | - | 1 | 1 | 1 | -- | - |  | 0 | 0 | 1 |  | 0 |  | 2022-11-09 | 2022-11-10 | 1 |  | Mr.Vinodkumar
832 | 2023-06-24 | 10:03:43 AM | Sapl0335 | 1 | 10 | A036 | 846 | 866 | verbal_NMC_9-11-22 | 35 | 0 | N0282 | 2022-11-09 | Robotic & Manual fixture | Mr.gurunath | 5 | 2022-11-09 | 2022-11-14 | 2022-11-15 | 2022-11-19 | 2022-11-19 | 2022-11-28 | 2022-12-06 | 2022-12-10 | 2022-12-12 | 2022-12-13 | 2022-11-28 | 2022-12-05 | 2022-12-06 | 2022-12-16 | 2022-12-14 | 2022-12-17 | Gate ?392?/?2 ?Mahalunge?, ? Chakan?-?Talegaon Road Pune? | 1 | 21 | 405 | Pramod Tathe | 8446410903 | acppl1.development@pansegroup.com | Pramod Tathe | 8446410903 | acppl1.development@pansegroup.com | - | - | - | - | 1 | 1 | 1 | -- | - |  | 1 | 1 | 1 |  | 0 |  | 2022-11-14 | 2022-11-14 | 1 |  | Mr.Vinodkumar
834 | 2022-11-09 | 12:00:29 PM | Sapl0335 | 1 | 10 | P014 | 848 | 868 | verbal_NMC_9-11-22 | 35 | 0 | N0284 | 2022-11-09 | Robotic and CMM stand | Mr.Sanket raut | 5 | 2022-11-15 | 2022-11-17 | 2022-11-17 | 2022-11-21 | 2022-11-22 | 2022-12-03 | 2022-12-13 | 2022-12-14 | 2022-12-16 | 2022-12-19 | 2022-12-03 | 2022-12-09 | 2022-12-13 | 2022-12-20 | 2022-12-20 | 2022-12-21 | B-78, Midc Ambad, Nashik, Maharashtra 422010 | 1 | 21 | 402 | xyz | 9090909090 | xyz@gmail.com | xyz | 9090909090 | xyz@gmail.com | - | - | - | - | 1 | 1 | 1 | -- | - |  | 0 | 0 | 1 |  | 0 |  | 2022-11-17 | 2022-11-17 | 1 |  | Mr.Vinodkumar
835 | 2022-11-09 | 2:51:53 PM | Sapl0335 | 1 | 10 | S007 | 849 | 869 | verbal_NMC_9-11-22 | 35 | 0 | N0285 | 2022-11-09 | Manual fixture | Mr.mayur todkar | 5 | 2022-11-14 | 2022-11-16 | 2022-11-18 | 2022-11-21 | 2022-11-21 | 2022-12-02 | 2022-12-19 | 2022-12-20 | 2022-12-21 | 2022-12-23 | 2022-12-03 | 2022-12-15 | 2022-12-25 | 2022-12-30 | 2022-12-30 | 2022-12-31 | Unit Ii?, ?Plot No?. ?305?-?306?,?Sector ? 7?,?Pcntda?,?Bhosari? | 1 | 21 | 405 | KANCHAN PANT | 9552503553 | kanchan@sharadaindustries.com | KANCHAN PANT | 9552503553 | kanchan@sharadaindustries.com | - | - | - | - | 1 | 1 | 1 | -- | - |  | 0 | 0 | 1 |  | 0 |  | 2022-11-16 | 2022-11-17 | 1 |  | Mr.Vinodkumar
836 | 2022-11-17 | 10:00:06 AM | Sapl0335 | 1 | 10 | G007 | 850 | 870 | 1800/1DR026470/CA1026586 | 35 | 0 | N0286 | 2022-11-17 | Low dip trolley | Mr.Sanket raut | 5 | 2022-11-17 | 2022-11-18 | 2022-11-17 | 2022-11-18 | 2022-11-18 | 2022-11-26 | 2022-11-26 | 2022-11-27 | 2022-11-29 | 2022-11-29 | 2022-11-28 | 2022-11-28 | 2022-11-28 | 2022-11-29 | 2022-11-29 | 2022-11-30 | GODREJ & BOYCE MFG.CO.LTD. PLANT- 7 TOOL ROOM PL-07 MUMBAI MH 400079 INDIA 0091 2267962757 State : Maharashtra | 1 | 21 | 398 | Atul patil | 9819817965 | patul@godrej.com | Atul patil | 9819817965 | patul@godrej.com | - | - | - | - | 1 | 1 | 1 | -- | - |  | 0 | 0 | 1 |  | 0 |  | 2022-11-17 | 2022-11-17 | 1 |  | Mr.Vinodkumar
837 | 2022-12-28 | 8:56:41 AM | Sapl0335 | 1 | 10 | E004 | 851 | 871 | 3261 | 34 | 0 | S0212 | 2022-11-21 | Gunr rail | Mr.mayur todkar | 5 | 2022-11-21 | 2022-11-22 | 2022-11-22 | 2022-11-22 | 2022-11-22 | 2022-11-26 | 2022-11-26 | 2022-11-27 | 2022-11-26 | 2022-11-26 | 2022-11-25 | 2022-11-25 | 2022-11-26 | 2022-11-28 | 2022-11-28 | 2022-11-28 | Topline Logistic Park Pvt Ltd At ? Village Aurangabad Mitnol ? &?Dighot Palwal Haryana ?121105? | 1 | 13 | 173 | Sachin goyal | 9090909090 | sachin.goyal@eulermotors.com | Sachin goyal | 9090909090 | sachin.goyal@eulermotors.com | - | - | - | - | 1 | 1 | 1 | -- | - |  | 0 | 1 | 1 |  | 0 |  | 2022-11-22 | 2022-11-22 | 1 |  | Mr.Vinodkumar
838 | 2022-11-22 | 11:48:49 AM | Sapl0335 | 1 | 10 | G017 | 852 | 872 | 1800/1DR026470/CA1026966 | 35 | 0 | N0287 | 2022-11-22 | Roof transfer trolley | Mr.mayur todkar | 5 | 2022-11-22 | 2022-11-23 | 2022-11-24 | 2022-11-26 | 2022-11-26 | 2022-12-09 | 2022-12-14 | 2022-12-16 | 2022-12-17 | 2022-12-19 | 2022-12-10 | 2022-12-13 | 2022-12-20 | 2022-12-22 | 2022-12-22 | 2022-12-24 | Plant ?7?, ?Pirojshanagar?, ?Wikhroli?, ? Mumbai ?400079? | 1 | 21 | 398 | Gajendrasingh J Bhadauria | 9820389211 | gjb@godrej.com | Gajendrasingh J Bhadauria | 9820389211 | gjb@godrej.com | - | - | - | - | 1 | 1 | 1 | -- | - |  | 1 | 1 | 1 |  | 0 |  | 2022-11-24 | 2022-11-24 | 1 |  | Mr.Vinodkumar
839 | 2022-11-29 | 10:08:25 AM | Sapl0335 | 1 | 10 | G017 | 853 | 873 | 1800/1DR026470/CA1026635 | 35 | 0 | N0288 | 2022-11-29 | Low dip trolley | Mr.mayur todkar | 5 | 2022-11-29 | 2022-11-30 | 2022-11-30 | 2022-12-01 | 2022-12-01 | 2022-12-16 | 2022-12-22 | 2022-12-24 | 2022-12-23 | 2022-12-24 | 2022-12-16 | 2022-12-22 | 2022-12-24 | 2022-12-26 | 2022-12-25 | 2022-12-28 | Plant ?7?, ?Pirojshanagar?, ?Wikhroli?, ? Mumbai ?400079? | 1 | 21 | 398 | Gajendrasingh J Bhadauria | 9820389211 | gjb@godrej.com | Gajendrasingh J Bhadauria | 9820389211 | gjb@godrej.com | - | - | - | - | 1 | 1 | 1 | -- | - |  | 0 | 0 | 1 |  | 0 |  | 2023-01-02 | 2022-12-03 | 1 |  | Mr.Vinodkumar
840 | 2022-12-08 | 1:59:06 PM | Sapl0335 | 1 | 10 | G020 | 854 | 874 | verbal_nmc_1-12-22 | 34 | 0 | S0213 | 2022-12-01 | Rear wheel house pallets | Mr.mayur todkar | 5 | 2022-12-01 | 2022-12-01 | 2022-12-01 | 2022-12-02 | 2022-12-02 | 2022-12-10 | 2022-12-16 | 2022-12-17 | 2022-12-17 | 2022-12-20 | 2022-12-10 | 2022-12-14 | 2022-12-16 | 2022-12-15 | 2022-12-15 | 2022-12-16 | E?1 ?(?Part?)?,?Chakan Midc Road?, ? Phase?-?Iii?,?Kharabwadi?, ?Chakan?, ? Talegaon Chakan Road?, ? Mahalunge Ingale?, ?Maharashtra? | 1 | 21 | 405 | Sagar Jadhav | 9673334857 | sagjadhav@in.gestamp.com | Sagar Jadhav | 9673334857 | sagjadhav@in.gestamp.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 0 |  | 2022-12-03 | 2022-12-03 | 1 |  | Mr.Vinodkumar kadepure
841 | 2022-12-01 | 4:45:31 PM | Sapl0335 | 1 | 10 | P015 | 856 | 875 | verbal_dns_1-12-22 | 34 | 0 | S0214 | 2022-12-01 | Gunr rail | Mr.mayur todkar | 5 | 2022-12-01 | 2022-12-01 | 2022-12-02 | 2022-12-02 | 2022-12-02 | 2022-12-02 | 2022-12-02 | 2022-12-03 | 2022-12-03 | 2022-12-03 | 2022-12-03 | 2022-12-04 | 2022-12-04 | 2022-12-05 | 2022-12-05 | 2022-12-05 | Topline Logistic Park Pvt Ltd ? At ? Village Aurangabad Mitnol ? &?Dighot Palwal Haryana ? 121005? | 1 | 13 | 169 | xyz | 9810615569 | NSH61569@gmail.com | xyz | 9810615569 | NSH61569@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 0 |  | 2022-12-02 | 2022-12-02 | 1 |  | Mr.Vinodkumar kadepure
842 | 2023-03-27 | 5:34:06 PM | Sapl0335 | 1 | 10 | S040 | 857 | 876 | Nmc_verbal_23-12-22 | 35 | 0 | N0289 | 2022-12-23 | BRACKET ASSY DEAD PEDAL | Mr. Sanket Raut | 5 | 2022-12-23 | 2023-01-04 | 2022-12-24 | 2023-01-04 | 2022-12-25 | 2023-01-04 | 2022-12-26 | 2022-12-28 | 2022-12-26 | 2022-12-27 | 2022-12-26 | 2022-12-26 | 2022-12-26 | 2022-12-27 | 2022-12-27 | 2022-12-27 | D-92, M.?I?.?D?.?C?. ?Satpur?, ?Nasik?-?07?. ? Phone?: ?0253?-?2350988?, ?Fax – ? 0253?-?6614154?.? | 1 | 21 | 402 | Anil patil | 9090909090 | smi22@rediffmail.com | Anil patil | 9090909090 | smi22@rediffmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 0 |  | 2022-12-23 | 2022-12-23 | 1 |  | Mr. vinodkumar
843 | 2023-01-04 | 9:00:25 AM | Sapl0335 | 1 | 10 | T019 | 858 | 877 | RP122-23/56 | 35 | 0 | N0290 | 2023-01-04 | Manual fixture | Mr.Vinodkumar | 5 | 2023-01-01 | 2023-01-02 | 2023-01-02 | 2023-01-03 | 2023-01-03 | 2023-01-05 | 2023-01-05 | 2023-01-06 | 2023-01-07 | 2023-01-07 | 2023-01-06 | 2023-01-06 | 2023-01-08 | 2023-01-09 | 2023-01-09 | 2023-01-10 | A?1?/?4 ?Mvml Vendor Park ? ,?Chakan Phase Iv?,, ?Midc?, ? Bhosari?, ?Pimpri?-?Chinchwad?, ? Maharashtra ?410501 | 1 | 21 | 405 | Rahul Agnihotri | 9090909090 | rahul.agnihotri@trackcomponents.in | Rahul Agnihotri | 9090909090 | rahul.agnihotri@trackcomponents.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 0 |  | 2023-01-04 | 2023-01-04 | 1 |  | Mr. vinodkumar
844 | 2023-01-09 | 1:28:39 PM | Sapl0335 | 1 | 10 | G017 | 859 | 878 | Nmc_verbal_04-01-23 | 35 | 0 | N0291 | 2023-01-04 | STILLAGE | Mr.mayur todkar | 5 | 2023-01-04 | 2023-01-07 | 2023-01-07 | 2023-01-09 | 2023-01-09 | 2023-01-11 | 2023-01-12 | 2023-01-14 | 2023-01-19 | 2023-01-20 | 2023-01-14 | 2023-01-18 | 2023-01-12 | 2023-01-21 | 2023-01-21 | 2023-01-23 | Plant ?7?, ?Pirojshanagar?, ?Wikhroli?, ? Mumbai ?400079? | 1 | 21 | 398 | Gajendrasingh J Bhadauria | 9820225024 | gjb@godrej.com | Gajendrasingh J Bhadauria | 9820225024 | gjb@godrej.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 0 |  | 2023-01-04 | 2023-01-04 | 1 |  | Mr. vinodkumar
846 | 2023-03-02 | 5:37:01 PM | Sapl0335 | 1 | 10 | J009 | 862 | 880 | 4500536639 | 37 | 0 | P0081 | 2023-03-02 | LOAD TROLLEY | Mr.mayur todkar | 5 | 2023-03-02 | 2023-03-02 | 2023-03-02 | 2023-03-04 | 2023-03-03 | 2023-03-04 | 2023-03-04 | 2023-03-05 | 2023-03-09 | 2023-03-10 | 2023-03-07 | 2023-03-08 | 2023-03-10 | 2023-03-11 | 2023-03-10 | 2023-03-12 | JBM Ogihara Automotive India Limited, Building No.06,Onsite Supplier Park,Toyota Kirloskar Motors,562109, Ramnagara | 1 | 17 | 293 | Mr. Joe Nirmal | 96633 02664 | purchase@joai.co.in | Mr. Joe Nirmal | 96633 02664 | purchase@joai.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 0 |  | 2023-03-02 | 2023-03-02 | 1 |  | Mr.Vinodkumar
848 | 2023-04-28 | 12:23:55 PM | Sapl0335 | 1 | 11 | G007 | 865 | 883 | CA1029330 | 35 | 0 | N0294 | 2023-04-28 | Roof trolley | Mr.mayur todkar | 5 | 2023-04-28 | 2023-04-28 | 2023-04-28 | 2023-04-29 | 2023-04-30 | 2023-05-03 | 2023-05-03 | 2023-05-05 | 2023-05-05 | 2023-05-12 | 2023-05-03 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-19 | 2023-05-20 | Plant - 17,Pirojshanager,Vikhroli | 1 | 21 | 405 | Gajendrasingh J Bhadauria | 9820225024 | gjb@godrej.com | Gajendrasingh J Bhadauria | 9820225024 | gjb@godrej.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 0 |  | 2023-04-28 | 2023-04-28 | 1 |  | Mr.Vinodkumar
851 | 2023-06-08 | 3:26:20 PM | Sapl0335 | 1 | 11 | S036 | 870 | 887 | Nmc_verbal_8-june-23 | 38 | 0 | J0153 | 2023-06-08 | Oil sampling unit | Mr.Sourabh Kamlbe | 5 | 2023-06-07 | 2023-06-08 | 2023-06-08 | 2023-06-09 | 2023-06-09 | 2023-06-12 | 2023-06-13 | 2023-06-13 | 2023-06-14 | 2023-06-14 | 2023-06-12 | 2023-06-12 | 2023-06-14 | 2023-06-15 | 2023-06-15 | 2023-06-15 | Gut ?205?, ?Kasurdi?,?Khed Shivapur ? Off Pune?-?Bangalore Highway ? Tal?.?Bhor?, ?Pune ?412205? | 1 | 21 | 405 | Vinod | 9156476626 | vinodkumar.kadepure@synergytechs.com | Vinod | 9156476626 | vinodkumar.kadepure@synergytechs.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 0 |  | 2023-06-09 | 2023-06-09 | 1 |  | Mr. Joshi
861 | 2023-07-21 | 4:21:20 PM | Sapl0335 | 1 | 11 | P018 | 875 | 895 | RM-2023-2024/Factory/07/24 | 35 | 0 | N0300 | 2023-07-21 | Scrap Conveyor | Mr.Sourabh Kamlbe | 2 | 2023-07-10 | 2023-07-14 | 2023-07-15 | 2023-07-19 | 2023-07-18 | 2023-07-31 | 2023-08-07 | 2023-08-10 | 2023-08-08 | 2023-08-11 | 2023-08-01 | 2023-08-07 | 2023-08-11 | 2023-08-16 | 2023-08-16 | 2023-08-18 | Gat No ?537?-??538?, ?Badhalwadi? Village ??Navlakh Umbre ? Talegaon Dabhade?, Taluka ? Maval? ? Pune?, ?Maharashtra ??410507?, In? | 1 | 21 | 405 | Siddhart | 7796687011 | siddharth.kadam@posco.net | Siddhart | 7796687011 | siddharth.kadam@posco.net | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 0 |  | 2023-07-21 | 2023-07-21 | 1 |  | Mr.Joshi
862 | 2023-08-07 | 1:45:54 PM | Sapl0335 | 1 | 11 | I002 | 876 | 896 | PMV073310-00 | 43 | 0 | T0043 | 2023-08-07 | HMI PANEL | Mr.Vinodkumar | 22 | 2023-08-07 | 2023-08-09 | 2023-08-09 | 2023-08-11 | 2023-08-11 | 2023-08-15 | 2023-08-17 | 2023-08-19 | 2023-08-23 | 2023-08-25 | 2023-08-15 | 2023-08-18 | 2023-08-17 | 2023-08-22 | 2023-08-23 | 2023-08-25 | B?-?13 ?Midc?, ?Baramati ?413133?, ? Maharashtra?, ?India? | 1 | 21 | 405 | VAIBHAV PAWAR | 9767056263 | vaibhav.pawar@ismt.co.in | VAIBHAV PAWAR | 9767056263 | vaibhav.pawar@ismt.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 0 |  | 2023-08-07 | 2023-08-07 | 1 |  | Mr. Joshi
864 | 2023-08-29 | 5:33:16 PM | Sapl0335 | 1 | 11 | I002 | 878 | 898 | PMV073444-00 | 37 | 0 | P0082 | 2023-08-29 | SPROCKET | Mr.Vinodkumar | 13 | 2023-08-29 | 2023-08-29 | 2023-08-30 | 2023-08-31 | 2023-08-31 | 2023-09-11 | 2023-09-15 | 2023-09-15 | 2023-09-16 | 2023-09-16 | 2023-09-12 | 2023-09-15 | 2023-09-15 | 2023-09-19 | 2023-09-18 | 2023-09-20 | B?-?13 ?Midc?, ?Baramati ?413133?, ? Maharashtra?, ?India? | 1 | 21 | 405 | VAIBHAV PAWAR | 9767056263 | vaibhav.pawar@ismt.co.in | VAIBHAV PAWAR | 9767056263 | vaibhav.pawar@ismt.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 0 |  | 2023-08-29 | 2023-08-29 | 1 |  | Mr. Joshi
865 | 2024-03-31 | 10:56:28 AM | Sapl0335 | 1 | 11 | T019 | 879 | 899 | Verbal_nmc_30-8-23 | 35 | 0 | N0302 | 2023-08-30 | CCB WELDING FIXTURE | Mr.Vinodkumar | 5 | 2023-09-06 | 2023-09-08 | 2023-09-08 | 2023-09-13 | 2023-09-13 | 2023-09-22 | 2023-09-29 | 2023-09-30 | 2023-10-10 | 2023-10-11 | 2023-09-23 | 2023-09-28 | 2023-09-29 | 2023-10-20 | 2023-10-20 | 2023-10-21 | TRACK COMPONENTS LIMITED- PLOT-NO F8 NASHIK INDIA 422007 STATE MAHARASTRA -27 | 1 | 21 | 405 | Rahul Agnihotri | 8010420497 | rahul.agnihotri@trackcomponents.in | Rahul Agnihotri | 8010420497 | rahul.agnihotri@trackcomponents.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 0 |  | 2023-08-30 | 2023-08-30 | 1 |  | Mr.Joshi
866 | 2023-09-02 | 10:38:51 AM | Sapl0335 | 1 | 11 | T019 | 880 | 900 | 23-24/1CO00056 | 35 | 0 | N0303 | 2023-09-02 | Cell Modification | Mr.Vinodkumar | 22 | 2023-09-02 | 2023-09-04 | 2023-09-04 | 2023-09-09 | 2023-09-09 | 2023-09-15 | 2023-09-20 | 2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-16 | 2023-09-19 | 2023-09-21 | 2023-09-22 | 2023-09-22 | 2023-09-23 | PLOT A-1/4, PHASE IV, MVML VENDOR PARK CHAKAN Phone No.: 07507925792 purchasepune@trackcomponents.in | 1 | 21 | 405 | Rahul Agnihotri | 8010420497 | rahul.agnihotri@trackcomponents.in | Rahul Agnihotri | 8010420497 | rahul.agnihotri@trackcomponents.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 0 |  | 2023-09-02 | 2023-09-02 | 1 |  | Mr.Joshi
867 | 2023-09-16 | 10:25:40 AM | Sapl0335 | 1 | 11 | S043 | 881 | 901 | Verbal_nmc_16-9-23 | 35 | 0 | N0304 | 2023-09-16 | Robotic fixture | Mr.Vinodkumar | 5 | 2023-09-16 | 2023-09-17 | 2023-09-17 | 2023-09-19 | 2023-09-19 | 2023-09-25 | 2023-09-28 | 2023-09-28 | 2023-09-29 | 2023-09-29 | 2023-09-25 | 2023-09-28 | 2023-09-28 | 2023-09-30 | 2023-09-30 | 2023-09-30 | B?-?5?, ?M?.?I?.?D?.?C?. ?Satpur?, ?Nasik?-?07?. ? Phone?: ?0253?-?2350988?, ?Fax – ? 0253?-?6614154?.? | 1 | 21 | 402 | Anil patil | 0253-2350988 | smi22@rediffmail.com | Anil patil | 0253-2350988 | smi22@rediffmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 0 |  | 2023-09-16 | 2023-09-16 | 1 |  | Mr. Joshi
868 | 2023-09-22 | 11:30:51 AM | Sapl0335 | 1 | 11 | I002 | 882 | 902 | PMV073666-00 | 35 | 0 | N0305 | 2023-09-22 | Hydrotester emulsion system | Mr.Vinodkumar | 5 | 2023-09-22 | 2023-09-23 | 2023-09-23 | 2023-09-24 | 2023-09-24 | 2023-10-07 | 2023-10-11 | 2023-10-11 | 2023-10-13 | 2023-10-13 | 2023-10-08 | 2023-10-10 | 2023-10-16 | 2023-10-17 | 2023-10-17 | 2023-10-18 | B?-?13 ?Midc?, ?Baramati ?413133?, ? Maharashtra?, ?India? | 1 | 21 | 405 | VAIBHAV PAWAR | 9767056263 | vaibhav.pawar@ismt.co.in | VAIBHAV PAWAR | 9767056263 | vaibhav.pawar@ismt.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 0 |  | 2023-09-22 | 2023-09-22 | 1 |  | Mr.Joshi
869 | 2023-10-09 | 12:09:31 PM | Sapl0335 | 1 | 11 | I002 | 883 | 903 | PCV061141-00 | 35 | 0 | N0306 | 2023-10-09 | Spare parts | Mr.Vinodkumar | 5 | 2023-10-09 | 2023-10-10 | 2023-10-09 | 2023-10-10 | 2023-10-10 | 2023-10-19 | 2023-10-20 | 2023-10-21 | 2023-10-23 | 2023-10-23 | 2023-10-19 | 2023-10-20 | 2023-10-25 | 2023-10-27 | 2023-10-27 | 2023-10-31 | B?-?13 ?Midc?, ?Baramati ?413133?, ? Maharashtra?, ?India? | 1 | 21 | 405 | VAIBHAV PAWAR | 9767056263 | vaibhav.pawar@ismt.co.in | VAIBHAV PAWAR | 9767056263 | vaibhav.pawar@ismt.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 0 |  | 2023-10-09 | 2023-10-09 | 1 |  | Mr.Joshi
870 | 2023-10-12 | 8:51:07 AM | Sapl0335 | 1 | 11 | G017 | 884 | 904 | 1800/1DR026470/CA1032112 | 35 | 0 | N0307 | 2023-10-12 | Tackle 10 TON | Mr.Vinodkumar | 5 | 2023-10-07 | 2023-10-09 | 2023-10-10 | 2023-10-10 | 2023-10-10 | 2023-10-11 | 2023-10-10 | 2023-10-11 | 2023-10-11 | 2023-10-12 | 2023-10-09 | 2023-10-10 | 2023-10-12 | 2023-10-13 | 2023-10-13 | 2023-10-14 | Plant ?7?, ?Pirojshanagar?, ?Wikhroli?, ? Mumbai ?400079? | 1 | 21 | 398 | Gajendrasingh J Bhadauria | 9820225024 | gjb@godrej.com | Gajendrasingh J Bhadauria | 9820225024 | gjb@godrej.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 0 |  | 2023-10-12 | 2023-10-12 | 1 |  | Mr. Joshi
871 | 2023-10-18 | 11:25:22 AM | Sapl0335 | 1 | 11 | G020 | 885 | 905 | 5850001307 | 35 | 0 | N0308 | 2023-10-18 | TROLLEY | Mr.Vinodkumar | 5 | 2023-10-23 | 2023-10-25 | 2023-10-25 | 2023-10-27 | 2023-10-28 | 2023-11-03 | 2023-11-04 | 2023-11-04 | 2023-11-06 | 2023-11-08 | 2023-11-03 | 2023-11-04 | 2023-11-11 | 2023-11-13 | 2023-11-13 | 2023-11-13 | GESTAMP PUNE AUTOMOTIVE Gate No. 374/517-521,523 Takv Pune, Maharashtra (INDIA) 13 412106 India | 1 | 21 | 405 | sushil Temgire | 999999999 | gaipl@in.gestamp.com | sushil Temgire | 999999999 | gaipl@in.gestamp.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 0 |  | 0 |  | 2023-10-18 | 2023-10-18 | 1 |  | Mr. Joshi
872 | 2023-10-18 | 4:38:32 PM | Sapl0335 | 1 | 11 | S026 | 886 | 906 | Verbal_nmc_18-10-23 | 34 | 0 | S0216 | 2023-10-18 | Gunr rail | Mr.Vinodkumar | 5 | 2023-10-18 | 2023-10-19 | 2023-10-19 | 2023-10-20 | 2023-10-21 | 2023-10-22 | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-22 | 2023-10-23 | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-10-31 | 5?B?/ ?301?, ?Kalpataru Estate?, ? Jawalkar Nagar?, ?Pimple Gurav?, ? Pune ?- ?411027? | 1 | 21 | 405 | MR. KAKADE | 1212121212 | kakade01@yahoo.com | MR. KAKADE | 1212121212 | kakade01@yahoo.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 0 |  | 0 |  | 2023-10-18 | 2023-10-18 | 1 |  | Mr.Joshi
873 | 2023-11-04 | 12:25:51 PM | Sapl0335 | 1 | 11 | T016 | 887 | 907 | 0559/23-24 | 34 | 0 | S0217 | 2023-11-04 | GUN RAIL | Mr.Vinodkumar | 5 | 2023-11-04 | 2023-11-04 | 2023-11-05 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-09 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-09 | 2023-11-10 | 2023-11-11 | 78?, ?Shivane Industrial Area?, ? Shivane?,?Off Nda Road?, ?Pune ? -?411023 | 1 | 21 | 405 | Pankaj Jadhav | 9890013871 | info@techexpertindia.com | Pankaj Jadhav | 9890013871 | info@techexpertindia.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 0 |  | 2023-11-04 | 2023-11-04 | 1 |  | Mr. Joshi
874 | 2023-11-04 | 1:06:24 PM | Sapl0335 | 1 | 11 | G007 | 888 | 908 | 1800/1DR026470/CA1031155 | 35 | 0 | N0309 | 2023-11-04 | Rework cost trolley | Mr.Vinodkumar | 5 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-02 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-04 | 2023-11-05 | 2023-11-06 | 2023-11-03 | 2023-11-04 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-09 | Plant - 17,Pirojshanager,Vikhroli | 1 | 21 | 398 | Gajendrasingh J Bhadauria | 022 - 6796 1509 | gjb@godrej.com | Gajendrasingh J Bhadauria | 022 - 6796 1509 | gjb@godrej.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 0 |  | 2023-11-04 | 2023-11-04 | 1 |  | Mr.Vinodkumar
875 | 2023-11-08 | 9:04:37 AM | Sapl0335 | 1 | 11 | I003 | 889 | 909 | verbal_dns_8-11 | 35 | 0 | N0310 | 2023-11-08 | Cylinder spare | Mr.Vinodkumar | 15 | 2023-11-01 | 2023-11-01 | 2023-11-02 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-04 | 2023-11-04 | 2023-11-05 | 2023-11-06 | 2023-11-08 | 2023-11-07 | 2023-11-09 | 2023-11-08 | 2023-11-09 | 2023-11-09 | Plot No. 79/1/A, First Floor, Gala No. 45 & 46, S Block, M.I.D.C., Near Century Enka, Telco Road Bhosari, Pune 411026. | 1 | 21 | 405 | Mr. Mahadev Salunkhe | 999999999 | abc@gmail.com | Mr. Mahadev Salunkhe | 999999999 | abc@gmail.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 0 |  | 2023-11-02 | 2023-11-02 | 1 |  | Mr.Vinodkumar
877 | 2023-11-10 | 5:14:13 PM | Sapl0335 | 1 | 11 | T019 | 891 | 911 | Verbal_nmc_10-11-23 | 35 | 0 | N0312 | 2023-11-10 | Robotic fixture and integration | Mr.Vinodkumar | 5 | 2023-11-06 | 2023-11-11 | 2023-11-11 | 2023-11-18 | 2023-11-18 | 2023-11-25 | 2023-11-24 | 2023-11-25 | 2023-11-30 | 2023-11-30 | 2023-11-25 | 2023-11-29 | 2023-11-30 | 2023-12-06 | 2023-12-06 | 2023-12-08 | A?1?/?4 ?Mvml Vendor Park ? ,?Chakan Phase Iv?,, ?Midc?, ? Bhosari?, ?Pimpri?-?Chinchwad?, ? Maharashtra ?410501? | 1 | 21 | 405 | Rahul Agnihotri | 9090909090 | rahul.agnihotri@trackcomponents.in | Rahul Agnihotri | 9090909090 | rahul.agnihotri@trackcomponents.in | - | - | - | - | 1 | 1 | 1 | -- | - |  | 1 | 1 | 1 |  | 0 |  | 2023-11-10 | 2023-11-10 | 1 |  | Mr.Vinodkumar
879 | 2024-03-29 | 10:39:52 AM | Sapl0335 | 1 | 11 | A037 | 895 | 913 | 7523000271 | 35 | 0 | N0314 | 2024-03-29 | Robotic fixture | Mr.Vinodkumar | 5 | 2024-02-01 | 2024-02-02 | 2024-02-02 | 2024-02-05 | 2024-02-06 | 2024-02-14 | 2024-02-20 | 2024-02-23 | 2024-02-24 | 2024-02-26 | 2024-02-13 | 2024-02-20 | 2024-03-01 | 2024-03-06 | 2024-03-07 | 2024-03-11 | AUTOCOMP CORPORATION PANSE PVT LTD UNIT-III PLOT A-21/1 CHAKAN INDUSTRIAL AREA PHASE -II KHALUMBRE CHAKAN TALUKA KHED DIST PUNE 410501 | 1 | 21 | 405 | Mr.Tiwari | 7709444198 | sktiwari@pansegroup.com | Mr.Tiwari | 7709444198 | sktiwari@pansegroup.com | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 0 |  | 2024-02-07 | 2024-02-07 | 1 |  | Mr.Vinodkumar
880 | 2024-03-29 | 11:22:09 AM | Sapl0335 | 1 | 11 | T020 | 896 | 914 | CA223-24/20 | 35 | 0 | N0315 | 2024-03-29 | Material handling system | Mr.Joshi | 5 | 2024-03-28 | 2024-04-02 | 2024-04-02 | 2024-04-07 | 2024-04-07 | 2024-04-23 | 2024-05-06 | 2024-05-11 | 2024-05-13 | 2024-05-14 | 2024-04-23 | 2024-05-08 | 2024-05-15 | 2024-05-20 | 2024-05-20 | 2024-05-22 | Gat no 154 Behind GE company phase-11 Sudumbare, chakan pune | 1 | 21 | 405 | Sangeet raman | 9960033973 | sangeet@trackcomponents.in | Sangeet raman | 9960033973 | sangeet@trackcomponents.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 0 |  | 2024-04-02 | 2024-04-02 | 1 |  | Mr. Joshi
881 | 2024-03-31 | 1:29:43 PM | Sapl0335 | 1 | 11 | S044 | 897 | 915 | verbal_nmc_1-4-2024 | 35 | 0 | N0316 | 2024-03-31 | ROBOTIC SPOT WELDING FIXTURE | Mr.Joshi | 5 | 2024-04-01 | 2024-04-04 | 2024-04-04 | 2024-04-07 | 2024-04-02 | 2024-04-15 | 2024-04-18 | 2024-04-20 | 2024-04-21 | 2024-04-22 | 2024-04-08 | 2024-04-18 | 2024-04-22 | 2024-04-24 | 2024-04-17 | 2024-04-18 | 58 km Milestone, NH-8, Delhi Jaipur Highway, Binola, Gurgaon (HR) | 1 | 13 | 171 | Pradeep Chauhan | 8826131726 | Pradeep.chauhan@skhtechnologies.co.in | Pradeep Chauhan | 8826131726 | Pradeep.chauhan@skhtechnologies.co.in | - | - | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 0 |  | 2024-04-02 | 2024-04-02 | 1 |  | Mr. Joshi
61 | 2013-08-28 | 10:42:55 AM | Sapl0005 | 1 | 1 | M001 | 64 | 75 | 3100255148 | 37 | 0 | P0006 | 2013-05-24 | CAST RISERS | ATUL NAIK | 7 | 2013-05-24 | 2013-05-24 | 2013-05-24 | 2013-05-24 | 2013-05-24 | 2013-05-24 | 2013-05-24 | 2013-05-24 | 2013-05-29 | 2013-06-06 | 2013-06-07 | 2013-06-07 | 2013-06-07 | 2013-06-07 | 2013-06-07 | 2013-06-07 | M&M Automotive Sector Nasik Plant-2 Plant II, 80,MIDC ,Satpur, Nasik 422007 | 1 | 21 | 402 | MALGE SNEHAL | +91 253 6613052 | MALGE.SNEHAL@mahindra.com | - | - | MALGE.SNEHAL@mahindra.com | - | AAACM3025EXM003 | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-05-24 | 2013-05-24 | 1 |  | ATUL NAIK
66 | 2018-01-11 | 1:44:57 PM | Sapl0005 | 1 | 1 | M001 | 70 | 80 | 3100258148 | 35 | 0 | N0016 | 2013-06-05 | BWF UNITS 13F467 | MANOJ SHINDE | 3 | 2013-06-05 | 2013-06-06 | 2013-06-07 | 2013-06-08 | 2013-06-10 | 2013-06-17 | 2013-06-18 | 2013-06-19 | 2013-06-20 | 2013-06-20 | 2013-06-21 | 2013-06-21 | 2013-06-22 | 2013-06-22 | 2013-06-21 | 2013-06-21 | Plant II, 80,MIDC ,Satpur, Nasik 422007 Maharashtra India | 1 | 21 | 402 | Snehal Malge | +91 253 6613052 | MALGE.SNEHAL@mahindra.com | DEOGHARE.ROOPAL | - | DEOGHARE.ROOPAL@mahindra.com | - | AAACM3025EXM003 | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-06-07 | 2013-06-07 | 1 |  | MANOJ SHINDE
67 | 2013-08-28 | 10:46:59 AM | Sapl0005 | 1 | 1 | M001 | 71 | 81 | 3100258150 | 35 | 0 | N0017 | 2013-06-05 | BWF UNITS 13F465 | MANOJ SHINDE | 3 | 2013-06-07 | 2013-06-07 | 2013-06-08 | 2013-06-08 | 2013-06-08 | 2013-06-17 | 2013-06-18 | 2013-06-19 | 2013-06-20 | 2013-06-20 | 2013-06-21 | 2013-06-21 | 2013-06-22 | 2013-06-22 | 2013-06-21 | 2013-06-21 | Plant II, 80,MIDC ,Satpur, Nasik 422007 Maharashtra India | 1 | 21 | 402 | Snehal Malge | - | MALGE.SNEHAL@mahindra.com | DEOGHARE.ROOPAL | - | DEOGHARE.ROOPAL@mahindra.com | - | AAACM3025EXM003 | - | - | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-06-07 | 2013-06-07 | 1 |  | MANOJ SHINDE
70 | 2013-08-28 | 10:46:26 AM | Sapl0005 | 1 | 1 | M001 | 72 | 83 | SMALGE | 35 | 0 | N0020 | 2013-06-07 | BWF UNITS 13F491 | MANOJ SHINDE | 3 | 2013-06-07 | 2013-06-07 | 2013-06-08 | 2013-06-08 | 2013-06-10 | 2013-06-15 | 2013-06-17 | 2013-06-18 | 2013-06-19 | 2013-06-19 | 2013-06-20 | 2013-06-20 | 2013-06-21 | 2013-06-21 | 2013-06-22 | 2013-06-22 | Plant II, 80,MIDC ,Satpur, Nasik 422007 Maharashtra India | 1 | 21 | 402 | Snehal Malge | +91 253 6613052 | MALGE.SNEHAL@mahindra.com | DEOGHARE.ROOPAL | - | DEOGHARE.ROOPAL@mahindra.com | - | AAACM3025EXM003 | - | - | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2013-06-08 | 2013-06-08 | 1 |  | MANOJ SHINDE
814 | 2022-09-08 | 10:06:54 AM | Sapl0335 | 1 | 10 | G017 | 812 | 848 | 1800/1DR026470/CA1024924 | 35 | 0 | N0269 | 2022-09-08 | Screen Printing Machine | Mr.Sanket raut | 5 | 2022-09-01 | 2022-09-01 | 2022-09-02 | 2022-09-02 | 2022-09-02 | 2022-09-03 | 2022-09-03 | 2022-09-04 | 2022-09-08 | 2022-09-08 | 2022-09-09 | 2022-09-09 | 2022-09-13 | 2022-09-13 | 2022-09-14 | 2022-09-14 | Plant ?7?, ?Pirojshanagar?, ? Wikhroli?, ?Mumbai ?400079? | 1 | 21 | 398 | Gajendrasingh J Bhadauria | 9820389211 | gjb@godrej.com | Atul patil | 9820389211 | gjb@godrej.com | - | -- | - | - | 1 | 1 | 1 | -- | - |  | 0 | 0 | 0 |  | 0 |  | 2022-09-08 | 2022-09-06 | 1 |  | Mr.Vinodkumar
819 | 2022-09-12 | 4:08:32 PM | Sapl0335 | 1 | 10 | L004 | 832 | 853 | 0061-227137 | 37 | 0 | P0080 | 2022-09-12 | Electrical spare parts | Mr.mayur todkar | 13 | 2022-09-08 | 2022-09-09 | 2022-09-09 | 2022-09-09 | 2022-09-08 | 2022-09-20 | 2022-09-22 | 2022-09-23 | 2022-09-28 | 2022-09-28 | 2022-09-28 | 2022-09-29 | 2022-09-29 | 2022-09-30 | 2022-09-30 | 2022-09-30 | Plot?-?85?, ?Kiadb Industrial Area?,? Phase Ii?, ?Dabaspet Bangalore? 562111? Karnataka? India? | 1 | 17 | 293 | Ravikiran | 8951794310 | Ravikiran.BabuDevadiga@lmwindpower.com | Ravikiran | 8951794310 | Ravikiran.BabuDevadiga@lmwindpower.com | - | -- | - | - | 1 | 1 | 1 | ---- | - |  | 0 | 1 | 1 |  | 0 |  | 2022-09-12 | 2022-09-12 | 1 |  | Mr.Vinodkumar
820 | 2022-09-14 | 9:23:06 AM | Sapl0335 | 1 | 10 | E004 | 833 | 854 | verbal_dns_09-14 | 35 | 0 | N0274 | 2022-09-14 | Materials | Mr.mayur todkar | 5 | 2022-09-01 | 2022-09-02 | 2022-09-01 | 2022-09-03 | 2022-09-03 | 2022-09-04 | 2022-09-04 | 2022-09-05 | 2022-09-13 | 2022-09-14 | 2022-09-14 | 2022-09-15 | 2022-09-15 | 2022-09-16 | 2022-09-16 | 2022-09-17 | Topline Logistic Park Pvt Ltd At ? Village Aurangabad Mitnol ? &?Dighot Palwal Haryana ?121005? | 1 | 13 | 173 | abcd | 9090909090 | xyz@gmail.com | abcd | 9090909090 | xyz@gmail.com | - | --- | - | - | 1 | 1 | 1 | ---- | - |  | 0 | 0 | 0 |  | 0 |  | 2022-09-14 | 2022-09-14 | 1 |  | Mr.sanket raut
821 | 2022-09-16 | 10:26:11 AM | Sapl0335 | 1 | 10 | E004 | 834 | 855 | verbal_dns_09-16 | 35 | 0 | N0275 | 2022-09-16 | Steel materials | Mr.mayur todkar | 5 | 2022-09-08 | 2022-09-09 | 2022-09-10 | 2022-09-11 | 2022-09-11 | 2022-09-12 | 2022-09-12 | 2022-09-14 | 2022-09-14 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-16 | 2022-09-17 | 2022-09-17 | 2022-09-17 | Topline logistic park pvt ltd at village aurangabad mitnol &dighot palwal haryana 121005 | 1 | 13 | 173 | abcd | 9090909090 | xyz@gmail.com | abcd | 9090909090 | xyz@gmail.com | - | -- | - | - | 1 | 1 | 1 | -- | - |  | 0 | 0 | 0 |  | 0 |  | 2022-09-16 | 2022-09-16 | 1 |  | Mr.Vinodkumar
823 | 2022-09-21 | 9:02:57 AM | Sapl0335 | 1 | 10 | G020 | 836 | 857 | verbal_NMC_21-9-22 | 34 | 0 | S0209 | 2022-09-21 | Roof pallets | Mr.mayur todkar | 5 | 2022-09-21 | 2022-09-21 | 2022-09-22 | 2022-09-22 | 2022-09-22 | 2022-09-24 | 2022-09-25 | 2022-09-26 | 2022-09-26 | 2022-09-26 | 2022-09-24 | 2022-09-24 | 2022-09-26 | 2022-09-26 | 2022-09-26 | 2022-09-26 | E?1 ?(?Part?)?,?Chakan Midc Road?, ? Phase?-?Iii?,?Kharabwadi?, ?Chakan?, ? Talegaon Chakan Road?, ? Mahalunge Ingale?, ?Maharashtra | 1 | 21 | 405 | Sagar Jadhav | 9673337705 | gaipl@in.gestamp.com | Sagar Jadhav | 9673337705 | gaipl@in.gestamp.com | - | --- | - | - | 1 | 1 | 1 | -- | - |  | 0 | 0 | 1 |  | 0 |  | 2022-09-21 | 2022-09-21 | 1 |  | Mr.Vinodkumar
825 | 2022-09-26 | 2:47:38 PM | Sapl0335 | 1 | 10 | E004 | 838 | 859 | 2200 | 35 | 0 | N0276 | 2022-09-26 | Railing work | Mr.Sanket raut | 5 | 2022-09-10 | 2022-09-04 | 2022-09-11 | 2022-09-12 | 2022-09-12 | 2022-09-13 | 2022-09-15 | 2022-09-22 | 2022-09-16 | 2022-09-17 | 2022-09-17 | 2022-09-19 | 2022-09-22 | 2022-09-23 | 2022-09-23 | 2022-09-24 | Topline Logistic Park Pvt Ltd At ? Village Aurangabad Mitnol ? &?Dighot Palwal Haryana ?121105? | 1 | 13 | 173 | abcd | 9090909090 | xyz@gmail.com | abcd | 9090909090 | xyz@gmail.com | - | -- | - | - | 1 | 1 | 1 | ----- | - |  | 0 | 0 | 0 |  | 0 |  | 2022-09-26 | 2022-09-26 | 1 |  | Mr.Vinodkumar
829 | 2023-01-21 | 2:42:30 PM | Sapl0331 | 1 | 10 | S040 | 842 | 863 | verbal_NMC_31-10-22 | 35 | 0 | N0279 | 2022-10-31 | Robotic & Manual fixture | Mr.gurunath | 5 | 2022-11-04 | 2022-11-05 | 2022-11-16 | 2022-11-23 | 2022-11-17 | 2022-11-30 | 2022-11-30 | 2022-12-09 | 2022-11-30 | 2022-11-04 | 2022-11-18 | 2022-11-25 | 2022-11-30 | 2022-12-08 | 2022-12-09 | 2022-12-09 | D-92, M.I.D.C. SATPUR, NASIK-07. Phone: 0253-2350988, Fax – 0253-6614154. | 1 | 21 | 405 | ANIL PATIL | 9090909090 | smi22@rediffmail.com | ANIL PATIL | 9090909090 | smi22@rediffmail.com | - | --- | - | - | 1 | 1 | 1 | -- | - |  | 1 | 1 | 1 |  | 0 |  | 2022-11-04 | 2022-11-04 | 1 |  | Mr.Vinodkumar
830 | 2022-11-03 | 5:23:25 PM | Sapl0335 | 1 | 10 | S006 | 843 | 864 | verbal_dns_03-11 | 35 | 0 | N0280 | 2022-11-03 | AGV trolley | Mr. Vikas Sawant | 22 | 2022-11-03 | 2022-11-03 | 2022-11-03 | 2022-11-04 | 2022-11-04 | 2022-11-05 | 2022-11-05 | 2022-11-07 | 2022-11-09 | 2022-11-09 | 2022-11-10 | 2022-11-11 | 2022-11-11 | 2022-11-12 | 2022-11-11 | 2022-11-12 | Khed shivapur | 1 | 21 | 405 | vinodkumar | 9090909090 | vinodkumar.kadepure@synergytechs.com | vinodkumar | 9090909090 | vinodkumar.kadepure@synergytechs.com | - | ---- | - | - | 1 | 1 | 1 | ---- | - |  | 0 | 0 | 0 |  | 0 |  | 2022-11-03 | 2022-11-03 | 1 |  | Mr.Vinodkumar
833 | 2023-02-27 | 6:42:34 PM | Sapl0335 | 1 | 10 | T019 | 847 | 867 | verbal_NMC_9-11-22 | 35 | 0 | N0283 | 2022-11-09 | Robotic & Manual fixture | Mr.gurunath | 5 | 2022-11-12 | 2022-11-14 | 2022-11-14 | 2022-11-19 | 2022-11-21 | 2022-11-29 | 2022-12-16 | 2022-12-19 | 2022-12-21 | 2022-11-22 | 2022-12-30 | 2022-12-09 | 2022-12-16 | 2022-12-29 | 2022-12-29 | 2022-12-30 | A1/4 Mvml Vendor Park ,Chakan Phase Iv,, Midc, Bhosari, Pimpri-Chinchwad, Maharashtra ?410501 | 1 | 21 | 405 | Rahul Agnihotri | 9090909090 | rahul.agnihotri@trackcomponents.in | Rahul Agnihotri | 9090909090 | rahul.agnihotri@trackcomponents.in | - | -- | - | - | 1 | 1 | 1 | -- | - |  | 0 | 0 | 1 |  | 0 |  | 2022-11-09 | 2022-11-09 | 1 |  | Mr.Vinodkumar
876 | 2023-11-10 | 10:29:43 AM | Sapl0335 | 1 | 11 | M033 | 890 | 910 | Verbal_nmc_10-11-23 | 35 | 0 | N0311 | 2023-11-10 | Robotic fixture | Mr.Vinodkumar | 5 | 2023-11-10 | 2023-11-13 | 2023-11-13 | 2023-11-16 | 2023-11-16 | 2023-11-20 | 2023-11-24 | 2023-11-25 | 2023-11-26 | 2023-11-27 | 2023-11-20 | 2023-11-23 | 2023-11-27 | 2023-11-30 | 2023-11-30 | 2023-12-01 | Plot No A ?12?,?Talegaon Midc ? Industrial Area?, ?Taluka Maval?, ? Pune?, ?Maharashtra ?410507? | 1 | 21 | 405 | Premdeep Ahire | 9960617213 | premdeep.ahire@magna.com | Premdeep Ahire | 9960617213 | premdeep.ahire@magna.com | - | -- | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 0 |  | 2023-11-10 | 2023-11-10 | 1 |  | Mr.Vinodkumar
878 | 2024-01-12 | 10:48:49 AM | Sapl0335 | 1 | 11 | J020 | 893 | 912 | Verbal_nmc_25-12-23 | 35 | 0 | N0313 | 2023-12-25 | Fixture Refurnishment | Mr.Vinodkumar | 5 | 2023-12-25 | 2023-12-25 | 2023-12-25 | 2023-12-26 | 2023-12-26 | 2023-12-27 | 2023-12-27 | 2023-12-27 | 2023-12-28 | 2023-12-28 | 2023-12-27 | 2023-12-27 | 2023-12-27 | 2023-12-29 | 2023-12-29 | 2023-12-29 | 71-72, Midc, Satpur,,422007,Nashik | 1 | 21 | 402 | Mr. Bijay Agarwal | - | bijay.agrawal@jbmgroup.com | Mr. Bijay Agarwal | - | bijay.agrawal@jbmgroup.com | - | -- | - | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 0 |  | 2023-12-25 | 2023-12-25 | 1 |  | Mr. Joshi
882 | 2024-03-31 | 1:27:29 PM | Sapl0335 | 1 | 11 | G021 | 898 | 916 | verbal_nmc_8-4-2024 | 35 | 0 | N0317 | 2024-03-31 | TROLLEY | Mr.Joshi | 5 | 2024-04-08 | 2024-04-09 | 2024-04-09 | 2024-04-12 | 2024-04-11 | 2024-04-15 | 2024-04-15 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-04-19 | 2024-04-20 | 2024-04-20 | 2024-04-23 | 2024-04-24 | 2024-04-24 | Gestamp Pune Atomotive India Pvt Ltd. Gat No 374/517- 521,523 Takve Budruk , Taluka – Maval , Pune , Maharashtra – 412106 | 1 | 21 | 405 | Uday Kabade | 8983023990 | ukabade@in.gestamp.com | Uday Kabade | 8983023990 | ukabade@in.gestamp.com | - | -- | - | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 0 |  | 2024-03-31 | 2024-03-31 | 1 |  | Mr. Joshi
1 | 2013-08-28 | 5:22:59 PM | Sapl0005 | 1 | 1 | T002 | 6 | 11 | 9000025349 | 35 | 0 | N0001 | 2013-04-03 | Air Hoist with Tackle for Door handling at Safari Weld Line at J Block | Mr. Rajkumar Jagtap | 2 | 2013-04-06 | 2013-04-30 | 2013-05-02 | 2013-05-08 | 2013-05-09 | 2013-05-29 | 2013-06-17 | 2013-06-24 | 2013-06-25 | 2013-06-30 | 2013-05-30 | 2013-06-15 | 2013-07-01 | 2013-07-08 | 2013-06-20 | 2013-06-22 | PUNE AUTO Tata Motors Ltd. Pune PUNE 411018 MPLP SL70 Capitl | 1 | 21 | 405 | abhijit.medhekar | 020-6613 2426 | abhijit.medhekar@tatamotors.com | vijay.kothawade | 9922443196 | vijay.kothawade@tatamotors.com | - | AAACT2727QXM007 | 27390247811C DT.01/04/08 | 27390247811V DT.01/04/08 | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2013-05-03 | 2013-05-03 | 4 |  | Mr. Rajkumar Jagtap
21 | 2014-01-13 | 12:10:46 PM | Sapl0005 | 1 | 1 | M018 | 25 | 30 | 13-14_Z-0032 | 34 | 0 | S0003 | 2013-04-12 | OVERHEAD RAIL , TYPE C63 | RAJKUMAR JAGTAP | 2 | 2013-04-09 | 2013-04-09 | 2013-04-10 | 2013-04-10 | 2013-04-12 | 2013-04-13 | 2013-04-19 | 2013-04-19 | 2013-04-22 | 2013-04-22 | 2013-04-23 | 2013-04-23 | 2013-04-19 | 2013-04-24 | 2013-04-22 | 2013-04-23 | GAT NO. 307, KONDHAPURI, PUNE-NAGAR ROAD, TAL. SHIRUR, PUNE - 412209 INDIA | 1 | 21 | 405 | NAGESH JADHAV | +91 20 66 27 27 00 | njadhav@masterzippel.com | MANOJ PAWAR | +91 08805026331 | mpawar@masterzippel.com | +91 20 25 43 85 25 | AAGCM0004KEM001 | 27730763276C | 27730763276V | 1 | 1 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | COMPLETE | 2013-04-12 | 2013-04-12 | 1 |  | RAJKUMAR JAGTAP
32 | 2013-08-28 | 10:45:04 AM | Sapl0005 | 1 | 1 | M013 | 36 | 47 | 3200058160 | 37 | 0 | P0003 | 2013-04-18 | AFM PINON & SHAFT | RAJKUMAR JAGTAP | 2 | 2013-04-18 | 2013-04-18 | 2013-04-19 | 2013-04-19 | 2013-04-20 | 2013-04-20 | 2013-04-20 | 2013-04-20 | 2013-04-22 | 2013-04-22 | 2013-04-23 | 2013-04-23 | 2013-04-24 | 2013-04-24 | 2013-04-23 | 2013-04-23 | PLOT NO.A 1,PHASE IV,CHAKAN INDUSTRIAL AREA,KHED,PUNE-410 501 | 1 | 21 | 405 | JOSHI.MAHESH | 9011689378 | JOSHI.MAHESH@mahindra.com | MR. DATTARAM DABHOLKAR | 7875067127 | DABHOLKAR.DATTARAM@mahindra.com | - | AAFCM1217MXM001 | 27750410573C | 27750410573V | 0 | 0 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | COMPLETED | 2013-04-19 | 2013-04-19 | 1 |  | RAJKUMAR JAGTAP
39 | 2013-08-28 | 10:40:30 AM | Sapl0005 | 1 | 1 | M001 | 43 | 54 | 3100244928 | 34 | 0 | S0008 | 2013-04-27 | CAST RISERS | ATUL NAIK | 7 | 2013-04-27 | 2013-04-27 | 2013-04-27 | 2013-04-27 | 2013-04-27 | 2013-04-27 | 2013-04-27 | 2013-04-27 | 2013-05-03 | 2013-05-03 | 2013-05-04 | 2013-05-04 | 2013-05-04 | 2013-05-04 | 2013-05-04 | 2013-05-04 | M&M Automotive Sector Nasik Plant-2 Plant II, 80,MIDC ,Satpur, Nasik 422007 | 1 | 21 | 402 | MALGE SNEHAL | +91 253 6613052 | MALGE.SNEHAL@mahindra.com | - | +91 253 6613052 | MALGE.SNEHAL@mahindra.com | - | AAACM3025EXM003 | 400039/S/3 | 400039/C/27 | 0 | 0 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | COMPLETED | 2013-04-27 | 2013-04-27 | 1 |  | ATUL NAIK
56 | 2013-08-28 | 10:39:42 AM | Sapl0005 | 1 | 1 | J013 | 60 | 71 | 4300010160 | 34 | 0 | S0012 | 2013-05-21 | LONG RAIL C63 | RAJKUMAR JAGTAP | 2 | 2013-05-21 | 2013-05-21 | 2013-05-21 | 2013-05-21 | 2013-05-21 | 2013-05-21 | 2013-05-21 | 2013-05-21 | 2013-05-28 | 2013-05-28 | 2013-05-31 | 2013-05-31 | 2013-06-01 | 2013-05-02 | 2013-05-27 | 2013-05-27 | JBM AUTO LTD PLOT NO 5, SECTOR - 31, KASNA 201306 GREATER NOIDA | 1 | 33 | 682 | SANJAY MURGAI | - | smurgai@jbm.co.in | GIRISH KUMAR | 7838432466 | girish.kumar@jbm.co.in | - | AAACJ9630NXM002 | 09366300628 | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-05-21 | 2013-05-21 | 1 |  | RAJKUMAR JAGTAP
57 | 2013-08-28 | 10:39:28 AM | Sapl0005 | 1 | 1 | J013 | 60 | 71 | 4300010160 | 34 | 0 | S0013 | 2013-05-21 | LONG RAIL C63 | RAJKUMAR JAGTAP | 2 | 2013-05-21 | 2013-05-21 | 2013-05-21 | 2013-05-21 | 2013-05-21 | 2013-05-21 | 2013-05-21 | 2013-05-21 | 2013-05-28 | 2013-05-28 | 2013-05-31 | 2013-05-31 | 2013-06-01 | 2013-06-02 | 2013-05-27 | 2013-05-27 | JBM AUTO LIMITED PLOT NO 5, SECTOR 31, KASNA 201306 | 1 | 33 | 682 | SANJAY MURGAI | - | smurgai@jbm.co.in | GIRISH KUMAR | 7838432466 | girish.kumar@jbm.co.in | - | AAACJ9630NXM002 | 09366300628 | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-05-21 | 2013-05-21 | 1 |  | RAJKUMAR JAGTAP
58 | 2013-08-28 | 10:44:47 AM | Sapl0005 | 1 | 1 | S011 | 61 | 72 | PUOR13000690 | 37 | 0 | P0005 | 2013-05-22 | Spares For Hoist - Brake Coil | HEMAKSH PATIL | 4 | 2013-05-22 | 2013-05-22 | 2013-05-22 | 2013-05-22 | 2013-05-22 | 2013-05-22 | 2013-05-22 | 2013-05-22 | 2013-05-22 | 2013-05-22 | 2013-05-22 | 2013-05-22 | 2013-05-22 | 2013-05-22 | 2013-05-22 | 2013-05-22 | 690, Udyambag Industrial Estate | 1 | 17 | 295 | SHANTILAL V PORWAL | +91-831-2440972 | svp@shantiiron.net | SHANTILAL V PORWAL | +91-831-2440972 | svp@shantiiron.net | +91-831-2440975 | AAFFS4372N-XM001 | 29580076808 | - | 0 | 0 | 0 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-05-22 | 2013-05-22 | 1 |  | HEMAKSH PATIL
135 | 2015-09-11 | 9:43:29 AM | Sapl0005 | 1 | 1 | T002 | 137 | 147 | 900021884 | 35 | 0 | N0050 | 2013-08-07 | Modification of Manipulators for Y1 projects. | Mr. Rajkumar Jagtap | 2 | 2013-08-07 | 2014-01-13 | 2013-08-09 | 2014-01-21 | 2013-08-11 | 2013-08-12 | 2013-08-13 | 2013-08-14 | 2014-01-31 | 2014-01-31 | 2013-08-17 | 2013-08-18 | 2013-08-13 | 2013-08-20 | 2013-08-21 | 2013-08-22 | store location:MP03,Plant:1001,Tata Motors Ltd.,Pune-411018 | 1 | 21 | 405 | N.Y.Dodake | 9922434879 | n.dodake@tatamotors.com | S. Karajgikar | 7276097057 | karajgikar.s@tatamotors.com | - | AACT2727QXM003 | 27390247811V | 27390247811V | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-08-10 | 2013-08-12 | 1 |  | Mr. Rajkumar Jagtap
136 | 2016-11-03 | 11:17:34 AM | Sapl0005 | 1 | 1 | A023 | 138 | 148 | TL-SAPL-002/2013 | 35 | 0 | N0051 | 2013-08-08 | Welding Assy Fixtures for Manufacture of CCB | AMIT POTDAR | 3 | 2013-08-08 | 2013-08-19 | 2013-08-20 | 2013-08-30 | 2013-08-31 | 2013-09-10 | 2013-09-20 | 2013-09-27 | 2013-09-28 | 2013-09-30 | 2013-09-11 | 2013-09-18 | 2013-10-01 | 2013-10-08 | 2013-09-23 | 2013-09-26 | E6/3 MIDC PHASE III, NANEKARWADI, CHAKAN , PUNE | 1 | 21 | 405 | Pankaj A Sheth | 9823059005 | amtekpune@gmail.com | Dhiren A Sheth | 9823359006 | amtekpune@gmail.com | - | AAFCA 6352B EM 002 | 27900542168 C | 27900542168 V | 0 | 0 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | COMPLETE | 2013-08-26 | 2013-08-26 | 1 |  | AMIT POTDAR
200 | 2014-03-31 | 5:32:03 PM | Sapl0005 | 1 | 1 | J003 | 201 | 211 | 4300012989 | 34 | 0 | S0041 | 2014-01-29 | Rails & trolleys for sliding Door | RAJKUMAR JAGTAP | 2 | 2014-01-29 | 2014-01-30 | 2014-01-30 | 2014-01-30 | 2014-01-30 | 2014-01-30 | 2014-01-30 | 2014-01-30 | 2014-01-31 | 2014-01-31 | 2014-01-30 | 2014-01-30 | 2014-01-30 | 2014-01-30 | 2014-01-30 | 2014-01-30 | C-1/2, Chakan MIDC Area 410501 Pune INDIA | 1 | 21 | 405 | Mr. Kishan Shinde | 09922435919 | Kishan.Shinde@jbmmagnetto.com | Mr. V. S. Kanade | 9922435918 | vilas.kanade@jbmmagnetto.com | - | AALCS4205RXM001 | 27750643955C | 27750643955V | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2014-01-29 | 2014-01-29 | 1 |  | RAJKUMAR JAGTAP
221 | 2017-05-15 | 9:41:06 AM | Sapl0005 | 1 | 1 | A018 | 222 | 232 | 110 | 35 | 0 | N0070 | 2014-03-01 | Modification Charges for Fixture No ML10 to ML90 | MANOJ SHINDE | 3 | 2014-03-01 | 2014-03-06 | 2014-03-07 | 2014-03-12 | 2014-03-13 | 2014-03-17 | 2014-03-18 | 2014-03-19 | 2014-03-19 | 2014-03-22 | 2014-03-27 | 2014-03-27 | 2014-03-28 | 2014-03-31 | 2014-03-18 | 2014-03-18 | Autoline Industries, Uttarakhand | 1 | 34 | 679 | dattatraya kute | 0 | dattatraya.kute@autoline.com | dattatraya kute | 0 | dattatraya.kute@autoline.com | 0 | 0 | 0 | 0 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-03-07 | 2014-03-07 | 1 |  | MANOJ SHINDE
262 | 2014-08-30 | 12:03:48 PM | Sapl0005 | 1 | 2 | N003 | 265 | 273 | 011415CPCAPX084 | 34 | 0 | S0060 | 2014-07-08 | SPARES FOR C-63 SECTION RAIL | MR. RAJKUMAR RAMCHANDRA JAGTAP | 2 | 2014-07-08 | 2014-07-08 | 2014-07-08 | 2014-07-08 | 2014-07-08 | 2014-07-08 | 2014-07-08 | 2014-07-08 | 2014-07-08 | 2014-07-08 | 2014-07-08 | 2014-07-08 | 2014-07-08 | 2014-07-08 | 2014-07-08 | 2014-07-08 | NEEL AUTO PRIVATE LIMITED, NO. 1, 2, 5 & 6, TVS INDUSTRIAL ESTATE, HARITA, HOSUR, KRISHNAGIRI DISTRICT - 635109. TAMILNADU, INDIA. | 1 | 31 | 680 | MR. N. SATHISH | 82200007523 | sathish.narashiman@jbm-group.com | MR. S. MURUGARAJU | 8870001513 | murugaraju.senthurpandi@jbm-group.com | - | AABCT9860DXM0003 | 888232, DT. 2/01/06 | 33323363536 | 1 | 1 | 1 | NA | NA |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2014-07-08 | 2014-07-08 | 1 |  | MR. RAJKUMAR RAMCHANDRA JAGTAP
263 | 2015-02-13 | 2:43:24 PM | Sapl0005 | 1 | 2 | J016 | 266 | 274 | 4300015078 | 34 | 0 | S0061 | 2014-07-14 | SUPPLY OF LONG RAIL, CROSS RAIL & TROLLEY SET C-63 SECTION RAILS FOR MM NAGAR - 155 K PROJECT | MR. RAJKUMAR RAMCHANDRA JAGTAP | 2 | 2014-07-14 | 2014-07-14 | 2014-07-15 | 2014-07-15 | 2014-07-16 | 2014-07-16 | 2014-07-17 | 2014-07-17 | 2014-07-18 | 2014-07-18 | 2014-07-17 | 2014-07-17 | 2014-07-28 | 2014-07-28 | 2014-07-31 | 2014-07-31 | JBM AUTO SYSTEM PRIVATE LIMITED., NO. 1, FORD SUPPLIER PARK, S. P. KOIL POST, MARAIMALAINAGAR, CHENGALPET TALUKA, KANCHIPURAM DISTRICT, | 1 | 31 | 687 | MR. VEERAPERUMAL THAVAMANI | 04467417777 | veeraperumal.thavamani@jbm-group.com | MR. N. KANNAN | 04467417777 | n.kannan@jbm-group.com | 04467417788 | AAACK899RXM001 | 797097 DT. 28-09-98 | 33671602648 | 1 | 1 | 1 | WOODEN PACKING | LAY OUT 1 1. LONG RAIL C-63 Section - 15Mx2Nos.=30M, 2. CROSS RAIL C-63 Section -3.0Mx7Nos.=21M, 3. Trolley Set for C-63 Section Rails=No. of Cross Rails=7Nos. LAY OUT 2 1. LONG RAIL C-63 Section - 6Mx4Nos.=24M, 2. CROSS RAIL C-63 Section -3.0Mx4Nos.=12M, 3. Trolley Set for C-63 Section Rails=No. of Cross Rails=4Nos. LAY OUT 3 1. LONG RAIL C-63 Section - 30Mx8Nos.=240M, 2. CROSS RAIL C-63 Section -3.0Mx28Nos.=84M, 3. Trolley Set for C-63 Section Rails=No. of Cross Rails=28Nos. |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-07-15 | 2014-07-15 | 1 |  | MR. RAJKUMAR RAMCHANDRA JAGTAP
264 | 2014-12-09 | 11:53:31 AM | Sapl0005 | 1 | 2 | J016 | 267 | 275 | 4100035382 | 36 | 0 | E0012 | 2014-07-14 | INSTALLATION CHARGES | MR. RAJKUMAR RAMCHANDRA JAGTAP | 2 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-31 | 2014-07-31 | JBM AUTO SYSTEM PRIVATE LIMITED, NO. 1, FORD SUPPLIER PARK, S. P. KOIL POST, MARAIMALAINAGAR, CHENGALPET TALUKA, KANCHIPURAM DISTRICT, PIN - 603204. | 1 | 31 | 687 | MR. VEERAPERUMAL THAVAMANI | 04467417777 | veeraperumal.thavamani@jbm-group.com | MR. N. KANNAN | 04467417777 | n.kannan@jbm-group.com | 04467417788 | AAACK899RXM001 | 797097 DT. 28-09-98 | 33671602648 | 0 | 0 | 0 | NA | NA |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-07-15 | 2014-07-15 | 1 |  | MR. RAJKUMAR RAMCHANDRA JAGTAP
265 | 2015-02-13 | 2:43:37 PM | Sapl0005 | 1 | 2 | J016 | 268 | 276 | 4300015066 | 34 | 0 | S0062 | 2014-07-14 | SUPPLY OF LONG RAIL, CROSS RAIL & TROLLEY SET C-63 SECTION RAILS FOR ORAGADAM - J92 PROJECT | MR. RAJKUMAR RAMCHANDRA JAGTAP | 2 | 2014-07-14 | 2014-07-14 | 2014-07-15 | 2014-07-15 | 2014-07-16 | 2014-07-16 | 2014-07-17 | 2014-07-17 | 2014-07-18 | 2014-07-18 | 2014-07-17 | 2014-07-17 | 2014-07-17 | 2014-07-28 | 2014-07-31 | 2014-07-31 | JBM AUTO SYSTEM PRIVATE LIMITED, PLOT NO. RNS-1 RENAULT NISSAN SUPPLIERS PARK, ORAGADAM, 603109, DISTRICT KANCHEEPURAM | 1 | 31 | 688 | MR. VEERAPERUMAL THAVAMANI | 04467417777 | veeraperumal.thavamani@jbm-group.com | MR. N. KANNAN | 04467417777 | n.kannan@jbm-group.com | 04467417788 | AAACK8997REM002 | 797097 DT. 28-09-98 | 33671602648 | 1 | 1 | 1 | WOODEN PACKING | PO ANNEXURE 1) LONG RAIL - TOTAL 147 MTRS. 3MTR.X24NOS., 4MTR.X8NOS., 5MTR.X2NOS., 5.5MTR.X2NOS., 11MTR.X2NOS. 2) CROSS RAIL - TOTAL - 120 MTRS., 3 MTR.X40NOS., 3) Trolley Set for C-63 Section Rails - 40 Nos. |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-07-15 | 2014-07-15 | 1 |  | MR. RAJKUMAR RAMCHANDRA JAGTAP
266 | 2014-12-09 | 11:53:35 AM | Sapl0005 | 1 | 2 | J016 | 269 | 277 | 4100035383 | 36 | 0 | E0013 | 2014-07-14 | INSTALLATION CHARGES | MR. RAJKUMAR RAMCHANDRA JAGTAP | 2 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-31 | 2014-07-31 | PLOT NO. RNS-1, RENAULT NISSAN SUPPLIERS PARK, ORAGADAM 603109, DISTRICT KANCHEEPURAM, | 1 | 31 | 688 | MR. VEERAPERUMAL THAVAMANI | 04467417777 | veeraperumal.thavamani@jbm-group.com | MR. N. KANNAN | 04467417777 | n.kannan@jbm-group.com | 04467417788 | AAACK8997REM002 | 797097 DT. 28-09-98 | 33671602648 | 0 | 0 | 0 | NA | NA |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-07-15 | 2014-07-15 | 1 |  | MR. RAJKUMAR RAMCHANDRA JAGTAP
267 | 2014-12-08 | 2:26:00 PM | Sapl0005 | 1 | 2 | M009 | 271 | 279 | 3200080845 | 34 | 0 | S0063 | 2014-07-24 | LONG RAILS & TROLLEYS FOR HANGING TORQUEING TOOL. | MR. RAJKUMAR RAMCHANDRA JAGTAP | 2 | 2014-07-24 | 2014-07-24 | 2014-07-24 | 2014-07-24 | 2014-07-24 | 2014-07-24 | 2014-07-24 | 2014-07-24 | 2014-07-25 | 2014-07-25 | 2014-07-25 | 2014-07-25 | 2014-07-26 | 2014-07-26 | 2014-07-26 | 2014-07-26 | Mahindra Ugione Steel Co. Ltd.,(MUSCO STAMPINGS), At & Post Kanhe, Taluka Maval, Dist. Pune 412106. | 1 | 21 | 405 | MR. ANAND SATALKAR | 9552540076 | satalkar.anand@mahindra.com | MR. SANDIP JAGTAP | 9552504796 | jagtap.sandip@mahindra.com | 02114255292 | AAACM4998GXM002 | 27360370484/C W.E.F. 01.04.2006 | 27360370484/V W.E.F. 01.04.2006 | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-07-25 | 2014-07-25 | 1 |  | MR. RAJKUMAR RAMCHANDRA JAGTAP
268 | 2015-01-12 | 12:36:25 PM | Sapl0005 | 1 | 2 | V002 | 272 | 280 | 8000048272 | 35 | 0 | N0080 | 2014-07-25 | SKID GUIDE PIVOTED STOPPER ASSEMBLY | MR. RAJKUMAR RAMCHANDRA JAGTAP | 2 | 2014-07-26 | 2014-07-26 | 2014-07-28 | 2014-07-28 | 2014-08-11 | 2014-08-11 | 2014-08-15 | 2014-08-15 | 2014-08-18 | 2014-08-18 | 2014-08-19 | 2014-08-19 | 2014-08-20 | 2014-08-20 | 2014-08-21 | 2014-08-21 | Volkswagen India Private Limited,E-1, MIDC Industrial Area (Phase III), Chakan, Village Nigoje Mhalunge, Kharabwadi, Tal. Khed, Chakan, Pune - 410501, Maharashtra, India. | 1 | 21 | 405 | Mr. Ram Anubhule | 9765404809 | ram.anbhule@volkswagen.co.in | Mr. Ranganathan Balegatte | 8411009153 | ranganathan.balegatte@volkswagen.co.in | 02135661050 | AACCV4229PXM001 | 27580611505C | 27580611505V | 1 | 1 | 1 | WOODEN BOX PACKING | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-07-31 | 2014-08-12 | 1 |  | MR. RAJKUMAR RAMCHANDRA JAGTAP
269 | 2015-01-12 | 12:49:21 PM | Sapl0005 | 1 | 2 | K007 | 273 | 282 | 123456789 | 43 | 0 | T0016 | 2014-07-25 | SINGLE STAGE AND DOUBLE STAGE CONTROL, PANELS | MR. DHANANJAY N. SIRSIKAR | 4 | 2014-07-31 | 2014-07-31 | 2014-08-05 | 2014-08-05 | 2014-08-11 | 2014-08-11 | 2014-08-15 | 2014-08-15 | 2014-08-18 | 2014-08-18 | 2014-08-26 | 2014-08-26 | 2014-08-15 | 2014-08-27 | 2014-08-29 | 2014-08-29 | KIRLOSKAR PNEUMATIC CO. LTD., SASWAD, TALUKA PURANDAR, DISTRICT PUNE. | 1 | 21 | 405 | MR. MAHESH M. SHINDE | 02115224132 | shindemm@kpcl.net | MR. DEEPAK R. SHINDE | 02115224132 | shindedr@kpcl.net | 02115224133 | AAAKPC12345 | 12345CST | 67890VAT | 1 | 1 | 1 | WOODEN BOX PACKING | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-08-08 | 2014-07-31 | 1 |  | MR. DHANANJAY N. SIRSIKAR
270 | 2015-02-13 | 2:44:04 PM | Sapl0005 | 1 | 2 | J017 | 270 | 278 | 4300015185 | 34 | 0 | S0064 | 2014-07-22 | LONG RAIL, CROSS RAIL & TROLLEY SET FOR C100 SECTION RAILS. | MR. RAJKUMAR RAMCHANDRA JAGTAP | 2 | 2014-07-22 | 2014-07-22 | 2014-07-23 | 2014-07-23 | 2014-07-29 | 2014-07-29 | 2014-07-30 | 2014-07-30 | 2014-08-02 | 2014-08-02 | 2014-08-12 | 2014-08-12 | 2014-07-30 | 2014-08-14 | 2014-08-15 | 2014-08-15 | JBM Auto Limited, Plot No. 157-E, Sector - 3, Industrial Area, 454775, Pithampur, Distt. Dhar, Madhya Pradesh(M.P.), India. | 1 | 20 | 689 | Mr. Amit Raghav | 9958475174 | amit.raghav@jbm.co.in | Mr. Rishabh | 9039005123 | surendra.yadav@jbm.co.in | 011-26427100 | AAACJ9630NEM010 | 23839049139 | 23839049139 | 1 | 1 | 1 | WOODEN BOX PACKING | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-07-25 | 2014-07-30 | 1 |  | MR. RAJKUMAR RAMCHANDRA JAGTAP
271 | 2015-01-12 | 12:37:20 PM | Sapl0005 | 1 | 2 | J006 | 274 | 283 | 4300015263 | 35 | 0 | N0081 | 2014-08-01 | MODIFICATION MATERIAL FOR SPOT WELDING FIXTURE AND CHECKING FIXTURE AS PER ECN REQUIRED FOR Y9T BIW ECN AT J1. | MR. PRABHJYOT GENJI | 3 | 2014-08-10 | 2014-08-10 | 2014-08-12 | 2014-08-12 | 2014-08-16 | 2014-08-16 | 2014-08-18 | 2014-08-18 | 2014-08-22 | 2014-08-22 | 2014-08-25 | 2014-08-25 | 2014-08-28 | 2014-08-28 | 2014-08-30 | 2014-08-30 | JAY BHARAT MARUTI LIMITED. PLANT-I, MARUTI JOINT VENTURE COMPLEX, 122015 GURGAON, HARYANA, INDIA. | 1 | 13 | 171 | MR. SAROJ CHAUDHARY | 9818459495 | saroj.chaudhary@jbm.co.in | MR. J. C. PATHAK | 9811600399 | jcpathak@jbm.co.in | 011-26427100 | AAAJ2021KXM001 | 06181814435 | 06181814435 | 1 | 1 | 1 | WOODEN BOX PACKING | - |  | 0 | 0 | 1 |  | 1 | COMPLETE | 2014-08-08 | 2014-08-16 | 1 |  | MR. PRABHJYOT GENJI
272 | 2015-02-13 | 2:44:15 PM | Sapl0005 | 1 | 2 | J017 | 275 | 284 | 4300015323 | 34 | 0 | S0065 | 2014-08-01 | LONG RAILS, CROSS RAILS & TROLLEY SETS FOR C-63 SECTION. | MR. RAJKUMAR RAMCHANDRA JAGTAP | 2 | 2014-08-06 | 2014-08-06 | 2014-08-07 | 2014-08-07 | 2014-08-08 | 2014-08-08 | 2014-08-09 | 2014-08-09 | 2014-08-10 | 2014-08-10 | 2014-08-11 | 2014-08-11 | 2014-08-13 | 2014-08-13 | 2014-08-14 | 2014-08-14 | JBM Auto Limited, Plot No. 157-E, Sector-3, Industrial Area, 454775, Pithampur, Distt. Dhar, INDIA. | 1 | 20 | 689 | Mr. Rohit Rakheja | 09999702774 | rohit.rakheja@jbm.co.in | Mr. Rishabh | 09039005123 | surendra.yadav@jbm.co.in | 011-26427100 | AAACJ9630NEM010 | 23839049139 | 23839049139 | 1 | 1 | 1 | WOODEN BOX PACKING | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-08-07 | 2014-08-09 | 1 |  | MR. RAJKUMAR RAMCHANDRA JAGTAP
275 | 2015-01-17 | 4:33:42 PM | Sapl0005 | 1 | 2 | S011 | 278 | 287 | PUOR14002289 | 34 | 0 | S0066 | 2014-08-14 | BRAKE COIL LIFTO HOIST | Mr. Hemaksh Patil | 4 | 2014-08-14 | 2014-08-14 | 2014-08-14 | 2014-08-14 | 2014-08-14 | 2014-08-14 | 2014-08-14 | 2014-08-14 | 2014-08-14 | 2014-08-14 | 2014-08-14 | 2014-08-14 | 2014-08-14 | 2014-08-14 | 2014-08-14 | 2014-08-14 | # 690, Udyambag Industrial Estate, BELGAUM - 590 008 KARNATAKA - INDIA | 1 | 17 | 295 | MR. M. N. PATIL | 8314218308 | purchase@shantiiron.net | MR. S. V. PORWAL | 8123230623 | svp@shantiiron.net | 08312440975 | AAFFS4372N-XM001 | 29580076808 | - | 0 | 0 | 1 | WOODEN BOX PACKING | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-08-14 | 2014-08-14 | 1 |  | Mr. Hemaksh Patil
276 | 2015-01-17 | 4:35:21 PM | Sapl0005 | 1 | 2 | J003 | 279 | 288 | 4300015505 | 34 | 0 | S0067 | 2014-08-21 | LONG RAILS. CROSS RAILS, TROLLEY SET FOR C-63 RAILS | MR. RAJKUMAR RAMCHANDRA JAGTAP | 2 | 2014-08-22 | 2014-08-22 | 2014-08-23 | 2014-08-23 | 2014-08-24 | 2014-08-30 | 2014-08-31 | 2014-08-31 | 2014-09-01 | 2014-09-01 | 2014-09-02 | 2014-09-02 | 2014-08-31 | 2014-09-03 | 2014-09-04 | 2014-09-04 | C1/2, CHAKAN MIDC AREA, 410501, | 1 | 21 | 405 | Mr. N. S. MALI | 8605004940 | nagnath.mali@jbmmagnetto.com | Mr. VILAS KANADE | 9922435918 | vilas.kanade@jbmmagnetto.com | - | AALCS4205RXM001 | 27750643955C | 27750643955V | 1 | 1 | 1 | WOODEN BOX PACKING | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-08-25 | 2014-08-28 | 1 |  | MR. RAJKUMAR RAMCHANDRA JAGTAP
277 | 2015-01-17 | 4:36:14 PM | Sapl0005 | 1 | 2 | A007 | 280 | 289 | 2801500052 | 34 | 0 | S0068 | 2014-08-25 | Supply Set of Long Rail, cross Rail with Trolley Set For NON-IT GUN at Bhosari PLANT Safari 65L Fuel Tank PROJECT. | MR. RAJKUMAR RAMCHANDRA JAGTAP | 2 | 2014-08-25 | 2014-08-25 | 2014-08-25 | 2014-08-25 | 2014-08-25 | 2014-08-25 | 2014-08-25 | 2014-08-25 | 2014-08-25 | 2014-08-25 | 2014-08-26 | 2014-08-26 | 2014-08-27 | 2014-08-27 | 2014-08-27 | 2014-08-27 | Automotive Stampings and Assemblies Ltd G-71/2, M.I.D.C, BHOSARI Pune-411026 | 1 | 21 | 405 | Mr. Harshad Rathod | 8805016498 | Harshad.Rathod@autostampings.com | Mr. T. S. Rao | 9881060286 | TS.Rao@autostampings.com | 02113-281800 | AAACJ2116M | 27980410010C | 27980410010V | 1 | 1 | 1 | BUBBLE SHEET PACKING & GUNNY BAG PACKING. | NA |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-08-25 | 2014-08-25 | 1 |  | MR. RAJKUMAR RAMCHANDRA JAGTAP
278 | 2020-11-04 | 5:06:52 PM | sapl0313 | 1 | 2 | A007 | 281 | 290 | 2801532251 | 36 | 0 | E0015 | 2014-08-25 | Installation of Gantry Long and Cross rail with Trolley for Safari 65L Fuel Tank at Bhosari Plant. | MR. RAJKUMAR RAMCHANDRA JAGTAP | 2 | 2014-08-25 | 2014-08-25 | 2014-08-25 | 2014-08-25 | 2014-08-25 | 2014-08-25 | 2014-08-25 | 2014-08-25 | 2014-08-26 | 2014-08-26 | 2014-08-27 | 2014-08-27 | 2014-08-27 | 2014-08-27 | 2014-08-27 | 2014-08-27 | Automotive Stampings and Assemblies Ltd G-71/2, M.I.D.C, BHOSARI Pune-411026 | 1 | 21 | 405 | Mr. Harshad Rathod | 8805016498 | Harshad.Rathod@autostampings.com | Mr. T. S. Rao | 9881060286 | TS.Rao@autostampings.com | 02113-281800 | AAACJ2116MXM004 | 27980410010C | 27980410010V | 0 | 0 | 1 | NA | NA |  | 0 | 0 | 0 |  | 1 | Material Delivered | 2014-08-25 | 2014-08-25 | 1 |  | MR. RAJKUMAR RAMCHANDRA JAGTAP
279 | 2015-01-17 | 4:37:16 PM | Sapl0005 | 1 | 2 | N003 | 282 | 291 | 011415CPCAPX163 | 34 | 0 | S0069 | 2014-09-05 | Long Rails, Cross Rails & Trolley Sets for Cowl Line. | MR. RAJKUMAR RAMCHANDRA JAGTAP | 2 | 2014-09-06 | 2014-09-06 | 2014-09-08 | 2014-09-08 | 2014-09-11 | 2014-09-11 | 2014-09-12 | 2014-09-12 | 2014-09-13 | 2014-09-13 | 2014-09-15 | 2014-09-15 | 2014-09-19 | 2014-09-19 | 2014-09-20 | 2014-09-20 | NO. 1, 12, 5 & 6, TVS INDUSTRIAL ESTATE, HARITA, HOSUR, KRISHNAGIRI DISTRICT - 635 109, TAMIL NADU, INDIA. | 1 | 31 | 680 | MR. N. SATHISH | 8220007523 | sathish.narashiman@jbm-group.com | MR. S. MURUGARAJU | 8870001513 | murugaraju.senthurpandi@jbm-group.com | - | AABCT9860DXM0003 | 888232, DT. 2/01/06 | 33323363536 | 1 | 1 | 1 | WOODEN BOX PACKING | NA |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-09-09 | 2014-09-10 | 1 |  | MR. RAJKUMAR RAMCHANDRA JAGTAP
280 | 2015-01-17 | 4:38:42 PM | Sapl0005 | 1 | 2 | J009 | 283 | 292 | JOAI/A/1300070 | 34 | 0 | S0070 | 2014-09-05 | JBM OGIHARA AUTOMOTIVE INDIA LIMITED | MR. RAJKUMAR RAMCHANDRA JAGTAP | 2 | 2014-09-05 | 2014-09-05 | 2014-09-05 | 2014-09-05 | 2014-09-06 | 2014-09-06 | 2014-09-07 | 2014-09-07 | 2014-09-08 | 2014-09-08 | 2014-09-09 | 2014-09-09 | 2014-09-15 | 2014-09-15 | 2014-09-16 | 2014-09-16 | ilding No. 6, Onsite Supplier Park, Plot No. 1, Toyota Kirloskar Motors Pvt. Ltd., Bidadi Industrial Area, Ramnagaram District, Karnataka - 562109. | 1 | 17 | 293 | Mr. Aradhya T.C. | 9916889090 | purchase@joai.co.in | Mr. Shivaprasad | 9902498009 | shivaprasad@joai.co.in | 80-23182636 | AACCJ1334PXM001 | 29140853147 | - | 1 | 1 | 1 | BUBBLE SHEET PACKING & GUNNY BAG PACKING. | NA |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-09-06 | 2014-09-07 | 1 |  | MR. RAJKUMAR RAMCHANDRA JAGTAP
281 | 2015-01-17 | 4:23:47 PM | Sapl0005 | 1 | 2 | N003 | 284 | 293 | 011415CPCAPX240 | 34 | 0 | S0071 | 2014-09-06 | LONG RAILS, CROSS RAILS & RAILS ACCESSORIES FOR COWL LINE. | MR. RAJKUMAR RAMCHANDRA JAGTAP | 2 | 2014-09-06 | 2014-09-06 | 2014-09-07 | 2014-09-07 | 2014-09-08 | 2014-09-08 | 2014-09-09 | 2014-09-09 | 2014-09-10 | 2014-09-10 | 2014-09-13 | 2014-09-13 | 2014-09-09 | 2014-09-15 | 2014-09-16 | 2014-09-16 | NO. 1, 2, 5 & 6 TVS INDUSTRIAL ESTATE, HARITA, HOSUR, KRISHNAGIRI DISTRUICT - 635 109, TAMIL NADU, INDIA. | 1 | 31 | 680 | MR. N. SATHISH | 8220007523 | sathish.narashiman@jbm-group.com | MR. S. MURUGARAJU | 8870001513 | murugaraju.senthurpandi@jbm-group.com | 011-26427100 | AABCT9860DXM0003 | 888232, DT. 2/01/06 | 33323363536 | 1 | 1 | 1 | WOODEN BOX PACKING | NA |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-09-09 | 2014-09-09 | 1 |  | MR. RAJKUMAR RAMCHANDRA JAGTAP
282 | 2015-02-13 | 2:44:38 PM | Sapl0005 | 1 | 2 | J018 | 285 | 294 | 4300015089 | 34 | 0 | S0072 | 2014-09-07 | LONG RAIL C-63 SECTION & JOINT COUPLER ASSLY C-63 SECTION RAILS. | MR. RAJKUMAR RAMCHANDRA JAGTAP | 2 | 2014-09-07 | 2014-09-07 | 2014-09-07 | 2014-09-07 | 2014-09-08 | 2014-09-08 | 2014-09-09 | 2014-09-09 | 2014-09-10 | 2014-09-10 | 2014-09-15 | 2014-09-15 | 2014-09-16 | 2014-09-16 | 2014-09-17 | 2014-09-17 | PLOT NO. RNS-1, RENAULT NISSAN SUPPLIERS PARK, ORAGADAM 603109, DISTRICT KANCHEEPURAM, TAMIL NADU, INDIA. | 1 | 31 | 688 | Mr. Veeraperumal.T | 9994458722 | veeraperumal.thavamani@jbm-group.com | Ms. R. Anusha | 9840916963 | corppurchase.bg6@jbm-group.com | 04467417788 | AAACK8997REM002 | 797097 DT. 28-09-98 | 33671602648 | 1 | 1 | 1 | WOODEN BOX PACKING | NA |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-09-07 | 2014-09-09 | 1 |  | MR. RAJKUMAR RAMCHANDRA JAGTAP
283 | 2015-03-05 | 2:52:08 PM | Sapl0005 | 1 | 2 | J018 | 286 | 295 | 4100037249 | 36 | 0 | E0016 | 2014-09-07 | INSTALLATION CHARGES LONG RAIL | MR. RAJKUMAR RAMCHANDRA JAGTAP | 2 | 2014-09-07 | 2014-09-07 | 2014-09-07 | 2014-09-07 | 2014-09-08 | 2014-09-08 | 2014-09-09 | 2014-09-09 | 2014-09-10 | 2014-09-10 | 2014-09-15 | 2014-09-15 | 2014-09-16 | 2014-09-16 | 2014-09-17 | 2014-09-17 | PLOT NO. RNS-1, RENAULT NISSAN SUPPLIERS PARK, ORAGADAM 603109, DISTRICT KANCHEEPURAM, | 1 | 31 | 688 | MR. VEERAPERUMAL THAVAMANI | 9994458722 | veeraperumal.thavamani@jbm-group.com | Ms. R. Anusha | 9840916963 | corppurchase.bg6@jbm-group.com | 044 67417788 | AAACK8997REM002 | 797097 DT. 28-09-98 | 33671602648 | 0 | 0 | 0 | NA | NA |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-09-09 | 2014-09-09 | 1 |  | MR. RAJKUMAR RAMCHANDRA JAGTAP
284 | 2015-01-17 | 4:27:33 PM | Sapl0005 | 1 | 2 | A007 | 287 | 296 | 2802500124 | 34 | 0 | S0073 | 2014-09-16 | SUPPLY SET OF LONG RAIL, CROSS RAIL WITH TROLLEY FOR NON-IT GUN AT CHAKAN PLANT Y1 ASSLY PROJECT. | MR. RAJKUMAR RAMCHANDRA JAGTAP | 2 | 2014-09-16 | 2014-09-16 | 2014-09-16 | 2014-09-16 | 2014-09-17 | 2014-09-17 | 2014-09-18 | 2014-09-18 | 2014-09-19 | 2014-09-19 | 2014-09-20 | 2014-09-20 | 2014-09-22 | 2014-09-22 | 2014-09-23 | 2014-09-23 | AUTOMOTIVE STAMPINGS AND ASSEMBLIES LTD., GAT NO. 427, MEDANKARWADI, CHAKAN, TALUKA KHED, | 1 | 21 | 405 | Mr. Harshad Rathod | 8805016498 | Harshad.Rathod@autostampings.com | Mr. T. S. Rao | 9881060286 | TS.Rao@autostampings.com | 02066314343 | AAACJ2116M | 27980410010C | 27980410010V | 1 | 1 | 1 | NA | NA |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-09-17 | 2014-09-17 | 1 |  | MR. RAJKUMAR RAMCHANDRA JAGTAP
286 | 2015-03-07 | 12:22:03 PM | Sapl0005 | 1 | 2 | S006 | 289 | 298 | SAPL/14-15/LRCR007 | 34 | 0 | S0075 | 2014-09-20 | LONG RAILS & CROSS RAILS - C63 SECTION. | MR. RAJKUMAR RAMCHANDRA JAGTAP | 2 | 2014-09-20 | 2014-09-20 | 2014-09-22 | 2014-09-22 | 2014-09-30 | 2014-09-30 | 2014-09-30 | 2014-09-30 | 2014-10-01 | 2014-10-01 | 2014-10-02 | 2014-10-02 | 2014-10-03 | 2014-10-03 | 2014-10-04 | 2014-10-04 | GAT NO. 205, KASURDI, KHED SHIVAPUR, PUNE-SATARA ROAD, TALUKA BHOR, DISTRICT PUNE. | 1 | 21 | 405 | MR. ATUL NAIK | 9011060714 | atul@synergytechs.com | MR. RAJKUMAR JAGTAP | 9850839283 | rajkumar.jagtap@synergytechs.com | - | AAHCS9857MXM001 | 27600029882/C W.E.F. 1/4/2006 | 27600029882/V W.E.F. 1/4/2006 | 1 | 1 | 1 | WOODEN BOX PACKING | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2014-09-25 | 2014-09-25 | 1 |  | MR. RAJKUMAR RAMCHANDRA JAGTAP
289 | 2015-01-17 | 4:30:49 PM | Sapl0005 | 1 | 2 | S011 | 291 | 300 | PUOR14002990 | 34 | 0 | S0076 | 2014-09-26 | LONG RAIL & TELESCOPIC RAIL C-75 SECTION | MR. RAJKUMAR RAMCHANDRA JAGTAP | 2 | 2014-09-26 | 2014-09-26 | 2014-09-27 | 2014-09-27 | 2014-09-29 | 2014-09-29 | 2014-09-30 | 2014-09-30 | 2014-10-01 | 2014-10-01 | 2014-10-02 | 2014-10-02 | 2014-10-03 | 2014-10-03 | 2014-10-04 | 2014-10-04 | # 690, Udyambag Industrial Estate, BELGAUM - 590 008 KARNATAKA - INDIA | 1 | 17 | 295 | MR. M. N. PATIL | 8314218328 | purchase@shantiiron.net | MR. SUNEEL NAGATHAN | 8314218332 | projects@shantiiron.net | 831-2440975 | AAFFS4372N-XM001 | 29580076808 | 29580076808 | 1 | 1 | 1 | FLEXIBLE BUBBLE SHEET PACKING | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-09-27 | 2014-09-29 | 1 |  | MR. RAJKUMAR RAMCHANDRA JAGTAP
290 | 2015-03-07 | 12:19:02 PM | Sapl0005 | 1 | 2 | W003 | 293 | 302 | PO-PO0814-15/00127 | 37 | 0 | P0028 | 2014-10-10 | SPARES FOR ELECTRIC CHAIN HOIST - LIFTO MAKE | Mr. Hemaksh Patil | 4 | 2014-10-10 | 2014-10-10 | 2014-10-11 | 2014-10-11 | 2014-10-12 | 2014-10-12 | 2014-10-13 | 2014-10-13 | 2014-10-14 | 2014-10-14 | 2014-10-15 | 2014-10-15 | 2014-10-16 | 2014-10-16 | 2014-10-17 | 2014-10-17 | Kuruli, Tal.Khed, Dist. Pune 410 501 Gat no.203, Moi Road, Murhe Wasti, Pune, 410501 | 1 | 21 | 405 | Mr. Vikram Kanase | 8605595514 | vikram.kanase@windalsauto.com | Mr. Deepak Rawat | 8605017919 | deepak.rawat@windalsauto.com | 02135 661286 | AAACW0964GEM008 | 27400000892 | 27400000892 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2014-10-13 | 2014-10-13 | 1 |  | Mr. Hemaksh Patil
648 | 2020-12-05 | 11:21:03 AM | sapl0313 | 1 | 7 | T016 | 676 | 675 | 0128/ 18-19 | 34 | 0 | S0182 | 2019-08-03 | Slido Rails & Load Trolleys | Mr. Pravin Suryavanshi | 5 | 2019-08-01 | 2019-08-01 | 2019-08-01 | 2019-08-01 | 2019-08-01 | 2019-08-03 | 2019-08-02 | 2019-08-03 | 2019-08-03 | 2019-08-03 | 2019-08-03 | 2019-08-03 | 2019-08-03 | 2019-08-03 | 2019-08-03 | 2019-08-03 | Gat No. 734 to 722, Velu Phata, Pune Satara Road, Velu, Tal. - Bhor, Dist.- Pune - 412205 | 1 | 21 | 405 | Mr. Pankaj Jadhav | 9168608340 | purchase@techexpertindia.com | Mr. Pankaj Jadhav | 9168608340 | purchase@techexpertindia.com | - | - | 27AAFCT7235C1ZF | - | 1 | 1 | 1 | - | Bubble Sheet Wrapping |  | 1 | 0 | 0 |  | 1 | WO Close | 2019-08-03 | 2019-08-03 | 1 |  | Mr. Pravin Suryavanshi
649 | 2019-12-29 | 6:59:31 PM | Sapl0002 | 1 | 7 | O002 | 677 | 676 | Verbal 677 | 38 | 0 | J0120 | 2019-08-16 | Assy Weldments & Floor Structures | Mr. Pravin Suryavanshi | 5 | 2019-08-12 | 2019-08-12 | 2019-08-12 | 2019-08-12 | 2019-08-24 | 2019-08-24 | 2019-08-24 | 2019-08-24 | 2019-08-26 | 2019-08-26 | 2019-08-27 | 2019-08-27 | 2019-08-28 | 2019-08-28 | 2019-08-28 | 2019-08-28 | PLOT NO. E-14,CHAKAN INDUSTRIAL AREA PH-III, VILLAGE - NIGHOJE, TALUKA - KHED PUNE 410501, Pune,Maharashtra, India. 410501 | 1 | 21 | 405 | Mr. Dheeraj Prasad | 9922941202 | dheeraj.prasad@olcieng.co.in | Mr. Amit kokane | 8308361607 | amit.kokane@olcieng.co.in | - | - | 27AAFCT7235C1ZF | - | 0 | 0 | 1 | - | Bubble Sheet Wrapping |  | 1 | 1 | 0 |  | 1 | COMPLETED | 2019-08-24 | 2019-08-20 | 1 |  | Mr. Pravin Suryavanshi
650 | 2021-01-25 | 10:22:00 AM | sapl0313 | 1 | 7 | T002 | 678 | 679 | 9000035349 | 35 | 0 | N0204 | 2019-09-24 | Frame Assembly line for TML ILCV BS6 Truck Frame varients | Mr. Sanjay D Shinde | 3 | 2019-09-20 | 2020-01-20 | 2019-09-20 | 2020-01-20 | 2019-09-28 | 2020-01-20 | 2019-11-20 | 2020-01-20 | 2019-10-25 | 2020-01-20 | 2019-11-20 | 2020-01-20 | 2019-11-20 | 2020-01-20 | 2019-12-23 | 2020-01-20 | Tata Motor Ltd., Pimpri, Pune | 1 | 21 | 405 | Mr. Nagesh Kulkarni | 9028097910 | nagesh.kulkarni@tatamotors.com | Mr. Vaibhav | 8237008430 | vaibhav.babhulkar@tatamotors.com | - | - | 27390247811C DT 01.04.2006 | - | 1 | 1 | 1 | Painting, Packing & Transport in Our Scope | Not aplicablle |  | 0 | 1 | 1 |  | 0 | To add new Parts as per Customer site requirement | 2020-10-20 | 2020-01-20 | 1 |  | Mr. Sanjay D Shinde
651 | 2020-12-05 | 11:21:31 AM | sapl0313 | 1 | 7 | N003 | 679 | 680 | 4300041027 | 34 | 0 | S0183 | 2019-09-24 | Slido Rails & Load Trolleys | Mr. Sanjay D Shinde | 4 | 2019-09-24 | 2019-09-25 | 2019-09-25 | 2019-09-25 | 2019-09-25 | 2019-09-27 | 2019-09-27 | 2019-09-27 | 2019-09-27 | 2019-09-28 | 2019-09-28 | 2019-09-28 | 2019-09-28 | 2019-09-28 | 2019-09-28 | 2019-09-28 | Neel Metal Products Ltd., Neel Metal Products Ltd Plot No.-1,2,5&6,TVS Industrial Estate,Harita,,635109, Hosur GSTIN NO. - 33AABCN6304Q1ZB STATE CODE - 33 ( Tamil Nadu ) | 1 | 31 | 680 | Mr. Nishanth Bolar | 9003342354 | nishanth.bolar@jbmgroup.com | Mr Ritesh Mittal | 8686858517 | ritesh.mittal@jbmgroup.com | - | - | 33AABCN6304Q1ZB | - | 1 | 1 | 1 | Packing with Bubble Sheet and Transport in SAPL Scope. | Not aplicablle |  | 1 | 1 | 1 |  | 1 | WO Close | 2019-09-25 | 2019-09-25 | 1 |  | Mr. Sanjay D Shinde
662 | 2022-02-11 | 10:40:02 AM | sapl0001 | 1 | 7 | N003 | 690 | 693 | 4300042059 | 34 | 0 | S0184 | 2019-12-04 | Railing System | Mr. S. D. Shinde | 5 | 2019-12-04 | 2019-12-04 | 2019-12-04 | 2019-12-04 | 2019-12-05 | 2019-12-13 | 2019-12-13 | 2019-12-13 | 2019-12-13 | 2019-12-13 | 2019-12-13 | 2019-12-13 | 2019-12-13 | 2019-12-13 | 2019-12-13 | 2019-12-13 | Neel Metal Products Ltd., Plot No.-1,2,5&6,TVS Industrial Estate,Harita,,635109, Hosur STATE CODE - 33 ( Tamil Nadu ) Plant Code:8041 | 1 | 31 | 680 | Mr. Neeshanth Bolar | 9003342354 | nishanth.bolar@jbmgroup.com | Mr. Neeshanth Bolar | 9003342354 | nishanth.bolar@jbmgroup.com | - | - | GSTIN NO. - 33AABCN6304Q1ZB | GSTIN NO. - 33AABCN6304Q1ZB | 1 | 1 | 1 | Packing with Bubble Sheet | SAPL Scope of Packing & Forwarding |  | 0 | 1 | 1 |  | 0 | FOR BOM | 2019-12-12 | 2019-12-07 | 1 |  | Mr. S. D. Shinde
784 | 2022-07-20 | 5:20:49 PM | Sapl0335 | 1 | 9 | S040 | 817 | 818 | SSPPL/2022-2023/22 | 35 | 0 | N0247 | 2022-05-06 | SPOT WELDING FIXTURES | Sanket raut | 5 | 2022-05-04 | 2022-05-10 | 2022-05-11 | 2022-05-18 | 2022-05-19 | 2022-06-19 | 2022-06-20 | 2022-06-28 | 2022-06-29 | 2022-07-06 | 2022-07-07 | 2022-07-11 | 2022-06-20 | 2022-07-19 | 2022-07-20 | 2022-07-31 | D-92, M.I.D.C. SATPUR, NASIK-07. Phone: 0253-2350988, Fax – 0253-6614154. | 1 | 21 | 402 | ANIL PATIL | 9090909090 | smi22@rediffmail.com | ANIL PATIL | 9090909090 | smi22@rediffmail.com | - | - | 27AACCS0042B1Z2 | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 0 |  | 2022-05-18 | 2022-06-28 | 1 |  | vinodkumar
642 | 2020-12-05 | 11:20:37 AM | sapl0313 | 1 | 7 | T016 | 670 | 669 | 121/ 18-19 | 34 | 0 | S0181 | 2019-06-28 | Slido Rail & Load Trolley - C63 | Mr. S Shinde | 7 | 2019-06-28 | 2019-06-28 | 2019-06-28 | 2019-06-28 | 2019-06-28 | 2019-06-28 | 2019-06-28 | 2019-06-28 | 2019-06-28 | 2019-06-28 | 2019-06-28 | 2019-06-28 | 2019-06-28 | 2019-06-28 | 2019-06-28 | 2019-06-28 | S. No. 78/1, Shivane Industrial Area, NDA Road, Near Hindustan Bakery, Shivane, Pune - 411023 | 1 | 21 | 405 | Mr. Pankaj Jadhav | 9160688340 | purchase@techexpertindia.com | - | - | purchase@techexpertindia.com | - | - | 27AAFCT7235CIZF | - | 1 | 1 | 1 | Standard packaging | Not Applicable |  | 1 | 0 | 0 |  | 1 | WO Close | 2019-06-28 | 2019-06-28 | 1 |  | Mr. S Shinde
3 | 2013-08-21 | 12:31:41 PM | Sapl0005 | 1 | 1 | C002 | 7 | 12 | 10296871 | 38 | 0 | J0001 | 2013-04-03 | ROBO PEDESTAL | MILIND TERAWDE | 13 | 2013-04-04 | 2013-04-06 | 2013-04-07 | 2013-04-09 | 2013-04-10 | 2013-04-11 | 2013-04-12 | 2013-04-13 | 2013-04-14 | 2013-04-15 | 2013-04-11 | 2013-04-12 | 2013-04-16 | 2013-04-18 | 2013-04-13 | 2013-04-14 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | RAVAL MANISH | - | manish.raval@comau.com | AMIT KOKANE | - | amit.kokane@comau.com | +91-2137-678110/11 | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2013-04-08 | 2013-04-08 | 4 |  | MILIND TERAWDE
4 | 2013-08-21 | 12:31:52 PM | Sapl0005 | 1 | 1 | C002 | 8 | 13 | 10297086 | 38 | 0 | J0002 | 2013-04-03 | RISERS | SANJAY SHINDE | 13 | 2013-04-03 | 2013-04-04 | 2013-04-04 | 2013-04-05 | 2013-04-05 | 2013-04-06 | 2013-04-06 | 2013-04-06 | 2013-04-08 | 2013-04-10 | 2013-04-06 | 2013-04-06 | 2013-04-11 | 2013-04-11 | 2013-04-09 | 2013-04-09 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | SANTOSH SAPARE | - | santosh.sapare@comau.com | AMIT KOKANE | - | amit.kokane@comau.com | +91-2137-678110/11 | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2013-04-05 | 2013-04-05 | 4 |  | SANJAY SHINDE
5 | 2013-08-28 | 10:36:33 AM | Sapl0005 | 1 | 1 | A015 | 9 | 14 | PO113000015 | 43 | 0 | T0001 | 2013-04-04 | SPARES FOR HOIST | HEMAKSH PATIL | 4 | 2013-04-03 | 2013-04-03 | 2013-04-03 | 2013-04-03 | 2013-04-03 | 2013-04-03 | 2013-04-04 | 2013-04-04 | 2013-04-04 | 2013-04-04 | 2013-04-05 | 2013-04-05 | 2013-04-05 | 2013-04-05 | 2013-04-06 | 2013-04-06 | Plot No. E-60/61/62, MIDC, Ambad, Nahsik, Maharashtra, PIN : 422010 | 1 | 21 | 405 | JANARDHAN SHINDE | 0253 - 662 8831 | sujitnair@alfengineering.com | DINESH RAUT | - | dineshraut@alfengineering.com | 2386820 | AAFCA6242GXM002 | 27180524522 - C | 27180524522 - V | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-04-03 | 2013-04-03 | 4 |  | HEMAKSH PATIL
6 | 2013-08-28 | 10:41:54 AM | Sapl0005 | 1 | 1 | P003 | 10 | 15 | 7013000069 | 34 | 0 | S0001 | 2013-04-08 | PVC TROLLEYS | HEMAKSH PATIL | 4 | 2013-04-08 | 2013-04-08 | 2013-04-08 | 2013-04-08 | 2013-04-08 | 2013-04-08 | 2013-04-08 | 2013-04-08 | 2013-04-08 | 2013-04-08 | 2013-04-08 | 2013-04-08 | 2013-04-08 | 2013-04-08 | 2013-04-08 | 2013-04-08 | PANSE AUTOCOMPS PVT LTD (UNIT-II) GAT NO.198/200, VILLAGE-BORHADEWADI , DEHU-ALANDI ROAD , MOSHI, PUNE-412 114 | 1 | 21 | 405 | YOGESH SHIRSAT | +91- 8600105940 | papl1.purchase@pansegroup.com | AVINASH BHONDE | - | adbhonde@pansegroup.com | 020-24378901 | AABCPO249CXM003 | 27420317004C w.e.f 01.04.2006 | 27420317004V w.e.f 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-04-08 | 2013-04-08 | 1 |  | HEMAKSH PATIL
7 | 2013-08-21 | 12:32:02 PM | Sapl0005 | 1 | 1 | C002 | 11 | 16 | 10297282 | 38 | 0 | J0003 | 2013-04-08 | 8120-01-32-BASE PLATE | MILIND TERAWDE | 13 | 2013-04-05 | 2013-04-06 | 2013-04-08 | 2013-04-09 | 2013-04-10 | 2013-04-14 | 2013-04-14 | 2013-04-14 | 2013-04-18 | 2013-04-18 | 2013-04-18 | 2013-04-18 | 2013-04-19 | 2013-04-19 | 2013-04-15 | 2013-04-15 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India Phone No: +91-2137-678100 | 1 | 21 | 405 | KULKARNI SUJEET | 91206678036 | sujeet.kulkarni@comau.com | AMIT KOKANE | - | amit.kokane@comau.com | +91-2137-678110/11 | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2013-04-05 | 2013-04-05 | 1 |  | MILIND TERAWDE
8 | 2013-08-21 | 12:32:11 PM | Sapl0005 | 1 | 1 | C002 | 12 | 17 | 10297283 | 38 | 0 | J0004 | 2013-04-08 | RISERS | SANJAY SHINDE | 13 | 2013-04-08 | 2013-04-08 | 2013-04-09 | 2013-04-09 | 2013-04-09 | 2013-04-09 | 2013-04-09 | 2013-04-09 | 2013-04-10 | 2013-04-10 | 2013-04-11 | 2013-04-11 | 2013-04-11 | 2013-04-11 | 2013-04-11 | 2013-04-11 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India Phone No: +91-2137-678100 | 1 | 21 | 405 | KULKARNI SUJEET | +91206678036 | sujeet.kulkarni@comau.com | AMIT KOKANE | - | amit.kokane@comau.com | +91-2137-678110/11 | AAACC6992QXM002 | 27650001482CWEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2013-04-08 | 2013-04-08 | 1 |  | SANJAY SHINDE
9 | 2018-09-10 | 9:14:40 AM | Sapl0005 | 1 | 1 | C011 | 13 | 18 | IND2448827 | 35 | 0 | N0002 | 2013-04-08 | SEZ MANIPULATOR | RAJKUMAR JAGTAP | 2 | 2013-04-08 | 2013-04-10 | 2013-04-10 | 2013-04-10 | 2013-04-10 | 2013-04-17 | 2013-04-18 | 2013-04-18 | 2013-04-29 | 2013-04-29 | 2013-04-19 | 2013-04-19 | 2013-04-18 | 2013-05-02 | 2013-04-28 | 2013-04-28 | Plot No. B-2:Phaltan Industrial Area:Village-Nandal and Surwadi, Satara Maharashtra 415523 India | 1 | 21 | 409 | SANDIP BHADANE | 9922434636 | sandip.v.bhadane@cummins.com | VIKAS MANE | - | vikas.s.mane@cummins.com | - | - | 27410344315C dated 1 April 2006 | 27410344315V dated 1 April 2006 | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-04-09 | 2013-04-09 | 1 |  | RAJKUMAR JAGTAP
10 | 2013-08-21 | 12:32:22 PM | Sapl0005 | 1 | 1 | C002 | 14 | 19 | 10295872 | 38 | 0 | J0005 | 2013-04-09 | BRACKETS | MILIND TERAWDE | 13 | 2013-03-21 | 2013-03-21 | 2013-03-22 | 2013-03-22 | 2013-03-23 | 2013-03-23 | 2013-03-25 | 2013-04-25 | 2013-04-09 | 2013-04-09 | 2013-03-26 | 2013-03-26 | 2013-04-09 | 2013-04-09 | 2013-04-08 | 2013-04-08 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | MANISH RAVAL | - | manish.raval@comau.com | AMIT KOKANE | - | amit.kokane@comau.com | 91-2137-678110/11 | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2013-03-23 | 2013-03-23 | 1 |  | MILIND TERAWDE
11 | 2013-08-28 | 10:41:39 AM | Sapl0005 | 1 | 1 | A002 | 15 | 20 | Con¦2010¦2¦34 | 34 | 0 | S0002 | 2013-04-09 | HOIST TROLLY & LONG RAIL | RAJKUMAR JAGTAP | 2 | 2013-04-09 | 2013-04-09 | 2013-04-09 | 2013-04-09 | 2013-04-09 | 2013-04-09 | 2013-04-09 | 2013-04-09 | 2013-04-10 | 2013-04-10 | 2013-04-10 | 2013-04-10 | 2013-04-11 | 2013-04-11 | 2013-04-10 | 2013-04-10 | Gat No.288,village-Mahalunge ,Talegaon-Chakan Road Chakan ,Pune-410501 | 1 | 21 | 405 | SANTOSH PUDAKE | 09881700821 | snpudake@wadhokar.com | Hiremath M.S. | - | mshiremath@wadhokar.com | (02135)259090 | AACCA3246KXM001 | 27620410014 C 01/04/2006 | 27620410014 V 01/04/2006 | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-04-09 | 2013-04-09 | 1 |  | RAJKUMAR JAGTAP
14 | 2017-09-04 | 9:42:55 AM | Sapl0005 | 1 | 1 | S020 | 19 | 24 | SI/SP/03.07/11-12 | 35 | 0 | N0005 | 2013-04-10 | WELDING FIXTURES OF HEPA ASSEMBLY | UJWAL SUPE | 3 | 2013-04-10 | 2016-08-31 | 2013-04-16 | 2016-08-31 | 2013-04-25 | 2013-04-30 | 2013-05-07 | 2013-05-18 | 2013-05-20 | 2013-05-25 | 2013-05-01 | 2013-05-07 | 2013-05-07 | 2013-06-10 | 2013-05-13 | 2013-05-17 | C-12 / 2A, TARAPUR ROAD, NEAR FLYOVER, TARAPUR M.I.D.C. AREA, BOISAR, THANE - 401506, MAHARASHTRA , INDIA | 1 | 21 | 412 | Jayesh Tale | +91-9819482348 | planning@cosmosadp.com | Bhushan Marde | - | bhushan@cosmosadp.com | - | AGRPM 6687QEM 003 | 27870399255C | 27870399255V | 0 | 0 | 1 | - | - |  | 0 | 1 | 1 |  | 1 | COMPLETE | 2013-04-18 | 2013-04-18 | 1 |  | UJWAL SUPE
15 | 2018-01-08 | 4:48:05 PM | Sapl0005 | 1 | 1 | T002 | 17 | 22 | 9000025135 | 35 | 0 | N0006 | 2013-04-09 | Overhead Transfer for SFC 407 Partial Body | More Tushar Ramchandra | 2 | 2013-04-09 | 2015-02-02 | 2013-12-05 | 2015-02-02 | 2013-05-06 | 2013-05-18 | 2013-05-28 | 2013-06-04 | 2013-06-05 | 2013-12-15 | 2013-05-20 | 2013-12-11 | 2013-05-28 | 2013-06-20 | 2013-04-29 | 2013-05-04 | PUNE AUTO Tata Motors Ltd. Pune PUNE 411018 | 1 | 21 | 405 | abhijit.medhekar | 020-6613 2426 | abhijit.medhekar@tatamotors.com | n.dodake | - | n.dodake@tatamotors.com | - | AACT2727QXM003 | 27390247811C DT.01/04/08 | 27390247811V DT.01/04/08 | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-05-04 | 2013-05-04 | 1 |  | More Tushar Ramchandra
16 | 2013-08-28 | 5:28:27 PM | Sapl0005 | 1 | 1 | M005 | 20 | 25 | A007/A72/3200054745 | 35 | 0 | N0007 | 2013-04-10 | WELDING & CHECKING FIXTURES FOR W201 PROJECT | Shinde Manoj Ravindra | 3 | 2013-04-11 | 2013-04-15 | 2013-04-16 | 2013-04-23 | 2013-04-24 | 2013-05-06 | 2013-05-15 | 2013-05-21 | 2013-05-22 | 2013-05-28 | 2013-05-07 | 2013-05-14 | 2013-05-15 | 2013-05-31 | 2013-05-16 | 2013-05-18 | Mahindra Vehicle Manufacturers Limited,Plot no. A-1,Phase-IV, MIDC, At Post : Chakan Dist. Pune 410 510 | 1 | 21 | 405 | RAJESHKUMAR | - | RAJESHKUMAR@MAHINDRA.COM | KAKADE.ASARAM | - | KAKADE.ASARAM@mahindra.com | - | AAFCM1217MXM001 | 27670630322C | 27670630322V | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-04-22 | 2013-04-22 | 1 |  | Shinde Manoj Ravindra
17 | 2013-08-28 | 5:28:45 PM | Sapl0005 | 1 | 1 | M005 | 21 | 26 | A007/A6V/3200055226 | 35 | 0 | N0008 | 2013-04-10 | WELDING & CHECKING FIXTURES FOR W201 PROJECT | Shinde Manoj Ravindra | 3 | 2013-04-11 | 2013-04-18 | 2013-04-19 | 2013-04-26 | 2013-04-27 | 2013-05-04 | 2013-05-14 | 2013-05-21 | 2013-05-22 | 2013-05-27 | 2013-05-06 | 2013-05-13 | 2013-05-14 | 2013-05-30 | 2013-05-14 | 2013-05-17 | Mahindra Vehicle Manufacturers Limited, Plot no. A-1,Phase-IV, MIDC, At Post : Chakan Dist. Pune 410 510 | 1 | 21 | 405 | RAJESHKUMAR | - | RAJESHKUMAR@MAHINDRA.COM | KAKADE.ASARAM | - | KAKADE.ASARAM@mahindra.com | - | AAFCM1217MXM001 | 27670630322C | 27670630322V | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-04-26 | 2013-04-26 | 1 |  | Shinde Manoj Ravindra
18 | 2016-02-08 | 9:45:01 AM | Sapl0005 | 1 | 1 | M005 | 22 | 27 | A007/A6M/3200055240 | 35 | 0 | N0009 | 2013-04-10 | WELDING & CHECKING FIXTURES FOR W201 PROJECT | Shinde Manoj Ravindra | 3 | 2013-04-10 | 2013-04-17 | 2013-04-18 | 2013-04-23 | 2013-04-24 | 2013-05-02 | 2013-05-13 | 2013-05-20 | 2013-05-21 | 2013-05-28 | 2013-05-03 | 2013-05-10 | 2013-05-13 | 2013-05-31 | 2013-05-14 | 2013-05-17 | Mahindra Vehicle Manufacturers Limited,Plot no. A-1,Phase-IV, MIDC, At Post : Chakan Dist. Pune 410 510 | 1 | 21 | 405 | RAJESHKUMAR | - | RAJESHKUMAR@MAHINDRA.COM | KAKADE.ASARAM | - | KAKADE.ASARAM@mahindra.com | - | AAFCM1217MXM001 | 27670630322C | 27670630322V | 0 | 0 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | COMPLETE | 2013-04-24 | 2013-04-24 | 1 |  | Shinde Manoj Ravindra
19 | 2013-08-28 | 5:29:01 PM | Sapl0005 | 1 | 1 | M005 | 23 | 28 | A007/A72/3200054203 | 35 | 0 | N0010 | 2013-04-10 | WELDING & CHECKING FIXTURES FOR W201 PROJECT | Shinde Manoj Ravindra | 3 | 2013-04-10 | 2013-04-17 | 2013-04-18 | 2013-04-25 | 2013-04-26 | 2013-04-30 | 2013-05-10 | 2013-05-15 | 2013-05-16 | 2013-05-22 | 2013-05-02 | 2013-05-09 | 2013-05-10 | 2013-05-29 | 2013-05-11 | 2013-05-21 | Mahindra Vehicle Manufacturers Limited,Plot no. A-1,Phase-IV, MIDC, At Post : Chakan Dist. Pune 410 510 | 1 | 21 | 405 | RAJESHKUMAR | - | RAJESHKUMAR@MAHINDRA.COM | KAKADE.ASARAM | - | KAKADE.ASARAM@mahindra.com | - | AAFCM1217MXM001 | 27670630322C | 27670630322V | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-04-25 | 2013-04-26 | 1 |  | Shinde Manoj Ravindra
20 | 2013-08-22 | 10:35:53 AM | Sapl0005 | 1 | 1 | C002 | 24 | 29 | 10297819 | 38 | 0 | J0006 | 2013-04-10 | TROLLEY UNIT -3043-01 FOR MARUTI PROJECT | MILIND TERAWDE | 13 | 2013-04-10 | 2013-04-10 | 2013-04-11 | 2013-04-11 | 2013-04-12 | 2013-04-16 | 2013-04-19 | 2013-04-19 | 2013-04-20 | 2013-04-20 | 2013-04-16 | 2013-04-18 | 2013-04-22 | 2013-04-22 | 2013-04-17 | 2013-04-19 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | MANISH RAWAL | - | manish.raval@comau.com | AMIT KOKANE | - | amit.kokane@comau.com | +91-2137-678110/11 | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2013-04-10 | 2013-04-10 | 1 |  | MILIND TERAWDE
22 | 2013-08-28 | 10:36:45 AM | Sapl0005 | 1 | 1 | C002 | 26 | 31 | 10295049 | 43 | 0 | T0002 | 2013-04-12 | PLC PANEL (FOR TVS) | HEMAKSH PATIL | 4 | 2013-04-12 | 2013-04-12 | 2013-04-15 | 2013-04-16 | 2013-04-16 | 2013-04-19 | 2013-04-20 | 2013-04-20 | 2013-04-22 | 2013-04-23 | 2013-04-24 | 2013-04-24 | 2013-04-24 | 2013-04-24 | 2013-04-20 | 2013-04-20 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | NILESH KHAIRNAR | 88066 61142 | nilesh.khairnar@comau.com | AMIT KOKANE | - | amit.kokane@comau.com | +91-2137-678110/11 | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-04-17 | 2013-04-17 | 1 |  | HEMAKSH PATIL
23 | 2013-08-28 | 10:36:57 AM | Sapl0005 | 1 | 1 | C002 | 27 | 32 | 10295716 | 43 | 0 | T0003 | 2013-04-12 | PLC PANEL | HEMAKSH PATIL | 4 | 2013-04-12 | 2013-04-12 | 2013-04-13 | 2013-04-13 | 2013-04-15 | 2013-04-15 | 2013-04-16 | 2013-04-16 | 2013-04-18 | 2013-04-18 | 2013-04-19 | 2013-04-19 | 2013-04-19 | 2013-04-19 | 2013-04-16 | 2013-04-16 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | NILESH KHAIRNAR | - | nilesh.khairnar@comau.com | AMIT KOKANE | - | amit.kokane@comau.com | +91-2137-678110/11 | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2013-04-15 | 2013-04-15 | 1 |  | HEMAKSH PATIL
24 | 2014-01-13 | 11:40:56 AM | Sapl0005 | 1 | 1 | C002 | 28 | 33 | 10295141 | 38 | 0 | J0007 | 2013-04-12 | TROLLEY FRAME & TROLLEYS | MILIND TERAWDE | 13 | 2013-04-12 | 2013-04-12 | 2013-04-13 | 2013-04-13 | 2013-04-15 | 2013-04-23 | 2013-04-23 | 2013-04-24 | 2013-04-25 | 2013-04-27 | 2013-04-29 | 2013-04-29 | 2013-04-29 | 2013-04-29 | 2013-04-24 | 2013-04-26 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | VISHWAS GANGAKHEDKAR | 9923200757 | vishwas.gangakhedkar@comau.com | AMIT KOKANE | - | amit.kokane@comau.com | +91-2137-678100 | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | COMPLETE | 2013-04-15 | 2013-04-15 | 1 |  | MILIND TERAWDE
25 | 2015-07-13 | 10:59:34 AM | Sapl0005 | 1 | 1 | T013 | 29 | 34 | 2840003860 | 37 | 0 | P0001 | 2013-04-13 | SPARES PARTS FOR KEMPPI MACHINE | HEMAKSH PATIL | 4 | 2013-04-13 | 2013-04-13 | 2013-04-15 | 2013-04-15 | 2013-04-16 | 2013-04-16 | 2013-04-17 | 2013-04-17 | 2013-04-22 | 2013-04-22 | 2013-04-23 | 2013-04-23 | 2013-04-24 | 2013-04-24 | 2013-04-22 | 2013-04-22 | Mummigatti Post, Belur Industrial Area, Dharwad-580011, Karnataka | 1 | 17 | 304 | RAVINDRA BABU | 8792002442 | ravindra.babu@tatamotors.com | PRANAB PRASAD | - | prasad.pranab@tatamotors.com | 0836-2486881 | AAACT2727QXM002 | 29220046257C | 29220046257V | 0 | 0 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | COMPLETE | 2013-04-15 | 2013-04-15 | 1 |  | HEMAKSH PATIL
26 | 2013-08-22 | 10:36:15 AM | Sapl0005 | 1 | 1 | C002 | 30 | 41 | 10298228 | 38 | 0 | J0008 | 2013-04-15 | RISER_CR-251 | SANJAY SHINDE | 13 | 2013-04-15 | 2013-04-15 | 2013-04-15 | 2013-04-15 | 2013-04-15 | 2013-04-15 | 2013-04-15 | 2013-04-15 | 2013-04-19 | 2013-04-19 | 2013-04-19 | 2013-04-19 | 2013-04-19 | 2013-04-19 | 2013-04-18 | 2013-04-18 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | SAMEER SAYYAD | - | sameer.sayyad@comau.com | AMIT KOKANE | - | amit.kokane@comau.com | +91-2137-678110/11 | AAACC6992QXM002 | 27650001482CWEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2013-04-16 | 2013-04-16 | 1 |  | SANJAY SHINDE
27 | 2014-01-13 | 12:10:31 PM | Sapl0005 | 1 | 1 | M018 | 31 | 42 | 13-14_Z-0071 | 34 | 0 | S0004 | 2013-04-16 | OVERHEAD RAIL & TROLLEY SET | RAJKUMAR JAGTAP | 2 | 2013-04-16 | 2013-04-16 | 2013-04-17 | 2013-04-17 | 2013-04-18 | 2013-04-18 | 2013-04-19 | 2013-04-19 | 2013-04-26 | 2013-04-26 | 2013-04-27 | 2013-04-27 | 2013-04-29 | 2013-04-29 | 2013-04-29 | 2013-04-29 | GAT NO. 307, KONDHAPURI, PUNE - NAGAR ROAD, TAL. SHIRUR, PUNE - 412209 | 1 | 21 | 405 | NAGESH JADHAV | +91 20 66 27 27 00 | njadhav@masterzippel.com | - | - | njadhav@masterzippel.com | +91 20 25 43 85 25 | AAGCM0004KEM001 | 27730763276C | 27730763276V | 1 | 1 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | COMPLETE | 2013-04-16 | 2013-04-16 | 1 |  | RAJKUMAR JAGTAP
28 | 2013-08-28 | 10:41:04 AM | Sapl0005 | 1 | 1 | A017 | 33 | 44 | 2803500116 | 34 | 0 | S0005 | 2013-04-16 | RAILS WITH TROLLEY SET | RAJKUMAR JAGTAP | 2 | 2013-04-16 | 2013-04-16 | 2013-04-16 | 2013-04-16 | 2013-04-16 | 2013-04-16 | 2013-04-16 | 2013-04-16 | 2013-04-17 | 2013-04-17 | 2013-04-17 | 2013-04-17 | 2013-04-18 | 2013-04-18 | 2013-04-18 | 2013-04-18 | S.No. 173,Village - Khakharia,Tal. – Savali, Dist. Vadodara, HALOL-391510, Gujarat, INDIA | 1 | 12 | 165 | T.S.RAO | 9881060286 | TS.Rao@autostampings.com | HARSHAD RATHOD | - | Harshad.Rathod@autostampings.com | 91-2667-288042 | AAACJ2116MXM001 | 24192100315 C | 24192100315 V | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-04-17 | 2013-04-17 | 1 |  | RAJKUMAR JAGTAP
29 | 2014-01-13 | 11:41:04 AM | Sapl0005 | 1 | 1 | C002 | 32 | 43 | 10298378 | 38 | 0 | J0009 | 2013-04-17 | RISERS (SP) & SHIMS | MILIND TERAWDE | 13 | 2013-04-16 | 2013-04-20 | 2013-04-20 | 2013-04-22 | 2013-04-22 | 2013-04-29 | 2013-04-29 | 2013-04-29 | 2013-04-30 | 2013-04-30 | 2013-05-01 | 2013-05-01 | 2013-04-29 | 2013-05-01 | 2013-04-28 | 2013-04-29 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | SANTOSH SAPARE | - | santosh.sapare@comau.com | AMIT KOKANE | - | amit.kokane@comau.com | +91-2137-678110/11 | AAACC6992QXM002 | 27650001482CWEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 1 | 0 | 1 |  | 1 | COMPLETE | 2013-04-17 | 2013-04-17 | 1 |  | MILIND TERAWDE
30 | 2013-08-28 | 10:48:05 AM | Sapl0005 | 1 | 1 | C011 | 34 | 45 | IND2376424 | 35 | 0 | N0011 | 2013-04-18 | SEZ MANIPULATOR | HEMAKSH PATIL | 4 | 2013-04-18 | 2013-04-20 | 2013-04-22 | 2013-04-26 | 2013-04-27 | 2013-04-30 | 2013-05-02 | 2013-05-08 | 2013-05-09 | 2013-05-09 | 2013-05-10 | 2013-05-20 | 2013-05-21 | 2013-05-25 | 2013-05-25 | 2013-05-25 | PLOT NO. B-2,PHALTAN SEZ INDUSTRIAL AREA,VILLAGE-NANDAL AND SURAWADI,TAL. PHALTAN,SATARA. | 1 | 21 | 409 | SANDIP BHADANE | 9922434636 | sandip.v.bhadane@cummins.com | VIKAS MANE | - | vikas.s.mane@cummins.com | - | - | 27410344315Cdated 1 April 2006 | 27410344315V dated 1 April 2006 | 0 | 0 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | COMPLETED | 2013-04-19 | 2013-04-19 | 1 |  | HEMAKSH PATIL
31 | 2015-02-28 | 10:19:28 AM | Sapl0005 | 1 | 1 | C004 | 35 | 46 | IND2425190 | 37 | 0 | P0002 | 2013-04-18 | CYLINDER BLOCK MOUNTING BOLTS | RAJKUMAR JAGTAP | 2 | 2013-04-18 | 2013-04-18 | 2013-04-20 | 2013-04-20 | 2013-04-22 | 2013-04-24 | 2013-04-25 | 2013-04-27 | 2013-04-29 | 2013-04-30 | 2013-05-02 | 2013-05-04 | 2013-05-06 | 2013-05-08 | 2013-05-09 | 2013-05-09 | CUMMINS INDIA LIMITED,KOTHRUD, PUNE -411038 | 1 | 21 | 405 | PRASHANT INAMDAR | 09822635362. | prashant.b.inamdar@cummins.com | ADESH SETH | - | adesh.a.sheth@cummins.com | - | AAACC7258BXM001 | 27410344315/C DT 01/04/06 | 27410344315/V DT 01/04/06 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2013-04-22 | 2013-04-22 | 1 |  | RAJKUMAR JAGTAP
33 | 2013-08-22 | 10:36:34 AM | Sapl0005 | 1 | 1 | C002 | 37 | 48 | 10298796 | 38 | 0 | J0010 | 2013-04-22 | 3041-01-11-BASE FRAME | MILIND TERAWDE | 13 | 2013-04-22 | 2013-04-22 | 2013-04-23 | 2013-04-23 | 2013-04-24 | 2013-04-24 | 2013-04-25 | 2013-04-25 | 2013-04-29 | 2013-04-29 | 2013-04-26 | 2013-04-26 | 2013-04-30 | 2013-04-30 | 2013-04-26 | 2013-04-27 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | MANISH RAWAL | - | manish.raval@comau.com | AMIT KOKANE | - | amit.kokane@comau.com | +91-2137-678110/11 | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | COMPLETE | 2013-04-24 | 2013-04-24 | 1 |  | MILIND TERAWDE
34 | 2014-01-13 | 12:07:10 PM | Sapl0005 | 1 | 1 | C002 | 38 | 49 | 10298977 | 38 | 0 | J0011 | 2013-04-22 | MYLAR & WELDMENT | MILIND TERAWDE | 13 | 2013-04-22 | 2013-04-22 | 2013-04-23 | 2013-04-23 | 2013-04-24 | 2013-04-25 | 2013-04-25 | 2013-04-25 | 2013-04-26 | 2013-04-26 | 2013-04-27 | 2013-04-27 | 2013-04-27 | 2013-04-27 | 2013-04-25 | 2013-04-25 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | SAMEER SAYYAD | - | sameer.sayyad@comau.com | AMIT KOKANE | - | amit.kokane@comau.com | +91-2137-678110/11 | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | COMPLETE | 2013-04-23 | 2013-04-23 | 1 |  | MILIND TERAWDE
35 | 2013-08-22 | 10:36:53 AM | Sapl0005 | 1 | 1 | C002 | 39 | 50 | 10299001 | 38 | 0 | J0012 | 2013-04-22 | BASE PLATE | MILIND TERAWDE | 13 | 2013-04-22 | 2013-04-27 | 2013-04-29 | 2013-05-03 | 2013-05-04 | 2013-05-08 | 2013-05-09 | 2013-05-09 | 2013-05-10 | 2013-05-10 | 2013-05-11 | 2013-05-11 | 2013-05-11 | 2013-05-11 | 2013-05-08 | 2013-05-09 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | SANTOSH SAPARE | - | santosh.sapare@comau.com | AMIT KOKANE | - | amit.kokane@comau.com | +91-2137-678110/11 | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | COMPLETE | 2013-04-30 | 2013-04-30 | 1 |  | MILIND TERAWDE
36 | 2014-01-13 | 12:11:03 PM | Sapl0005 | 1 | 1 | A021 | 40 | 51 | 7013000308 | 34 | 0 | S0006 | 2013-04-23 | PVC TROLLEYS & WIRE ROPE | RAJKUMAR JAGTAP | 2 | 2013-04-23 | 2013-04-23 | 2013-04-23 | 2013-04-23 | 2013-04-23 | 2013-04-23 | 2013-04-24 | 2013-04-24 | 2013-04-24 | 2013-04-24 | 2013-04-24 | 2013-04-25 | 2013-04-25 | 2013-04-25 | 2013-04-25 | 2013-04-25 | GAT NO.198/200, VILLAGE-BORHADEWADI , DEHU-ALANDI ROAD , MOSHI, PUNE-412 114 | 1 | 21 | 405 | YOGESH SHIRSAT | +91- 8600105940 | papl1.purchase@pansegroup.com | AVINASH BHONDE | - | adbhonde@pansegroup.com | 020-24378901 | AAFCA6224NEM006 | 27940527984 C w.e.f. 01.04.2006 | 27940527984 V w.e.f. 01.04.2006 | 1 | 1 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | COMPLETE | 2013-04-23 | 2013-04-23 | 1 |  | RAJKUMAR JAGTAP
37 | 2014-01-13 | 12:05:30 PM | Sapl0005 | 1 | 1 | A021 | 41 | 53 | 7013000349 | 34 | 0 | S0007 | 2013-04-24 | TROLLEY SET | RAJKUMAR JAGTAP | 2 | 2013-04-24 | 2013-04-24 | 2013-04-24 | 2013-04-24 | 2013-04-24 | 2013-04-24 | 2013-04-24 | 2013-04-24 | 2013-04-24 | 2013-04-24 | 2013-04-24 | 2013-04-24 | 2013-04-24 | 2013-04-24 | 2013-04-24 | 2013-04-24 | AUTOCOMPS CORPORATION PANSE PVT LTD MOSHI-II GAT NO.198/200, VILLAGE-BORHADEWADI , DEHU-ALANDI ROAD , MOSHI, PUNE-412 114 | 1 | 21 | 405 | YOGESH SHIRSAT | - | papl1.purchase@pansegroup.com | AVINASH BHONDE | - | adbhonde@pansegroup.com | - | AAFCA6224NEM006 | 27940527984 C w.e.f. 01.04.2006 | 27940527984 V w.e.f. 01.04.2006 | 0 | 0 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | COMPLETE | 2013-04-24 | 2013-04-24 | 1 |  | RAJKUMAR JAGTAP
41 | 2013-08-28 | 10:37:09 AM | Sapl0005 | 1 | 1 | C002 | 45 | 56 | 10299526 | 43 | 0 | T0004 | 2013-04-27 | PLC CONTROL PANEL | HEMAKSH PATIL | 4 | 2013-04-30 | 2013-05-10 | 2013-05-11 | 2013-05-15 | 2013-05-15 | 2013-05-21 | 2013-05-22 | 2013-05-24 | 2013-05-23 | 2013-05-25 | 2013-05-24 | 2013-05-24 | 2013-05-22 | 2013-05-26 | 2013-04-22 | 2013-04-22 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | KHAIRNAR Nilesh | +91206678036 | nilesh.khairnar@comau.com | AMIT KOKANE | - | amit.kokane@comau.com | 912066002865 | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2013-04-15 | 2013-04-15 | 1 |  | HEMAKSH PATIL
42 | 2013-08-28 | 10:44:55 AM | Sapl0005 | 1 | 1 | S019 | 46 | 57 | U1SR11304000001 | 37 | 0 | P0004 | 2013-04-29 | DRAG CHAIN FOR PICK & PLACE GANTRY OF FACE COWL LINE | HEMAKSH PATIL | 4 | 2013-04-29 | 2013-04-29 | 2013-04-29 | 2013-04-29 | 2013-04-29 | 2013-04-29 | 2013-04-29 | 2013-04-29 | 2013-04-30 | 2013-04-30 | 2013-05-02 | 2013-05-02 | 2013-04-29 | 2013-05-02 | 2013-05-02 | 2013-05-02 | W-199-B, S BLOCK, MIDC,BHOSARI,PUNE-411 026, MAHARASHTRA, INDIA | 1 | 21 | 405 | SHREEPAD PATANKAR | - | sharadalucknow@gmail.com | NILESH GADHAVE | - | nilesh.gadhave@sharadaindustries.com | +90-20-27121514 | AAZPM6524EXM001 | 27900001393C w.e.f 01-04-2006 | 27900001393V w.e.f 01-04-2006 | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2013-04-29 | 2013-04-29 | 1 |  | HEMAKSH PATIL
43 | 2013-08-22 | 10:37:02 AM | Sapl0005 | 1 | 1 | C002 | 47 | 58 | 10299741 | 38 | 0 | J0013 | 2013-04-30 | L BRACKET | MILIND TERAWDE | 13 | 2013-04-30 | 2013-04-30 | 2013-04-30 | 2013-04-30 | 2013-04-30 | 2013-04-30 | 2013-05-02 | 2013-05-04 | 2013-05-07 | 2013-05-07 | 2013-05-08 | 2013-05-08 | 2013-05-08 | 2013-05-08 | 2013-05-07 | 2013-05-07 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | MANISH RAWAL | - | manish.raval@comau.com | AMIT KOKANE | - | amit.kokane@comau.com | - | AAACC6992QXM002 | 27650001482CWEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | COMPLETE | 2013-05-02 | 2013-05-02 | 1 |  | MILIND TERAWDE
44 | 2013-08-22 | 10:37:12 AM | Sapl0005 | 1 | 1 | C002 | 48 | 59 | 10300005 | 38 | 0 | J0014 | 2013-05-04 | SHIMS | MILIND TERAWDE | 13 | 2013-05-03 | 2013-05-03 | 2013-05-03 | 2013-05-03 | 2013-05-04 | 2013-05-04 | 2013-05-06 | 2013-05-06 | 2013-05-07 | 2013-05-07 | 2013-05-08 | 2013-05-08 | 2013-05-09 | 2013-05-09 | 2013-05-08 | 2013-05-08 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | SANTOSH SAPARE | - | santosh.sapare@comau.com | AMIT KOKANE | - | amit.kokane@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | COMPLETE | 2013-05-04 | 2013-05-04 | 1 |  | MILIND TERAWDE
46 | 2013-08-22 | 10:38:28 AM | Sapl0005 | 1 | 1 | C002 | 50 | 61 | 10300400 | 38 | 0 | J0016 | 2013-05-08 | SHIMPACK, RISERS & HARDENED WASHER | MILIND TERAWDE | 13 | 2013-05-08 | 2013-05-08 | 2013-05-08 | 2013-05-08 | 2013-05-08 | 2013-05-08 | 2013-05-08 | 2013-05-08 | 2013-05-10 | 2013-05-15 | 2013-05-11 | 2013-05-11 | 2013-05-11 | 2013-05-11 | 2013-05-11 | 2013-05-11 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | SANTOSH SAPARE | - | santosh.sapare@comau.com | SAMEER SAYYAD | - | sameer.sayyad@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | COMPLETE | 2013-05-08 | 2013-05-08 | 1 |  | MILIND TERAWDE
47 | 2013-08-28 | 10:40:17 AM | Sapl0005 | 1 | 1 | N002 | 51 | 62 | SMUR | 34 | 0 | S0009 | 2013-05-11 | LONG RAIL, CROSS RAIL & TROLLEY SET | RAJKUMAR JAGTAP | 2 | 2013-05-11 | 2013-05-11 | 2013-05-11 | 2013-05-11 | 2013-05-13 | 2013-05-14 | 2013-05-14 | 2013-05-14 | 2013-05-21 | 2013-05-21 | 2013-05-22 | 2013-05-24 | 2013-05-14 | 2013-05-27 | 2013-05-22 | 2013-05-22 | Neel Metal Products Ltd. Plot No.-22, Sector-12,ITBT Park, SIDCUL Pantnagar, Udam Singh Nagar (U.K) | 1 | 34 | 679 | SANJAY MURGAI | - | smurgai@jbm.co.in | - | - | smurgai@jbm.co.in | - | AABCN6304QHM006 | 05001872319 | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-05-11 | 2013-05-11 | 1 |  | RAJKUMAR JAGTAP
48 | 2013-08-22 | 10:38:50 AM | Sapl0005 | 1 | 1 | C002 | 52 | 63 | 10301330 | 38 | 0 | J0017 | 2013-05-16 | SHIMS | MILIND TERAWDE | 13 | 2013-05-16 | 2013-05-16 | 2013-05-17 | 2013-05-17 | 2013-05-18 | 2013-05-18 | 2013-05-19 | 2013-05-19 | 2013-05-20 | 2013-05-22 | 2013-05-23 | 2013-05-23 | 2013-05-24 | 2013-05-24 | 2013-05-22 | 2013-05-22 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | SAMEER SAYYAD | - | sameer.sayyad@comau.com | SANTOSH SAPARE | - | santosh.sapare@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | COMPLETE | 2013-05-16 | 2013-05-16 | 1 |  | MILIND TERAWDE
49 | 2013-08-22 | 10:40:32 AM | Sapl0005 | 1 | 1 | C002 | 53 | 64 | 10301393 | 38 | 0 | J0018 | 2013-05-16 | SHIM PACK | MILIND TERAWDE | 13 | 2013-05-16 | 2013-05-16 | 2013-05-16 | 2013-05-16 | 2013-05-16 | 2013-05-16 | 2013-05-16 | 2013-05-16 | 2013-05-22 | 2013-05-22 | 2013-05-16 | 2013-05-16 | 2013-05-16 | 2013-05-16 | 2013-05-23 | 2013-05-23 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | SANTOSH SAPARE | - | santosh.sapare@comau.com | AMIT KOKANE | - | amit.kokane@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2013-05-16 | 2013-05-16 | 1 |  | MILIND TERAWDE
51 | 2013-08-28 | 10:39:54 AM | Sapl0005 | 1 | 1 | A017 | 55 | 66 | 2803500132 | 34 | 0 | S0011 | 2013-05-17 | Trolley Set for it guns hanging | RAJKUMAR JAGTAP | 2 | 2013-05-17 | 2013-05-17 | 2013-05-17 | 2013-05-17 | 2013-05-17 | 2013-05-17 | 2013-05-17 | 2013-05-17 | 2013-05-20 | 2013-05-22 | 2013-05-17 | 2013-05-17 | 2013-05-17 | 2013-05-17 | 2013-05-17 | 2013-05-17 | Automotive Stampings and Assemblies Ltd S.No. 173, Village - Khakharia, Tal. # Savali, Dist. Vadodara HALOL-391510 | 1 | 12 | 165 | HARSHAD RATHOD | 8805016498 | Harshad.Rathod@autostampings.com | T S RAO | - | tsrao@autostampings.com | - | AAACJ2116MXM001 | 24192100315 C | 24192100315 V | 0 | 0 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | COMPLETED | 2013-05-17 | 2013-05-17 | 1 |  | RAJKUMAR JAGTAP
52 | 2013-08-22 | 10:41:02 AM | Sapl0005 | 1 | 1 | C002 | 56 | 67 | 10301300 | 38 | 0 | J0019 | 2013-05-17 | MBR ASSY MAIN TROLLEY & DOOR OTR TROLLEY | MILIND TERAWDE | 13 | 2013-05-17 | 2013-05-17 | 2013-05-18 | 2013-05-18 | 2013-05-18 | 2013-05-21 | 2013-05-22 | 2013-05-22 | 2013-05-23 | 2013-05-23 | 2013-05-24 | 2013-05-24 | 2013-05-24 | 2013-05-24 | 2013-05-22 | 2013-05-22 | Comau India Pvt.Ltd 34 km stone, Nagar Pune Highway, Shikarpur ,Pune-412208 | 1 | 21 | 405 | VISHWAS GANGAKHEDKAR | 9923200757 | vishwas.gangakhedkar@comau.com | AMIT KOKANE | - | amit.kokane@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2013-05-17 | 2013-05-17 | 1 |  | MILIND TERAWDE
53 | 2014-01-13 | 11:41:35 AM | Sapl0005 | 1 | 1 | C002 | 57 | 68 | 10300694 | 38 | 0 | J0020 | 2013-05-17 | TROLLEYS | MILIND TERAWDE | 13 | 2013-05-17 | 2013-05-17 | 2013-05-18 | 2013-05-18 | 2013-05-20 | 2013-05-23 | 2013-05-23 | 2013-05-23 | 2013-05-24 | 2013-05-24 | 2013-05-25 | 2013-05-25 | 2013-05-23 | 2013-05-25 | 2013-05-23 | 2013-05-23 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | VISHWAS GANGAKHEDKAR | 9923200757 | vishwas.gangakhedkar@comau.com | AMIT KOKANE | - | amit.kokane@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-05-17 | 2013-05-17 | 1 |  | MILIND TERAWDE
54 | 2013-08-28 | 10:28:32 AM | Sapl0005 | 1 | 1 | C002 | 58 | 69 | 10301744 | 38 | 0 | J0021 | 2013-05-20 | SHIMS PACK | MILIND TERAWDE | 13 | 2013-05-20 | 2013-05-20 | 2013-05-20 | 2013-05-20 | 2013-05-20 | 2013-05-20 | 2013-05-20 | 2013-05-20 | 2013-05-24 | 2013-05-24 | 2013-05-25 | 2013-05-25 | 2013-05-25 | 2013-05-25 | 2013-05-25 | 2013-05-25 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | SANTOSH SAPARE | - | santosh.sapare@comau.com | AMIT KOKANE | - | amit.kokane@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-05-20 | 2013-05-20 | 1 |  | MILIND TERAWDE
55 | 2013-08-28 | 10:28:51 AM | Sapl0005 | 1 | 1 | C002 | 59 | 70 | 10301760 | 38 | 0 | J0022 | 2013-05-20 | SHIMS | MILIND TERAWDE | 13 | 2013-05-20 | 2013-05-20 | 2013-05-20 | 2013-05-20 | 2013-05-20 | 2013-05-20 | 2013-05-20 | 2013-05-20 | 2013-05-24 | 2013-05-24 | 2013-05-25 | 2013-05-25 | 2013-05-25 | 2013-05-25 | 2013-05-25 | 2013-05-25 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | SANTOSH SAPARE | - | santosh.sapare@comau.com | AMIT KOKANE | - | amit.kokane@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-05-20 | 2013-05-20 | 1 |  | MILIND TERAWDE
60 | 2013-08-28 | 10:29:01 AM | Sapl0005 | 1 | 1 | C002 | 63 | 74 | 10302181 | 38 | 0 | J0023 | 2013-05-23 | BRACKET & 5102BF0301-132 | MILIND TERAWDE | 13 | 2013-05-23 | 2013-05-23 | 2013-05-23 | 2013-05-23 | 2013-05-24 | 2013-05-26 | 2013-05-26 | 2013-05-26 | 2013-05-27 | 2013-05-27 | 2013-05-28 | 2013-05-28 | 2013-05-28 | 2013-05-28 | 2013-05-25 | 2013-05-25 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | SAMEER SAYYAD | - | sameer.sayyad@comau.com | AMIT KOKANE | - | amit.kokane@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-05-23 | 2013-05-23 | 1 |  | MILIND TERAWDE
62 | 2013-08-28 | 10:29:13 AM | Sapl0005 | 1 | 1 | C002 | 65 | 76 | 10302482 | 38 | 0 | J0024 | 2013-05-25 | SHIMS & RISER | MILIND TERAWDE | 13 | 2013-05-25 | 2013-05-25 | 2013-05-25 | 2013-05-25 | 2013-05-25 | 2013-05-25 | 2013-05-25 | 2013-05-25 | 2013-05-31 | 2013-05-31 | 2013-06-01 | 2013-06-01 | 2013-06-01 | 2013-06-01 | 2013-05-27 | 2013-05-29 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | MANISH RAWAL | - | manish.raval@comau.com | SANTOSH SAPARE | - | santosh.sapare@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-05-25 | 2013-05-25 | 1 |  | MILIND TERAWDE
64 | 2013-08-28 | 10:42:18 AM | Sapl0005 | 1 | 1 | A015 | 67 | 78 | PO113000247 | 37 | 0 | P0007 | 2013-05-28 | SPARES FOR HOIST | HEMAKSH PATIL | 4 | 2013-05-28 | 2013-05-28 | 2013-05-28 | 2013-05-28 | 2013-05-28 | 2013-05-28 | 2013-05-28 | 2013-05-28 | 2013-05-28 | 2013-05-28 | 2013-05-28 | 2013-05-28 | 2013-05-28 | 2013-05-28 | 2013-05-28 | 2013-05-28 | ALF ENGINEERING PVT LTD-UNIT-1 Plot No. E-60/61/62, MIDC,, Ambad, Nasihk, Maharashtra,PIN : 422010 | 1 | 21 | 405 | JANARDHAN SHINDE | 0253-6628831 | sujitnair@alfengineering.com | - | - | sujitnair@alfengineering.com | 2386820 | AAFCA6242GXM002 | 27180524522 - V | 27180524522 - C | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-05-28 | 2013-05-28 | 1 |  | HEMAKSH PATIL
65 | 2015-01-12 | 12:20:25 PM | Sapl0005 | 1 | 1 | P001 | 68 | 79 | 3170029157 | 35 | 0 | N0015 | 2013-05-29 | 4W BNA 1000 & Porter 600 power pack S/A conveyor | RAJKUMAR JAGTAP | 2 | 2013-05-30 | 2013-11-30 | 2013-11-30 | 2013-11-30 | 2013-06-22 | 2013-07-10 | 2013-07-20 | 2013-07-26 | 2013-07-31 | 2013-07-31 | 2013-07-11 | 2013-07-19 | 2013-07-20 | 2013-08-17 | 2013-07-23 | 2013-07-25 | E-2 & F-1, KATPHAL ROAD, MIDC AREA,BARAMATI- 413133, Dist.- PUNE , MAHARASHTRA, INDIA | 1 | 21 | 405 | JAGDISH GANDHE | - | jgandhe@piaggio.co.in | PRADYUMNA KSHIRSAGAR | - | pyk@piaggio.co.in | - | AABCP1225GXM002 | 27490410619C | 27490410619V | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-06-15 | 2013-06-15 | 1 |  | RAJKUMAR JAGTAP
69 | 2015-03-07 | 12:02:28 PM | Sapl0005 | 1 | 1 | G014 | 69 | 82 | GI/13-14/PO/106 | 35 | 0 | N0019 | 2013-06-06 | DESIGNING OF GRIPPER | AMIT POTDAR | 3 | 2013-06-06 | 2013-06-10 | 2013-06-10 | 2013-06-10 | 2013-06-10 | 2013-06-10 | 2013-06-10 | 2013-06-10 | 2013-06-11 | 2013-06-11 | 2013-06-10 | 2013-06-10 | 2013-06-10 | 2013-06-10 | 2013-06-10 | 2013-06-10 | Gat No.40, Village Chimbli, Tal Khed, Dist:- Pune-410 501 | 1 | 21 | 405 | KIRAN SASANE | 020-27242122 | kiran@genixautomation.com | GOKUL | - | gokul@genixautomation.com | +91-20-27242128 | - | 27480601569 V | 27480601569 C | 0 | 0 | 0 | - | - |  | 1 | 1 | 0 |  | 1 | COMPLETE | 2013-06-07 | 2013-06-07 | 1 |  | AMIT POTDAR
71 | 2014-01-04 | 5:29:25 PM | Sapl0005 | 1 | 1 | P001 | 73 | 84 | 3170029230 | 35 | 0 | N0021 | 2013-06-08 | New Fixtures for Stage no-11 LH/RH, Stage No-12, Stage no-23.5 BIW Pneumatic fixtures | PADMASINHA JOSHI | 3 | 2013-06-08 | 2013-11-30 | 2013-11-30 | 2013-11-30 | 2013-07-02 | 2013-07-26 | 2013-07-27 | 2013-08-16 | 2013-08-17 | 2013-08-30 | 2013-09-01 | 2013-09-06 | 2013-07-27 | 2013-09-24 | 2013-07-29 | 2013-08-13 | E-2 & F-1 KATPHAL ROAD, M.I.D.C. AREA BARAMATI - 413 133, MAHARASHTRA | 1 | 21 | 405 | SUNIL YEOLA | 09881066797 | sunil.yeola@piaggio.co.in | J G GANDHE | - | jgandhe@piaggio.co.in | - | AABCP1225GXM002 | 27490410619C | 27490410619V | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2013-11-30 | 2013-11-30 | 1 |  | PADMASINHA JOSHI
72 | 2013-08-28 | 10:39:03 AM | Sapl0005 | 1 | 1 | A017 | 74 | 85 | 2803500138 | 34 | 0 | S0015 | 2013-06-11 | CROSS TROLLY for cross Rail | RAJKUMAR JAGTAP | 2 | 2013-06-11 | 2013-06-11 | 2013-06-11 | 2013-06-11 | 2013-06-11 | 2013-06-11 | 2013-06-11 | 2013-06-11 | 2013-06-11 | 2013-06-11 | 2013-06-11 | 2013-06-11 | 2013-06-11 | 2013-06-11 | 2013-06-11 | 2013-06-11 | Automotive Stampings and Assemblies Ltd S.No. 173, Village - Khakharia, Tal. # Savali, Dist. Vadodara HALOL-391510 | 1 | 12 | 165 | HARSHAD RATHOD | - | Harshad.Rathod@autostampings.com | HARSHAD RATHOD | - | Harshad.Rathod@autostampings.com | - | AAACJ2116MXM001 | 24692100315C | 24692100315V | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-06-11 | 2013-06-11 | 1 |  | RAJKUMAR JAGTAP
73 | 2014-01-13 | 12:07:28 PM | Sapl0005 | 1 | 1 | C002 | 75 | 86 | 10304333 | 38 | 0 | J0025 | 2013-06-12 | SHIM & RISER | MILIND TERAWDE | 13 | 2013-06-13 | 2013-06-13 | 2013-06-14 | 2013-06-14 | 2013-06-17 | 2013-06-19 | 2013-06-20 | 2013-06-20 | 2013-06-21 | 2013-06-21 | 2013-06-22 | 2013-06-22 | 2013-06-20 | 2013-06-24 | 2013-06-20 | 2013-06-20 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | SANTOSH SAPARE | - | santosh.sapare@comau.com | SAMEER SAYYAD | - | sameer.sayyad@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | COMPLETE | 2013-06-12 | 2013-06-12 | 1 |  | MILIND TERAWDE
89 | 2013-08-28 | 10:29:39 AM | Sapl0005 | 1 | 1 | C002 | 90 | 102 | 10304970 | 38 | 0 | J0026 | 2013-06-19 | RISER (SP) & SHIM PACK (SP) | MILIND TERAWDE | 13 | 2013-06-19 | 2013-06-19 | 2013-06-20 | 2013-06-20 | 2013-06-21 | 2013-06-25 | 2013-06-27 | 2013-06-27 | 2013-06-28 | 2013-06-28 | 2013-06-26 | 2013-06-26 | 2013-06-29 | 2013-06-29 | 2013-06-27 | 2013-06-27 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | KULKARNI SUJEET | +91206678036 | sujeet.kulkarni@comau.com | Manish Raval | - | manish.raval@comau.com | - | - | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-06-21 | 2013-06-21 | 1 |  | MILIND TERAWDE
90 | 2013-08-28 | 10:45:50 AM | Sapl0005 | 1 | 1 | C002 | 91 | 103 | 10305211 | 35 | 0 | N0037 | 2013-06-20 | 5102-BS-27HT1-11 (DM-61) | MILIND TERAWDE | 13 | 2013-06-20 | 2013-06-21 | 2013-06-22 | 2013-06-23 | 2013-06-24 | 2013-06-25 | 2013-06-27 | 2013-06-27 | 2013-06-28 | 2013-06-28 | 2013-06-26 | 2013-06-26 | 2013-06-29 | 2013-06-29 | 2013-06-26 | 2013-06-27 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | KULKARNI SUJEET | - | sujeet.kulkarni@comau.com | Sameer.Sayyad | - | sameer.sayyad@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-06-22 | 2013-06-22 | 1 |  | MILIND TERAWDE
91 | 2013-08-28 | 10:29:53 AM | Sapl0005 | 1 | 1 | C002 | 92 | 104 | 10305328 | 38 | 0 | J0027 | 2013-06-20 | SHIMS | MILIND TERAWDE | 13 | 2013-06-20 | 2013-06-21 | 2013-06-22 | 2013-06-24 | 2013-06-25 | 2013-06-26 | 2013-06-27 | 2013-06-27 | 2013-06-28 | 2013-06-28 | 2013-06-27 | 2013-06-27 | 2013-06-29 | 2013-06-29 | 2013-06-26 | 2013-06-27 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | SANTOSH SAPARE | - | santosh.sapare@comau.com | SUJEET KULKARNI | - | sujeet.kulkarni@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-06-22 | 2013-06-22 | 1 |  | MILIND TERAWDE
99 | 2018-04-16 | 3:31:56 PM | Sapl0005 | 1 | 1 | C002 | 99 | 111 | 60009748 | 36 | 0 | E0001 | 2013-06-29 | LABOUR WORK | HEMAKSH PATIL | 4 | 2013-06-29 | 2013-06-29 | 2013-06-29 | 2013-06-29 | 2013-06-29 | 2013-06-29 | 2013-06-29 | 2013-06-29 | 2013-06-29 | 2013-06-29 | 2013-06-29 | 2013-06-29 | 2013-06-29 | 2013-06-29 | 2013-06-29 | 2013-06-29 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | nilesh.khairnar | - | nilesh.khairnar@comau.com | PRIYADARSHI Soumyaranjan | - | PRIYADARSHI.Soumyaranjan@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | COMPLETE | 2013-06-29 | 2013-06-29 | 1 |  | HEMAKSH PATIL
100 | 2013-08-21 | 12:31:28 PM | Sapl0005 | 1 | 1 | C002 | 100 | 112 | 10306308 | 36 | 0 | E0002 | 2013-06-29 | MATERIAL | HEMAKSH PATIL | 4 | 2013-06-29 | 2013-06-29 | 2013-06-29 | 2013-06-29 | 2013-06-29 | 2013-06-29 | 2013-06-29 | 2013-06-29 | 2013-06-29 | 2013-06-29 | 2013-06-29 | 2013-06-29 | 2013-06-29 | 2013-06-29 | 2013-06-29 | 2013-06-29 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | nilesh.khairnar | - | nilesh.khairnar@comau.com | PRIYADARSHI Soumyaranjan | - | PRIYADARSHI.Soumyaranjan@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 0 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETE | 2013-06-29 | 2013-06-29 | 1 |  | HEMAKSH PATIL
103 | 2013-08-28 | 10:38:04 AM | Sapl0005 | 1 | 1 | G015 | 104 | 115 | GP/SA/13 14/037-IV | 34 | 0 | S0020 | 2013-07-03 | LONG RAIL, CROSS RAIL & TROLLEY SET | RAJKUMAR JAGTAP | 2 | 2013-07-03 | 2013-07-03 | 2013-07-03 | 2013-07-03 | 2013-07-03 | 2013-07-03 | 2013-07-03 | 2013-07-03 | 2013-07-04 | 2013-07-04 | 2013-07-05 | 2013-07-05 | 2013-07-03 | 2013-07-06 | 2013-07-05 | 2013-07-05 | GAT NO.1326, SHELARWASTI,DEHU ALANDI ROAD, PUNE | 1 | 21 | 405 | AMIT AGARWAL | - | amit.agarwal@gloriagroup.co.in | S.K.KADAM | - | purchase@gloriagroup.co.in | - | AACFG5559LXM004 | 27260000969C | 27260000969V | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-07-02 | 2013-07-02 | 1 |  | RAJKUMAR JAGTAP
110 | 2013-08-28 | 5:06:41 PM | Sapl0005 | 1 | 1 | C002 | 111 | 122 | 10308585 | 38 | 0 | J0034 | 2013-07-19 | RISERS (VCXXX) | MILIND TERAWDE | 13 | 2013-07-19 | 2013-07-22 | 2013-07-23 | 2013-07-24 | 2013-07-25 | 2013-07-31 | 2013-08-01 | 2013-08-02 | 2013-08-05 | 2013-08-05 | 2013-07-30 | 2013-07-31 | 2013-08-06 | 2013-08-06 | 2013-07-29 | 2013-07-31 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | SAMEER SAYYAD | - | sameer.sayyad@comau.com | SUJEET KULKARNI | - | sujeet.kulkarni@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-07-24 | 2013-07-24 | 1 |  | MILIND TERAWDE
111 | 2013-08-28 | 10:37:51 AM | Sapl0005 | 1 | 1 | J013 | 112 | 123 | 4300010958 | 34 | 0 | S0022 | 2013-07-23 | LONG RAIL, CROSS RAIL & TROLLEY SET | RAJKUMAR JAGTAP | 2 | 2013-07-23 | 2013-07-23 | 2013-07-24 | 2013-07-24 | 2013-07-24 | 2013-07-30 | 2013-07-31 | 2013-07-31 | 2013-07-31 | 2013-08-02 | 2013-07-24 | 2013-07-24 | 2013-07-31 | 2013-08-07 | 2013-08-03 | 2013-08-03 | PLOT NO. 5, SECTOR - 31, KASNA 201306 GREATER NOIDA | 1 | 33 | 682 | GIRISH CHAUDHARY | - | girish@jbm.com | GIRISH CHAUDHARY | - | girish@jbm.com | - | AAACJ9630NXM002 | 09366300628 | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2013-07-23 | 2013-07-23 | 1 |  | RAJKUMAR JAGTAP
112 | 2013-08-28 | 5:17:20 PM | Sapl0005 | 1 | 1 | C002 | 113 | 124 | 10308907 | 38 | 0 | J0035 | 2013-07-24 | SHIMPACK | MILIND TERAWDE | 13 | 2013-07-24 | 2013-07-24 | 2013-07-25 | 2013-07-26 | 2013-07-27 | 2013-07-31 | 2013-07-31 | 2013-08-01 | 2013-08-05 | 2013-08-05 | 2013-08-02 | 2013-08-03 | 2013-08-06 | 2013-08-06 | 2013-08-02 | 2013-08-03 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | SANTOSH.SAPARE | - | santosh.sapare@comau.com | SUJEET KULKARNI | - | sujeet.kulkarni@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-07-24 | 2013-07-24 | 1 |  | MILIND TERAWDE
125 | 2013-08-28 | 5:18:25 PM | Sapl0005 | 1 | 1 | C002 | 125 | 136 | 10309199 | 38 | 0 | J0036 | 2013-07-26 | RISERS (VCXXX) | MILIND TERAWDE | 13 | 2013-07-26 | 2013-07-27 | 2013-07-28 | 2013-07-28 | 2013-07-29 | 2013-08-04 | 2013-08-06 | 2013-08-06 | 2013-08-05 | 2013-08-05 | 2013-08-04 | 2013-08-04 | 2013-08-07 | 2013-08-07 | 2013-08-02 | 2013-08-03 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | SAMEER SAYYAD | - | sameer.sayyad@comau.com | SUJEET KULKARNI | - | sujeet.kulkarni@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-07-27 | 2013-07-27 | 1 |  | MILIND TERAWDE
126 | 2013-08-28 | 5:19:08 PM | Sapl0005 | 1 | 1 | C002 | 126 | 137 | 10309515 | 38 | 0 | J0037 | 2013-07-26 | RISERS (VCXXX) | MILIND TERAWDE | 13 | 2013-07-26 | 2013-07-29 | 2013-07-30 | 2013-08-02 | 2013-08-03 | 2013-08-10 | 2013-08-13 | 2013-08-13 | 2013-08-12 | 2013-08-12 | 2013-08-10 | 2013-08-11 | 2013-08-13 | 2013-08-13 | 2013-08-10 | 2013-08-10 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | SAMEER SAYYAD | - | sameer.sayyad@comau.com | SUJEET KULKARNI | - | sujeet.kulkarni@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-07-31 | 2013-07-31 | 1 |  | MILIND TERAWDE
129 | 2013-08-28 | 5:19:46 PM | Sapl0005 | 1 | 1 | C002 | 129 | 140 | 10309780 | 38 | 0 | J0038 | 2013-07-31 | RISERS (VCXXX) | MILIND TERAWDE | 13 | 2013-07-31 | 2013-08-02 | 2013-08-03 | 2013-08-05 | 2013-08-06 | 2013-08-08 | 2013-08-11 | 2013-08-11 | 2013-08-12 | 2013-08-12 | 2013-08-09 | 2013-08-10 | 2013-08-13 | 2013-08-13 | 2013-08-10 | 2013-08-11 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | SAMEER SAYYAD | - | sameer.sayyad@comau.com | SUJEET KULKARNI | - | sujeet.kulkarni@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-08-02 | 2013-08-02 | 1 |  | MILIND TERAWDE
131 | 2013-08-28 | 5:20:28 PM | Sapl0005 | 1 | 1 | C002 | 131 | 142 | 10309959 | 38 | 0 | J0039 | 2013-07-31 | 5102-ET-MFL-03-00-TROLLEY | MILIND TERAWDE | 13 | 2013-07-31 | 2013-08-05 | 2013-08-06 | 2013-08-08 | 2013-08-09 | 2013-08-13 | 2013-08-15 | 2013-08-15 | 2013-08-15 | 2013-08-15 | 2013-08-13 | 2013-08-14 | 2013-08-16 | 2013-08-16 | 2013-08-13 | 2013-08-14 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | dheeraj.prasad | - | dheeraj.prasad@comau.com | SUJEET KULKARNI | - | sujeet.kulkarni@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2013-08-06 | 2013-08-06 | 1 |  | MILIND TERAWDE
133 | 2013-08-28 | 5:21:27 PM | Sapl0005 | 1 | 1 | C002 | 133 | 144 | 10310105 | 38 | 0 | J0040 | 2013-08-03 | ROUND PLATE | MILIND TERAWDE | 13 | 2013-08-02 | 2013-08-02 | 2013-08-02 | 2013-08-02 | 2013-08-03 | 2013-08-03 | 2013-08-04 | 2013-08-04 | 2013-08-05 | 2013-08-05 | 2013-08-04 | 2013-08-04 | 2013-08-06 | 2013-08-06 | 2013-08-03 | 2013-08-05 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | dheeraj.prasad | - | dheeraj.prasad@comau.com | SUJEET KULKARNI | - | sujeet.kulkarni@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-08-03 | 2013-08-03 | 1 |  | MILIND TERAWDE
134 | 2014-01-13 | 12:07:49 PM | Sapl0005 | 1 | 1 | C002 | 134 | 145 | 10310389 | 38 | 0 | J0041 | 2013-08-05 | SHIM, RISER & BUTTON STOPPER | MILIND TERAWDE | 13 | 2013-08-05 | 2013-08-07 | 2013-08-08 | 2013-08-09 | 2013-08-10 | 2013-08-13 | 2013-08-14 | 2013-08-14 | 2013-08-16 | 2013-08-16 | 2013-08-14 | 2013-08-14 | 2013-08-17 | 2013-08-17 | 2013-08-13 | 2013-08-14 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | MANISH RAVAL | - | manish.raval@comau.com | SUJEET KULKARNI | - | sujeet.kulkarni@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | COMPLETE | 2013-08-05 | 2013-08-05 | 1 |  | MILIND TERAWDE
137 | 2015-01-12 | 12:23:29 PM | Sapl0005 | 1 | 1 | T011 | 136 | 146 | TGPO470088 | 35 | 0 | N0052 | 2013-08-08 | TROLLEY FOR Y-1 | RAJKUMAR JAGTAP | 2 | 2013-08-08 | 2013-08-18 | 2013-08-19 | 2013-08-26 | 2013-08-27 | 2013-09-05 | 2013-09-14 | 2013-09-17 | 2013-09-18 | 2013-09-21 | 2013-09-06 | 2013-09-13 | 2013-09-23 | 2013-09-26 | 2013-09-18 | 2013-09-20 | AT POST KANHE TAL. MAVAL DIST. PUNE PUNE, MHR 412 106 | 1 | 21 | 405 | Uday Vaidya | - | uday_vaidya@supreme.co.in | Viajy Dakhole | - | vijay_dakhole@supreme.co.in | - | AAACT1344FXM010 | 27390253728 C | 27390253728 V | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-08-24 | 2013-08-24 | 1 |  | RAJKUMAR JAGTAP
138 | 2013-09-30 | 5:40:08 PM | Sapl0005 | 1 | 1 | C005 | 139 | 149 | 13/14-1172 | 43 | 0 | T0006 | 2013-08-12 | MATERIAL HANDLING SYSTEM WITH ELECTRIC LIFTER | HEMAKSH PATIL | 4 | 2013-08-12 | 2013-08-13 | 2013-08-13 | 2013-08-13 | 2013-08-14 | 2013-08-14 | 2013-08-16 | 2013-08-16 | 2013-08-17 | 2013-08-17 | 2013-08-14 | 2013-08-14 | 2013-08-17 | 2013-08-18 | 2013-08-16 | 2013-08-16 | GAT NO. 351, AT KASURDI, KHED SHIVAPUR, TAL. BHOR | 1 | 21 | 405 | ganesh.oulkar | 919922942820 | ganesh.oulkar@cleantechsystems.in | vishal.mandekar | - | vishal.mandekar@cleantechsystems.in | - | AACCC7648B ST001 | 27550523203C W.E.F 03/04/2006 | 27550523203V W.E.F 03/04/2006 | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2013-08-13 | 2013-08-13 | 1 |  | HEMAKSH PATIL
139 | 2013-09-30 | 5:34:32 PM | Sapl0005 | 1 | 1 | C002 | 140 | 150 | 10311283 | 38 | 0 | J0042 | 2013-08-14 | E269871611 & E270261611 SUPPORT | MILIND TERAWDE | 13 | 2013-08-14 | 2013-08-14 | 2013-08-16 | 2013-08-17 | 2013-08-19 | 2013-08-21 | 2013-08-21 | 2013-08-21 | 2013-08-22 | 2013-08-22 | 2013-08-21 | 2013-08-21 | 2013-08-23 | 2013-08-23 | 2013-08-21 | 2013-08-21 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | SAMEER SAYYAD | - | sameer.sayyad@comau.com | SUJEET KULKARNI | - | sujeet.kulkarni@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-08-17 | 2013-08-17 | 1 |  | MILIND TERAWDE
140 | 2013-08-28 | 10:36:18 AM | Sapl0005 | 1 | 1 | B007 | 141 | 151 | 4300006320 | 34 | 0 | S0026 | 2013-08-14 | LONG RAIL, CROSS RAIL & TROLLEY SET (C63) | RAJKUMAR JAGTAP | 2 | 2013-08-14 | 2013-08-14 | 2013-08-14 | 2013-08-14 | 2013-08-14 | 2013-08-14 | 2013-08-14 | 2013-08-14 | 2013-08-16 | 2013-08-16 | 2013-08-14 | 2013-08-14 | 2013-08-16 | 2013-08-17 | 2013-08-16 | 2013-08-16 | PLOT NO.A-23/1,CHAKAN INDUSTRIAL AREA, PHASE-II VILLAGE: KHALUMBRE, TQ.KHED PUNE 410501 | 1 | 21 | 405 | R.K.JADHAV | 09881150811 | rkjadhav@badvegroup.com | Mahesh A Chengta | - | machengta@badvegroup.com | - | AAACB9378FEM014 | 27680000350C | 27680000350V | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-08-14 | 2013-08-14 | 1 |  | RAJKUMAR JAGTAP
142 | 2014-01-13 | 12:08:08 PM | Sapl0005 | 1 | 1 | C002 | 143 | 153 | 10311790 | 38 | 0 | J0043 | 2013-08-21 | SHIMPACK | MILIND TERAWDE | 13 | 2013-08-21 | 2013-08-22 | 2013-08-23 | 2013-08-24 | 2013-08-24 | 2013-08-28 | 2013-08-30 | 2013-08-30 | 2013-08-30 | 2013-08-30 | 2013-08-29 | 2013-08-29 | 2013-08-30 | 2013-08-30 | 2013-08-30 | 2013-08-30 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | sameer sayeed | - | sameer.sayyed@comau.com | sujeet.kulkarni | - | sujeet.kulkarni@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | COMPLETE | 2013-08-24 | 2013-08-24 | 1 |  | MILIND TERAWDE
143 | 2014-01-13 | 12:08:29 PM | Sapl0005 | 1 | 1 | C002 | 144 | 154 | 10312195 | 38 | 0 | J0044 | 2013-08-24 | SHIMPACK | MILIND TERAWDE | 13 | 2013-08-24 | 2013-08-26 | 2013-08-26 | 2013-08-27 | 2013-08-28 | 2013-09-05 | 2013-09-06 | 2013-09-06 | 2013-09-06 | 2013-09-06 | 2013-09-06 | 2013-09-06 | 2013-09-07 | 2013-09-07 | 2013-09-07 | 2013-09-07 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur -Pune - 412208 Maharashtra, India | 1 | 21 | 405 | SUJEET KULKARNI | - | sujeet.kulkarni@comau.com | SANTOSH SAPARE | - | santosh.sapare@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | COMPLETE | 2013-08-27 | 2013-08-27 | 1 |  | MILIND TERAWDE
144 | 2013-09-21 | 10:26:15 AM | Sapl0005 | 1 | 1 | J013 | 145 | 155 | 4300011323 | 34 | 0 | S0027 | 2013-08-26 | LONG RAIL | RAJKUMAR JAGTAP | 2 | 2013-08-26 | 2013-08-26 | 2013-08-26 | 2013-08-26 | 2013-08-26 | 2013-08-26 | 2013-08-26 | 2013-08-26 | 2013-08-27 | 2013-08-28 | 2013-08-26 | 2013-08-26 | 2013-09-02 | 2013-09-03 | 2013-08-30 | 2013-08-30 | Plot No. 5, Sector-31,Kasna 201306 Greater Noida INDIA | 1 | 33 | 682 | GIRISH CHAUDHARY | 7838432466 | girish.kumar@jbm.co.in | ASHISH | - | ashish.jbmn@jbm.co.in | - | AAACJ9630NXM002 | 09366300628 | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 1 | COMPLETED | 2013-08-26 | 2013-08-26 | 1 |  | RAJKUMAR JAGTAP
145 | 2013-09-30 | 5:35:48 PM | Sapl0005 | 1 | 1 | C002 | 146 | 156 | 10312416 | 38 | 0 | J0045 | 2013-08-28 | WELDMENT, PLATE SPACER & SHIMS | MILIND TERAWDE | 13 | 2013-08-28 | 2013-08-29 | 2013-08-30 | 2013-08-31 | 2013-09-01 | 2013-09-04 | 2013-09-04 | 2013-09-04 | 2013-09-05 | 2013-09-05 | 2013-09-04 | 2013-09-04 | 2013-09-04 | 2013-09-04 | 2013-09-03 | 2013-09-04 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | SANTOSH SAPARE | - | santosh.sapare@comau.com | RAVAL MANISH | - | manish.raval@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-08-30 | 2013-08-30 | 1 |  | MILIND TERAWDE
146 | 2014-01-13 | 12:08:48 PM | Sapl0005 | 1 | 1 | C002 | 147 | 157 | 10312418 | 38 | 0 | J0046 | 2013-08-28 | BASEFRAME, PLATE, BREACKETS & SHIM PACK | MILIND TERAWDE | 13 | 2013-08-28 | 2013-08-29 | 2013-08-30 | 2013-08-31 | 2013-08-31 | 2013-09-05 | 2013-09-05 | 2013-09-05 | 2013-09-06 | 2013-09-06 | 2013-09-05 | 2013-09-05 | 2013-09-09 | 2013-09-09 | 2013-09-04 | 2013-09-05 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | SANTOSH SAPARE | - | santosh.sapare@comau.com | RAVAL MANISH | - | manish.raval@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | COMPLETE | 2013-08-30 | 2013-08-30 | 1 |  | MILIND TERAWDE
147 | 2014-01-13 | 12:09:15 PM | Sapl0005 | 1 | 1 | C002 | 148 | 158 | 10312338 | 38 | 0 | J0047 | 2013-08-28 | WELDMENT | MILIND TERAWDE | 13 | 2013-08-28 | 2013-08-30 | 2013-08-31 | 2013-09-02 | 2013-09-03 | 2013-09-09 | 2013-09-09 | 2013-09-09 | 2013-09-10 | 2013-09-10 | 2013-09-09 | 2013-09-09 | 2013-09-12 | 2013-09-12 | 2013-09-07 | 2013-09-10 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | SANTOSH SAPARE | - | santosh.sapare@comau.com | sujeet.kulkarni | - | sujeet.kulkarni@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | COMPLETE | 2013-08-31 | 2013-08-31 | 1 |  | MILIND TERAWDE
149 | 2013-10-16 | 11:14:00 AM | Sapl0005 | 1 | 1 | C002 | 150 | 160 | 10313223 | 38 | 0 | J0048 | 2013-09-04 | SHIMS | MILIND TERAWDE | 13 | 2013-09-04 | 2013-09-04 | 2013-09-04 | 2013-09-04 | 2013-09-04 | 2013-09-05 | 2013-09-05 | 2013-09-05 | 2013-09-06 | 2013-09-06 | 2013-09-05 | 2013-09-05 | 2013-09-07 | 2013-09-07 | 2013-09-07 | 2013-09-07 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | MANISH RAVAL | - | manish.raval@comau.com | sujeet.kulkarni | - | sujeet.kulkarni@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-09-04 | 2013-09-04 | 1 |  | MILIND TERAWDE
151 | 2013-09-30 | 5:36:35 PM | Sapl0005 | 1 | 1 | C002 | 152 | 162 | 10313430 | 38 | 0 | J0049 | 2013-09-06 | Risers VCXXX9999014251 & 52 | MILIND TERAWDE | 13 | 2013-09-06 | 2013-09-07 | 2013-09-08 | 2013-09-09 | 2013-09-10 | 2013-09-12 | 2013-09-12 | 2013-09-12 | 2013-09-13 | 2013-09-13 | 2013-09-12 | 2013-09-12 | 2013-09-14 | 2013-09-14 | 2013-09-12 | 2013-09-12 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | Sayyed Sameer | - | sameer.sayyad@comau.com | sujeet.kulkarni | - | sujeet.kulkarni@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-09-09 | 2013-09-09 | 1 |  | MILIND TERAWDE
152 | 2013-09-25 | 12:06:22 PM | Sapl0005 | 1 | 1 | C002 | 153 | 163 | 10313014 | 38 | 0 | J0050 | 2013-09-10 | ROUND PLATE & SQUARE PLATE | MILIND TERAWDE | 13 | 2013-09-10 | 2013-09-11 | 2013-09-11 | 2013-09-11 | 2013-09-11 | 2013-09-15 | 2013-09-16 | 2013-09-16 | 2013-09-16 | 2013-09-16 | 2013-09-15 | 2013-09-15 | 2013-09-17 | 2013-09-17 | 2013-09-14 | 2013-09-14 | GAT NO 1394, 1395, 1397 Village Shikrapur, Tal shirur 412208 PUNE India | 1 | 21 | 405 | Sayyed Sameer | - | sameer.sayyad@comau.com | sujeet.kulkarni | - | sujeet.kulkarni@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-09-11 | 2013-09-11 | 1 |  | MILIND TERAWDE
153 | 2013-10-16 | 11:14:18 AM | Sapl0005 | 1 | 1 | C002 | 154 | 164 | 10313782 | 38 | 0 | J0051 | 2013-09-11 | 7135-01-11R&L-STOOL | MILIND TERAWDE | 13 | 2013-09-11 | 2013-09-11 | 2013-09-11 | 2013-09-11 | 2013-09-11 | 2013-09-11 | 2013-09-11 | 2013-09-11 | 2013-09-12 | 2013-09-12 | 2013-09-11 | 2013-09-11 | 2013-09-13 | 2013-09-13 | 2013-09-11 | 2013-09-11 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | dheeraj.prasad | - | dheeraj.prasad@comau.com | sujeet.kulkarni | - | sujeet.kulkarni@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-09-11 | 2013-09-11 | 1 |  | MILIND TERAWDE
154 | 2014-01-13 | 11:57:29 AM | Sapl0005 | 1 | 1 | A021 | 155 | 165 | 7013002186 | 34 | 0 | S0028 | 2013-09-11 | CROSS TROLLEY & JOINT COUPLER | RAJKUMAR JAGTAP | 2 | 2013-09-11 | 2013-09-11 | 2013-09-11 | 2013-09-11 | 2013-09-11 | 2013-09-11 | 2013-09-11 | 2013-09-11 | 2013-09-12 | 2013-09-13 | 2013-09-11 | 2013-09-11 | 2013-09-16 | 2013-09-16 | 2013-09-14 | 2013-09-14 | AUTOCOMPS CORPORATION PANSE PVT LTD MOSHI-II GAT NO.198/200, VILLAGE-BORHADEWADI , DEHU-ALANDI ROAD , MOSHI, PUNE-412 114 | 1 | 21 | 405 | YOGESH SHIRSAT | 91- 8600105940 | papl1.purchase@pansegroup.com | PRADIP RAJGURU | - | papl2.purchase@pansegroup.com | - | AAFCA6224NEM007 | 27940527984 V w.e.f. 01.04.2006 | 27940527984 C w.e.f. 01.04.2006 | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-09-11 | 2013-09-11 | 1 |  | RAJKUMAR JAGTAP
155 | 2013-09-30 | 5:38:52 PM | Sapl0005 | 1 | 1 | S011 | 157 | 166 | PUOR13002568 | 37 | 0 | P0011 | 2013-09-14 | BREAK COIL | HEMAKSH PATIL | 4 | 2013-09-14 | 2013-09-14 | 2013-09-14 | 2013-09-14 | 2013-09-14 | 2013-09-14 | 2013-09-14 | 2013-09-14 | 2013-09-14 | 2013-09-14 | 2013-09-14 | 2013-09-14 | 2013-09-14 | 2013-09-14 | 2013-09-14 | 2013-09-14 | 690,, Udyambag,, Belgaum., Belgaum, PIN : . Karnataka, India | 1 | 17 | 295 | AMIT | - | amit.k@shantiiron.net | MNPATIL | - | purchase@shantiiron.net | - | AAFFS4372N-XM001 | 29580076808c | 29580076808V | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2013-09-14 | 2013-09-14 | 1 |  | HEMAKSH PATIL
159 | 2013-09-30 | 5:39:41 PM | Sapl0005 | 1 | 1 | A002 | 160 | 170 | Con¦2013¦0446/03 | 34 | 0 | S0029 | 2013-09-18 | GUN-TELESCOPIC TROLLEY SET | RAJKUMAR JAGTAP | 2 | 2013-09-18 | 2013-09-18 | 2013-09-18 | 2013-09-18 | 2013-09-18 | 2013-09-18 | 2013-09-18 | 2013-09-18 | 2013-09-20 | 2013-09-20 | 2013-09-18 | 2013-09-18 | 2013-09-21 | 2013-09-21 | 2013-09-20 | 2013-09-20 | Gat No.288,village-Mahalunge, Talegaon-Chakan Road Chakan ,Pune-410501 | 1 | 21 | 405 | SANTOSH PUDAKE | - | snpudake@wadhokar.com | - | - | snpudake@wadhokar.com | - | AACCA3246KXM001 | 27620410014 V 01/04/2006 | 27620410014 V 01/04/2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-09-18 | 2013-09-18 | 1 |  | RAJKUMAR JAGTAP
164 | 2013-10-10 | 10:16:39 AM | Sapl0005 | 1 | 1 | J003 | 165 | 175 | 4300011551 | 34 | 0 | S0030 | 2013-09-30 | LONG RAIL, CROSS RAIL & TROLLEY SET | RAJKUMAR JAGTAP | 2 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-09-30 | 2013-10-01 | 2013-10-02 | 2013-09-30 | 2013-09-30 | 2013-10-03 | 2013-10-04 | 2013-10-02 | 2013-10-02 | JBM MA Automotive Pvt. Limited C-1/2, Chakan MIDC Area 410501 Pune INDIA | 1 | 21 | 405 | VILAS KANADE | 9922435918 | vilas.kanade@jbmmagnetto.com | N.S.MALI | - | nagnath.mali@jbmmagnetto.com | - | AALCS4205RXM001 | 27750643955C | 27750643955V | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-09-30 | 2013-09-30 | 1 |  | RAJKUMAR JAGTAP
166 | 2014-01-13 | 12:09:34 PM | Sapl0005 | 1 | 1 | C002 | 167 | 177 | 10317025 | 38 | 0 | J0054 | 2013-10-09 | SHIMS | MILIND TERAWDE | 13 | 2013-10-09 | 2013-10-09 | 2013-10-09 | 2013-10-09 | 2013-10-09 | 2013-10-09 | 2013-10-09 | 2013-10-09 | 2013-10-10 | 2013-10-10 | 2013-10-11 | 2013-10-11 | 2013-10-11 | 2013-10-11 | 2013-10-11 | 2013-10-11 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | SUJEET KULKARNI | - | sujeet.kulkarni@comau.com | Manish Raval | - | manish.raval@comau.com | - | - | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 1 | 0 | 0 |  | 1 | COMPLETE | 2013-10-09 | 2013-10-09 | 1 |  | MILIND TERAWDE
171 | 2013-11-07 | 10:06:34 AM | Sapl0005 | 1 | 1 | C002 | 172 | 182 | 10316321 | 38 | 0 | J0056 | 2013-10-15 | SHIMS | MILIND TERAWDE | 13 | 2013-10-15 | 2013-10-15 | 2013-10-15 | 2013-10-15 | 2013-10-15 | 2013-10-16 | 2013-10-18 | 2013-10-18 | 2013-10-17 | 2013-10-17 | 2013-10-16 | 2013-10-16 | 2013-10-18 | 2013-10-18 | 2013-10-18 | 2013-10-18 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | manish.raval | - | manish.raval@comau.com | SUJEET KULKARNI | - | sujeet.kulkarni@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-10-15 | 2013-10-15 | 1 |  | MILIND TERAWDE
172 | 2014-01-13 | 11:57:51 AM | Sapl0005 | 1 | 1 | C002 | 173 | 183 | 10318048 | 34 | 0 | S0031 | 2013-10-16 | GALAVI Buffer | SANJAY SHINDE | 13 | 2013-10-16 | 2013-10-16 | 2013-10-17 | 2013-10-17 | 2013-10-17 | 2013-10-17 | 2013-11-15 | 2013-11-16 | 2013-11-18 | 2013-11-18 | 2013-10-17 | 2013-10-17 | 2013-11-19 | 2013-11-19 | 2013-11-15 | 2013-11-16 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | SUJEET KULKARNI | - | sujeet.kulkarni@comau.com | SUJEET KULKARNI | - | sujeet.kulkarni@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-10-17 | 2013-10-17 | 1 |  | SANJAY SHINDE
174 | 2013-11-06 | 9:27:32 AM | Sapl0005 | 1 | 1 | C002 | 175 | 185 | 10318368 | 38 | 0 | J0057 | 2013-10-18 | 4230-1-11-BASE FRAME | MILIND TERAWDE | 13 | 2013-10-18 | 2013-10-18 | 2013-10-18 | 2013-10-18 | 2013-10-18 | 2013-10-21 | 2013-10-23 | 2013-10-23 | 2013-10-22 | 2013-10-22 | 2013-10-21 | 2013-10-21 | 2013-10-23 | 2013-10-23 | 2013-10-19 | 2013-10-21 | Gate No. 1394, 1413, 34 KM Milestone, Pune Nagar Road,, Shikrapur - Pune - 412208 Maharashtra, India | 1 | 21 | 405 | manish.raval | - | manish.raval@comau.com | SUJEET KULKARNI | - | sujeet.kulkarni@comau.com | - | AAACC6992QXM002 | 27650001482C WEF 01.04.2006 | 27650001482V WEF 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-10-18 | 2013-10-18 | 1 |  | MILIND TERAWDE
175 | 2014-01-13 | 11:58:10 AM | Sapl0005 | 1 | 1 | M018 | 176 | 186 | 13-14_Z-0773 | 34 | 0 | S0032 | 2013-10-18 | Overhead Rail | RAJESHKUMAR JAGTAP | 2 | 2013-10-18 | 2013-10-18 | 2013-10-18 | 2013-10-18 | 2013-10-19 | 2013-10-19 | 2013-10-22 | 2013-10-22 | 2013-10-21 | 2013-10-21 | 2013-10-21 | 2013-10-21 | 2013-10-21 | 2013-10-21 | 2013-10-21 | 2013-10-21 | GAT NO. 307, KONDHAPURI, PUNE-NAGAR RD., SHIRUR, PUNE-412209 | 1 | 21 | 405 | NAGESH JADHAV | 91 90110 42521 | njadhav@masterzippel.com | - | - | njadhav@masterzippel.com | - | AAGCM0004KEM001 | 27730763276C | 27730763276V | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-10-19 | 2013-10-19 | 1 |  | RAJESHKUMAR JAGTAP
178 | 2013-11-19 | 9:28:54 AM | Sapl0005 | 1 | 1 | A024 | 179 | 189 | 7013002786 | 34 | 0 | S0033 | 2013-10-25 | LONG RAIL, CROSS RAIL & TROLLEY SET | RAJESHKUMAR JAGTAP | 2 | 2013-10-25 | 2013-10-25 | 2013-10-25 | 2013-10-25 | 2013-10-25 | 2013-10-26 | 2013-10-31 | 2013-10-31 | 2013-10-26 | 2013-10-26 | 2013-10-26 | 2013-10-26 | 2013-10-31 | 2013-10-31 | 2013-10-31 | 2013-10-31 | Plot No. 125, Survey No. 258,Belur Industrial Area,Village-Belur,Garag Hubli,Tal : Dharwad,(Karnataka)-580011 | 1 | 17 | 304 | YOGESH SHIRSAT | 7387103990 | papl1.purchase@pansegroup.com | PRADIP RAJGURU | - | papl2.purchase@pansegroup.com | - | AAFCA6224NEM007 | 29291145762C | 29291145762V | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETE | 2013-10-25 | 2013-10-25 | 1 |  | RAJESHKUMAR JAGTAP
180 | 2013-11-09 | 9:26:45 AM | Sapl0005 | 1 | 1 | B005 | 181 | 191 | 4500041287 | 34 | 0 | S0034 | 2013-11-06 | LONG RAIL C63 & CABLE TROLLEY C63 | RAJKUMAR JAGTAP | 2 | 2013-11-06 | 2013-11-07 | 2013-11-07 | 2013-11-12 | 2013-11-12 | 2013-11-12 | 2013-11-12 | 2013-11-12 | 2013-11-12 | 2013-11-12 | 2013-11-12 | 2013-11-12 | 2013-11-12 | 2013-11-14 | 2013-11-14 | 2013-11-14 | BADVE ENGINEERING LIMITED. UNIT-II(3 W-Chassis Div.) Gut No 15, Naigavan, Tal.Paithan, Dist.Aurangabad-431 107 (M.S),India | 1 | 21 | 385 | Chetan Kulkarni | 9552558042 | clkulkarni@badvegroup.com | S.D.YEOLA | - | sdyeole@badvegroup.com | - | AAACB9379FXM002 | 27680000350C | 27680000350V | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 1 | COMPLETED | 2013-11-07 | 2013-11-07 | 1 |  | RAJKUMAR JAGTAP
181 | 2013-11-19 | 9:29:23 AM | Sapl0005 | 1 | 1 | A021 | 182 | 192 | 7013002951 | 34 | 0 | S0035 | 2013-11-16 | TROLLEY SET C63 | RAJKUMAR JAGTAP | 2 | 2013-11-16 | 2013-11-16 | 2013-11-16 | 2013-11-16 | 2013-11-16 | 2013-11-16 | 2013-11-16 | 2013-11-16 | 2013-11-16 | 2013-11-16 | 2013-11-16 | 2013-11-16 | 2013-11-16 | 2013-11-16 | 2013-11-16 | 2013-11-16 | GAT NO.198/200, VILLAGE-BORHADEWADI , DEHU-ALANDI ROAD , MOSHI, PUNE-412 114 | 1 | 21 | 405 | YOGESH SHIRSAT | - | papl1.purchase@pansegroup.com | PRADIP RAJGURU | - | papl2.purchase@pansegroup.com | - | AAFCA6224NEM006 | 27940527984 C w.e.f. 01.04.2006 | 27940527984 V w.e.f. 01.04.2006 | 0 | 0 | 1 | - | - |  | 0 | 0 | 0 |  | 1 | COMPLETED | 2013-11-16 | 2013-11-16 | 1 |  | RAJKUMAR JAGTAP
199 | 2014-03-31 | 5:31:50 PM | Sapl0005 | 1 | 1 | J013 | 200 | 210 | 4300012996 | 34 | 0 | S0040 | 2014-01-25 | LONG RAIL C63 & CROSS RAIL C63 | RAJKUMAR JAGTAP | 2 | 2014-01-25 | 2014-01-27 | 2014-01-27 | 2014-01-29 | 2014-01-30 | 2014-01-30 | 2014-01-30 | 2014-01-30 | 2014-01-30 | 2014-01-30 | 2014-01-30 | 2014-01-30 | 2014-01-30 | 2014-01-30 | 2014-01-30 | 2014-01-30 | JBM Auto Limited Plot No. 5, Sector-31,Kasna 201306 Greater Noida INDIA | 1 | 33 | 682 | Jitender Kumar | 09899143035 | jitender.kumar1@jbm.co.in | SANJAY MURGAI | - | smurgai@jbm.co.in | - | AAACJ9630NXM002 | 09366300628 | 09366300628 | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | COMPLETED | 2014-01-27 | 2014-01-27 | 1 |  | RAJKUMAR JAGTAP
614 | 2020-12-05 | 10:55:33 AM | sapl0313 | 1 | 6 | C019 | 643 | 641 | verbal638 | 35 | 0 | N0190 | 2019-01-01 | Common welding & fabrication fixtures sets | PADMASINHA JOSHI | 3 | 2019-01-05 | 2019-03-30 | 2019-01-09 | 2019-03-30 | 2019-03-09 | 2019-03-30 | 2019-03-09 | 2019-03-30 | 2019-03-09 | 2019-03-30 | 2019-03-09 | 2019-03-30 | 2019-03-09 | 2019-03-30 | 2019-03-09 | 2019-03-30 | CEPL H/INJEWADI S NO.239/240 NEAR RAJIV GANDHI IT PARK, TAL- MULSHI, HINJEWADI, PUNE. 411057 | 1 | 21 | 405 | RAVINDRA CHAPHEKAR | 9518507008 | ravindra@chaphekarengg.com | S D SHINDE | - | sdshind@synergytechs.com | - | - | 27320000548C | 27320000548V | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 1 | WO Close | 2019-03-15 | 2019-03-15 | 1 |  | PADMASINHA JOSHI
776 | 2022-02-28 | 2:11:00 PM | sapl0325 | 1 | 9 | S036 | 797 | 811 | verbal_dns_15/01/2022 | 43 | 0 | T0040 | 2022-01-15 | Refurbishment of Pick & Place machine | Mr Vinodkumar Kadepure | 2 | 2022-01-15 | 2022-01-16 | 2022-01-16 | 2022-01-17 | 2022-01-17 | 2022-01-27 | 2022-01-27 | 2022-02-07 | 2022-02-08 | 2022-03-01 | 2022-03-02 | 2022-03-05 | 2022-03-05 | 2022-03-08 | 2022-03-08 | 2022-03-10 | Gut ?205?, ?Kasurdi?,?Khed Shivapur Off Pune?-?Bangalore Highway Tal?.?Bhor?, ?Pune ?412205? Pune?, ?Maharashtra?, ?India ?- ?412205?.? | 1 | 21 | 405 | Mr Vinodkumar Kadepure | 9156465854 | vinodkumar.kadepure@synergytechs.com | - | - | a@a.com | - | - | 27AAHCS9857M1ZD | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 0 |  | 0 |  | 2022-01-26 | 2022-02-16 | 1 |  | Mr Vinodkumar Kadepure
777 | 2022-03-05 | 3:46:04 PM | Sapl0335 | 1 | 9 | C004 | 798 | 812 | IND7011431 | 35 | 0 | N0244 | 2022-03-05 | Modification of RGV for oil pan fitment | Mr Vinodkumar Kadepure | 5 | 2022-03-05 | 2022-03-08 | 2022-03-08 | 2022-03-12 | 2022-03-16 | 2022-03-21 | 2022-03-21 | 2022-03-25 | 2022-03-26 | 2022-03-29 | 2022-03-30 | 2022-04-05 | 2022-04-06 | 2022-04-11 | 2022-04-10 | 2022-04-13 | Dhanukar Colony Kothrud Pune Maharashtra 411038 India | 1 | 21 | 405 | Prajakta Suresh Brahme | 9075564236 | adesh.a.sheth@cummins.com | - | - | a@a.com | - | - | 27AAACC7258B1ZW | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 1 |  | 0 |  | 2022-03-17 | 2022-03-17 | 1 |  | Mr Vinodkumar Kadepure
779 | 2022-09-29 | 11:10:22 AM | Sapl0335 | 1 | 9 | S037 | 800 | 814 | PO/21-22/023 | 34 | 0 | S0203 | 2022-03-16 | Gun rail spare part | Mr.mayur todkar | 5 | 2022-03-18 | 2022-03-20 | 2022-03-20 | 2022-03-21 | 2022-03-21 | 2022-03-28 | 2022-03-28 | 2022-03-31 | 2022-03-31 | 2022-04-02 | 2022-04-03 | 2022-04-04 | 2022-04-06 | 2022-04-08 | 2022-04-09 | 2022-04-11 | Plot-72 sector-11 IIE Sidcul Pantnagar Uttarakhand-263153 | 1 | 34 | 679 | Pradeep | 9090909090 | utk@srfpl.in | - | - | a@a.com | - | - | 05AARCS2337Q1ZO | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 0 |  | 1 | Dispatch completed | 2022-03-19 | 2022-03-20 | 1 |  | Mr.mayur todkar
783 | 2022-03-31 | 10:42:48 AM | sapl0325 | 1 | 9 | C004 | 803 | 817 | IND7055016 | 35 | 0 | N0246 | 2022-04-22 | RGV Front and Rear Engine mounting support | vinodkumar | 5 | 2022-04-18 | 2022-04-22 | 2022-04-23 | 2022-04-27 | 2022-04-25 | 2022-04-27 | 2022-04-27 | 2022-04-29 | 2022-04-29 | 2022-04-30 | 2022-04-30 | 2022-05-02 | 2022-05-03 | 2022-05-10 | 2022-05-10 | 2022-05-13 | Dhanukar Colony Kothrud Pune Maharashtra 411038 India | 1 | 21 | 405 | Prajakta Brahme | 9075564236 | OF141@cummins.com | - | - | a@a.com | - | - | 27AAACC7258B1ZW | - | 1 | 1 | 1 | - | - |  | 1 | 0 | 1 |  | 0 |  | 2022-04-24 | 2022-04-27 | 1 |  | vinodkumar
785 | 2022-05-10 | 1:21:48 PM | sapl0325 | 1 | 9 | F009 | 805 | 819 | 4300054822 | 35 | 0 | N0248 | 2022-05-06 | INTERNAL ? CLEANING STATION? | Mr.mayur todkar | 5 | 2022-05-06 | 2022-05-09 | 2022-05-10 | 2022-05-15 | 2022-05-15 | 2022-05-25 | 2022-05-26 | 2022-05-29 | 2022-05-30 | 2022-06-05 | 2022-06-10 | 2022-06-12 | 2022-05-26 | 2022-06-17 | 2022-06-17 | 2022-06-18 | Opp ?24?Th ? Milestone?,?Sh?-?7?,?Village?-?Vithalapu? r?, ?382130?,?Tq?-?Mandal ? ,?Ahmedabad St Code?-?24? | 1 | 12 | 142 | Dharam Pal Yadav | 9992500769 | dharm.pal@jbmgroup.com | - | - | a@a.com | - | - | 24AABCF6572C1ZX | - | 1 | 1 | 1 | - | - |  | 1 | 1 | 1 |  | 0 |  | 2022-05-15 | 2022-05-15 | 1 |  | Mr.mayur todkar
786 | 2022-05-10 | 1:24:53 PM | sapl0325 | 1 | 9 | F009 | 805 | 820 | 4300054824 | 35 | 0 | N0249 | 2022-05-06 | STATION FRAME ASSY STAND | Mr.mayur todkar | 5 | 2022-05-06 | 2022-05-09 | 2022-05-10 | 2022-05-15 | 2022-05-15 | 2022-05-25 | 2022-05-25 | 2022-05-27 | 2022-05-27 | 2022-05-29 | 2022-05-30 | 2022-05-31 | 2022-05-25 | 2022-06-01 | 2022-07-02 | 2022-06-02 | Opp ?24?Th ? Milestone?,?Sh?-?7?,?Village?-?Vithalapu? r?, ?382130?,?Tq?-?Mandal ? ,?Ahmedabad St Code?-?24 | 1 | 12 | 142 | Dharam Pal Yadav | 9992500769 | dharm.pal@jbmgroup.com | - | - | a@a.com | - | - | 24AABCF6572C1ZX | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 0 |  | 2022-05-11 | 2022-05-14 | 1 |  | Mr.mayur todkar
787 | 2022-05-10 | 1:27:49 PM | sapl0325 | 1 | 9 | F009 | 805 | 821 | 4300054825 | 35 | 0 | N0250 | 2022-05-06 | VACCUM ? CLEANING STATION? | Mr.mayur todkar | 5 | 2022-05-06 | 2022-05-10 | 2022-05-10 | 2022-05-13 | 2022-05-13 | 2022-05-20 | 2022-05-20 | 2022-05-21 | 2022-05-21 | 2022-05-26 | 2022-05-26 | 2022-05-29 | 2022-05-20 | 2022-05-29 | 2022-05-30 | 2022-05-31 | Opp ?24?Th ? Milestone?,?Sh?-?7?,?Village?-?Vithalapu? r?, ?382130?,?Tq?-?Mandal ? ,?Ahmedabad St Code?-?24? | 1 | 12 | 142 | Dharam Pal Yadav | 9992500769 | dharm.pal@jbmgroup.com | - | - | a@a.com | - | - | 24AABCF6572C1ZX | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2022-05-15 | 2022-05-15 | 1 |  | Mr.mayur todkar
788 | 2022-05-10 | 1:30:29 PM | sapl0325 | 1 | 9 | F009 | 805 | 822 | 4300054826 | 35 | 0 | N0251 | 2022-05-06 | VALVE ASSY. AUTOMATIC STATION | Mr.mayur todkar | 5 | 2022-05-06 | 2022-05-10 | 2022-05-10 | 2022-05-13 | 2022-05-13 | 2022-05-22 | 2022-05-22 | 2022-05-23 | 2022-05-23 | 2022-05-28 | 2022-05-28 | 2022-05-30 | 2022-05-22 | 2022-05-31 | 2022-05-31 | 2022-06-01 | Opp ?24?Th ? Milestone?,?Sh?-?7?,?Village?-?Vithalapu? r?, ?382130?,?Tq?-?Mandal ? ,?Ahmedabad St Code?-?24? | 1 | 12 | 142 | Dharam Pal Yadav | 9992500769 | dharm.pal@jbmgroup.com | - | - | a@a.com | - | - | 24AABCF6572C1ZX | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 0 |  | 2022-05-15 | 2022-05-15 | 1 |  | Mr.mayur todkar
790 | 2022-05-18 | 10:20:15 AM | Sapl0335 | 1 | 10 | S019 | 807 | 824 | U1RPM2223000020 | 35 | 0 | N0253 | 2022-05-18 | Assembly dashboard | Mr.Vinodkumar | 5 | 2022-05-19 | 2022-05-19 | 2022-05-20 | 2022-05-22 | 2022-05-22 | 2022-05-26 | 2022-05-26 | 2022-05-27 | 2022-05-27 | 2022-05-28 | 2022-05-30 | 2022-05-31 | 2022-06-04 | 2022-06-06 | 2022-06-06 | 2022-06-08 | W-199 Midc Bhosari B s Block Pune 411026 Maharashtra lndia | 1 | 21 | 405 | KANCHAN PANT | 9552503553 | info@sharadaindustries.com | - | - | a@a.com | - | - | 27AAZPM6524E1Z9 | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 0 |  | 2022-05-20 | 2022-05-21 | 1 |  | Mr.Vinodkumar
791 | 2022-05-18 | 10:27:14 AM | Sapl0335 | 1 | 10 | S019 | 807 | 825 | U1CG12223000057 | 35 | 0 | N0254 | 2022-05-18 | Assembly dashboard | Mr Vinodkumar Kadepure | 5 | 2022-05-19 | 2022-05-19 | 2022-05-20 | 2022-05-22 | 2022-05-22 | 2022-05-28 | 2022-05-28 | 2022-05-29 | 2022-05-29 | 2022-05-31 | 2022-05-31 | 2022-05-31 | 2022-06-03 | 2022-06-04 | 2022-06-06 | 2022-06-07 | W-199, B s Block Midc Bhosari Pune 41 1026 Maharashtra India | 1 | 21 | 405 | KANCHAN PANT | 9552503553 | info@sharadaindustries.com | - | - | a@a.com | - | - | 27 AAZPM6524E1Z9 | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 0 |  | 2022-05-20 | 2022-05-21 | 1 |  | Mr Vinodkumar Kadepure
792 | 2022-05-18 | 10:30:41 AM | Sapl0335 | 1 | 10 | S019 | 807 | 826 | U1RPM2223000016 | 35 | 0 | N0255 | 2022-05-18 | Assembly dashboard | Mr Vinodkumar Kadepure | 5 | 2022-05-19 | 2022-05-19 | 2022-05-19 | 2022-05-22 | 2022-05-22 | 2022-05-27 | 2022-05-27 | 2022-05-28 | 2022-05-28 | 2022-05-29 | 2022-05-31 | 2022-05-31 | 2022-06-03 | 2022-06-04 | 2022-06-04 | 2022-06-04 | W-199, B s Block Midc Bhosari Pune 41 1026 Maharashtra India | 1 | 21 | 405 | KANCHAN PANT | 9552503553 | info@sharadaindustries.com | - | - | a@a.com | - | - | 27 AAZPM6524E1Z9 | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 0 |  | 2022-05-20 | 2022-05-21 | 1 |  | Mr Vinodkumar Kadepure
793 | 2022-05-18 | 1:21:53 PM | Sapl0335 | 1 | 10 | S019 | 807 | 827 | U1RPM2223000017 | 35 | 0 | N0256 | 2022-05-18 | Assembly dashboard | Mr Vinodkumar Kadepure | 5 | 2022-05-19 | 2022-05-19 | 2022-05-20 | 2022-05-22 | 2022-05-22 | 2022-05-26 | 2022-05-26 | 2022-05-28 | 2022-05-28 | 2022-05-30 | 2022-05-31 | 2022-05-31 | 2022-06-01 | 2022-06-01 | 2022-06-02 | 2022-06-02 | W?-?199?-?B?,?S Block?,?Midc?,?Bhosari? Pune?, ?Maharashtra?, ?India ?- ?411 026 | 1 | 21 | 405 | KANCHAN PANT | 9552503553 | info@sharadaindustries.com | - | - | a@a.com | - | - | 27 AAZPM6524E1Z9 | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 0 |  | 2022-05-20 | 2022-05-21 | 1 |  | Mr Vinodkumar Kadepure
794 | 2022-05-18 | 1:25:45 PM | Sapl0335 | 1 | 10 | S019 | 807 | 828 | U1RPM2223000018 | 35 | 0 | N0257 | 2022-05-18 | Assembly dashboard | Mr Vinodkumar Kadepure | 5 | 2022-05-19 | 2022-05-19 | 2022-05-20 | 2022-05-22 | 2022-05-22 | 2022-05-26 | 2022-05-26 | 2022-05-29 | 2022-05-28 | 2022-05-30 | 2022-05-30 | 2022-05-31 | 2022-06-01 | 2022-06-01 | 2022-06-02 | 2022-06-03 | W-199-B,S Block,Midc,Bhosari | 1 | 21 | 405 | KANCHAN PANT | 9552503553 | info@sharadaindustries.com | - | - | a@a.com | - | - | 27 AAZPM6524E1Z9 | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 0 |  | 2022-05-21 | 2022-05-21 | 1 |  | Mr Vinodkumar Kadepure
795 | 2022-05-18 | 1:28:55 PM | Sapl0335 | 1 | 10 | S019 | 807 | 829 | U1RPM2223000019 | 35 | 0 | N0258 | 2022-05-18 | Assembly dashboard | Mr Vinodkumar Kadepure | 5 | 2022-05-19 | 2022-05-19 | 2022-05-20 | 2022-05-22 | 2022-05-22 | 2022-05-26 | 2022-05-27 | 2022-05-28 | 2022-05-27 | 2022-05-30 | 2022-05-31 | 2022-05-31 | 2022-06-01 | 2022-06-01 | 2022-06-02 | 2022-06-02 | W?-?199?-?B?,?S Block?,?Midc?,?Bhosari? Pune?, ?Maharashtra?, ?India ?- ?411 026?.? | 1 | 21 | 405 | KANCHAN PANT | 9552503553 | info@sharadaindustries.com | - | - | a@a.com | - | - | 27 AAZPM6524E1Z9 | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 1 |  | 0 |  | 2022-05-21 | 2022-05-21 | 1 |  | Mr Vinodkumar Kadepure
796 | 2022-05-24 | 4:31:18 PM | Sapl0335 | 1 | 10 | G017 | 808 | 830 | 1800/1DR026470/CA1024526 | 35 | 0 | N0259 | 2022-05-22 | Supply & Manufacturing and Inspection of Front Loading Platform | Mr.Vinodkumar | 5 | 2022-05-20 | 2022-05-22 | 2022-05-23 | 2022-05-26 | 2022-05-27 | 2022-06-20 | 2022-06-21 | 2022-06-28 | 2022-06-20 | 2022-06-29 | 2022-06-30 | 2022-07-05 | 2022-06-21 | 2022-07-13 | 2022-07-14 | 2022-07-20 | Plant ?7?, ?Pirojshanagar?, ? Wikhroli?, ?Mumbai ?400079? | 1 | 21 | 398 | Gajendrasingh J Bhadauria | 9820225024 | gjb@godrej.com | - | - | a@a.com | - | - | 27AAACG1395D1ZU | - | 1 | 1 | 1 | - | - |  | 0 | 1 | 1 |  | 0 |  | 2022-05-31 | 2022-06-05 | 1 |  | Mr.Vinodkumar
797 | 2022-05-27 | 4:00:21 PM | Sapl0335 | 1 | 10 | S039 | 810 | 831 | Verbal_NMC_16-05-2022 | 43 | 0 | T0041 | 2022-05-27 | Plasma machine topwell procut 75 | Mr Vinodkumar Kadepure | 22 | 2022-05-05 | 2022-05-05 | 2022-05-05 | 2022-05-06 | 2022-05-06 | 2022-05-06 | 2022-05-07 | 2022-05-08 | 2022-05-21 | 2022-05-10 | 2022-05-12 | 2022-05-20 | 2022-05-20 | 2022-05-25 | 2022-05-27 | 2022-05-24 | Gat.74/75 sonawane wasti talawade pune-412114 | 1 | 21 | 405 | Ansar shaik | 8087118866 | info@cnccuttingindia.com | - | - | a@a.com | - | - | 27GOOPS4511C2ZR | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 0 |  | 2022-05-13 | 2022-05-14 | 1 |  | Mr Vinodkumar Kadepure
798 | 2022-06-03 | 10:17:01 AM | Sapl0335 | 1 | 10 | J009 | 811 | 832 | 4500488543 | 37 | 0 | P0077 | 2022-06-03 | Gun rail spare part | Mr Vinodkumar Kadepure | 5 | 2022-06-03 | 2022-06-03 | 2022-06-03 | 2022-06-04 | 2022-06-05 | 2022-06-09 | 2022-06-10 | 2022-06-11 | 2022-06-11 | 2022-06-13 | 2022-06-13 | 2022-06-13 | 2022-06-13 | 2022-06-13 | 2022-06-13 | 2022-06-14 | JBM Ogihara Automotive India Limited, Building No.06,Onsite Supplier Park,Toyota Kirloskar Motors,562109,Ramnagara GSTIN NO. - 29AACCJ1334P1Z9 STATE CODE - 29 ( Karnataka ) | 1 | 17 | 293 | NISHANT | 7503685867 | aradhya.sidhu@jbmgroup.com | - | - | a@a.com | - | - | 29AACCJ1334P1Z9 | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 0 |  | 2022-06-03 | 2022-06-04 | 1 |  | Mr Vinodkumar Kadepure
800 | 2022-06-15 | 10:53:32 AM | Sapl0335 | 1 | 10 | N003 | 813 | 834 | 4300055386 | 37 | 0 | P0078 | 2022-06-15 | Gun rail spare part | Mr.Vinodkumar | 5 | 2022-06-15 | 2022-06-15 | 2022-06-15 | 2022-06-16 | 2022-06-16 | 2022-06-17 | 2022-06-17 | 2022-06-17 | 2022-06-17 | 2022-06-17 | 2022-06-18 | 2022-06-18 | 2022-06-18 | 2022-06-18 | 2022-06-19 | 2022-06-19 | Neel Metal Products Limited, Plot No.-1,2,5&6,TVS Industrial Estate,Harita,,635109,Hosur GSTIN NO. - 33AABCN6304Q1ZB STATE CODE - 33 ( Tamil Nadu ) | 1 | 31 | 680 | sathish.narashima | 999999999 | sathish.narashiman@jbmgroup.com | - | - | a@a.com | - | - | 33AABCN6304Q1ZB | - | 1 | 1 | 1 | - | - |  | 0 | 0 | 0 |  | 0 |  | 2022-06-15 | 2022-06-15 | 1 |  | Mr.Vinodkumar