## tblPM_Project_Hardware_Assemly_
Id | PRJCTNO | ItemCode | Description | UOM | BOMQ | Design | VendorPlanDate | VendorAct | WONo | VendorPlan | AssemlyDate | Remark | AssemlyNo
1 | 11 | E100-181-015 | Type:-Gas Spring ,Type of Gas Spring:-Mounting Direction Fixed Type ,Stroke:-100MM, Min Length:-181 ,Cylinder Dia(Ø):-15, Part number:- GS142 | NOS | 2 | 13-03-2021 | 13-03-2021 | 14-03-2021 | J0142 | 8 | 15-03-2021 |  | 2
2 | 3 | B032-000-010 | TAPER ROLLER BEARING 32010 X - 50X80X20 - SKF | NOS | 2 | 23-02-2021 | 05-03-2021 | 02-03-2021 | J0139 | 3 | 08-03-2021 |  | 3
3 | 3 | H045-022-200 | CHEMICAL ANCHORE FASTNER -22X200 | NOS | 10 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | NA |  | 3
4 | 3 | H045-120-200 | CHEMICAL ANCHORE FASTNER -20X200 | NOS | 5 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 09-03-2021 |  | 3
41 | 17 | H004-012-050 | HEX BOLT - IS 1364 - GRADE 10.9 - M12X50 | NOS | 128 | 17-03-2021 | 17-03-2021 | Planned | N0235 | 18 | 27-03-2021 |  | 6
42 | 17 | H004-020-080 | HEX BOLT - IS 1364 - GRADE 10.9 - M20X80 | NOS | 48 | 17-03-2021 | 17-03-2021 | Planned | N0235 | 18 | 27-03-2021 |  | 6
43 | 17 | H004-020-150 | HEX BOLT - IS 1364 - GRADE 10.9 - M20X150 | NOS | 48 | 17-03-2021 | 17-03-2021 | Planned | N0235 | 18 | 27-03-2021 |  | 6
44 | 17 | H042-012-000 | PUNCHED WASHER TYPE A - M12 (OD=24, ID=14, T=2.5) - IS 2016 -1967 | NOS | 128 | 17-03-2021 | 17-03-2021 | Planned | N0235 | 18 | 27-03-2021 |  | 6
45 | 17 | H042-020-000 | PUNCHED WASHER TYPE A - M20 (OD=37, ID=22, T=3.15) - IS 2016 -1967 | NOS | 100 | 17-03-2021 | 17-03-2021 | Planned | N0235 | 18 | 27-03-2021 |  | 6
46 | 17 | H044-012-000 | SPRING WASHER - M12 (OD=18, ID=12.2, T=2.5) - IS 3063 - 1972 | NOS | 128 | 17-03-2021 | 17-03-2021 | Planned | N0235 | 18 | 27-03-2021 |  | 6
47 | 17 | H044-020-000 | SPRING WASHER - M20 (OD=30.6, ID=20.2, T=4.5) - IS 3063 - 1972 | NOS | 100 | 17-03-2021 | 17-03-2021 | Planned | N0235 | 18 | 27-03-2021 |  | 6
48 | 17 | H023-020-150 | HEX NUT- IS 1364 - M20X1.5 - GRADE-10 | NOS | 150 | 17-03-2021 | 17-03-2021 | Planned | N0235 | 18 | 27-03-2021 |  | 6
49 | 17 | H450-220-150 | ANCHORE FASTNER -22X150 | NOS | 72 | 17-03-2021 | 17-03-2021 | Planned | N0235 | 18 | 28-03-2021 M20x 150 used 48 nos recieved |  | 6
50 | 14 | B021-012-010 | PAP BUSH - 1210 - P10 - ID 12 x OD 14 x 10L | NOS | 4 | 13-03-2021 | 15-03-2021 | 16-03-2021 | J0142 | 6 | 24-03-2021 |  | 7
51 | 7 | Z001-150-050 | Castor Wheels Ø150x50 With brake | NOS | 4 | 04-03-2021 | 10-03-2021 | 17-03-2021 | N0231 | 9 | 22-03-2021 |  | 8
57 | 12 | C900-000-004 | WIRE ROPE - DIA 4 | MTR | 10 | 13-03-2021 | 13-03-2021 | Available | N0235 | 15 | 30-03-2021 |  | 11
58 | 12 | C900-000-006 | WIRE ROPE - DIA 6 | MTR | 48 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 | 30-03-2021 |  | 11
59 | 12 | C920-000-004 | Wire Rope U CLAMP - M4 | NOS | 32 | 13-03-2021 | 13-03-2021 | Available | N0235 | 15 | 31-03-2021 |  | 11
60 | 12 | C920-000-006 | Wire Rope U CLAMP - M6 | NOS | 96 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 | 30-03-2021 |  | 11
61 | 12 | H002-012-060 | CSK ALLEN SCREW - IS 6761 - GRADE 12.9 -M12X60 | NOS | 48 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 | 31-03-2021 |  | 11
62 | 12 | H023-008-125 | HEX NUT- IS 1364 - M8X1.25 - GRADE-8 | NOS | 224 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 | 30-03-2021 |  | 11
63 | 12 | H023-012-175 | HEX NUT- IS 1364 - M12X1.75 - GRADE-10 | NOS | 96 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 | 31-03-2021 |  | 11
64 | 12 | H024-010-000 | NYLOCK NUT- M10 | NOS | 22 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 | 30-03-2021 |  | 11
65 | 12 | H004-008-035 | HEX BOLT - IS 1364 - GRADE 10.9 - M8X35 | NOS | 32 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 | 31-03-2021 |  | 11
66 | 12 | H025-008-000 | WELD HEX NUT - M8 | NOS | 192 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 | 30-03-2021 |  | 11
67 | 12 | H004-012-035 | HEX BOLT - IS 1364 - GRADE 10.9 - M12X35 | NOS | 46 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 | 30-03-2021 |  | 11
68 | 12 | H004-010-100 | HEX BOLT - IS 1364 - GRADE 10.9 - M10X100 | NOS | 22 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 | 31-03-2021 |  | 11
69 | 12 | H042-010-000 | PUNCHED WASHER TYPE A - M10 (OD=21, ID=11, T=2) - IS 2016 -1967 | NOS | 44 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 | 31-03-2021 |  | 11
70 | 12 | H042-012-000 | PUNCHED WASHER TYPE A - M12 (OD=24, ID=14, T=2.5) - IS 2016 -1967 | NOS | 192 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 | 31-03-2021 |  | 11
71 | 12 | H044-012-000 | SPRING WASHER - M12 (OD=18, ID=12.2, T=2.5) - IS 3063 - 1972 | NOS | 192 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 | 31-03-2021 |  | 11
72 | 12 | H024-012-000 | NYLOCK NUT - M12 | NOS | 46 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 | 31-03-2021 |  | 11
73 | 12 | H004-008-025 | HEX BOLT - IS 1364 - GRADE 10.9 - M8X25 | NOS | 224 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 | 30-03-2021 |  | 11
74 | 12 | H004-112-070 | HEX BOLT-IS 1364-GRADE 10.9 - M12X70 (FULL THREAD) | NOS | 96 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 | 30-03-2021 |  | 11
75 | 12 | B101-025-052 | BALL BEARING - 6205 ZZ - 25 X 52 X 15 - KGN MAKE | NOS | 124 | 13-03-2021 | 13-03-2021 | Confirmation required | N0235 | 15 | 30-03-2021 |  | 11
76 | 12 | K000-001-003 | Stopper M6-Rubber | NOS | 32 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 |  |  | 11
77 | 12 | K000-001-004 | Pin Bearing - Dia25x50-MS | NOS | 46 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 | 30-03-2021 |  | 11
78 | 12 | K000-001-005 | Spacer Bearing ID25, OD32, Th5 | NOS | 92 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 | 30-03-2021 |  | 11
79 | 12 | K000-001-008 | Retainer Pin | NOS | 23 | 13-03-2021 | 13-03-2021 | Available | N0235 | 15 | 30-03-2021 |  | 11
80 | 12 | K000-001-011 | Shoulder Washer | NOS | 64 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 | 30-03-2021 |  | 11
81 | 12 | K000-001-015 | Z-PLATE CROSS TROLLEY BLUE ZINC PLATED Dia-17 | NOS | 46 | 13-03-2021 | 13-03-2021 | Available | N0235 | 15 | 31-03-2021 |  | 11
82 | 12 | K000-001-016 | PIN Dia -16 | NOS | 23 | 13-03-2021 | 13-03-2021 | Available | N0235 | 15 | 30-03-2021 |  | 11
83 | 12 | K005-001-001 | Weldment Cross Trolley | NOS | 16 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 | 31-03-2021 |  | 11
84 | 12 | K005-001-003 | Weldment Cross Rail Support | NOS | 16 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 | 31-03-2021 |  | 11
85 | 12 | K005-002-001 | Weldment Plate Load Trolley | NOS | 7 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 | 31-03-2021 |  | 11
86 | 12 | K005-003-001 | Weldment Channel Support C-75 100L | NOS | 16 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 | 31-03-2021 |  | 11
87 | 12 | K005-004-001 | Weldment Joint Coupler | NOS | 48 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 | 31-03-2021 |  | 11
88 | 12 | K000-000-006 | Square Nut M12 | NOS | 144 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 | 31-03-2021 |  | 11
89 | 12 | K000-000-007 | Clamp Beam | NOS | 96 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 | 28-03-2021 |  | 11
90 | 12 | K005-006-001 | Beam Support | NOS | 48 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 | 28-03-2021 |  | 11
91 | 12 | K005-007-001 | RUBBER PAD FOR C63 | NOS | 22 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 |  |  | 11
92 | 12 | Z063-063-005 | LONG RAIL 63 - 6MTR | NOS | 20 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 |  |  | 11
93 | 12 | Z121-222-500 | Hoist 500KG | NOS | 7 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 |  |  | 11
94 | 12 | Z004-005-025 | Cross Rail (63)- 2.5Mtr | NOS | 6 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 | 31-03-2021 |  | 11
5 | 3 | H023-022-250 | HEX NUT- IS 1364 - M22X2.5 - GRADE-10 | NOS | 10 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 08-03-2021 |  | 3
6 | 3 | H023-024-300 | HEX NUT- IS 1364 - M24X3 - GRADE-10 | NOS | 10 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 09-03-2021 |  | 3
7 | 3 | H023-008-125 | HEX NUT- IS 1364 - M8X1.25 - GRADE-8 | NOS | 115 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 09-03-2021 |  | 3
8 | 3 | H023-020-150 | HEX NUT- IS 1364 - M20X1.5 - GRADE-10 | NOS | 5 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 09-03-2021 |  | 3
9 | 3 | H004-024-080 | HEX BOLT - IS 1364 - GRADE 10.9 - M24X80 | NOS | 10 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 09-03-2021 |  | 3
10 | 3 | H004-014-050 | HEX BOLT - IS 1364 - GRADE 10.9 - M14X50 | NOS | 10 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 09-03-2021 |  | 3
11 | 3 | H001-006-010 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M6X10 | NOS | 20 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 09-03-2021 |  | 3
12 | 3 | H001-008-040 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M8X40 | NOS | 12 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 09-03-2021 |  | 3
13 | 3 | H001-010-020 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M10X20 | NOS | 16 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 09-03-2021 |  | 3
14 | 3 | H001-008-030 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M8X30 | NOS | 65 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 09-03-2021 |  | 3
15 | 3 | H001-008-016 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M8X16 | NOS | 55 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 08-03-2021 |  | 3
16 | 3 | H002-006-025 | CSK ALLEN SCREW - IS 6761 - GRADE 12.9 -M6X25 | NOS | 6 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 08-03-2021 |  | 3
17 | 3 | H008-004-012 | ALLEN GRUB SCREW - IS 6094 - M4X12 | NOS | 30 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 09-03-2021 |  | 3
18 | 3 | H006-020-030 | EYE BOLT MILD STEEL FORGED IS:4190 - M20X30L,EYE HOLE - 40MM SWL -570 KG | NOS | 2 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 09-03-2021 |  | 3
19 | 3 | Z015-492-100 | MAGNET 20X10 MM | NOS | 14 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 09-03-2021 |  | 3
20 | 3 | C900-006-000 | WIRE ROPE U CLAMPS WITH NUT FOR Ø6 WIRE ROPE | NOS | 12 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 08-03-2021 |  | 3
21 | 3 | H061-010-050 | Lock Washer MB10 - ID50 - SKF | NOS | 1 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 09-03-2021 |  | 3
22 | 3 | H060-010-150 | Lock Nut - KM 10 - M50 x 1.5 - SKF | NOS | 2 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 09-03-2021 |  | 3
23 | 3 | K002-002-002 | TURN BUCKLES | NOS | 2 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 10-03-2021 |  | 3
24 | 3 | K004-005-005 | HINGE | NOS | 6 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 09-03-2021 |  | 3
25 | 3 | B008-210-000 | SQUARE FLANGE BEARING UCF 210 D1,NTN MAKE | NOS | 2 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 08-03-2021 |  | 3
26 | 3 | B001-010-026 | Ball Bearing - 6000 Zz - 10 x 26 x 8 - SKF | NOS | 4 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 08-03-2021 |  | 3
27 | 3 | C900-000-006 | WIRE ROPE - DIA 6 | MTR | 5 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 08-03-2021 |  | 3
28 | 3 | H042-002-022 | PUNCHED WASHER TYPE A - M22 | NOS | 10 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 09-03-2021 |  | 3
29 | 3 | H042-020-000 | PUNCHED WASHER TYPE A - M20 (OD=37, ID=22, T=3.15) - IS 2016 -1967 | NOS | 5 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 08-03-2021 |  | 3
30 | 3 | H042-024-000 | PUNCHED WASHER TYPE A - M24 (OD=44, ID=26, T=4) - IS 2016 -1967 | NOS | 10 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 08-03-2021 |  | 3
31 | 3 | H042-014-000 | PUNCHED WASHER TYPE A - M14 (OD=28, ID=15.5, T=2.8) - IS 2016 -1967 | NOS | 10 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 08-03-2021 |  | 3
32 | 3 | H042-006-000 | PUNCHED WASHER TYPE A - M6 (OD=12.5, ID=6.6, T=1.6) - IS 2016 -1967 | NOS | 20 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 08-03-2021 |  | 3
33 | 3 | H042-008-000 | PUNCHED WASHER TYPE A - M8 (OD=17, ID=9, T=1.6) - IS 2016 -1967 | NOS | 135 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 08-03-2021 |  | 3
34 | 3 | H042-010-000 | PUNCHED WASHER TYPE A - M10 (OD=21, ID=11, T=2) - IS 2016 -1967 | NOS | 16 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 09-03-2021 |  | 3
35 | 3 | H044-024-002 | SPRING WASHER - M24 (OD=35.9, ID=24.5, T=5) - IS 3063 - 1972 | NOS | 10 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 09-03-2021 |  | 3
36 | 3 | H044-014-005 | SPRING WASHER - M14 (OD=24, ID=14 T=2) - IS 3063 - 1972 | NOS | 10 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 08-03-2021 |  | 3
37 | 3 | H044-006-000 | SPRING WASHER - M6 (OD=9.9, ID=6.1, T=1.6) - IS 3063 - 1972 | NOS | 20 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 08-03-2021 |  | 3
38 | 3 | H044-008-000 | SPRING WASHER - M8 (OD=12.7, ID=8.1, T=2) - IS 3063 - 1972 | NOS | 135 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 08-03-2021 |  | 3
39 | 3 | H044-010-000 | SPRING WASHER - M10 (OD=16, ID=10.2, T=2.5) - IS 3063 - 1972 | NOS | 16 | 03-03-2021 | 07-03-2021 | 09-03-2021 | J0139 | 3 | 08-03-2021 |  | 3
40 | 13 | E100-181-015 | Type:-Gas Spring ,Type of Gas Spring:-Mounting Direction Fixed Type ,Stroke:-100MM, Min Length:-181 ,Cylinder Dia(Ø):-15, Part number:- GS142 | NOS | 2 | 13-03-2021 | 13-03-2021 | 14-03-2021 | J0141 | 7 | 16-03-2021 |  | 4
95 | 12 | Z005-006-055 | Cross Rail (63)- 5.6Mtr | NOS | 1 | 13-03-2021 | 13-03-2021 | Planned | N0235 | 15 | 31-03-2021 |  | 11
96 | 12 | C900-000-004 | WIRE ROPE - DIA 4 | MTR | 10 | 13-03-2021 | 13-03-2021 | Available | N0235 | 15 | 31-03-2021 |  | 11
97 | 20 | B001-015-032 | Ball Bearing - 6002 Zz - 15 x 32 x 9 - SKF | NOS | 16 | 22-03-2021 | 21-03-2021 | 21-03-2021 | N0231 | 19 | 21-03-2021 |  | 12
52 | 7 | Z001-150-500 | Castor Wheels Ø150x50 Without brake | NOS | 4 | 04-03-2021 | 10-03-2021 | 17-03-2021 | N0231 | 9 | 22-03-2021 |  | 8
53 | 5 | H035-025-025 | SPLIT PIN - DIA 2.5X25-ISO 549 | NOS | 104 | 04-03-2021 | 06-03-2021 | 06-03-2021 | N0231 | 11 | 08-03-2021 |  | 9
54 | 5 | H035-004-040 | SPLIT PIN - DIA 4X40 -ISO 549 | NOS | 26 | 04-03-2021 | 06-03-2021 | 06-03-2021 | N0231 | 11 | 08-03-2021 |  | 9
55 | 13 | B021-012-010 | PAP BUSH - 1210 - P10 - ID 12 x OD 14 x 10L | NOS | 4 | 13-03-2021 | 14-03-2021 | 19-03-2021 | J0141 | 12 | 22-03-2021 |  | 10
56 | 13 | E100-181-015 | Type:-Gas Spring ,Type of Gas Spring:-Mounting Direction Fixed Type ,Stroke:-100MM, Min Length:-181 ,Cylinder Dia(Ø):-15, Part number:- GS142 | NOS | 2 | 13-03-2021 | 13-03-2021 | 19-03-2021 | J0141 | 12 | 22-03-2021 |  | 10

## tblPM_Project_Hardware_As_m
Id | SysDate | SysTime | CompId | SessionId | FinYearId | PRJCTNO | WONo | GenDate | VendorPlan | VendorDate | AssemlyDate | AssemlyNo
1 | [8 empty] | 1 |  |  | 1
2 | 2021-03-17 | 12:10:32 PM | 1 | sapl0326 | 8 | 11 | J0142 | 17/03/2021 | 8 | 13/03/2021 | 17/03/2021 | 2
3 | 2021-03-17 | 12:16:35 PM | 1 | sapl0326 | 8 | 3 | J0139 | 17/03/2021 | 3 | 04/03/2021 | 17/03/2021 | 3
4 | 2021-03-17 | 2:34:34 PM | 1 | sapl0326 | 8 | 13 | J0141 | 17/03/2021 | 7 | 13/03/2021 | 17/03/2021 | 4
5 | 2021-03-23 | 3:58:14 PM | 1 | sapl0326 | 8 | 20 | N0231 | 23/03/2021 | 19 | 22/03/2021 | 23/03/2021 | 5
6 | 2021-03-31 | 1:35:07 PM | 1 | sapl0326 | 8 | 17 | N0235 | 31/03/2021 | 18 | 17/03/2021 | 31/03/2021 | 6
7 | 2021-03-31 | 1:36:31 PM | 1 | sapl0326 | 8 | 14 | J0142 | 31/03/2021 | 6 | 13/03/2021 | 31/03/2021 | 7
12 | 2021-03-31 | 1:45:20 PM | 1 | sapl0326 | 8 | 20 | N0231 | 31/03/2021 | 19 | 22/03/2021 | 31/03/2021 | 12
8 | 2021-03-31 | 1:37:11 PM | 1 | sapl0326 | 8 | 7 | N0231 | 31/03/2021 | 9 | 06/03/2021 | 31/03/2021 | 8
9 | 2021-03-31 | 1:37:38 PM | 1 | sapl0326 | 8 | 5 | N0231 | 31/03/2021 | 11 | 04/03/2021 | 31/03/2021 | 9
10 | 2021-03-31 | 1:38:24 PM | 1 | sapl0326 | 8 | 13 | J0141 | 31/03/2021 | 12 | 13/03/2021 | 31/03/2021 | 10
11 | 2021-03-31 | 1:44:10 PM | 1 | sapl0326 | 8 | 12 | N0235 | 31/03/2021 | 15 | 13/03/2021 | 31/03/2021 | 11

## tblPM_Project_Hardware_Master_D
Id | PRJCTNO | ItemCode | Description | UOM | BOMQ | Rdesign | Design | WONo | Remark | Vendor1 | Vendor2
3 | 2 | Z157-001-000 | Drill Bit-RL 10, Kennametal Part No. 1010785 | NOS | 48 | 1 | 05-02-2021 | P0061
4 | 3 | B032-000-010 | TAPER ROLLER BEARING 32010 X - 50X80X20 - SKF | NOS | 2 | 1 | 23-02-2021 | J0139
5 | 3 | H045-022-200 | CHEMICAL ANCHORE FASTNER -22X200 | NOS | 10 | 1 | 03-03-2021 | J0139
6 | 3 | H045-120-200 | CHEMICAL ANCHORE FASTNER -20X200 | NOS | 5 | 1 | 03-03-2021 | J0139
7 | 3 | H023-022-250 | HEX NUT- IS 1364 - M22X2.5 - GRADE-10 | NOS | 10 | 1 | 03-03-2021 | J0139
8 | 3 | H023-024-300 | HEX NUT- IS 1364 - M24X3 - GRADE-10 | NOS | 10 | 1 | 03-03-2021 | J0139
9 | 3 | H023-008-125 | HEX NUT- IS 1364 - M8X1.25 - GRADE-8 | NOS | 115 | 1 | 03-03-2021 | J0139
10 | 3 | H023-020-150 | HEX NUT- IS 1364 - M20X1.5 - GRADE-10 | NOS | 5 | 1 | 03-03-2021 | J0139
11 | 3 | H004-024-080 | HEX BOLT - IS 1364 - GRADE 10.9 - M24X80 | NOS | 10 | 1 | 03-03-2021 | J0139
12 | 3 | H004-014-050 | HEX BOLT - IS 1364 - GRADE 10.9 - M14X50 | NOS | 10 | 1 | 03-03-2021 | J0139
13 | 3 | H001-006-010 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M6X10 | NOS | 20 | 1 | 03-03-2021 | J0139
14 | 3 | H001-008-040 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M8X40 | NOS | 12 | 1 | 03-03-2021 | J0139
15 | 3 | H001-010-020 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M10X20 | NOS | 16 | 1 | 03-03-2021 | J0139
16 | 3 | H001-008-030 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M8X30 | NOS | 65 | 1 | 03-03-2021 | J0139
17 | 3 | H001-008-016 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M8X16 | NOS | 55 | 1 | 03-03-2021 | J0139
18 | 3 | H002-006-025 | CSK ALLEN SCREW - IS 6761 - GRADE 12.9 -M6X25 | NOS | 6 | 1 | 03-03-2021 | J0139
19 | 3 | H008-004-012 | ALLEN GRUB SCREW - IS 6094 - M4X12 | NOS | 30 | 1 | 03-03-2021 | J0139
20 | 3 | H006-020-030 | EYE BOLT MILD STEEL FORGED IS:4190 - M20X30L,EYE HOLE - 40MM SWL -570 KG | NOS | 2 | 1 | 03-03-2021 | J0139
21 | 3 | Z015-492-100 | MAGNET 20X10 MM | NOS | 14 | 1 | 03-03-2021 | J0139
22 | 3 | C900-006-000 | WIRE ROPE U CLAMPS WITH NUT FOR Ø6 WIRE ROPE | NOS | 12 | 1 | 03-03-2021 | J0139
23 | 3 | H061-010-050 | Lock Washer MB10 - ID50 - SKF | NOS | 1 | 1 | 03-03-2021 | J0139
24 | 3 | H060-010-150 | Lock Nut - KM 10 - M50 x 1.5 - SKF | NOS | 2 | 1 | 03-03-2021 | J0139
25 | 3 | K007-007-007 | PLASTIC HANDLES | NOS | 4 | 1 | 03-03-2021 | J0139
26 | 3 | K002-002-002 | TURN BUCKLES | NOS | 2 | 1 | 03-03-2021 | J0139
27 | 3 | K004-005-005 | HINGE | NOS | 6 | 1 | 03-03-2021 | J0139
28 | 3 | B008-210-000 | SQUARE FLANGE BEARING UCF 210 D1,NTN MAKE | NOS | 2 | 1 | 03-03-2021 | J0139
29 | 3 | B001-010-026 | Ball Bearing - 6000 Zz - 10 x 26 x 8 - SKF | NOS | 4 | 1 | 03-03-2021 | J0139
30 | 3 | C900-000-006 | WIRE ROPE - DIA 6 | MTR | 5 | 1 | 03-03-2021 | J0139
31 | 3 | H042-002-022 | PUNCHED WASHER TYPE A - M22 | NOS | 10 | 1 | 03-03-2021 | J0139
32 | 3 | H042-020-000 | PUNCHED WASHER TYPE A - M20 (OD=37, ID=22, T=3.15) - IS 2016 -1967 | NOS | 5 | 1 | 03-03-2021 | J0139
33 | 3 | H042-024-000 | PUNCHED WASHER TYPE A - M24 (OD=44, ID=26, T=4) - IS 2016 -1967 | NOS | 10 | 1 | 03-03-2021 | J0139
34 | 3 | H042-014-000 | PUNCHED WASHER TYPE A - M14 (OD=28, ID=15.5, T=2.8) - IS 2016 -1967 | NOS | 10 | 1 | 03-03-2021 | J0139
35 | 3 | H042-006-000 | PUNCHED WASHER TYPE A - M6 (OD=12.5, ID=6.6, T=1.6) - IS 2016 -1967 | NOS | 20 | 1 | 03-03-2021 | J0139
36 | 3 | H042-008-000 | PUNCHED WASHER TYPE A - M8 (OD=17, ID=9, T=1.6) - IS 2016 -1967 | NOS | 135 | 1 | 03-03-2021 | J0139
37 | 3 | H042-010-000 | PUNCHED WASHER TYPE A - M10 (OD=21, ID=11, T=2) - IS 2016 -1967 | NOS | 16 | 1 | 03-03-2021 | J0139
38 | 3 | H044-024-002 | SPRING WASHER - M24 (OD=35.9, ID=24.5, T=5) - IS 3063 - 1972 | NOS | 10 | 1 | 03-03-2021 | J0139
39 | 3 | H044-014-005 | SPRING WASHER - M14 (OD=24, ID=14 T=2) - IS 3063 - 1972 | NOS | 10 | 1 | 03-03-2021 | J0139
40 | 3 | H044-006-000 | SPRING WASHER - M6 (OD=9.9, ID=6.1, T=1.6) - IS 3063 - 1972 | NOS | 20 | 1 | 03-03-2021 | J0139
41 | 3 | H044-008-000 | SPRING WASHER - M8 (OD=12.7, ID=8.1, T=2) - IS 3063 - 1972 | NOS | 135 | 1 | 03-03-2021 | J0139
42 | 3 | H044-010-000 | SPRING WASHER - M10 (OD=16, ID=10.2, T=2.5) - IS 3063 - 1972 | NOS | 16 | 1 | 03-03-2021 | J0139
43 | 4 | B001-015-032 | Ball Bearing - 6002 Zz - 15 x 32 x 9 - SKF | NOS | 4 | 1 | 04-03-2021 | N0231
44 | 4 | Z001-150-500 | Castor Wheels Ø150x50 Without brake | NOS | 4 | 1 | 04-03-2021 | N0231
45 | 4 | Z001-150-050 | Castor Wheels Ø150x50 With brake | NOS | 4 | 1 | 04-03-2021 | N0231
46 | 5 | H035-025-025 | SPLIT PIN - DIA 2.5X25-ISO 549 | NOS | 104 | 1 | 04-03-2021 | N0231
47 | 5 | H035-004-040 | SPLIT PIN - DIA 4X40 -ISO 549 | NOS | 26 | 1 | 04-03-2021 | N0231
48 | 6 | H035-025-025 | SPLIT PIN - DIA 2.5X25-ISO 549 | NOS | 104 | 1 | 04-03-2021 | N0231
49 | 6 | H035-004-040 | SPLIT PIN - DIA 4X40 -ISO 549 | NOS | 26 | 1 | 04-03-2021 | N0231
52 | 8 | H004-008-045 | HEX BOLT - IS 1364 - GRADE 10.9 - M8X45 | NOS | 0 | 1 | 05-03-2021 | N0231
53 | 8 | H001-008-020 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M8X20 | NOS | 40 | 1 | 05-03-2021 | N0231
54 | 8 | H001-008-025 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M8X25 | NOS | 32 | 1 | 05-03-2021 | N0231
55 | 8 | H001-008-035 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M8X35 | NOS | 20 | 1 | 05-03-2021 | N0231
56 | 8 | H002-004-020 | CSK ALLEN SCREW - IS 6761 - GRADE 12.9 -M4X20 | NOS | 56 | 1 | 05-03-2021 | N0231
57 | 8 | H023-012-175 | HEX NUT- IS 1364 - M12X1.75 - GRADE-10 | NOS | 8 | 1 | 05-03-2021 | N0231
58 | 8 | H004-008-040 | HEX BOLT - IS 1364 - GRADE 10.9 - M8X40 | NOS | 80 | 1 | 05-03-2021 | N0231
59 | 8 | H004-008-045 | HEX BOLT - IS 1364 - GRADE 10.9 - M8X45 | NOS | 160 | 1 | 05-03-2021 | N0231
60 | 8 | H039-108-025 | DOWEL PIN WITH INTERNAL THREAD - DIA 8 M6 X 25 IS 3524 - 1966 | NOS | 8 | 1 | 05-03-2021 | N0231
61 | 8 | H039-108-040 | DOWEL PIN WITH INTERNAL THREAD - DIA 8 M6 X 40 IS 3524 - 1966 | NOS | 40 | 1 | 05-03-2021 | N0231
62 | 8 | H039-108-045 | DOWEL PIN WITH INTERNAL THREAD - DIA 8 M6 X 45 IS 3524 - 1966 | NOS | 80 | 1 | 05-03-2021 | N0231
63 | 8 | H042-008-000 | PUNCHED WASHER TYPE A - M8 (OD=17, ID=9, T=1.6) - IS 2016 -1967 | NOS | 288 | 1 | 05-03-2021 | N0231
64 | 8 | B001-015-032 | Ball Bearing - 6002 Zz - 15 x 32 x 9 - SKF | NOS | 4 | 1 | 05-03-2021 | N0231
65 | 8 | H004-008-025 | HEX BOLT - IS 1364 - GRADE 10.9 - M8X25 | NOS | 16 | 1 | 05-03-2021 | N0231
66 | 8 | H042-012-001 | PUNCHED WASHER TYPE A - M12 (OD=30, ID=14, T=3) - IS 2016 -1967 | NOS | 8 | 1 | 05-03-2021 | N0231
67 | 9 | H023-008-125 | HEX NUT- IS 1364 - M8X1.25 - GRADE-8 | NOS | 16 | 1 | 09-03-2021 | N0231
68 | 9 | H004-006-020 | HEX BOLT - IS 1364 - GRADE 10.9 - M6X20 | NOS | 232 | 1 | 09-03-2021 | N0231
69 | 9 | H004-008-050 | HEX BOLT - IS 1364 - GRADE 10.9 - M8X50 | NOS | 16 | 1 | 09-03-2021 | N0231
70 | 9 | H004-010-065 | HEX BOLT - IS 1364 - GRADE 10.9 - M10X65 | NOS | 58 | 1 | 09-03-2021 | N0231
71 | 9 | H042-008-000 | PUNCHED WASHER TYPE A - M8 (OD=17, ID=9, T=1.6) - IS 2016 -1967 | NOS | 32 | 1 | 09-03-2021 | N0231
50 | 7 | Z001-150-050 | Castor Wheels Ø150x50 With brake | NOS | 4 | 1 | 04-03-2021 | N0231
51 | 7 | Z001-150-500 | Castor Wheels Ø150x50 Without brake | NOS | 4 | 1 | 04-03-2021 | N0231
72 | 9 | H042-010-000 | PUNCHED WASHER TYPE A - M10 (OD=21, ID=11, T=2) - IS 2016 -1967 | NOS | 58 | 1 | 09-03-2021 | N0231
73 | 9 | H042-006-000 | PUNCHED WASHER TYPE A - M6 (OD=12.5, ID=6.6, T=1.6) - IS 2016 -1967 | NOS | 232 | 1 | 09-03-2021 | N0231
76 | 12 | C900-000-004 | WIRE ROPE - DIA 4 | MTR | 10 | 1 | 13-03-2021 | N0235
77 | 12 | C900-000-006 | WIRE ROPE - DIA 6 | MTR | 48 | 1 | 13-03-2021 | N0235
78 | 12 | C920-000-004 | Wire Rope U CLAMP - M4 | NOS | 32 | 1 | 13-03-2021 | N0235
79 | 12 | C920-000-006 | Wire Rope U CLAMP - M6 | NOS | 96 | 1 | 13-03-2021 | N0235
80 | 12 | H002-012-060 | CSK ALLEN SCREW - IS 6761 - GRADE 12.9 -M12X60 | NOS | 48 | 1 | 13-03-2021 | N0235
81 | 12 | H023-008-125 | HEX NUT- IS 1364 - M8X1.25 - GRADE-8 | NOS | 224 | 1 | 13-03-2021 | N0235
82 | 12 | H023-012-175 | HEX NUT- IS 1364 - M12X1.75 - GRADE-10 | NOS | 96 | 1 | 13-03-2021 | N0235
83 | 12 | H024-010-000 | NYLOCK NUT- M10 | NOS | 22 | 1 | 13-03-2021 | N0235
84 | 12 | H004-008-035 | HEX BOLT - IS 1364 - GRADE 10.9 - M8X35 | NOS | 32 | 1 | 13-03-2021 | N0235
85 | 12 | H025-008-000 | WELD HEX NUT - M8 | NOS | 192 | 1 | 13-03-2021 | N0235
86 | 12 | H004-012-035 | HEX BOLT - IS 1364 - GRADE 10.9 - M12X35 | NOS | 46 | 1 | 13-03-2021 | N0235
87 | 12 | H004-010-100 | HEX BOLT - IS 1364 - GRADE 10.9 - M10X100 | NOS | 22 | 1 | 13-03-2021 | N0235
88 | 12 | H042-010-000 | PUNCHED WASHER TYPE A - M10 (OD=21, ID=11, T=2) - IS 2016 -1967 | NOS | 44 | 1 | 13-03-2021 | N0235
89 | 12 | H042-012-000 | PUNCHED WASHER TYPE A - M12 (OD=24, ID=14, T=2.5) - IS 2016 -1967 | NOS | 192 | 1 | 13-03-2021 | N0235
90 | 12 | H044-012-000 | SPRING WASHER - M12 (OD=18, ID=12.2, T=2.5) - IS 3063 - 1972 | NOS | 192 | 1 | 13-03-2021 | N0235
91 | 12 | H024-012-000 | NYLOCK NUT - M12 | NOS | 46 | 1 | 13-03-2021 | N0235
92 | 12 | H004-008-025 | HEX BOLT - IS 1364 - GRADE 10.9 - M8X25 | NOS | 224 | 1 | 13-03-2021 | N0235
93 | 12 | H004-112-070 | HEX BOLT-IS 1364-GRADE 10.9 - M12X70 (FULL THREAD) | NOS | 96 | 1 | 13-03-2021 | N0235
94 | 12 | B101-025-052 | BALL BEARING - 6205 ZZ - 25 X 52 X 15 - KGN MAKE | NOS | 124 | 1 | 13-03-2021 | N0235
95 | 12 | K000-001-003 | Stopper M6-Rubber | NOS | 32 | 1 | 13-03-2021 | N0235
96 | 12 | K000-001-004 | Pin Bearing - Dia25x50-MS | NOS | 46 | 1 | 13-03-2021 | N0235
97 | 12 | K000-001-005 | Spacer Bearing ID25, OD32, Th5 | NOS | 92 | 1 | 13-03-2021 | N0235
98 | 12 | K000-001-008 | Retainer Pin | NOS | 23 | 1 | 13-03-2021 | N0235
99 | 12 | K000-001-011 | Shoulder Washer | NOS | 64 | 1 | 13-03-2021 | N0235
100 | 12 | K000-001-015 | Z-PLATE CROSS TROLLEY BLUE ZINC PLATED Dia-17 | NOS | 46 | 1 | 13-03-2021 | N0235
101 | 12 | K000-001-016 | PIN Dia -16 | NOS | 23 | 1 | 13-03-2021 | N0235
102 | 12 | K005-001-001 | Weldment Cross Trolley | NOS | 16 | 1 | 13-03-2021 | N0235
103 | 12 | K005-001-003 | Weldment Cross Rail Support | NOS | 16 | 1 | 13-03-2021 | N0235
104 | 12 | K005-002-001 | Weldment Plate Load Trolley | NOS | 7 | 1 | 13-03-2021 | N0235
105 | 12 | K005-003-001 | Weldment Channel Support C-75 100L | NOS | 16 | 1 | 13-03-2021 | N0235
106 | 12 | K005-004-001 | Weldment Joint Coupler | NOS | 48 | 1 | 13-03-2021 | N0235
107 | 12 | K000-000-006 | Square Nut M12 | NOS | 144 | 1 | 13-03-2021 | N0235
108 | 12 | K000-000-007 | Clamp Beam | NOS | 96 | 1 | 13-03-2021 | N0235
109 | 12 | K005-006-001 | Beam Support | NOS | 48 | 1 | 13-03-2021 | N0235
110 | 12 | K005-007-001 | RUBBER PAD FOR C63 | NOS | 22 | 1 | 13-03-2021 | N0235
111 | 12 | Z063-063-005 | LONG RAIL 63 - 6MTR | NOS | 20 | 1 | 13-03-2021 | N0235
112 | 12 | Z121-222-500 | Hoist 500KG | NOS | 7 | 1 | 13-03-2021 | N0235
113 | 12 | Z004-005-025 | Cross Rail (63)- 2.5Mtr | NOS | 6 | 1 | 13-03-2021 | N0235
114 | 12 | Z005-006-055 | Cross Rail (63)- 5.6Mtr | NOS | 1 | 1 | 13-03-2021 | N0235
115 | 13 | B021-012-010 | PAP BUSH - 1210 - P10 - ID 12 x OD 14 x 10L | NOS | 4 | 1 | 13-03-2021 | J0141
116 | 13 | E100-181-015 | Type:-Gas Spring ,Type of Gas Spring:-Mounting Direction Fixed Type ,Stroke:-100MM, Min Length:-181 ,Cylinder Dia(Ø):-15, Part number:- GS142 | NOS | 2 | 1 | 13-03-2021 | J0141
118 | 15 | H001-010-085 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M10X85 | NOS | 15 | 1 | 15-03-2021 | J0141
119 | 15 | H023-008-125 | HEX NUT- IS 1364 - M8X1.25 - GRADE-8 | NOS | 10 | 1 | 15-03-2021 | J0141
120 | 15 | H023-010-150 | HEX NUT- IS 1364 - M10X1.5 - GRADE-10 | NOS | 10 | 1 | 15-03-2021 | J0141
121 | 15 | H023-012-175 | HEX NUT- IS 1364 - M12X1.75 - GRADE-10 | NOS | 5 | 1 | 15-03-2021 | J0141
122 | 15 | H004-008-020 | HEX BOLT - IS 1364 - GRADE 10.9 - M8X20 | NOS | 5 | 1 | 15-03-2021 | J0141
123 | 15 | H004-008-060 | HEX BOLT - IS 1364 - GRADE 10.9 - M8X60 | NOS | 5 | 1 | 15-03-2021 | J0141
124 | 15 | H004-012-070 | HEX BOLT - IS 1364 - GRADE 10.9 - M12X70 | NOS | 5 | 1 | 15-03-2021 | J0141
125 | 15 | H042-008-000 | PUNCHED WASHER TYPE A - M8 (OD=17, ID=9, T=1.6) - IS 2016 -1967 | NOS | 10 | 1 | 15-03-2021 | J0141
126 | 15 | H042-010-000 | PUNCHED WASHER TYPE A - M10 (OD=21, ID=11, T=2) - IS 2016 -1967 | NOS | 15 | 1 | 15-03-2021 | J0141
127 | 15 | H042-012-000 | PUNCHED WASHER TYPE A - M12 (OD=24, ID=14, T=2.5) - IS 2016 -1967 | NOS | 5 | 1 | 15-03-2021 | J0141
128 | 15 | H044-008-000 | SPRING WASHER - M8 (OD=12.7, ID=8.1, T=2) - IS 3063 - 1972 | NOS | 10 | 1 | 15-03-2021 | J0141
129 | 15 | H044-010-000 | SPRING WASHER - M10 (OD=16, ID=10.2, T=2.5) - IS 3063 - 1972 | NOS | 15 | 1 | 15-03-2021 | J0141
130 | 15 | H044-012-000 | SPRING WASHER - M12 (OD=18, ID=12.2, T=2.5) - IS 3063 - 1972 | NOS | 5 | 1 | 15-03-2021 | J0141
131 | 16 | H001-010-085 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M10X85 | NOS | 15 | 1 | 15-03-2021 | J0142
132 | 16 | H023-008-125 | HEX NUT- IS 1364 - M8X1.25 - GRADE-8 | NOS | 10 | 1 | 15-03-2021 | J0142
133 | 16 | H023-010-150 | HEX NUT- IS 1364 - M10X1.5 - GRADE-10 | NOS | 10 | 1 | 15-03-2021 | J0142
134 | 16 | H023-012-175 | HEX NUT- IS 1364 - M12X1.75 - GRADE-10 | NOS | 5 | 1 | 15-03-2021 | J0142
135 | 16 | H004-008-020 | HEX BOLT - IS 1364 - GRADE 10.9 - M8X20 | NOS | 5 | 1 | 15-03-2021 | J0142
136 | 16 | H004-008-060 | HEX BOLT - IS 1364 - GRADE 10.9 - M8X60 | NOS | 5 | 1 | 15-03-2021 | J0142
137 | 16 | H004-012-070 | HEX BOLT - IS 1364 - GRADE 10.9 - M12X70 | NOS | 5 | 1 | 15-03-2021 | J0142
138 | 16 | H042-008-000 | PUNCHED WASHER TYPE A - M8 (OD=17, ID=9, T=1.6) - IS 2016 -1967 | NOS | 10 | 1 | 15-03-2021 | J0142
139 | 16 | H042-010-000 | PUNCHED WASHER TYPE A - M10 (OD=21, ID=11, T=2) - IS 2016 -1967 | NOS | 15 | 1 | 15-03-2021 | J0142
140 | 16 | H042-012-000 | PUNCHED WASHER TYPE A - M12 (OD=24, ID=14, T=2.5) - IS 2016 -1967 | NOS | 5 | 1 | 15-03-2021 | J0142
141 | 16 | H044-008-000 | SPRING WASHER - M8 (OD=12.7, ID=8.1, T=2) - IS 3063 - 1972 | NOS | 10 | 1 | 15-03-2021 | J0142
142 | 16 | H044-010-000 | SPRING WASHER - M10 (OD=16, ID=10.2, T=2.5) - IS 3063 - 1972 | NOS | 15 | 1 | 15-03-2021 | J0142
74 | 10 | H004-008-055 | HEX BOLT - IS 1364 - GRADE 10.9 - M8X55 | NOS | 72 | 1 | 09-03-2021 | N0231
75 | 11 | E100-181-015 | Type:-Gas Spring ,Type of Gas Spring:-Mounting Direction Fixed Type ,Stroke:-100MM, Min Length:-181 ,Cylinder Dia(Ø):-15, Part number:- GS142 | NOS | 2 | 1 | 13-03-2021 | J0142
117 | 14 | B021-012-010 | PAP BUSH - 1210 - P10 - ID 12 x OD 14 x 10L | NOS | 4 | 1 | 13-03-2021 | J0142
144 | 17 | H004-012-050 | HEX BOLT - IS 1364 - GRADE 10.9 - M12X50 | NOS | 128 | 1 | 17-03-2021 | N0235
145 | 17 | H004-020-080 | HEX BOLT - IS 1364 - GRADE 10.9 - M20X80 | NOS | 48 | 1 | 17-03-2021 | N0235
146 | 17 | H004-020-150 | HEX BOLT - IS 1364 - GRADE 10.9 - M20X150 | NOS | 48 | 1 | 17-03-2021 | N0235
147 | 17 | H042-012-000 | PUNCHED WASHER TYPE A - M12 (OD=24, ID=14, T=2.5) - IS 2016 -1967 | NOS | 128 | 1 | 17-03-2021 | N0235
148 | 17 | H042-020-000 | PUNCHED WASHER TYPE A - M20 (OD=37, ID=22, T=3.15) - IS 2016 -1967 | NOS | 100 | 1 | 17-03-2021 | N0235
149 | 17 | H044-012-000 | SPRING WASHER - M12 (OD=18, ID=12.2, T=2.5) - IS 3063 - 1972 | NOS | 128 | 1 | 17-03-2021 | N0235
150 | 17 | H044-020-000 | SPRING WASHER - M20 (OD=30.6, ID=20.2, T=4.5) - IS 3063 - 1972 | NOS | 100 | 1 | 17-03-2021 | N0235
151 | 17 | H023-020-150 | HEX NUT- IS 1364 - M20X1.5 - GRADE-10 | NOS | 150 | 1 | 17-03-2021 | N0235
152 | 17 | H450-220-150 | ANCHORE FASTNER -22X150 | NOS | 72 | 1 | 17-03-2021 | N0235
153 | 18 | H100-030-000 | Student Exam Clip Board 100mmX30mm Metal Wire clip | NOS | 2 | 1 | 18-03-2021 | J0141
154 | 19 | H100-030-000 | Student Exam Clip Board 100mmX30mm Metal Wire clip | NOS | 2 | 1 | 18-03-2021 | J0142
155 | 20 | H004-008-020 | HEX BOLT - IS 1364 - GRADE 10.9 - M8X20 | NOS | 16 | 1 | 22-03-2021 | N0231
156 | 20 | H004-010-060 | HEX BOLT - IS 1364 - GRADE 10.9 - M10X60 | NOS | 32 | 1 | 22-03-2021 | N0231
157 | 20 | B001-015-032 | Ball Bearing - 6002 Zz - 15 x 32 x 9 - SKF | NOS | 16 | 1 | 22-03-2021 | N0231
159 | 22 | H001-006-030 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M6X30 | NOS | 26 | 1 | 24-03-2021 | N0236
160 | 22 | H001-012-035 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M12X35 | NOS | 192 | 1 | 24-03-2021 | N0236
161 | 22 | H001-016-035 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M16X35 | NOS | 312 | 1 | 24-03-2021 | N0236
162 | 22 | H001-020-070 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M20X70 | NOS | 104 | 1 | 24-03-2021 | N0236
163 | 22 | H002-006-035 | CSK ALLEN SCREW - IS 6761 - GRADE 12.9 -M6X35 | NOS | 52 | 1 | 24-03-2021 | N0236
164 | 22 | H039-106-020 | DOWEL PIN WITH INTERNAL THREAD - DIA 6 M4 X 20 IS 3524 - 1966 | NOS | 104 | 1 | 24-03-2021 | N0236
165 | 22 | H039-106-030 | DOWEL PIN WITH INTERNAL THREAD - DIA 6 M4 X 30 IS 3524 - 1966 | NOS | 208 | 1 | 24-03-2021 | N0236
166 | 22 | H039-106-035 | DOWEL PIN WITH INTERNAL THREAD - DIA 6 M4 X 35 IS 3524 - 1966 | NOS | 52 | 1 | 24-03-2021 | N0236
167 | 22 | H039-110-030 | DOWEL PIN WITH INTERNAL THREAD - DIA 10 M6 X 30 IS 3524 - 1966 | NOS | 96 | 1 | 24-03-2021 | N0236
168 | 22 | H039-112-035 | DOWEL PIN WITH INTERNAL THREAD - DIA 12 M6 X 35 IS 3524 - 1966 | NOS | 52 | 1 | 24-03-2021 | N0236
169 | 22 | H042-016-000 | PUNCHED WASHER TYPE A - M16 (OD=30, ID=18, T=3.15) - IS 2016 -1967 | NOS | 312 | 1 | 24-03-2021 | N0236
170 | 22 | H042-006-000 | PUNCHED WASHER TYPE A - M6 (OD=12.5, ID=6.6, T=1.6) - IS 2016 -1967 | NOS | 208 | 1 | 24-03-2021 | N0236
171 | 22 | H023-020-150 | HEX NUT- IS 1364 - M20X1.5 - GRADE-10 | NOS | 104 | 1 | 24-03-2021 | N0236
172 | 22 | H042-012-001 | PUNCHED WASHER TYPE A - M12 (OD=30, ID=14, T=3) - IS 2016 -1967 | NOS | 192 | 1 | 24-03-2021 | N0236
173 | 22 | H001-006-015 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M6X15 | NOS | 182 | 1 | 24-03-2021 | N0236
174 | 22 | H002-006-015 | CSK ALLEN SCREW - IS 6761 - GRADE 12.9 -M6X15 | NOS | 104 | 1 | 24-03-2021 | N0236
175 | 22 | H045-200-200 | CHEMICAL ANCHORE BOLT M20X200 | NOS | 52 | 1 | 24-03-2021 | N0236
183 | 24 | B009-212-000 | PILLOW BLOCK -UCP 212 D-NTN | NOS | 2 | 1 | 02-04-2021 | N0237
184 | 24 | B827-032-042 | LM BUSH - LM 20UU-ID20XOD32X42L | NOS | 4 | 1 | 02-04-2021 | N0237
185 | 25 | J013-003-540 | TOGGLE CLAMP - STRAIGHT LINE - HTC - 3540 PS/BS - STEEL SMITH MAKE | NOS | 1 | 1 | 03-04-2021 | N0237
227 | 26 | H001-012-035 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M12X35 | NOS | 357 | 1 | 31-05-2021 | N0233
228 | 26 | H044-012-000 | SPRING WASHER - M12 (OD=18, ID=12.2, T=2.5) - IS 3063 - 1972 | NOS | 377 | 1 | 31-05-2021 | N0233
229 | 26 | H042-012-001 | PUNCHED WASHER TYPE A - M12 (OD=30, ID=14, T=3) - IS 2016 -1967 | NOS | 373 | 1 | 31-05-2021 | N0233
230 | 27 | Z150-120-600 | SWIVEL TYPE WHEEL WITH BRAKE-UHM-150 DIA -MOUNTING PLATE CD-120X60,PIONEER MAKE | NOS | 88 | 1 | 31-05-2021 | N0233
231 | 28 | H001-008-025 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M8X25 | NOS | 1035 | 1 | 25-07-2021 | N0233
232 | 28 | H001-008-025 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M8X25 | NOS | 1035 | 1 | 25-07-2021 | N0233
233 | 28 | H001-010-020 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M10X20 | NOS | 360 | 1 | 25-07-2021 | N0233
234 | 28 | H001-008-025 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M8X25 | NOS | 1035 | 1 | 25-07-2021 | N0233
235 | 28 | H001-010-020 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M10X20 | NOS | 360 | 1 | 25-07-2021 | N0233
236 | 28 | H044-008-000 | SPRING WASHER - M8 (OD=12.7, ID=8.1, T=2) - IS 3063 - 1972 | NOS | 2119 | 1 | 25-07-2021 | N0233
237 | 28 | H001-008-025 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M8X25 | NOS | 1035 | 1 | 25-07-2021 | N0233
238 | 28 | H001-010-020 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M10X20 | NOS | 360 | 1 | 25-07-2021 | N0233
239 | 28 | H044-008-000 | SPRING WASHER - M8 (OD=12.7, ID=8.1, T=2) - IS 3063 - 1972 | NOS | 2119 | 1 | 25-07-2021 | N0233
240 | 28 | H044-010-000 | SPRING WASHER - M10 (OD=16, ID=10.2, T=2.5) - IS 3063 - 1972 | NOS | 360 | 1 | 25-07-2021 | N0233
241 | 28 | H001-008-025 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M8X25 | NOS | 1035 | 1 | 25-07-2021 | N0233
242 | 28 | H001-010-020 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M10X20 | NOS | 360 | 1 | 25-07-2021 | N0233
243 | 28 | H042-008-000 | PUNCHED WASHER TYPE A - M8 (OD=17, ID=9, T=1.6) - IS 2016 -1967 | NOS | 2103 | 1 | 25-07-2021 | N0233
244 | 28 | H044-008-000 | SPRING WASHER - M8 (OD=12.7, ID=8.1, T=2) - IS 3063 - 1972 | NOS | 2119 | 1 | 25-07-2021 | N0233
245 | 28 | H044-010-000 | SPRING WASHER - M10 (OD=16, ID=10.2, T=2.5) - IS 3063 - 1972 | NOS | 360 | 1 | 25-07-2021 | N0233
246 | 28 | H001-008-025 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M8X25 | NOS | 1035 | 1 | 25-07-2021 | N0233
247 | 28 | H001-010-020 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M10X20 | NOS | 360 | 1 | 25-07-2021 | N0233
248 | 28 | H042-008-000 | PUNCHED WASHER TYPE A - M8 (OD=17, ID=9, T=1.6) - IS 2016 -1967 | NOS | 2103 | 1 | 25-07-2021 | N0233
249 | 28 | H042-010-000 | PUNCHED WASHER TYPE A - M10 (OD=21, ID=11, T=2) - IS 2016 -1967 | NOS | 360 | 1 | 25-07-2021 | N0233
250 | 28 | H044-008-000 | SPRING WASHER - M8 (OD=12.7, ID=8.1, T=2) - IS 3063 - 1972 | NOS | 2119 | 1 | 25-07-2021 | N0233
251 | 28 | H044-010-000 | SPRING WASHER - M10 (OD=16, ID=10.2, T=2.5) - IS 3063 - 1972 | NOS | 360 | 1 | 25-07-2021 | N0233
252 | 28 | H001-008-025 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M8X25 | NOS | 1035 | 1 | 25-07-2021 | N0233
143 | 16 | H044-012-000 | SPRING WASHER - M12 (OD=18, ID=12.2, T=2.5) - IS 3063 - 1972 | NOS | 5 | 1 | 15-03-2021 | J0142
186 | 25 | H001-005-020 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M5X20 | NOS | 20 | 1 | 03-04-2021 | N0237
253 | 28 | H001-010-020 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M10X20 | NOS | 360 | 1 | 25-07-2021 | N0233
254 | 28 | H042-008-000 | PUNCHED WASHER TYPE A - M8 (OD=17, ID=9, T=1.6) - IS 2016 -1967 | NOS | 2103 | 1 | 25-07-2021 | N0233
255 | 28 | H042-010-000 | PUNCHED WASHER TYPE A - M10 (OD=21, ID=11, T=2) - IS 2016 -1967 | NOS | 360 | 1 | 25-07-2021 | N0233
256 | 28 | H044-008-000 | SPRING WASHER - M8 (OD=12.7, ID=8.1, T=2) - IS 3063 - 1972 | NOS | 2119 | 1 | 25-07-2021 | N0233
257 | 28 | H044-010-000 | SPRING WASHER - M10 (OD=16, ID=10.2, T=2.5) - IS 3063 - 1972 | NOS | 360 | 1 | 25-07-2021 | N0233
258 | 28 | Z150-120-600 | SWIVEL TYPE WHEEL WITH BRAKE-UHM-150 DIA -MOUNTING PLATE CD-120X60,PIONEER MAKE | NOS | 264 | 1 | 25-07-2021 | N0233
259 | 30 | B051-025-001 | RAIL-HGR25CC-HAIWIN MAKE | MTR | 5 | 1 |  | T0035
260 | 30 | B052-025-002 | LM BLOCK -HGW25CC-HAIWIN MAKE | NOS | 8 | 1 |  | T0035
261 | 30 | E063-090-000 | PNEUMATIC SWING CLAMP CYLINDER -MAS L-63X90 Degree- MINDMAN MAKE | NOS | 1 | 1 |  | T0035
262 | 30 | E063-090-001 | PNEUMATIC SWING CLAMP CYLINDER -MAS R-63X90 Degree- MINDMAN MAKE | NOS | 1 | 1 |  | T0035
263 | 30 | E311-063-100 | MCQI2-11-63-100M+LB+I | NOS | 1 | 1 |  | T0035
264 | 30 | E500-400-300 | MCQI2-11-40-135+CB+I | NOS | 2 | 1 |  | T0035
265 | 30 | E500-401-301 | MCMI-11-25-130+LB_POS_0_Mindman Make | NOS | 4 | 1 |  | T0035
266 | 30 | B500-400-302 | HGH 15CA ZAC-Hiwin Make | NOS | 16 | 1 |  | T0035
267 | 30 | B500-400-303 | HGR 15R 220C-Hiwin Make | NOS | 3.7 | 1 |  | T0035
268 | 30 | D500-400-302 | ISO - Spur gear 4M 25T 20PA 40FW | NOS | 1 | 1 |  | T0035
269 | 30 | D500-400-303 | ISO - Spur gear 4M 62T 20PA 35FW | NOS | 1 | 1 |  | T0035
270 | 30 | D500-400-305 | Chain Wheel Plate Duplex for chain 12B-2,3/4x7/16 RØ12.07mm(1029ZR-21) | NOS | 8 | 1 |  | T0035
271 | 30 | D500-400-306 | BLDC MOTOR TYPE DC motor BM70-0.7H ( 200W, 0.64 N-m, 3000rpm) Jayshree Make | NOS | 4 | 1 |  | T0035
272 | 30 | D500-400-307 | PAER 90T ( Ratio 100, 14 dia input, right angle planetory with 90% efficiency) output dia 22mm . Output speed 21 m/min at 3000 input_Sesame make | NOS | 4 | 1 |  | T0035
273 | 30 | Q500-400-309 | Roboteq BLDC motor controller SBL2360_Roboteq make | NOS | 2 | 1 |  | T0035
274 | 30 | Q500-400-311 | SRX04-S SRX 4 Amp Drive, std terminal,block type | NOS | 4 | 1 |  | T0035
275 | 30 | D500-300-201 | AM24RS3DMA-PG10 Step Servo Motor with 10:1 gearbox, with 1024ppr encoder NEMA24,25NM | NOS | 4 | 1 |  | T0035
276 | 30 | Q500-400-304 | RS06-P-A Close Loop Step Servo drive,6Amp,Pulse Type_Moon Make | NOS | 4 | 1 |  | T0035
277 | 30 | Q500-400-205 | 2116-300,Encoder Cable_Moon Make | NOS | 4 | 1 |  | T0035
278 | 30 | Q500-400-206 | 2103-300 Motor Power Cable_Moon Make | NOS | 4 | 1 |  | T0035
279 | 30 | Q500-400-207 | 1115-100 I/O Cable_Moon Make | NOS | 4 | 1 |  | T0035
280 | 30 | Q700-602-503 | Angle Sensor PST360G2-1A-C0000-ERA360-RE , 360DEG WIRE LEADS_Digikey Make | NOS | 4 | 1 |  | T0035
281 | 30 | D502-303-410 | DC Servo Motor SM0803GE4-KCF-NNV Motor,750w with brake,2500 lines encoder, 2.4 Nm_Moon make | NOS | 1 | 1 |  | T0035
282 | 30 | Q501-602-202 | M2DC-20D5S Servo Drive,24-70VDC,20.0A,Basic type 1_Moon Make | NOS | 1 | 1 |  | T0035
283 | 30 | D601-502-906 | Gear Box Ratio 100:1 ,o/p rpm 15,640 Nm Torque,lift speed 6mtr/min,swl 300kg_Bonfiglioli make | NOS | 0 | 1 |  | T0035
284 | 30 | D500-400-588 | NEMA24(60mm) 1.8°2-Phase Hybrid Stepper Motor with planetary gearbox,Length 158.5mm, Gear ratio 10 Output Torque 25N.m, Rated Current 4.0A/Phase_Moon Make | NOS | 4 | 1 |  | T0035
285 | 30 | R401-090-210 | Simens Contactor ,24 VDC coil Current 9 amp 3TF30[With Auxiliary contacts 1NC $ Type 3TF30 01-0B] | NOS | 4 | 1 |  | T0037
286 | 30 | S214-001-060 | TEKNIC MAKE INDICATING LIMIT SWITCH WITH ADJUSTABLE ROLLER LEVER ARM VS(METAL) NG1-VS-510 L024 | NOS | 2 | 1 |  | T0037
287 | 30 | B001-025-047 | Ball Bearing - 6005 Zz - 25 x 47 x 12 - SKF | NOS | 26 | 1 |  | T0037
288 | 30 | B001-015-032 | Ball Bearing - 6002 Zz - 15 x 32 x 9 - SKF | NOS | 14 | 1 |  | T0037
289 | 30 | B001-020-042 | Ball Bearing - 6004 Zz - 20 x 42 x 12 - SKF | NOS | 12 | 1 |  | T0037
290 | 30 | M001-050-000 | CRIMPING TOOL | NOS | 2 | 1 |  | T0037
291 | 30 | S311-001-020 | EMERGENCY SWITCH BOX TYPE â XALK01 | NOS | 2 | 1 |  | T0037
292 | 30 | P141-100-000 | GC35MH-32MR-D 16DI,16DO RELAY O/P, 3.5 DISPLAY | NOS | 2 | 1 | 24-10-2021 | T0037
293 | 30 | S802-011-010 | OMRON MAKE SMPS DIN RAIL MOUNTING ,INPUT VOLTAGE: 230VAC,POWER RATING : 120 W ,OUTPUT VOLTAGE(VDC): 24VDC, MODEL NO.- S8VK-C12024 | NOS | 2 | 1 | 24-10-2021 | T0037
294 | 30 | C002-005-001 | SERIES - INTERROLL FRICTION CONVEYOR ROLLER SERIES 3800 (POWER & FREE) TUBE - MS TUBE DIA 50X1.5 (MS Z/P) WITH 5MM THICK PU COATING AFTER WHICH THE DIA IS GOING TO BECOME 60MM DIA ROD - MS ROD 14MM FEMALE THREADED M8X15 (MS Z/P) BEARING - MS STD BEARING 6002 END CAP - POLYAMIDE END CAP WITH YELLOW SEAL TYPE - SINGLE STEEL SPROCKET 1/2 PITCH , Z=14T RL=343MM,EL=AGL=383MM | NOS | 7 | 1 | 24-10-2021 | T0037
295 | 32 | K021-000-200 | CAST RISER HEIGHT OF DOWEL -201 | NOS | 5 | 1 | 06-06-2023 | N0297
296 | 32 | K021-000-250 | CAST RISER HEIGHT OF DOWEL -251 | NOS | 6 | 1 | 06-06-2023 | N0297
297 | 32 | K021-000-300 | CAST RISER HEIGHT OF DOWEL -301 | NOS | 2 | 1 | 06-06-2023 | N0297
298 | 32 | K029-140-050 | SHIMMING BLOCK- 40X50X16MM-THK | NOS | 1 | 1 | 06-06-2023 | N0297
299 | 32 | K031-016-065 | PIN RETAINER 4 HOLE 16MM | NOS | 1 | 1 | 06-06-2023 | N0297
300 | 32 | J020-098-000 | M20-T1-98-B-SANDFIELD MAKE TOGGLE CLAMP | NOS | 14 | 1 | 06-06-2023 | N0297
301 | 33 | K021-000-200 | CAST RISER HEIGHT OF DOWEL -201 | NOS | 5 | 1 | 13-06-2023 | N0297
302 | 33 | K021-000-250 | CAST RISER HEIGHT OF DOWEL -251 | NOS | 6 | 1 | 13-06-2023 | N0297
303 | 33 | K021-000-300 | CAST RISER HEIGHT OF DOWEL -301 | NOS | 2 | 1 | 13-06-2023 | N0297
304 | 33 | K029-140-050 | SHIMMING BLOCK- 40X50X16MM-THK | NOS | 1 | 1 | 13-06-2023 | N0297
305 | 33 | K031-016-065 | PIN RETAINER 4 HOLE 16MM | NOS | 1 | 1 | 13-06-2023 | N0297
306 | 33 | J020-098-000 | M20-T1-98-B-SANDFIELD MAKE TOGGLE CLAMP | NOS | 14 | 1 | 13-06-2023 | N0297
307 | 33 | E302-002-001 | SPATTER PROOF TUBE Ø8MM(Blue) CKD MAKE | MTR | 15 | 1 | 13-06-2023 | N0297
308 | 33 | E302-200-002 | SPATTER PROOF TUBE Ø8MM(Black)CKD MAKE | MTR | 15 | 1 | 13-06-2023 | N0297
309 | 33 | K031-021-070 | PIN RETAINER | NOS | 1 | 1 | 13-06-2023 | N0297
310 | 33 | E000-003-028 | FR CKD MAKE W4000-15-W | NOS | 1 | 1 | 13-06-2023 | N0297
311 | 33 | E132-200-020 | MANIFOLD M4GA3R-00-4 | NOS | 1 | 1 | 13-06-2023 | N0297
312 | 33 | E132-200-037 | Solenoid valve 5/2 4GA329R-08-B-3 | NOS | 2 | 1 | 13-06-2023 | N0297
313 | 33 | E132-200-040 | Blanking Plate(4G3R-MP) | NOS | 2 | 1 | 13-06-2023 | N0297
314 | 33 | E132-200-010 | CAC4-63B100-T0H3 | NOS | 3 | 1 |  | N0297
158 | 21 | H003-008-000 | D-SHACKLE 3/8 | NOS | 2 | 1 | 24-03-2021 | J0139
176 | 23 | H001-012-055 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M12X55 | NOS | 24 | 1 | 24-03-2021 | N0236
177 | 23 | H001-016-035 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M16X35 | NOS | 360 | 1 | 24-03-2021 | N0236
178 | 23 | H002-006-020 | CSK ALLEN SCREW - IS 6761 - GRADE 12.9 -M6X20 | NOS | 48 | 1 | 24-03-2021 | N0236
179 | 23 | H023-012-175 | HEX NUT- IS 1364 - M12X1.75 - GRADE-10 | NOS | 24 | 1 | 24-03-2021 | N0236
180 | 23 | H039-112-035 | DOWEL PIN WITH INTERNAL THREAD - DIA 12 M6 X 35 IS 3524 - 1966 | NOS | 64 | 1 | 24-03-2021 | N0236
181 | 23 | H042-016-000 | PUNCHED WASHER TYPE A - M16 (OD=30, ID=18, T=3.15) - IS 2016 -1967 | NOS | 360 | 1 | 24-03-2021 | N0236
182 | 23 | H042-012-001 | PUNCHED WASHER TYPE A - M12 (OD=30, ID=14, T=3) - IS 2016 -1967 | NOS | 216 | 1 | 24-03-2021 | N0236
315 | 33 | E132-200-011 | 1/4X8 Elbow Connector | NOS | 10 | 1 |  | N0297
187 | 25 | H001-006-020 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M6X20 | NOS | 4 | 1 | 03-04-2021 | N0237
188 | 25 | H001-006-025 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M6X25 | NOS | 4 | 1 | 03-04-2021 | N0237
189 | 25 | H001-006-030 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M6X30 | NOS | 8 | 1 | 03-04-2021 | N0237
190 | 25 | H001-006-035 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M6X35 | NOS | 6 | 1 | 03-04-2021 | N0237
191 | 25 | H001-008-025 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M8X25 | NOS | 8 | 1 | 03-04-2021 | N0237
192 | 25 | H001-008-030 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M8X30 | NOS | 55 | 1 | 03-04-2021 | N0237
193 | 25 | H001-008-035 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M8X35 | NOS | 15 | 1 | 03-04-2021 | N0237
194 | 25 | H001-008-040 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M8X40 | NOS | 25 | 1 | 03-04-2021 | N0237
195 | 25 | H001-008-045 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M8X45 | NOS | 18 | 1 | 03-04-2021 | N0237
196 | 25 | H001-010-040 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M10X40 | NOS | 2 | 1 | 03-04-2021 | N0237
197 | 25 | H001-010-045 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M10X45 | NOS | 12 | 1 | 03-04-2021 | N0237
198 | 25 | H001-012-045 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M12X45 | NOS | 15 | 1 | 03-04-2021 | N0237
199 | 25 | H001-012-050 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M12X50 | NOS | 12 | 1 | 03-04-2021 | N0237
200 | 25 | H001-016-050 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M16X50 | NOS | 6 | 1 | 03-04-2021 | N0237
201 | 25 | H002-006-020 | CSK ALLEN SCREW - IS 6761 - GRADE 12.9 -M6X20 | NOS | 10 | 1 | 03-04-2021 | N0237
202 | 25 | H002-006-025 | CSK ALLEN SCREW - IS 6761 - GRADE 12.9 -M6X25 | NOS | 4 | 1 | 03-04-2021 | N0237
203 | 25 | H002-006-030 | CSK ALLEN SCREW - IS 6761 - GRADE 12.9 -M6X30 | NOS | 2 | 1 | 03-04-2021 | N0237
204 | 25 | H039-108-020 | DOWEL PIN WITH INTERNAL THREAD - DIA 8 M6 X 20 IS 3524 - 1966 | NOS | 4 | 1 | 03-04-2021 | N0237
205 | 25 | H039-108-030 | DOWEL PIN WITH INTERNAL THREAD - DIA 8 M6 X 30 IS 3524 - 1966 | NOS | 15 | 1 | 03-04-2021 | N0237
206 | 25 | H039-108-035 | DOWEL PIN WITH INTERNAL THREAD - DIA 8 M6 X 35 IS 3524 - 1966 | NOS | 40 | 1 | 03-04-2021 | N0237
207 | 25 | H039-108-040 | DOWEL PIN WITH INTERNAL THREAD - DIA 8 M6 X 40 IS 3524 - 1966 | NOS | 20 | 1 | 03-04-2021 | N0237
208 | 25 | H039-110-035 | DOWEL PIN WITH INTERNAL THREAD - DIA 10 M6 X 35 IS 3524 - 1966 | NOS | 10 | 1 | 03-04-2021 | N0237
209 | 25 | H039-110-040 | DOWEL PIN WITH INTERNAL THREAD - DIA 10 M6 X 40 IS 3524 - 1966 | NOS | 4 | 1 | 03-04-2021 | N0237
210 | 25 | H042-008-000 | PUNCHED WASHER TYPE A - M8 (OD=17, ID=9, T=1.6) - IS 2016 -1967 | NOS | 75 | 1 | 03-04-2021 | N0237
211 | 25 | H042-010-000 | PUNCHED WASHER TYPE A - M10 (OD=21, ID=11, T=2) - IS 2016 -1967 | NOS | 14 | 1 | 03-04-2021 | N0237
212 | 25 | H042-014-000 | PUNCHED WASHER TYPE A - M14 (OD=28, ID=15.5, T=2.8) - IS 2016 -1967 | NOS | 2 | 1 | 03-04-2021 | N0237
213 | 25 | H044-006-000 | SPRING WASHER - M6 (OD=9.9, ID=6.1, T=1.6) - IS 3063 - 1972 | NOS | 20 | 1 | 03-04-2021 | N0237
214 | 25 | H044-008-000 | SPRING WASHER - M8 (OD=12.7, ID=8.1, T=2) - IS 3063 - 1972 | NOS | 75 | 1 | 03-04-2021 | N0237
215 | 25 | H044-010-000 | SPRING WASHER - M10 (OD=16, ID=10.2, T=2.5) - IS 3063 - 1972 | NOS | 14 | 1 | 03-04-2021 | N0237
216 | 25 | H044-012-000 | SPRING WASHER - M12 (OD=18, ID=12.2, T=2.5) - IS 3063 - 1972 | NOS | 16 | 1 | 03-04-2021 | N0237
217 | 25 | H044-014-005 | SPRING WASHER - M14 (OD=24, ID=14 T=2) - IS 3063 - 1972 | NOS | 2 | 1 | 03-04-2021 | N0237
218 | 25 | H042-006-000 | PUNCHED WASHER TYPE A - M6 (OD=12.5, ID=6.6, T=1.6) - IS 2016 -1967 | NOS | 20 | 1 | 03-04-2021 | N0237
219 | 25 | H042-012-001 | PUNCHED WASHER TYPE A - M12 (OD=30, ID=14, T=3) - IS 2016 -1967 | NOS | 16 | 1 | 03-04-2021 | N0237
220 | 25 | H001-014-035 | SOC HD SCREW - IS 2269 - GRADE 12.9 - M14X35 | NOS | 2 | 1 | 03-04-2021 | N0237
221 | 25 | J020-005-005 | CP 7 SANDFIELD MAKE TOGGLE CLAMP | NOS | 1 | 1 | 03-04-2021 | N0237
222 | 25 | H123-006-000 | HEX NUT- IS 1364 - IS 1364 - M6X1 - GRADE-8 | NOS | 15 | 1 | 03-04-2021 | N0237
223 | 25 | H445-016-125 | ANCHORE FASTNER - 16X125 | NOS | 8 | 1 | 03-04-2021 | N0237
224 | 25 | Z042-042-042 | CONICLE DOCK-ODØ25,42L | NOS | 2 | 1 | 03-04-2021 | N0237
225 | 25 | Z020-045-000 | SPRING-OD-20,45L | NOS | 1 | 1 | 03-04-2021 | N0237
226 | 25 | B016-020-030 | PAP BUSH ID 16 x OD 20 x 30L | NOS | 2 | 1 | 03-04-2021 | N0237

## tblPM_Project_Hardware_MasterD
Id | SysDate | SysTime | CompId | SessionId | FinYearId | PRJCTNO | WONo | GenDate
1 | [5 empty] | 1
3 | 2021-03-03 | 5:11:45 PM | 1 | Sapl0315 | 8 | 2 | P0061 | 03/03/2021
4 | 2021-03-04 | 8:48:07 AM | 1 | Sapl0315 | 8 | 3 | J0139 | 04/03/2021
5 | 2021-03-04 | 2:01:11 PM | 1 | Sapl0315 | 8 | 4 | N0231 | 04/03/2021
6 | 2021-03-04 | 3:39:27 PM | 1 | Sapl0315 | 8 | 5 | N0231 | 04/03/2021
7 | 2021-03-05 | 10:19:59 AM | 1 | Sapl0315 | 8 | 6 | N0231 | 05/03/2021
8 | 2021-03-06 | 8:48:01 AM | 1 | Sapl0315 | 8 | 7 | N0231 | 06/03/2021
9 | 2021-03-09 | 9:04:06 AM | 1 | Sapl0315 | 8 | 8 | N0231 | 09/03/2021
10 | 2021-03-09 | 11:57:20 AM | 1 | Sapl0315 | 8 | 9 | N0231 | 09/03/2021
11 | 2021-03-09 | 1:14:33 PM | 1 | Sapl0315 | 8 | 10 | N0231 | 09/03/2021
12 | 2021-03-13 | 9:20:15 AM | 1 | Sapl0315 | 8 | 11 | J0142 | 13/03/2021
15 | 2021-03-13 | 4:22:10 PM | 1 | Sapl0315 | 8 | 14 | J0142 | 13/03/2021
18 | 2021-03-17 | 9:39:06 AM | 1 | Sapl0315 | 8 | 17 | N0235 | 17/03/2021
19 | 2021-03-18 | 11:50:38 AM | 1 | Sapl0315 | 8 | 18 | J0141 | 18/03/2021
20 | 2021-03-18 | 11:50:55 AM | 1 | Sapl0315 | 8 | 19 | J0142 | 18/03/2021
21 | 2021-03-22 | 12:16:25 PM | 1 | Sapl0315 | 8 | 20 | N0231 | 22/03/2021
23 | 2021-03-24 | 2:20:43 PM | 1 | Sapl0315 | 8 | 22 | N0236 | 24/03/2021
25 | 2021-03-31 | 8:55:36 AM | 1 | Sapl0315 | 8 | 24 | N0237 | 31/03/2021
26 | 2021-03-31 | 2:34:31 PM | 1 | Sapl0315 | 8 | 25 | N0237 | 31/03/2021
27 | 2021-06-05 | 4:46:56 PM | 1 | Sapl0315 | 9 | 26 | N0233 | 05/06/2021
28 | 2021-06-05 | 4:52:16 PM | 1 | Sapl0315 | 9 | 27 | N0233 | 05/06/2021
29 | 2021-07-25 | 2:24:47 PM | 1 | sapl0338 | 9 | 28 | N0233 | 25/07/2021
31 | 2021-10-24 | 3:26:31 PM | 1 | Sapl0334 | 9 | 30 | T0037 | 24/10/2021
32 | 2022-02-14 | 9:05:11 AM | 1 | Sapl0356 | 9 | 31 | N0238 | 14/02/2022
33 | 2023-06-17 | 4:01:16 PM | 1 | Sapl0002 | 11 | 32 | N0297 | 17/06/2023
34 | 2023-06-17 | 4:16:16 PM | 1 | Sapl0002 | 11 | 33 | N0297 | 17/06/2023
13 | 2021-03-13 | 3:42:03 PM | 1 | Sapl0315 | 8 | 12 | N0235 | 13/03/2021
14 | 2021-03-13 | 4:21:53 PM | 1 | Sapl0315 | 8 | 13 | J0141 | 13/03/2021
16 | 2021-03-15 | 9:05:50 AM | 1 | Sapl0315 | 8 | 15 | J0141 | 15/03/2021
17 | 2021-03-15 | 9:26:02 AM | 1 | Sapl0315 | 8 | 16 | J0142 | 15/03/2021
30 | 2021-08-04 | 2:30:36 PM | 1 | sapl0338 | 9 | 29 | T0035 | 04/08/2021
22 | 2021-03-24 | 10:01:29 AM | 1 | Sapl0315 | 8 | 21 | J0139 | 24/03/2021
24 | 2021-03-24 | 2:35:09 PM | 1 | Sapl0315 | 8 | 23 | N0236 | 24/03/2021

## tblPM_Project_Hardware_VendorD
Id | SysDate | SysTime | CompId | SessionId | FinYearId | PRJCTNO | WONo | GenDate | VendorPlan | VendorDate
1 | [8 empty] | 1
2 | 2021-03-03 | 5:13:49 PM | 1 | Sapl0315 | 8 | 2 | P0061 | 03/03/2021 | 2 | 03/03/2021
3 | 2021-03-12 | 11:56:22 AM | 1 | Sapl0324 | 8 | 3 | J0139 | 04/03/2021 | 3 | 12/03/2021
4 | 2021-03-15 | 6:29:10 PM | 1 | Sapl0324 | 8 | 16 | J0142 | 15/03/2021 | 4 | 15/03/2021
5 | 2021-03-15 | 6:30:38 PM | 1 | Sapl0324 | 8 | 15 | J0141 | 15/03/2021 | 5 | 15/03/2021
6 | 2021-03-15 | 6:30:56 PM | 1 | Sapl0324 | 8 | 14 | J0142 | 13/03/2021 | 6 | 15/03/2021
7 | 2021-03-15 | 6:31:20 PM | 1 | Sapl0324 | 8 | 13 | J0141 | 13/03/2021 | 7 | 15/03/2021
8 | 2021-03-15 | 6:31:59 PM | 1 | Sapl0324 | 8 | 11 | J0142 | 13/03/2021 | 8 | 15/03/2021
9 | 2021-03-15 | 6:33:20 PM | 1 | Sapl0324 | 8 | 7 | N0231 | 06/03/2021 | 9 | 15/03/2021
11 | 2021-03-18 | 1:15:05 PM | 1 | Sapl0324 | 8 | 5 | N0231 | 04/03/2021 | 11 | 18/03/2021
12 | 2021-03-19 | 1:45:25 PM | 1 | Sapl0324 | 8 | 13 | J0141 | 13/03/2021 | 12 | 19/03/2021
13 | 2021-03-19 | 1:47:22 PM | 1 | Sapl0324 | 8 | 18 | J0141 | 18/03/2021 | 13 | 19/03/2021
14 | 2021-03-19 | 1:47:42 PM | 1 | Sapl0324 | 8 | 19 | J0142 | 18/03/2021 | 14 | 19/03/2021
17 | 2021-03-19 | 3:05:16 PM | 1 | Sapl0325 | 8 | 16 | J0142 | 15/03/2021 | 17 | 19/03/2021
19 | 2021-03-22 | 4:54:27 PM | 1 | Sapl0324 | 8 | 20 | N0231 | 22/03/2021 | 19 | 22/03/2021
20 | 2021-03-22 | 4:55:04 PM | 1 | Sapl0324 | 8 | 20 | N0231 | 22/03/2021 | 20 | 22/03/2021
21 | 2021-03-25 | 1:29:17 PM | 1 | Sapl0324 | 8 | 21 | J0139 | 24/03/2021 | 21 | 25/03/2021
22 | 2021-03-31 | 9:23:46 AM | 1 | sapl0337 | 8 | 23 | N0236 | 24/03/2021 | 22 | 31/03/2021
23 | 2021-03-31 | 9:29:24 AM | 1 | sapl0337 | 8 | 22 | N0236 | 24/03/2021 | 23 | 31/03/2021
24 | 2021-03-31 | 10:29:20 AM | 1 | sapl0337 | 8 | 24 | N0237 | 31/03/2021 | 24 | 31/03/2021
25 | 2021-03-31 | 10:54:27 AM | 1 | sapl0337 | 8 | 25 | N0237 | 31/03/2021 | 25 | 31/03/2021
26 | 2021-09-24 | 10:19:37 AM | 1 | Sapl0334 | 9 | 14 | J0142 | 13/03/2021 | 26 | 24/09/2021
27 | 2021-10-24 | 3:28:42 PM | 1 | Sapl0334 | 9 | 30 | T0037 | 24/10/2021 | 27 | 24/10/2021
10 | 2021-03-15 | 6:33:40 PM | 1 | Sapl0324 | 8 | 7 | N0231 | 06/03/2021 | 10 | 15/03/2021
15 | 2021-03-19 | 2:20:57 PM | 1 | Sapl0325 | 8 | 12 | N0235 | 13/03/2021 | 15 | 19/03/2021
16 | 2021-03-19 | 2:46:35 PM | 1 | Sapl0325 | 8 | 15 | J0141 | 15/03/2021 | 16 | 19/03/2021
18 | 2021-03-19 | 3:08:02 PM | 1 | Sapl0325 | 8 | 17 | N0235 | 17/03/2021 | 18 | 19/03/2021

## tblPM_Project_Manufacturing_Ass
Id | PRJCTNO | ItemCode | Description | UOM | BOMQ | Design | VendorPlanDate | VendorAct | WONo | VendorPlan | AssemlyDate | Remark | AssemlyNo
1 | 7 | 00777-01-00 | UNIT 01 | NOS | 1 | 11-03-2021 | 12-03-2021 | planned | J0142 | 2 | 17-03-2021

## tblPM_Project_Manufacturig_Ass
Id | SysDate | SysTime | CompId | SessionId | FinYearId | PRJCTNO | WONo | GenDate | VendorPlan | VendorDate | AssemlyDate | AssemlyNo
1 | 2021-03-23 | 9:41:24 AM | 1 | Sapl0326 | 8 | 7 | J0142 | 23/03/2021 | 2 | 12/03/2021 | 23/03/2021

## tblPM_Project_Manufacturing_Pla
Id | PRJCTNO | ItemCode | Description | UOM | BOMQ | Design | VendorPlanDate | VendorAct | WONo | VendorPlan
1 | 7 | 00777-01-00 | UNIT 01 | NOS | 1 | 11-03-2021 | 12-03-2021 | planned | J0142 | 2
2 | 11 | 00776-01-00 | UNIT 01 | NOS | 1 | 13-03-2021 | 13-03-2021 | planned | J0141 | 3
3 | 11 | 00776-02-00 | UNIT 02 | NOS | 1 | 13-03-2021 | 13-03-2021 | planned | J0141 | 3
4 | 11 | 00776-01-00 | UNIT 01 | NOS | 1 | 13-03-2021 | 13-03-2021 | planned | J0141 | 4
5 | 11 | 00776-02-00 | UNIT 02 | NOS | 1 | 13-03-2021 | 13-03-2021 | planned | J0141 | 4
8 | 10 | 00773-09-00 | UNIT 09 | NOS | 1 | 12-03-2021 | 13-03-2021 |  | J0139 | 6
9 | 9 | 00777-02-00 | UNIT 02 | NOS | 1 | 12-03-2021 | 13-03-2021 | 22-03-2021 | J0142 | 7
12 | 12 | 00894-17-00 | GA | NOS | 1 |  |  |  | T0042 | 10
6 | 11 | 00776-01-00 | UNIT 01 | NOS | 1 | 13-03-2021 | 13-03-2021 | 22-03-2021 | J0141 | 5
7 | 11 | 00776-02-00 | UNIT 02 | NOS | 1 | 13-03-2021 | 13-03-2021 | 22-03-2021 | J0141 | 5
11 | 11 | 00776-01-00 | UNIT 01 | NOS | 1 | 13-03-2021 | 30-03-2021 | 30-03-2021 | J0141 | 9
10 | 11 | 00776-01-00 | UNIT 01 | NOS | 1 | 13-03-2021 | 31-03-2021 | 31-03-2021 | J0141 | 8

## tblPM_Project_Manufacturing_Ven
Id | SysDate | SysTime | CompId | SessionId | FinYearId | PRJCTNO | WONo | GenDate | VendorPlan | VendorDate
1 | [8 empty] | 1
2 | 2021-03-22 | 4:58:20 PM | 1 | SAPL0324 | 8 | 7 | J0142 | 12/03/2021 | 2 | 22/03/2021
3 | 2021-03-22 | 5:04:43 PM | 1 | SAPL0324 | 8 | 11 | J0141 | 13/03/2021 | 3 | 22/03/2021
4 | 2021-03-23 | 9:06:32 AM | 1 | Sapl0325 | 8 | 11 | J0141 | 13/03/2021 | 4 | 23/03/2021
6 | 2021-03-25 | 2:02:25 PM | 1 | SAPL0324 | 8 | 10 | J0139 | 12/03/2021 | 6 | 25/03/2021
7 | 2021-03-25 | 2:05:24 PM | 1 | SAPL0324 | 8 | 9 | J0142 | 12/03/2021 | 7 | 25/03/2021
5 | 2021-03-25 | 2:01:19 PM | 1 | SAPL0324 | 8 | 11 | J0141 | 13/03/2021 | 5 | 25/03/2021
9 | 2021-03-31 | 11:57:23 AM | 1 | sapl0290 | 8 | 11 | J0141 | 13/03/2021 | 9 | 31/03/2021
8 | 2021-03-31 | 11:53:44 AM | 1 | sapl0290 | 8 | 11 | J0141 | 13/03/2021 | 8 | 31/03/2021

## tblPM_Project_Site_Master_Detai
Id | PRJCTNO | ItemCode | Description | UOM | BOMQ | Design | Manf | BOP | Assemly | WONo | GenDate | Hrs
1 | 1
4 | 2 | 00771-00-00 | 6 METER LENGTH STRUCTURE | NOS | 1 | 50 | 10 | 16-02-2021 | 95 | N0234
8 | 3 | 00760-00-00 | Roof Finalization Fixture | NOS | 1 | 02-02-2021 |  |  | Select | N0231 |  | 0
9 | 3 | 00760-00-00 | Roof Finalization Fixture | NOS | 1 | 02-02-2021 | 01-02-2021 |  | Select | N0231 |  | 0
10 | 4 | 00767-00-00 | GENERAL ASSEMBLY | NOS | 1 |  |  |  | Select | P0060 |  | 0
35 | 5 | 00771-01-02 | STRUCTURE | NOS | 2 | 18-02-2021 | 23-02-2021 |  | Select | N0234 |  | 0
36 | 5 | 00771-01-01 | VERTICAL PILLAR | NOS | 2 | 18-02-2021 | 23-02-2021 |  | Select | N0234 |  | 0
37 | 5 | 00771-01-05 | I SECTION | NOS | 1 | 20-02-2021 | 23-02-2021 |  | Select | N0234 |  | 0
38 | 5 | 00771-01-02 | STRUCTURE | NOS | 2 | 18-02-2021 | 23-02-2021 |  | 80% | N0234 |  | 32
39 | 5 | 00771-01-01 | VERTICAL PILLAR | NOS | 2 | 18-02-2021 | 23-02-2021 |  | Select | N0234 |  | 0
40 | 5 | 00771-01-05 | I SECTION | NOS | 1 | 20-02-2021 | 23-02-2021 |  | Select | N0234 |  | 0
51 | 10 | 00773-09-00 | UNIT 09 | NOS | 1 | 12-03-2021 |  |  | Select | J0139 |  | 0
52 | 11 | 00776-01-00 | UNIT 01 | NOS | 1 | 13-03-2021 |  |  | Select | J0141 |  | 0
53 | 11 | 00776-02-00 | UNIT 02 | NOS | 1 | 13-03-2021 |  |  | Select | J0141 |  | 0
54 | 12 | 00894-17-00 | GA | NOS | 1 |  |  |  | Select | T0042 |  | 0
55 | 13 | 01030-07-00 | GA | NOS | 1 |  |  |  | Select | N0297 |  | 0
56 | 13 | 01030-07-00 | GA | NOS | 1 | 14-06-2023 |  |  | Select | N0297 |  | 0
57 | 13 | 01030-09-00 | GA | NOS | 1 |  |  |  | Select | N0297 |  | 0
58 | 14 | 01030-07-00 | GA | NOS | 1 |  |  |  | Select | N0297 |  | 0
11 | 4 | 00767-00-00 | GENERAL ASSEMBLY | NOS | 1 |  |  |  | Select | P0060 |  | 0
12 | 4 | 00767-00-00 | GENERAL ASSEMBLY | NOS | 1 |  |  |  | 40% | P0060 |  | 0
47 | 7 | 00777-01-00 | UNIT 01 | NOS | 1 | 11-03-2021 |  |  | Select | J0142 |  | 0
48 | 8 | 00775-01-00 | UNIT 01 | NOS | 1 | 11-03-2021 |  |  | Select | N0235 |  | 0
49 | 8 | 00775-05-00 | UNIT 05 | NOS | 1 | 11-03-2021 |  |  | Select | N0235 |  | 0
50 | 9 | 00777-02-00 | UNIT 02 | NOS | 1 | 12-03-2021 |  |  | Select | J0142 |  | 0
13 | 4 | 99999-02-00 | Assly Cross Rail Support | NOS | 6 | 19-02-2021 | 23-02-2021 |  | Select | N0234 |  | 0
14 | 4 | 99999-04-00 | Assly of Channel Support C-75 100L | NOS | 8 | 19-02-2021 | 23-02-2021 |  | Select | N0234 |  | 0
15 | 4 | 99999-05-00 | Assly of Joint Coupler | NOS | 2 | 19-02-2021 | 23-02-2021 |  | Select | N0234 |  | 0
16 | 4 | 99999-07-00 | Assly Beam Support | NOS | 8 | 18-02-2021 | 23-02-2021 |  | Select | N0234 |  | 0
17 | 4 | 99999-08-00 | Assly of End Rubber Stopper | NOS | 10 | 19-02-2021 | 23-02-2021 |  | Select | N0234 |  | 0
18 | 4 | 00771-00-00 | 6 METER LENGTH STRUCTURE | NOS | 1 | 18-02-2021 | 23-02-2021 |  | Select | N0234 |  | 0
19 | 4 | 00771-01-00 | UNIT 01 | NOS | 1 | 19-02-2021 | 23-02-2021 |  | Select | N0234 |  | 0
20 | 4 | 00771-01-02 | STRUCTURE | NOS | 2 | 18-02-2021 | 23-02-2021 |  | Select | N0234 |  | 0
21 | 4 | 00771-01-01 | VERTICAL PILLAR | NOS | 2 | 18-02-2021 | 23-02-2021 |  | Select | N0234 |  | 0
22 | 4 | 00771-99-00 | GENERAL ASSEMBLY | NOS | 1 | 18-02-2021 | 23-02-2021 |  | Select | N0234 |  | 0
23 | 4 | 00771-01-05 | I SECTION | NOS | 1 | 18-02-2021 | 23-02-2021 |  | Select | N0234 |  | 0
24 | 4 | 99999-02-00 | Assly Cross Rail Support | NOS | 6 | 19-02-2021 | 23-02-2021 |  | Select | N0234 |  | 0
25 | 4 | 99999-04-00 | Assly of Channel Support C-75 100L | NOS | 8 | 19-02-2021 | 23-02-2021 |  | Select | N0234 |  | 0
26 | 4 | 99999-05-00 | Assly of Joint Coupler | NOS | 2 | 19-02-2021 | 23-02-2021 |  | Select | N0234 |  | 0
27 | 4 | 99999-07-00 | Assly Beam Support | NOS | 8 | 18-02-2021 | 23-02-2021 |  | Select | N0234 |  | 0
28 | 4 | 99999-08-00 | Assly of End Rubber Stopper | NOS | 10 | 19-02-2021 | 23-02-2021 |  | Select | N0234 |  | 0
29 | 4 | 00771-00-00 | 6 METER LENGTH STRUCTURE | NOS | 1 | 18-02-2021 | 23-02-2021 |  | Select | N0234 |  | 0
30 | 4 | 00771-01-00 | UNIT 01 | NOS | 1 | 19-02-2021 | 23-02-2021 |  | Select | N0234 |  | 0
31 | 4 | 00771-01-02 | STRUCTURE | NOS | 2 | 18-02-2021 | 23-02-2021 |  | Select | N0234 |  | 0
32 | 4 | 00771-01-01 | VERTICAL PILLAR | NOS | 2 | 18-02-2021 | 23-02-2021 |  | Select | N0234 |  | 0
33 | 4 | 00771-99-00 | GENERAL ASSEMBLY | NOS | 1 | 18-02-2021 | 23-02-2021 |  | Select | N0234 |  | 0
34 | 4 | 00771-01-05 | I SECTION | NOS | 1 | 18-02-2021 | 23-02-2021 |  | Select | N0234 |  | 0
41 | 6 | 00773-00-00 | JIG BOOM | NOS | 1 | 24-02-2021 |  |  | 40% | J0139 |  | 0
42 | 6 | 00773-99-00 | GENERAL ASSEMBLY | NOS | 1 | 24-02-2021 |  |  | Select | J0139 |  | 0
43 | 6 | 00773-02-00 | UNIT 02 | NOS | 1 | 24-02-2021 |  |  | Select | J0139 |  | 0
44 | 6 | 00773-02-11 | INSIDE HOSES GUIDE BKT | NOS | 10 | 24-02-2021 |  |  | Select | J0139 |  | 0
45 | 6 | 00773-03-00 | UNIT 03 | NOS | 1 |  |  |  | Select | J0139 |  | 0
46 | 6 | 00773-03-03 | COVER FRONT | NOS | 2 | 24-02-2021 |  |  | Select | J0139 |  | 0

## tblPM_Project_Site_MasterD
Id | SysDate | SysTime | CompId | SessionId | FinYearId | PRJCTNO | WONo | GenDate
1 | [5 empty] | 1
3 | 2021-02-15 | 4:11:41 PM | 1 | sapl0334 | 8 | 2 | N0234 | 15/02/2021
5 | 2021-02-17 | 4:38:54 PM | 1 | sapl0334 | 8 | 3 | N0231 | 17/02/2021
6 | 2021-02-23 | 10:35:46 AM | 1 | sapl0334 | 8 | 4 | N0234 | 23/02/2021
7 | 2021-02-23 | 11:43:27 AM | 1 | sapl0334 | 8 | 5 | N0234 | 23/02/2021
13 | 2021-03-13 | 12:00:07 PM | 1 | Sapl0315 | 8 | 11 | J0141 | 13/03/2021
14 | 2023-06-17 | 3:34:52 PM | 1 | Sapl0002 | 11 | 12 | T0042 | 17/06/2023
15 | 2023-06-17 | 4:18:13 PM | 1 | Sapl0002 | 11 | 13 | N0297 | 17/06/2023
8 | 2021-02-25 | 9:19:05 AM | 1 | sapl0334 | 8 | 6 | J0139 | 25/02/2021
9 | 2021-03-12 | 8:50:46 AM | 1 | Sapl0315 | 8 | 7 | J0142 | 12/03/2021
10 | 2021-03-12 | 8:51:22 AM | 1 | Sapl0315 | 8 | 8 | N0235 | 12/03/2021
11 | 2021-03-12 | 1:38:08 PM | 1 | Sapl0315 | 8 | 9 | J0142 | 12/03/2021
12 | 2021-03-12 | 1:38:39 PM | 1 | Sapl0315 | 8 | 10 | J0139 | 12/03/2021